## Sheet1
QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | category_id | LevelTwo | category_id | leveltwo | LevelFour | LevelFive | DifficultyLevel | category_id | leveltwo | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
SINGLE | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | 1 | People | 2 | Project Stakeholder Management |  |  | Complex | 3 | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 2020-12-04 23:10 | N | [6 empty] | NA | NA
SINGLE | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 4 | Contact senior management to discuss the possibility of reassigning the new resource to a different project. | Schedule time to chat with the new resource to assess their skills and understand their strength level. | Ask the team members to document task-related deficiencies displayed by the resource. | Contact the project sponsor to highlight these concerns and decide on an appropriate response. |  |  | 2 | 1 | PMP | 1 | People | 2 | Project Resource Management |  |  | Complex | 3 | Predictive Approach | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 2020-12-04 23:10
SINGLE | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 4 | Work with key stakeholders to identify project requirements that could be reduced. | Immediately ask project team members to increase the pace of each task within the project. | Ensure that substantial scope creep is included in the original project schedule, so that revised deadlines can be met. | Meet individually with project team members to discuss how aspects of the project can be completed more quickly than planned. |  |  | 1 | 1 | PMP | 1 | Process | 2 | Project Integration Management |  |  | Complex | 3 | Predictive Approach | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 2020-12-04 23:10
SINGLE | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 4 | Meet with both teams separately, and ask them to figure out a way to meet the required deadlines and complete the project on time. | Meet with the product owner to reprioritize the iteration backlog, so that it does not impact other teams or obligations. | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule. | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in lessons learned. |  |  | 2 | 1 | PMP | 1 | Process | 2 | Project Schedule Management |  |  | Complex | 3 | Predictive Approach | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 2020-12-04 23:10