## Sheet1
QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Question Category | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
SINGLE | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 4 | Contact senior management to discuss the possibility of reassigning the new resource to a different project. | Schedule time to chat with the new resource to assess their skills and understand their strength level. | Ask the team members to document task-related deficiencies displayed by the resource. | Contact the project sponsor to highlight these concerns and decide on an appropriate response. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 2020-12-04 23:10
SINGLE | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 4 | Work with key stakeholders to identify project requirements that could be reduced. | Immediately ask project team members to increase the pace of each task within the project. | Ensure that substantial scope creep is included in the original project schedule, so that revised deadlines can be met. | Meet individually with project team members to discuss how aspects of the project can be completed more quickly than planned. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 2020-12-04 23:10
SINGLE | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 4 | Meet with both teams separately, and ask them to figure out a way to meet the required deadlines and complete the project on time. | Meet with the product owner to reprioritize the iteration backlog, so that it does not impact other teams or obligations. | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule. | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in lessons learned. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 2020-12-04 23:10
SINGLE | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 4 | Invite project team members to a brainstorming session to identify an appropriate response. | Address the issue only after evaluating why these stakeholders are concerned. | Determine the impact of the conflict by listing the pros and cons of the situation. | Ask the project sponsor to act as a neutral party in negotiation with those stakeholders who are dissatisfied. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 2020-12-04 23:10
SINGLE | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 4 | Discuss the conflict with the project sponsor and formulate a response. | Replace the key team member with a new resource who has the same skills. | Meet with the change control board (CCB) to discuss the requested change. | Engage in the change management process to resolve the resource issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 2020-12-04 23:10
SINGLE | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 4 | Update the risk register to document the concerns, then continue with the meeting’s scheduled agenda items. | Recognize that the concern must be fully discussed and resolved prior to continuing with the meeting’s agenda items. | Address the team with a generic reminder about meeting etiquette, then ask if the team wants to use the time to fully discuss the concerns raised during the meeting. | Immediately acknowledge the team member’s concern, continue with the scheduled agenda, then privately meet with the team member to fully understand the concerns expressed. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 2020-12-04 23:10
SINGLE | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 4 | Notify the project sponsor about the lack of a technical resource. | Immediately escalate the issue to decision makers in the organization. | Check with the technical resource manager to see if there is an available technical resource. | Since time is short, hire an outside party to meet the need for a technical resource. |  |  | 3 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 2020-12-04 23:10
SINGLE | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 4 | Include agile training for these team members in a change request. | Ensure the project’s contingency reserve can cover agile training for all team members. | Create virtual training sessions for key team members, covering the main agile topics. | Identify and implement the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Medium | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 2020-12-04 23:10
SINGLE | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 4 | Offer more skill-specific training throughout the project. | Identify required strengths, and organize the team based on those strengths. | Meet with the project sponsor and team members to assign training for specific skills. | Empower team members to problem solve in situations where skills may be lacking. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 2020-12-04 23:10
SINGLE | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 4 | Ask team members to invite their managers to standup sessions, in order to find solutions more quickly. | Explain to team members that long discussions take time away from actual work on the project. | Insert a new team member who will manage obstacles and schedule additional meetings to discuss possible solutions. | Tell the team members that they are required to shorten the standup meetings and improve on finding solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Agile Hybrid | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 2020-12-04 23:10
SINGLE | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 4 | Required team sign off for each of the constant changes to the requirements | Set aside more resources for product testing after changes are made | Made sure that the customer was aware of the value of demos | Ensured that the team fully participated in developing the project scope |  |  | 3 | 1 | PMP | Process | Project Stakeholder Management |  |  | Medium | Predictive Approach | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 2020-12-04 23:10
SINGLE | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 4 | Meet the new demand by adding new resources with the required skills. | Hire a third-party vendor who can provide resources with the needed skills. | Change the distribution of partially dedicated resources with the needed skills. | Meet the new demand by upgrading the existing team members' skills. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 2020-12-04 23:10
SINGLE | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 4 | Preview the current stakeholder engagement plan for the way to resolve the difficulty. | Schedule a mandatory team meeting which will lead to the creation of a new social contract. | Notify team members that they should submit anonymous recommendations for a new social contract. | Send a survey to team members, requesting suggestions for dealing with the dissatisfaction. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 2020-12-04 23:10
SINGLE | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 4 | Immediately schedule a meeting with the stakeholders to review the situation. | Send the change control board (CCB) a change request. | Check with the organization's relevant legal practitioner for guidance. | Review the organization's lessons learned database for precedents and direction. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 4 | Help the team create a social contract that will encourage team cohesion. | Suggest that the team engage in multiple team-building events to normalize the team. | Keep the team informed by sending short daily project status updates. | Engage in face-to-face personal conversations with each team member to build relationships. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 4 | Renegotiate scope with the project sponsor after examining the work breakdown structure (WBS). | In consultation with the stakeholders and team members, identify the minimum viable product needed for launch. | Determine the schedule performance index (SPI), then escalate the schedule risk to the project sponsor. | Monitor progress using a burndown chart after modifying the schedule baseline to meet stakeholder requirements. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Medium | Predictive Approach | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 4 | Review the bounds of the negotiations for agreement. | Determine the project's ultimate objectives after carefully evaluating project priorities. | Engage in agreement negotiations for better resources. | Ensure that the impact of the unavailability of required resources is fully documented. |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Medium | Predictive Approach | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 4 | Reassure the team member about their abilities by reminding them that they were chosen for a reason. | Meet with the team member to discuss where they can contribute, based on their strengths. | Enroll the team member in targeted training to acquire the needed skills for their assigned role. | Schedule weekly touchpoints with the team member to discuss barriers that may impact their work. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 4 | Ask the product owner to sit in on the next iteration review meeting to learn more about the development status for the product. | Ask the quality assurance team to identify any mismatches in functionality compared to the initial design. | Ask the development team to rewrite the function so that it matches with the project scope. | Schedule time during the next retrospective session to discuss all corrective actions and ask the project owner to participate in the session. |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Agile Hybrid | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 4 | Agree that the functionality would offer a great opportunity, but the proposed addition is out of scope. | Schedule a meeting with the company's management team, and present the customer's request for additional functionality as a good opportunity. | Move forward, using the project's management reserve to add the requested functionality. | Identify an already-developed feature that could be combined with the new functionality and use the combination to meet the customer's request. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 4 | Work with team members to immediately implement the new approach. | Have the team decide on the appropriate approach, giving them authority to implement their decision and validating their decision in talks with stakeholders. | Discuss the pros and cons of the proposed approach with stakeholders, then select the approach that is best for the team and notify team members. | In order to obtain sponsor buy-in, have the team to benchmark the approach. |  |  | 2 | 1 | PMP | People | Project Integration Management |  |  | Medium | Agile Hybrid | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 4 | Assign one team member to update the project management plan template and document any risk. | Rank the need to update the template according to the business value for the upcoming iterations. | Avoid adding to team distraction by fixing the issue independently. | Document the issue as a new project risk and propose a solution. |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  | Complex | Agile Hybrid | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 4 | Send a request to the project sponsor, asking them to update the project charter then reassign the responsibilities and authorities. | Meet with the project team to add new and improved features to replace the features that were rejected. | Work with stakeholders to create a shared approach that will address the issues of concern. | File a change request with the change control board (CCB) in order to add budget to the baseline. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Agile Hybrid | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 4 | Use the Salience model of categorization. | Use the Transformation model of categorization. | Use the Transaction model of categorization. | Use the Collaboration method of categorization. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 4 | Assess the new resource’s ability to perform the necessary work by testing their communication skills with the current project team. | Evaluate the skills of the new resource to see how the resource can provide value to the project. | File a request with the project management office (PMO) manager in order to obtain a better resource. | Address the rumor with the new resource’s functional manager to mitigate any conflict within the project team. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 4 | Plan a database development specification, then regularly check to ensure the developer aligns with the specification. | Arrange for review of the data security status on a quarterly basis, and recommend remedial steps if noncompliance is found. | Tell the database developer to submit documentation of data security items and the steps they take to correct items that do not meet specifications. | Add a quality assurance specialist resource to the project team, who will be responsible for monitoring the data security quality of the project. |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 4 | Obtain a new resource to complete the needed tasks, resulting in less impact on the critical path. | Discuss the situation with the team member, and work with them to identify a practical solution. | Remind the team member that they needed to complete the work package in the agreed-upon timeframe. | Ask the functional manager for assistance communicating with the absent team member. |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 4 | Contract with a third-party company that specializes in helping businesses define scope of work on large projects. | Work with project stakeholders to recommend an iterative approach that will then help to define the project's scope. | Construct a project management plan that provides extra time within the schedule, then seek to revise the scope of work. | Suspend final delivery dates for the project in order to have time to revise the schedule once there is clarity on the scope of work |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 4 | Rank the importance of each improvement item, then implement actions identified during the last retrospective. | Engage in a cost-benefit analysis that can help predict the profits that could be realized through the use of new technology for the next phase. | Research new technology trends and management tools that have been successful on similar projects. | Use a backlog refinement meeting and include the customer's change requests in the discussion. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 4 | At the start of the team's performing stage | Immediately after the first benefit realization | During the next retrospective ceremony | During the next resource performance review |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Medium | Agile Hybrid | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 4 | Research the requirement and possible consequences, then give the sponsor a recommendation. | Address the requirement through the creation of a quality management plan. | Decline to address the issue, as the new requirement is not part of the project's documented scope. | Ensure that the requirement is documented in the risk register, then ask for further guidance from all stakeholders. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 4 | The functionality was formally approved, so initiate the change management process. | Schedule a meeting to discuss and brainstorm the functionality with the project team and business representative. | Ensure that the issue is addressed by escalating it to the project sponsor, who should discuss it with the representative. | Continue with the current sprint, recognizing that the issue will be identified during the testing phase. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 4 | Provide team training, so the team can do a better job of estimating story points. | Speed up the project by reducing the backlog. | Gain the needed time for story point completion by adding more iterations to the project. | Use burndown charts to evaluate team performance. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 4 | Try using a Kanban board for reviews. | Request that team members implement shorter iterations. | Request that the project owner maximizes the product value. | Engage in a process to manage a reduction in the product backlog. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 4 | Employ third-party specialists to fill the knowledge gap. | Add additional resources via a request to the sponsor. | Add cross-functional internal resources. | Where possible, reduce the sprint backlog. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Agile Hybrid | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 4 | Negotiate payment terms through a meeting with procurement and the contractor. | Authorize the payment by notifying accounts payable and follow up to ensure it was made. | Act according to the agreed upon commitments in the procurement management plan. | Authorize payment only after reviewing forecast spend versus actual spend to see if the actual status allows it. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 4 | Smooth/accommodate Recognize the team members’ feelings regarding the high level of requirements. | Compromise/reconcile Reconsider the distribution of work among the whole team to ensure that the work is equably distributed. | Force/direct Since all requirements were evaluated and organized by the full team, remind the team that the decisions were theirs. | Collaborate/problem solve Meet with the full team in order to discuss requirement allocation and the planning methodology. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 4 | Meet with key stakeholders to discuss ways to reduce some project requirements. | Add team members to work more quickly just this one time in order to satisfy stakeholder requirements. | Refuse to modify the timeline, explaining that scope creep should be discouraged. | Identify agreed-upon tasks in the original project and assign additional duties as needed to meet the new, shorter timeline. |  |  | 1 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 4 | Insist that the project team work a bit harder to complete on time, in order to avoid delaying the work of other teams. | Work with the product owner to reprioritize the iteration backlog, so that it does not delay work by other teams. | Increase the iteration length, and add additional resources to the project team, so that they can meet the appropriate deadlines. | am members to perform to the best of their abilities during the iteration, and engage in a retrospective after completion of the iteration. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Agile Hybrid | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 4 | Gather the project team for a brainstorming session and identify a solution. | Identify the reasons why there are issues with the feature, then address the issue. | Create a list of the pros and cons of the situation to define the impact of the conflict. | Add a neutral party, such as the project sponsor, to function as a negotiator with stakeholders. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 4 | Notify the project sponsor regarding the team’s disapproval and brainstorm a response. | Employ coaching tools and techniques to increase team motivation. | Add a resource with the same skills to replace the key team member. | Notify the change control board (CCB) and discuss possible ways to resolve the issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 4 | Continue with the meeting, and ensure that the concerns are added to the risk register after the meeting is finished. | Continue with the scheduled agenda items after reminding the team member of expected meeting etiquette. Then, solicit feedback about the etiquette expectations. | Remember that a project should not go forward when key team members are in disagreement and use the meeting to discuss the member’s concerns. | Make a short comment to acknowledge the team member’s concerns, continue with the meeting, and meet with the member in private to discuss their concerns. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 4 | Let the project sponsor know that an issue with a technical resource may put the project at risk. | Ensure that upper management is aware of the lack of needed resources which may put the project at risk. | Ask the technical resource manager about the availability of technical resources | Work with a third-party vendor to quickly acquire the needed resource. |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 4 | Creating the project charter | Preparing the scope statement document | Creating a project management plan | Documenting the risk management plan |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA
SINGLE | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 4 | File a change request that includes the agile training that members lack. | Use available funds in the contingency reserve to guarantee training all team members. | Train key team members on main agile topics by hosting virtual training sessions. | Identify the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 2013-09-23 12:25:49 | N | 4 | [5 empty] | NA | NA
SINGLE | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 4 | Create training sessions at the start of the project, so all necessary skills are learned. | List required skills for the project, and organize the project team based on those skills. | Consult with the project sponsor to add training once the lack of a specific skill becomes apparent. | Empower team members to problem solve where skills may be lacking, using the skills they do have. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 2013-09-23 12:29:13 | N | 4 | [5 empty] | NA | NA
SINGLE | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 4 | Invite department managers to participate in the team members’ discussions, in order to identify solutions in a business-like manner. | Request shorter discussion time during each standup, leaving more time for working. | Insert a new team member who will manage obstacles and meetings to discuss possible solutions. | Notify team members that they will be required to shorten all standup meetings and improve their method for identifying solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA
SINGLE | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 4 | Assess the new resource’s communication skills to evaluate their ability to perform acceptably as part of the project team. | Meet with the new resource to discuss their skills and then determine how they can contribute to the project. | Privately ask the program management officer (PMO) to assign a different resource with better skills. | Meet with the functional manager of the new resource to discuss the rumor and see if it is true. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA