## Sheet1
QuestionID | QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
50001 | SINGLE | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 4 | Determine how many resources are required to complete the project according to the project baseline | Adjust the schedule and cost baselines based on past performance | Obtain customer acceptance of project deliverables | Determine whether the project should continue to the next phase |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50002 | SINGLE | A project is considered complete when the : | 4 | SPI is 1 | CPI is 1 | The PV is equal to the AC. | The BAC is equal to the EV. |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50003 | SINGLE | Each project phase is marked by completion of one or more: | 4 | Tasks | Milestones | Deliverables | Life cycles |  |  | 3 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50004 | SINGLE | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 4 | Insuring that plans are produced to implement the project by phases. | Issuing work orders so that financial data can be collected. | Transition the lease of equipment to the owner | Satisfying the contractual obligations |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50005 | SINGLE | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 4 | Administrative closure | As the last task in the project plan | After the project is closed out | When requested by the program manager |  |  | 1 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50006 | SINGLE | Historical records during close-out are useful to __________ and ____________ for future projects: | 4 | Predict trends, highlight problems. | Analyze successes, shortfalls | Analyze strengths, document results | Justify results, set standards |  |  | 1 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50007 | SINGLE | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 4 | The qualify director | The head of the project management office | Vice President Finance | The customer |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50008 | SINGLE | Which of the following would be the most appropriate thing to do during the closing process group? | 4 | Hold Inspections of work packages. | Do Project performance review. | Obtain formal acceptance of the project scope from the customer. | Perform Procurement audits. |  |  | 2 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50009 | SINGLE | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 4 | Shift more of the work to later in the schedule to allow for the customer to get the funds | Stop work | Release part of the project team | Call for a Steering meeting to discuss Next steps |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50010 | SINGLE | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 4 | Complete and closed | Incomplete | Closed | All good to go |  |  | 2 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50011 | SINGLE | All the following are always part of the close project/phase process EXCEPT: | 4 | Complete lesson learned | Updating the archives | Releasing the team | Performing closure of the outside contract |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50012 | SINGLE | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 4 | Authorize the scope change for the next phase | Authorize the budget increases for the next phase based on scope changes | Decreasing scope to maintain the budge | Cancelling the project |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50013 | SINGLE | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 4 | Lesson learned | Updating records | Formal acceptance | Completion of the product features |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50014 | SINGLE | All the following are required to bring a project to closure except:- | 4 | Customer Acceptance | Procurement closure | Team appraisals | Raising Change Request |  |  | 4 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50015 | SINGLE | Two team members in the client organization are currently documenting and validating the product, the other team members are updating records, performing an audit, and archiving lessons learned. What activity are the team members engaged in? | 4 | Close Project/Phase | Close Procurements | Quality Assurance | Quality Control |  |  | 2 | 1 | PMP | Closing | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50016 | SINGLE | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 4 | Null and void. | Incomplete. | Complete. | Waived. |  |  | 3 | 1 | PMP | Closing | Project Procurement Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50017 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 4 | Improve the communication skills of the team for effective communication between team members | Improve the feeling of trust and agreement among team members in order to raise morale, lower conflict and increase team work | Create a dynamic and cohesive team culture to improve both individual and team productivity | Improve knowledge and skills of team members and to stop them from sharing knowledge and expertise |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50018 | SINGLE | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 4 | Thinking, planning, controlling, and monitoring | Planning, doing, briefing, and reviewing | Planning, controlling, tracking, and acting | Planning, organizing, leading, and controlling |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50019 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 4 | Issue Log | Project Staff Assignment | Human Resource Management Plan | Resource Calendars |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50020 | SINGLE | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 4 | Team Performance Assessment | Human Resource Plan | Change Request | Resource Calendars |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50021 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 4 | Hard Skills | Soft Skills | Communication Skills | Ground Rules |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50022 | SINGLE | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 4 | Training | Interpersonal Skills | Recognition and rewards | Co-Location |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50023 | SINGLE | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 4 | Training | Interpersonal Skills | Team-Building activities | Co-Location |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50024 | SINGLE | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 4 | The system of rewards that permits recognition of team members through monetary or nonmonetary awards | That top management will not be interfering with this project as it usually does with other projects | That key decisions have been made and how the key decisions impact the team | Clear, unambiguous goals as to where the project is headed |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50025 | SINGLE | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 4 | Adjourning | Forming | Norming | Selection |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50026 | SINGLE | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 4 | Forming | Storming | Norming | Performing |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50027 | SINGLE | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 4 | Forming | Storming | Performing | Adjourning |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50028 | SINGLE | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 4 | Forming | Norming | Performing | Adjourning |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50029 | SINGLE | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 4 | Forming | Departing | Performing | Adjourning |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-09-19 21:33:40 | N | 7 | [5 empty] | NA | NA
50030 | SINGLE | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 4 | Ground Rules | Co-Location | Team-Building activities | Performing |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50031 | SINGLE | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 4 | Ground Rules | Co-Location | Project Management Software | Performing |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50032 | SINGLE | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 4 | Ground Rules | Co-Location | Tight-Matrix | Reward and Recognition |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50033 | SINGLE | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 4 | Project office, functional divisions, field sites, and corporate offices | Scarce resources, scheduling priorities, and personal work styles | Team building, team integration, functional coordination, and customer coordination | Planning phase, implementation phase, execution phase, and close-out phase |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50034 | SINGLE | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 4 | Project Staff Assignment | Team Performance assessment | Human Resource Plan | Resource Calendars |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50035 | SINGLE | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 4 | Exercise his/her power and authority | Establish a reward and recognition system | Obtain support of functional managers in other locations | Build trust |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50036 | SINGLE | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 4 | Project Organization Chart | Reduced Staff turnover rate | Increased team cohesiveness where team members share information and experiences openly. | Improvement in competencies that help the team perform better as a team. |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50037 | SINGLE | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 4 | Clear organizational structure | Clear aims / goals | Improved individual creativity | Improved monetory rewards |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50038 | SINGLE | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 4 | Plan HR management | Acquire Project Team | Develop Project Team | Manage Project Team |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50039 | SINGLE | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 4 | Recognition and rewards | Training | Team building activities | Co-Location |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50040 | SINGLE | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 4 | War Room | Project Room | Help Room | Management Room |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50041 | SINGLE | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 4 | Bonuses at the end of the project | 360-degree feedback | Job rotation within the project | Release criteria |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50042 | SINGLE | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 4 | Let's work on it and try to find the root problem | Let's gather more information and then analyze it properly | I have another point for discussion if this is too difficult to solve now | I feel we can now come to agreement on this issue |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50043 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50044 | SINGLE | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-09-19 21:34:22 | N | 7 | [5 empty] | NA | NA
50045 | SINGLE | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50046 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50047 | SINGLE | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 4 | Expert power | Legitimate power | Punishment power | Referent power |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50048 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation-Hygiene Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50049 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation-Hygiene Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50050 | SINGLE | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 4 | Theory X | Theory Y | Theory Z | None of the above |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-09-19 18:05:34 | N | 7 | [5 empty] | NA | NA
50051 | SINGLE | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 4 | Theory X | Theory Y | Theory Z | All of the above |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50052 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50053 | SINGLE | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 4 | Plan HR management | Acquire Project Team | Develop Project Team | Manage Project Team |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50054 | SINGLE | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 4 | The project manager | All project team members share the responsibility for enforcing the rules once they are established | The HR team | The project manager and senior team members |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50055 | SINGLE | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 4 | Set limited times and opportunities for discussions; social contacts | Practice what s/he preaches; social contacts | Encourage frank discussions; making promises | Encourage open conversations; politics |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50056 | SINGLE | Ramie is working as Project Manager in Four-Wheeler CORP LTD located in Japan. He is currently in Manage Project Team process, which of the following is NOT an input to the above process? | 4 | Resource Calendars | Performance Reports | Team Performance assessments | Project Staff Assignments |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50057 | SINGLE | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 4 | Activity Resource Requirements | Resource calendars | Work Performance Reports | Training |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50058 | SINGLE | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 4 | Resource Calendars | Work Performance Reports | Team Performance assessments | Project Staff Assignments |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50059 | SINGLE | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 4 | They unfairly get bagged by the best of the team members | They help in inculcating a healthy competition amongst the team | They positively impact team cohesiveness | They negatively impact team cohesiveness |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50060 | SINGLE | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 4 | Resource Breakdown Structure | HR Management plan | Staffing Management Plan | Work Management plan |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50061 | SINGLE | As per Herzberg's theory, which of the following is not a motivating agent? | 4 | Recognition | Advancement in career | Responsibility | Salary |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50062 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 4 | Observation and conversation | Project performance appraisals | Conflict management | All of the above |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-09-19 21:35:54 | N | 7 | [5 empty] | NA | NA
50063 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 4 | Observation and Conversation | Project Performance Appraisals | Team Performance Assessments | Conflict Management |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50064 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 4 | Observation and Conversation | Project Performance Appraisals | Issue Log | Conflict Management |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50065 | SINGLE | When should a Project Manager get involved in resolving a conflict? | 4 | Immediately when Project Manager notices the conflict | If conflict escalates, the Project Manager should help to facilitate a solution | When conflict is about to occur | Project Manager should ignore the conflicts among team members |  |  | 2 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2014-06-05 08:35:11 | N | 7 | [5 empty] | NA | NA
50066 | SINGLE | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 4 | Force | Withdraw | Focus Groups | Avoid |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50067 | SINGLE | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 4 | Laissez-faire | Antipodal | Directive | Democratic |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50068 | SINGLE | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 4 | Observation | Communicating | Avoid | Ground Rules |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50069 | SINGLE | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 4 | Collaborating | Forcing | Smoothing | Observing |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50070 | SINGLE | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 4 | Collaborating | Forcing | Smoothing | Avoid |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50071 | SINGLE | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 4 | Collaborating | Avoid | Smoothing | Compromising |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50072 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 4 | Collaborating | Compromising | Smoothing | Withdrawal |  |  | 4 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50073 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 4 | Collaborating | Compromising | Smoothing | Withdrawal |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50074 | SINGLE | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 4 | Collaborating | Compromising | Forcing | Withdrawal |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50075 | SINGLE | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 4 | Problem Solving | Compromising | Forcing | Collaborating |  |  | 3 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50076 | SINGLE | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 4 | Problem Solving | Compromising | Forcing | Withdrawal |  |  | 1 | 1 | PMP | Executing | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50077 | SINGLE | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 4 | The project statement of work documenting the characteristics of the project | Check historical information on the previous project manufacturing of 2GB capacity memory chip. This information could be helpful since this new project is similar in nature. | Enterprise environmental factors, such as stakeholders risk tolerances and marketplace condition | The project constraints and assumptions to make sure that any significant project risk can be identified and mitigated |  |  | 1 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50078 | SINGLE | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 4 | Weighted scoring models are constrained optimization methods, which are used as a tool and technique in both the Initiating process group processes. | Weighted scoring models are benefit measurement methods, which are used as a tool and technique during the Develop Project Charter process. | Weighted scoring models are a type of mathematical model that can be used both for project selection and vendor selection. | Weighted scoring models are benefit measurement methods and are the least efficient method of project selection. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50079 | SINGLE | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 4 | Project A | Project B | Project C | Project D |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50080 | SINGLE | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 4 | Pay more attention to the stakeholder management | Review the charter more thoroughly, examine the business case for gaps. | Do a more thorough job of solicitation planning | Review the WBS dictionary more thoroughly, look for incomplete descriptions |  |  | 1 | 1 | PMP | Initiating | Project Stakeholder Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50081 | SINGLE | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 4 | Because each individual order is a "temporary endeavor", each order is a project. This is truly a project management. | This is a recurring process. | This is program management since there are multiple projects involved. | Orders incurring revenue over US $100,000 would be considered projects and would involve project management. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50082 | SINGLE | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 4 | The project manager for the project or a company functional manager | A member of the project management team working as per the direction of the project manager | The sponsor or the project manager | A manager or executive in the organization who is higher in the corporate hierarchy than the project manager |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50083 | SINGLE | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 4 | Project Fish'n for Chips, because the costs on Project Picnic are unknown. | Project Picnic, because Project Fish'n for Chips' payback period is two months longer than Project Picnic's. | Project Picnic, because Project Fish'n for Chips' payback period is four months longer than Project Picnic's. | Project Fish'n for Chips, because its payback period is two months shorter than Project Picnic's. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50084 | SINGLE | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 4 | Develop the preliminary project scope statement. | Get the project charter signed. | Start to create project plan | Start the initial project planning process. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50085 | SINGLE | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 4 | Require a preliminary budget to be established and a resource list be put together to alert other managers of the requirements of this project. This should be published and signed by the other managers who are impacted by this project. | Agree with the project sponsor because that person is your boss and has a lot of authority and power in the company. | Require a project charter to be written and signed off by concerned stakeholders before proceeding further. | Suggest that a preliminary scope statement to be written because this will outline the objectives of the project and it will greatly assist in the development of the scope statement in the planning processes. |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50086 | SINGLE | Which of the following is true regarding IRR? | 4 | IRR is a constrained optimization method | IRR assumes reinvestment at the cost of capital. | IRR is the discount rate when NPV is equal to zero. | Both B&C |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50087 | SINGLE | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 4 | Customer request | Technological advancement | Business need | Legal requirement |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50088 | SINGLE | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 4 | Suggest that a preliminary scope statement to be written. | Suggest that a project plan should be written. | Start project immediately because your senior management is asking the same. | Requires a project charter to be written and which needs to be signed off by all stakeholders before proceeding further. |  |  | 4 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50089 | SINGLE | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 4 | The project manager should document the project's objectives and business justification in a project charter document and recommend that the project should proceed. | The project manager should document the business need for the project and recommend that a feasibility study be performed to determine viability of the project. | The project manager knows that the project has a go ahead and should document the project's objectives and known deliverables in a scope statement document. | The project manager should document the high-level product requirements and stakeholder expectations in a scope statement. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50090 | SINGLE | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 4 | Project A, because the potential benefits plus the future operating costs are less in value than the same calculation for Project B. | Project A, because the cost to implement is cheaper than Project B. | Project B, because the potential benefits minus the implementation and future operating costs are greater in value than the same calculation for Project A. | Project B, because the potential benefits minus the costs to implement are greater in value than the same calculation for Project A. |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50091 | SINGLE | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 4 | Constraint | Objective | Requirement | Assumption |  |  | 4 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50092 | SINGLE | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 4 | Project A, because Project B's payback period is 24 months | Project A, because Project B's payback period is 20 months | Either Project A or Project B, because the payback periods are equal | Project A, because Project B's payback period is 21 months |  |  | 4 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50093 | SINGLE | Which of the following is the most complex type of project selection method? | 4 | Random choice method | Benefit measurement | Constrained optimization models | Optimistic random method |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50094 | SINGLE | According to the Guide to PMBoK, the project manager is identified and assigned during which process? | 4 | At the conclusion of the Develop Project Charter process | Prior to starting the Develop Project Charter process | Prior to beginning of the Planning processes | Prior to beginning the Define Scope. |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50095 | SINGLE | You are refining the product description for your company's new line of fit jeans. Which of the following statements is true? | 4 | You are in the Initiation phase of your project and know that the product description will contain more detail at this stage and that a decreasing amount of detail will be added to it as the project progresses. | You are in the Initiation phase of your project and know that the product description will contain less detail at this stage and greater detail would emerge, as the project progresses. | You are in the Planning phase of your project and know that the product description should contain all the details possible at this stage, because this is a critical information for the Planning process. | You are in the Planning processes of your project and know that the product description will contain less detail at this stage and greater detail would emerge , as the project progresses. |  |  | 2 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50096 | SINGLE | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 4 | $130,000 | $30,000 | $60,000 | $35,000 |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50097 | SINGLE | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 4 | 39 months | 41 months | 40 months | 38 months |  |  | 1 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50098 | SINGLE | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 4 | Project Kansas City, because the IRR is the highest | Project Kansas City, because the payback period is the longest | Project New Jersey, because the IRR is the lowest | Project New Jersey, because the payback period is the shortest |  |  | 1 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50099 | SINGLE | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 4 | The division of phases and determining which processes to use in each phase is called tailoring. | The storyboard phase marks the end of the Initiation process group, and the next phase of the project should begin. | The storyboard is a deliverable that marks the end of the phase. The deliverable must be approved before the next phase begins. | All the phases of this project together make up a program. |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50100 | SINGLE | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 4 | The project SOW, which describes the high-level details of the run/walk program | The strategic plan, because you'll want to make sure the project reflects the overall strategic direction of the organization | Historical information on the 10K run project | The organization's PMIS system |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50101 | SINGLE | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 4 | Customer-furnished equipment and facilities | Long-lead procurement items | Data item deliverables | Customer-imposed milestones |  |  | 3 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50102 | SINGLE | Which of the following is the logical flow of any project? | 4 | Planning, Initiating, Executing, Controlling, Closing | Initiating, Planning, Controlling, Executing, Closing | Planning, Initiating, Controlling, Executing, Closing | Initiating, Planning, Executing, Controlling, Closing |  |  | 4 | 1 | PMP | Initiating | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50103 | SINGLE | You are managing a construction project using a firm fixed price (FFP) contract. The contract is structured so that your company will be paid a fee of $85,000 to complete the work. There was a $15,000 overhead cost that your company had to cover. It’s now three months into the project, and your costs have just exceeded $70,000. The project has now consumed the entire fee, and your company will now be forced to pay for all costs on the project from this point forward. What’s the BEST way to describe this situation? | 4 | The project Manager has overspent the budget. | The project is overdrawn | The Project has reached the point of total assumption | The Project has ceased to be a profit centre for the company |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Procurement Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50104 | SINGLE | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 4 | First Validate Scope and then Control Scope | First Control Scope and then Validate Scope | There is not enough information to decide. | Both happen simultaneously. |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50105 | SINGLE | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 4 | Forecasting | Reporting | Manage Communications | Variance analysis |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50106 | SINGLE | In the earned values system, the focus is on "cost of work," which is divided into "scheduled" and "performed" work. This is further defined as "budgeted" and "actual" work. The formula "BCWP - BCWS" provides the ________. | 4 | Cost Difference | Cost Variance | Schedule Difference | Schedule Variance |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50107 | SINGLE | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 4 | Time Series Methods | Casual Methods | Econometric Methods | Judgmental Methods |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50108 | SINGLE | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 4 | Her sponsor has asked for the Planned Value which is INR 3,40,000.00 | Her sponsor has asked for the Earned Value which is INR 3,40,000.00 | Her sponsor has asked Earned Value which is INR 2,97,500.00 | Her sponsor has asked for Planned Value which is INR 2,97,500.00 |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50109 | SINGLE | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 4 | Issue the deliverable and get formal acceptance from the customer | Note the problem in the lessons learned so future projects do not encounter the same problem | Discuss the issue with the customer | Inform the customer that the deliverable will be late |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Quality Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50110 | SINGLE | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process: | 4 | Executing | Monitoring & Controlling | Planning | Closing |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50111 | SINGLE | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 4 | Good customer service | Scope creep | Due diligence | Gold plating |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50112 | SINGLE | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 4 | Project Time Management | Project Scope Management | Project Integration Management | Project Risk Management |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50113 | SINGLE | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 4 | A project coordination position. | Management planning | A change control system | Management attention to scope management |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50114 | SINGLE | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 4 | Bury the cost in the largest cost center available | Inform Project Sponsor | Put the payment in an escrow account | Ignore the payment |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50115 | SINGLE | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for unknown risk events. These adjustments are based on your past project experience when unknown risk events occurred and knocked the project off track. What should you do? | 4 | Document the unknown risk items and calculate the expected monetary value based on probability and impact that result from the occurrence | Apply a general contingency to try to compensate | Determine the unknown risk events and the associated cost, then add the cost to the project budget as reverses | Add a 10% contingency |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50116 | SINGLE | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 4 | The organization is relatively inexperienced in handling risks and wishes to take a cautious approach in handling risk. | The organization perceives that negative risk is a higher possibility than positive risk. | The organization is highly experienced in handling risk and has factored this into a model. | The organization wishes to avoid high-impact threats or exploit high-impact opportunities even if they have relatively low probability. |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50117 | SINGLE | Which of the following is NOT true about configuration management ? | 4 | Configuration management describes the physical characteristics of the product of the project. | Configuration management requires acceptance decisions for all change requests to be made through the CCB. | Change control systems are a subset of the configuration management system. | Configuration management controls changes to the product of the project. |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50118 | SINGLE | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 4 | Perform Quality Assurance | Monitor and Control Project Work | Performance Reporting | Manage Stakeholders |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50119 | SINGLE | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 4 | You've created a forecast, an output of the Monitor and Control Project Work process, using past performance to predict what the project's future condition might look like. | You should recommend a preventive action to reduce the possibility of future project performance veering off track because of this employee's failure to perform this activity. | You should recommend a corrective action to bring the expected future project performance back into line with the project management plan because of this employee's failure to perform this activity. | You might have to request a change to the project schedule as a result of this missed activity. |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50120 | SINGLE | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 4 | Determining that a change occurred | Influencing causes of change | Verifying change | Managing change |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50121 | SINGLE | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 4 | Stakeholder meeting. | Resource leveling activity. | Project audit. | Contract negotiation. |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50122 | SINGLE | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 4 | Create WBS | Scope reporting | Control Scope | Validate Scope |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50123 | SINGLE | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 4 | Preventing changes from occurring | Influencing the factors that result in scope changes to ensure that changes are agreed upon | Determining that a scope change has occurred | Managing the true changes when and if they occur |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50124 | SINGLE | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 4 | Tell him that the scope cannot be changed after the baseline is set. | Prepare a scope change document. | Adapt a passive-aggressive stance and do nothing. | Advise him about the potential impact to the timeline and resource allocation. |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50125 | SINGLE | In all of the following form change requests can occur EXCEPT: | 4 | Externally or internally initiated | Legally mandated or optional | verbal or written initiated | Informal |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50126 | SINGLE | Which of the following BEST describes the impact of scope change requests? | 4 | Either expansion or shrinking of the scope | Only expansion of the scope | Only shrinking of the scope | It depends on the original scope of the project |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50127 | SINGLE | You are a project manager of a project that has many sub-projects. You find it difficult to manage these sub-projects. Thus, to monitor and control these subprojects you have decided to develop a change control management system. Which of the following is a tool and technique used in scope change control? | 4 | Adjusted baseline | Lessons learned | Scope changes | Additional planning |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50128 | SINGLE | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 4 | Set up a meeting with the government to discuss this regulation. | Create a new project plan. | Create a new WBS. | Prepare a change request |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50129 | SINGLE | Which of the following statements are FALSE regarding Monte Carlo analysis? | 4 | Monte Carlo analysis uses Expected Monetory Value (EMV) calculations as one of its inputs | Monte Carlo is used to determine potential project outcomes by simulating the project under different scenarios | Monte Carlo analysis can be used during the Schedule Development and Quantitative Risk Analysis process | Monte Carlo is simulation technique that can help quantify risks associated with the project |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50130 | SINGLE | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 4 | Baselines must be adjusted to reflect the new project costs and schedule. | Corrective actions are taken, which in turn generate change requests that are managed through the scope change control system. | Development and Quantitative Risk Analysis process | Lessons learned are documented so that future projects take into consideration the impact of the change to this WBS. |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50131 | SINGLE | Which of the following is NOT an output of the Manage Communications process? | 4 | Project records | Project presentations | Stakeholder notifications | Work Performance Information |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Communications Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50132 | SINGLE | Variance analysis , trend analysis and earned value management techniques are:- | 4 | Quality control tools and techniques | Performance reporting techniques | Process analysis techniques | Cost benefit analysis techniques |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Communications Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50133 | SINGLE | What should the project manager be most concerned before moving to the final phase? | 4 | Control Quality | Performance reports | Validate Scope | Control Costs |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-09-19 21:38:06 | N | 7 | [5 empty] | NA | NA
50134 | SINGLE | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 4 | Complete the project within eight months without contacting the customer during this time | Complete the project as requested, but Validate its scope with the customer occasionally, throughout the project | Ask management to get in touch with the customer occasionally | Complete the project, but document that the customer did not want contact |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-09-19 21:39:39 | N | 7 | [5 empty] | NA | NA
50135 | SINGLE | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 4 | Contact management for help | Continue with the project | Document the situation | Call a meeting of the team |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50136 | SINGLE | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 4 | The project manager did not obtain adequate resources and did not set a realistic deadline based on resources available. | The project was within budget and time and achieved its objectives. Upper management is responsible for providing adequate resources, and the project manager managed the project well with available resources. | The project should be measured against how successfully it met its charter. This was not done during this project. | The functional manager is responsible for his staff and obtaining adequate resources to meet the schedule once it has been set. The project and project manager achieved all of its goals set forth in the charter. |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50137 | SINGLE | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 4 | Coordinate with team members the overtime necessary to complete the work. | Provide the management with an analysis, which shows how much amount of work of the entire scope can be completed with the available resource | Provide the team with opportunities to do a great job on the work that can be accomplished. | Use more experienced resources to complete the work faster |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50138 | SINGLE | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 4 | Initiate an escalation meeting & renegotiate a new scope of work & new contract | Have a meeting with the customer to identify all the items she thinks were left out of the contract | Contact your senior management and contract department to determine options. Then, schedule a meeting with management and the customer to discuss these options. | Look for ways to save time on other tasks so the new work can be done |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50139 | SINGLE | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 4 | Problem solving | Punishment | Negotiating | Withdrawal |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50140 | SINGLE | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 4 | Look for options with stakeholders using some combination of scaling back work, re-evaluating discretionary dependencies or adding resources. | Evaluate the impact on the company of completing this project late. | Drive the project team to work faster to make up for lost time. | Recalculate the project schedule and distribute it according to the communications management plan. |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50141 | SINGLE | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 4 | Investigate the delay. | Re-evaluate the critical path. | Change the project schedule. | Review the float time for the activity. |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50142 | SINGLE | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following project manager do to integrate this information into the project schedule? | 4 | Lengthen the estimated activity duration for all activities scheduled to occur the following winter. | Reevaluate the revised schedule to determine the potential impact and then raise a Change Request. | Leave the current project schedule unchanged and work the issues as they arise next year. | Make changes to the project management plan in order to maintain the current project schedule. |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Scope Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50143 | SINGLE | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 4 | Crashing always shortens the timeline but often increases risk. | Fast tracking often results in rework, and crashing often results in increased cost. | Crashing is only a viable alternative if earned value analysis indicates that the project is ahead of schedule and under budget. | Fast tracking will result in less parallel activities than crashing the project. |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50144 | SINGLE | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 4 | Her sponsor has asked for the Cost Variance which is USD - 42,500.00 | Her sponsor has asked for the Cost Variance which is USD - 1,27,500.00 | Her sponsor has asked for the Schedule Variance which is USD - 42,500.00 | Her sponsor has asked for the Schedule Variance which is USD - 1,27,500.00 |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-09-23 12:41:08 | N | 7 | [5 empty] | NA | NA
50145 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.7 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.875 | Her sponsor has asked for Schedule Performance Index (SPI) which is 0.7 | Her sponsor has asked for Schedule Performance Index which is 0.875 |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50146 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.7 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.875 | Her sponsor has asked for Schedule Performance Index (SPI) which is 0.7 | Her sponsor has asked for Schedule Performance Index which is 0.875 |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50147 | SINGLE | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of the schedule. |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50148 | SINGLE | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 2 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50149 | SINGLE | Ruby is working as a Project Manager. Upon calculating Earned Value and Present Value, she finds that Earned Value is more than Present Value. What is the status of her project? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50150 | SINGLE | Ruby is working as a Project Manager. Upon calculating Earned Value and Present Value she finds that Earned Value is less than Present Value. What is the status of her project? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 3 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50151 | SINGLE | Which of the following statement is NOT true about CPI and SPI? | 4 | CPI and SPI can be less than 1. | CPI and SPI can be more than 1. | CPI and SPI can be equal to 1. | CPI and SPI can be less than 0. |  |  | 4 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50152 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate to Complete (ETC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 7,89,286.00 | Her sponsor has asked for Estimate to Complete which is INR 7,89,286.00 |  |  | 1 | 1 | PMP | Monitoring & Controlling | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50153 | SINGLE | Which of the following shows roles and responsibilities on your project? | 4 | Bar Chart | Resource Histogram | RACI Matrix | Human resource Plan |  |  | 3 | 1 | PMP | Planning | Project Human Resource Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50154 | SINGLE | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 4 | Sequential Phases Approach | Overlapping relationship approach | Iterative approach | Constrained relationship approach |  |  | 3 | 1 | PMP | Planning | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50155 | SINGLE | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 4 | It is a temporary endeavor undertaken to create unique product, service or result. | It has a definitive beginning and an end | A Project is an ongoing task undertaken to create product, service or result | Both A & B |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50156 | SINGLE | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 4 | Project Manager | Project Coordinator | Project Expediter | Team Member |  |  | 2 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50157 | SINGLE | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 4 | Strong Matrix | Tight Matrix | Weak Matrix | Balanced Matrix |  |  | 1 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50158 | SINGLE | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 4 | Initiating | Executing | Planning | Closing |  |  | 3 | 1 | PMP | Planning | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50159 | SINGLE | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 4 | Risk Management | Time Management | Project Integration Management | Procurement Management |  |  | 2 | 1 | PMP | Planning | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50160 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 4 | Project management decisions needs to be taken from functional managers. | Project Manager has more authority than functional manager | The project team maintains a HOME | Both B & C |  |  | 1 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50161 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 4 | Functional manager has more authority than project manager | The Project team maintains a HOME. | Major decision needs to be made with functional manager approval | All of the above |  |  | 2 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50162 | SINGLE | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 4 | While meeting schedule constraints | While meeting cost constraints | During implementation phase | During design phase |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50163 | SINGLE | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 4 | Project management decisions needs to be taken from functional managers. | Functional Manager has more power than the project manager. | Team reports to functional managers | All of the above |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50164 | SINGLE | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 4 | Project Manager | Project Coordinator | Functional Manager | Both A and C |  |  | 1 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-09-19 21:40:48 | N | 7 | [5 empty] | NA | NA
50165 | SINGLE | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 4 | He shares authority with functional managers | Team members report to him and functional equally | He is acting as project expeditor | Teams are organized around project, once the project gets complete, the team is released |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50166 | SINGLE | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 4 | Teams are organized around project, once the project gets completed, the team is released | The project manager makes all the decisions about budget, schedule, quality and resources | Project manager is responsible for success or failure of the project | Project managers work as an assistant to functional managers |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50167 | SINGLE | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 4 | Expeditors have no authority at all, Coordinator has some authority | Coordinator have no authority at all, Expeditors has some authority | Expeditors are project managers | Coordinators are actually functional managers |  |  | 1 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50168 | SINGLE | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 4 | Organizational Process Assets | Project Management Plan | Network Diagram | Statement of Work |  |  | 1 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50169 | SINGLE | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 4 | Determine Budget | Perform Quality Assurance | Develop Schedule | Define Scope |  |  | 1 | 1 | PMP | Planning | Project Cost Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50170 | SINGLE | Thomas is a project manager working on a construction project near New York City. He is currently working to identify risks that may occur during course of project. Which process group is he currently in? | 4 | Planning | Executing | Monitor and Control | Closing |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50171 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50172 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 2 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50173 | SINGLE | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-09-19 21:41:22 | N | 7 | [5 empty] | NA | NA
50174 | SINGLE | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 4 | Risk Acceptance | Risk tolerance | Risk Avoidance | Both A & C |  |  | 2 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50175 | SINGLE | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 4 | Motivating your own team first | Identifying the problems faced so far and ensure actions are taken | Verifying that the changes are done as per process | Verification of customer's needs and expectations |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50176 | SINGLE | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 4 | Plan Risk Management | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Documentation reviews |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50177 | SINGLE | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 4 | Project Manager | Stakeholders | Team Member | All Project Personnel |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50178 | SINGLE | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 4 | Risks indicating whether funds are sufficient for completing the activities or not? | Risks indicating whether activity duration estimates are correct or not? | Risks indicating whether cost benefit analysis is done for all quality activities? | Both A & B |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50179 | SINGLE | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 4 | Uncertainty in project assumptions | Uncertainty in project cost | Uncertainty in project Schedule | All of the above |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50180 | SINGLE | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 4 | Spent to ensure that there is no extra money shown in the budget. | Reduced to decrease unnecessary extra accounting work | Retained at the balance dollar level | Reduced to reflect the true percentage of work performed. |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50181 | SINGLE | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 4 | Send a formal memorandum to each team member to outline the objectives, the requirements of the team, and the time frame for work | Personally talk to each team member to determine what he/she would like to do on the project and how that can be accommodated | Call a briefing session to set objectives of the management and direct how these objectives will be met | Call a kickoff meeting to present the objectives and open the floor for discussion on how the objectives will be achieved |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50182 | SINGLE | To come out with staffing requirement , Project Manager first needs:- | 4 | Organisation breakdown structure | Responsibility assignment matrix | Resource Breakdown structure | Work breakdown structure |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50183 | SINGLE | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 4 | Ishikawa Diagram | Process flow chart | SWOT analysis | Influence Diagram |  |  | 3 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50184 | SINGLE | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 4 | Expert Judgment | SWOT Analysis | Ishikava Diagrams | Delphi Techniques |  |  | 2 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50185 | SINGLE | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 4 | 45 | 36 | 3 | 50 |  |  | 1 | 1 | PMP | Planning | Project Communications Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50186 | SINGLE | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 4 | 21 | 15 | 132 | 20 |  |  | 1 | 1 | PMP | Planning | Project Communications Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50187 | SINGLE | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 4 | 24 | 21 | 45 | 40 |  |  | 1 | 1 | PMP | Planning | Project Communications Management |  |  | INTERMEDIATE |  | 2013-09-19 21:42:15 | N | 7 | [5 empty] | NA | NA
50188 | SINGLE | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 4 | The project has overlapping phases | The project has sequential phases | The phases of the project has iterative relationship | None of the above |  |  | 2 | 1 | PMP | Planning | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50189 | SINGLE | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 4 | The project has overlapping phases | The project has sequential phases | The phases of the project has iterative relationship | None of the above |  |  | 1 | 1 | PMP | Planning | Project Time Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50190 | SINGLE | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 4 | Temporary | Ongoing | Unique | Definite beginning and end |  |  | 2 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50191 | SINGLE | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 4 | Difference in frames of reference | Lack of credibility or trust | Perceived difference in status | Overly technical approach in communication |  |  | 4 | 1 | PMP | Planning | Project Integration Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50192 | SINGLE | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 4 | Create updates to risk response plan | Create a revised project plan | Perform risk response audits | Perform updated risk identification and analysis |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50193 | SINGLE | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 4 | Avoid, Mitigate | Avoid, Mitigate, Transfer | Avoid, Mitigate, Transfer, Accept | None of the above |  |  | 3 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50194 | SINGLE | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 2 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50195 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 3 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50196 | SINGLE | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 4 | Getting a quantitative analysis of the risk | Determining the risks that can impact the project ,most | Translating the uncertainties at a detailed level into potential impact on objectives expressed at the level of total project. | Determining the decision that yields the greatest expected value |  |  | 4 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50197 | SINGLE | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 2 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-09-19 21:44:53 | N | 7 | [5 empty] | NA | NA
50198 | SINGLE | Jack has just taken over a project. He is now currently identifying risks in the project. He gets all Team member in a room and started to pump out ideas. Which among the following information gathering techniques is he using? | 4 | Brainstorming | Interviews | The Delphi technique | Root Cause Identification |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50199 | SINGLE | You are Project Manager working in IT CORP LTD. You have been assigned a new project of Inventory management System. You are currently identifying risks in your project. You decided to send questionnaires to experts asking about important project risks. Which type of the following information gathering technique is he using? | 4 | Brainstorming | Interviews | The Delphi technique | Root Cause Identification |  |  | 3 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-08-20 11:11:56 | N | 7 | [5 empty] | NA | NA
50200 | SINGLE | You are Project Manager working in IT CORP LTD. You have been assigned a new project on Inventory management System. You are currently identifying risks in your project by looking at plans, requirements and documents from your organization process assets. Which type of the identify risk technique you are using? | 4 | Document Review | Assumption Analysis | SWOT Analysis | Checklist Analysis |  |  | 1 | 1 | PMP | Planning | Project Risk Management |  |  | INTERMEDIATE |  | 2013-09-19 21:46:32 | N | 7 | [5 empty] | NA | NA