## Sheet1
QuestionType | category_id | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Question Category | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
SINGLE | 1 | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | 2 | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA
SINGLE | 3 | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 2020-12-04 23:10 | N | 4 | [5 empty] | NA | NA