## Sheet1
QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Question Category | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
SINGLE | There is a serious defect in the finished product of a project that was completed a few months back and this resulted in a nation-wide campaign to recall the defective product. What would be the best classification for these types of costs? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Sarbanes-Oxley, Sarbox or SOX, is a United States federal law that set new or enhanced standards for all U.S. public company boards, management and public accounting firms. Sarbanes Oxley audit project was performed few days back on the company you work for, and now, as the project manager, you need to close few of the observations for formally closing the contract. A contract can be closed when:- | 4 | Contact senior management to discuss the possibility of reassigning the new resource to a different project. | Schedule time to chat with the new resource to assess their skills and understand their strength level. | Ask the team members to document task-related deficiencies displayed by the resource. | Contact the project sponsor to highlight these concerns and decide on an appropriate response. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 44169.9653
SINGLE | Precise Group - a NYSE listed multinational, manufacturing company with presence in 30 countries worldwide has agreed to implement Enterprise Resource Planning (ERP) System to streamline their operations. This implementation is expected to improve/enhance company's manufacturing, procurement, sales, supply chain & payment systems. The selected partner is expected to implement the system at their headquarters based in Newyork and train the workforce in 30 countries on how to use the system. The project would be considered complete when the : | 4 | Work with key stakeholders to identify project requirements that could be reduced. | Immediately ask project team members to increase the pace of each task within the project. | Ensure that substantial scope creep is included in the original project schedule, so that revised deadlines can be met. | Meet individually with project team members to discuss how aspects of the project can be completed more quickly than planned. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 44169.9653
SINGLE | The Close Project or Phase Process is concerned with the following EXCEPT: | 4 | Meet with both teams separately, and ask them to figure out a way to meet the required deadlines and complete the project on time. | Meet with the product owner to reprioritize the iteration backlog, so that it does not impact other teams or obligations. | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule. | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in lessons learned. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 44169.9653
SINGLE | Precise Group - a NYSE listed multinational, manufacturing company with presence in 30 countries worldwide has agreed to implement Enterprise Resource Planning (ERP) System to streamline their operations. This implementation is expected to improve/enhance company's manufacturing, procurement, sales, supply chain & payment systems. The selected partner is expected to implement the system at their headquarters based in Newyork and train the workforce in 30 countries on how to use the system. Getting sign off on deliverables would be performed using which one of the following processes? | 4 | Invite project team members to a brainstorming session to identify an appropriate response. | Address the issue only after evaluating why these stakeholders are concerned. | Determine the impact of the conflict by listing the pros and cons of the situation. | Ask the project sponsor to act as a neutral party in negotiation with those stakeholders who are dissatisfied. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 44169.9653
SINGLE | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. The overall sign off is taken during which process ? | 4 | Discuss the conflict with the project sponsor and formulate a response. | Replace the key team member with a new resource who has the same skills. | Meet with the change control board (CCB) to discuss the requested change. | Engage in the change management process to resolve the resource issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 44169.9653
SINGLE | Close Project or Phase is the process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. This process is marked complete only on:- | 4 | Update the risk register to document the concerns, then continue with the meeting’s scheduled agenda items. | Recognize that the concern must be fully discussed and resolved prior to continuing with the meeting’s agenda items. | Address the team with a generic reminder about meeting etiquette, then ask if the team wants to use the time to fully discuss the concerns raised during the meeting. | Immediately acknowledge the team member’s concern, continue with the scheduled agenda, then privately meet with the team member to fully understand the concerns expressed. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 44169.9653
SINGLE | You are the Project Manager at a leading E-Commerce Website selling products across various categories including movies, music, games, mobiles, cameras, computers, healthcare and personal products, home appliances and electronics just to name a few. When do you move to project closure? | 4 | Notify the project sponsor about the lack of a technical resource. | Immediately escalate the issue to decision makers in the organization. | Check with the technical resource manager to see if there is an available technical resource. | Since time is short, hire an outside party to meet the need for a technical resource. |  |  | 3 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 44169.9653
SINGLE | Which of the following would be the typically done in closing process group? | 4 | Include agile training for these team members in a change request. | Ensure the project’s contingency reserve can cover agile training for all team members. | Create virtual training sessions for key team members, covering the main agile topics. | Identify and implement the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Medium | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 44169.9653
SINGLE | Which of the following would be the typically done in closing procurements? | 4 | Offer more skill-specific training throughout the project. | Identify required strengths, and organize the team based on those strengths. | Meet with the project sponsor and team members to assign training for specific skills. | Empower team members to problem solve in situations where skills may be lacking. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 44169.9653
SINGLE | The customer has accepted the completed project scope and the archiving of project records is in progress. What is the status of the project? | 4 | Ask team members to invite their managers to standup sessions, in order to find solutions more quickly. | Explain to team members that long discussions take time away from actual work on the project. | Insert a new team member who will manage obstacles and schedule additional meetings to discuss possible solutions. | Tell the team members that they are required to shorten the standup meetings and improve on finding solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Agile Hybrid | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 44169.9653
SINGLE | All the following are always part of the closing process group EXCEPT: | 4 | Required team sign off for each of the constant changes to the requirements | Set aside more resources for product testing after changes are made | Made sure that the customer was aware of the value of demos | Ensured that the team fully participated in developing the project scope |  |  | 3 | 1 | PMP | Process | Project Stakeholder Management |  |  | Medium | Predictive Approach | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 44169.9653
SINGLE | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. What is the basic consideration,sponser has during an end-of-phase review meeting : | 4 | Meet the new demand by adding new resources with the required skills. | Hire a third-party vendor who can provide resources with the needed skills. | Change the distribution of partially dedicated resources with the needed skills. | Meet the new demand by upgrading the existing team members' skills. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 44169.9653
SINGLE | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 4 | Preview the current stakeholder engagement plan for the way to resolve the difficulty. | Schedule a mandatory team meeting which will lead to the creation of a new social contract. | Notify team members that they should submit anonymous recommendations for a new social contract. | Send a survey to team members, requesting suggestions for dealing with the dissatisfaction. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 44169.9653
SINGLE | All the following are required to bring a project to closure except:- | 4 | Immediately schedule a meeting with the stakeholders to review the situation. | Send the change control board (CCB) a change request. | Check with the organization's relevant legal practitioner for guidance. | Review the organization's lessons learned database for precedents and direction. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Two team members from customer organisation are finally validating the product, your team members are updating and archiving lessons learned. What activity are the team members engaged in? | 4 | Help the team create a social contract that will encourage team cohesion. | Suggest that the team engage in multiple team-building events to normalize the team. | Keep the team informed by sending short daily project status updates. | Engage in face-to-face personal conversations with each team member to build relationships. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Organization B is the buyer organization and Organization S is the seller organization. Organization S performed all the work as specified in the SOW and took appropriate sign offs, however, Organization B is not happy with the results. In this case, the contract would be considered as:- | 4 | Renegotiate scope with the project sponsor after examining the work breakdown structure (WBS). | In consultation with the stakeholders and team members, identify the minimum viable product needed for launch. | Determine the schedule performance index (SPI), then escalate the schedule risk to the project sponsor. | Monitor progress using a burndown chart after modifying the schedule baseline to meet stakeholder requirements. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Medium | Predictive Approach | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Great Style - a leading Fashion House based in Milan has decided to outsource its entire IT Infrastructure Support to your company. IT Infrastructure comprises of 4200 network devices, 150 high end servers, high capacity storage & back up devices, 1200 desktops & 500 notebook computers. Your company is required to provide network/technical support to all of their offices across Asia Pacific & Japan. You are the project manager for this project. You are currently focused on improving team performance. Which of the following is NOT an objective of developing a project team? | 4 | Review the bounds of the negotiations for agreement. | Determine the project's ultimate objectives after carefully evaluating project priorities. | Engage in agreement negotiations for better resources. | Ensure that the impact of the unavailability of required resources is fully documented. |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Medium | Predictive Approach | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Great Style - a leading Fashion House based in Milan has decided to outsource its entire IT Infrastructure Support to your company. IT Infrastructure comprises of 4200 network devices, 150 high end servers, high capacity storage & back up devices, 1200 desktops & 500 notebook computers. Your company is required to provide network/technical support to all of their offices across Asia Pacific & Japan. You are the project manager for this project. There is an expert who was also allocated to this project by management. Acquiring people for your project by this method is known as:- | 4 | Reassure the team member about their abilities by reminding them that they were chosen for a reason. | Meet with the team member to discuss where they can contribute, based on their strengths. | Enroll the team member in targeted training to acquire the needed skills for their assigned role. | Schedule weekly touchpoints with the team member to discuss barriers that may impact their work. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | New York Utilities Company has authorized your company to generate electricity from biogas at various Wastewater Treatment Plants. It intends to set up 8 cogeneration plants and 3 hydroelectric generation plants with a combined capacity of over 13 MW. The installed plants have a capacity to generate up to 80,000 MWh electricity per year thereby reducing over 80,000 tones of greenhouse gas emissions, which is equivalent to removing 20,000 cars from the road. At the time of executing, you do not get the resources from in-house and hence have to use people on contract basis. Acquiring people for your project by this method is:- | 4 | Ask the product owner to sit in on the next iteration review meeting to learn more about the development status for the product. | Ask the quality assurance team to identify any mismatches in functionality compared to the initial design. | Ask the development team to rewrite the function so that it matches with the project scope. | Schedule time during the next retrospective session to discuss all corrective actions and ask the project owner to participate in the session. |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Agile Hybrid | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. She had already identified the important people in the chain. She has plan in place which is approved. Ana now needs team members to start working on identified activities. She could get only one resource in her location and had to request the functional head of other region to allocate resources. She finally got the team allocated, however they were not co-located. This type of team can be best classified as:- | 4 | Agree that the functionality would offer a great opportunity, but the proposed addition is out of scope. | Schedule a meeting with the company's management team, and present the customer's request for additional functionality as a good opportunity. | Move forward, using the project's management reserve to add the requested functionality. | Identify an already-developed feature that could be combined with the new functionality and use the combination to meet the customer's request. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. What is the next step Ana should take? | 4 | Work with team members to immediately implement the new approach. | Have the team decide on the appropriate approach, giving them authority to implement their decision and validating their decision in talks with stakeholders. | Discuss the pros and cons of the proposed approach with stakeholders, then select the approach that is best for the team and notify team members. | In order to obtain sponsor buy-in, have the team to benchmark the approach. |  |  | 2 | 1 | PMP | People | Project Integration Management |  |  | Medium | Agile Hybrid | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. She planned to have trainings as per need, in order to do that Ana asked team members to do self evaluation. Which process is being performed? | 4 | Assign one team member to update the project management plan template and document any risk. | Rank the need to update the template according to the business value for the upcoming iterations. | Avoid adding to team distraction by fixing the issue independently. | Document the issue as a new project risk and propose a solution. |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  | Complex | Agile Hybrid | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Objectives of developing a project team include all of the following EXCEPT:- | 4 | Send a request to the project sponsor, asking them to update the project charter then reassign the responsibilities and authorities. | Meet with the project team to add new and improved features to replace the features that were rejected. | Work with stakeholders to create a shared approach that will address the issues of concern. | File a change request with the change control board (CCB) in order to add budget to the baseline. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Agile Hybrid | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. She is currently doing people appraisal to improve people efficiency and plan further trainings or any other means. Which process is being performed? | 4 | Use the Salience model of categorization. | Use the Transformation model of categorization. | Use the Transaction model of categorization. | Use the Collaboration method of categorization. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. Which of the following is NOT a stage of team development? | 4 | Assess the new resource’s ability to perform the necessary work by testing their communication skills with the current project team. | Evaluate the skills of the new resource to see how the resource can provide value to the project. | File a request with the project management office (PMO) manager in order to obtain a better resource. | Address the rumor with the new resource’s functional manager to mitigate any conflict within the project team. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. The team now is in place, however people are still at distance. They started working on some of the allocated work. Which team development stage are they? | 4 | Plan a database development specification, then regularly check to ensure the developer aligns with the specification. | Arrange for review of the data security status on a quarterly basis, and recommend remedial steps if noncompliance is found. | Tell the database developer to submit documentation of data security items and the steps they take to correct items that do not meet specifications. | Add a quality assurance specialist resource to the project team, who will be responsible for monitoring the data security quality of the project. |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Ana was given a project by senior management by virtue of her being the best auditor of network department in last quarter. She was very excited to take this as the end to end responsibility to carry out the 5G installation for selected region. Ana finally had a team in place, however each team member came from a different background and few of them lack necessary skills. The team now is in place. People often get into arguments as personalities are different and looks like the work is taking the hit. Which team development stage are they? | 4 | Obtain a new resource to complete the needed tasks, resulting in less impact on the critical path. | Discuss the situation with the team member, and work with them to identify a practical solution. | Remind the team member that they needed to complete the work package in the agreed-upon timeframe. | Ask the functional manager for assistance communicating with the absent team member. |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Nate is working as a manager in an Export House, hired to automate current manual processes. He hired few developers, designers and testers on contract basis to work on the project deliverables as per the scope. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 4 | Contract with a third-party company that specializes in helping businesses define scope of work on large projects. | Work with project stakeholders to recommend an iterative approach that will then help to define the project's scope. | Construct a project management plan that provides extra time within the schedule, then seek to revise the scope of work. | Suspend final delivery dates for the project in order to have time to revise the schedule once there is clarity on the scope of work |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Nate is working as a manager in an Export House, hired to automate current manual processes. He hired few developers, designers and testers on contract basis to work on the project deliverables as per the scope. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 4 | Rank the importance of each improvement item, then implement actions identified during the last retrospective. | Engage in a cost-benefit analysis that can help predict the profits that could be realized through the use of new technology for the next phase. | Research new technology trends and management tools that have been successful on similar projects. | Use a backlog refinement meeting and include the customer's change requests in the discussion. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 44169.9653 | N | 4 | [5 empty] | NA | NA
SINGLE | Nate is working as a manager in an Export House, hired to automate current manual processes. He hired few developers, designers and testers on contract basis to work on the project deliverables as per the scope. He called for a team meeting and ensured that every team member understand the value of being on time. He puts in fine if team members violate the punctuality. Which team handling technique is been used by Nate? | 4 | At the start of the team's performing stage | Immediately after the first benefit realization | During the next retrospective ceremony | During the next resource performance review |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Medium | Agile Hybrid | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Nate is working as a manager in an Export House, hired to automate current manual processes. He hired few developers, designers and testers on contract basis to work on the project deliverables as per the scope. The team was placed out of various locations in the buildings. However, Nate was not happy with the current output due to more mis-understanding, repetition of the context as why something is being done. What should Nate do to improve team efficiency? | 4 | Research the requirement and possible consequences, then give the sponsor a recommendation. | Address the requirement through the creation of a quality management plan. | Decline to address the issue, as the new requirement is not part of the project's documented scope. | Ensure that the requirement is documented in the risk register, then ask for further guidance from all stakeholders. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Sarbanes–Oxley, Sarbox or SOX, is a United States federal law that set new or enhanced standards for all U.S. public company boards, management and public accounting firms. Sarbanes Oxley audit was performed few days back on the company you work for, and now you need to close few of the observation as per need of SOX audit. Your team is putting lot of efforts, doing overtime to meet the compressed schedule. What should you put in place to motivate team? | 4 | The functionality was formally approved, so initiate the change management process. | Schedule a meeting to discuss and brainstorm the functionality with the project team and business representative. | Ensure that the issue is addressed by escalating it to the project sponsor, who should discuss it with the representative. | Continue with the current sprint, recognizing that the issue will be identified during the testing phase. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 4 | Provide team training, so the team can do a better job of estimating story points. | Speed up the project by reducing the backlog. | Gain the needed time for story point completion by adding more iterations to the project. | Use burndown charts to evaluate team performance. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | You are the Project Manager at a leading E-Commerce Website selling products across various categories including movies, music, games, mobiles, cameras, computers, healthcare and personal products, home appliances and electronics just to name a few. One of the key goal of develop project team is:- | 4 | Try using a Kanban board for reviews. | Request that team members implement shorter iterations. | Request that the project owner maximizes the product value. | Engage in a process to manage a reduction in the product backlog. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. What should Lia to in order to have optimal output from her team? | 4 | Employ third-party specialists to fill the knowledge gap. | Add additional resources via a request to the sponsor. | Add cross-functional internal resources. | Where possible, reduce the sprint backlog. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Agile Hybrid | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team. As per Guide to PMBoK, Where should Lia document this new change/announcement? | 4 | Negotiate payment terms through a meeting with procurement and the contractor. | Authorize the payment by notifying accounts payable and follow up to ensure it was made. | Act according to the agreed upon commitments in the procurement management plan. | Authorize payment only after reviewing forecast spend versus actual spend to see if the actual status allows it. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team. She also put in a system where outstanding performers will receive a CEO's Letter of Recommendation. Where should she look for letter of recommendation template? | 4 | Smooth/accommodate Recognize the team members’ feelings regarding the high level of requirements. | Compromise/reconcile Reconsider the distribution of work among the whole team to ensure that the work is equably distributed. | Force/direct Since all requirements were evaluated and organized by the full team, remind the team that the decisions were theirs. | Collaborate/problem solve Meet with the full team in order to discuss requirement allocation and the planning methodology. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team, and there seems lot of conflict with the way bonus was structured. Everyone on the team had some or the other issue. Since Lia was busy, she told the team to work on the issue themselves and she will pick up the issue later. Which conflict resolution technique did Lia used? | 4 | Meet with key stakeholders to discuss ways to reduce some project requirements. | Add team members to work more quickly just this one time in order to satisfy stakeholder requirements. | Refuse to modify the timeline, explaining that scope creep should be discouraged. | Identify agreed-upon tasks in the original project and assign additional duties as needed to meet the new, shorter timeline. |  |  | 1 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team, and there seems lot of conflict with the way bonus was structured. Everyone on the team had some or the other issue. Lia listened to few selected team members over call and then told the team, "This is such a small issue where we are a great team and have better things to worry about". Which conflict resolution technique did Lia used? | 4 | Insist that the project team work a bit harder to complete on time, in order to avoid delaying the work of other teams. | Work with the product owner to reprioritize the iteration backlog, so that it does not delay work by other teams. | Increase the iteration length, and add additional resources to the project team, so that they can meet the appropriate deadlines. | am members to perform to the best of their abilities during the iteration, and engage in a retrospective after completion of the iteration. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Agile Hybrid | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team, and there seems lot of conflict with the way bonus was structured. Everyone on the team had some or the other issue. Lia asked one senior team member to change the policy as per his views . Which conflict resolution technique did Lia used? | 4 | Gather the project team for a brainstorming session and identify a solution. | Identify the reasons why there are issues with the feature, then address the issue. | Create a list of the pros and cons of the situation to define the impact of the conflict. | Add a neutral party, such as the project sponsor, to function as a negotiator with stakeholders. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team, and there seems lot of conflict with the way bonus was structured. Everyone on the team had some or the other issue. Lia called for a meeting and modified the policy based on everyone's views. Which conflict resolution technique did Lia used? | 4 | Notify the project sponsor regarding the team’s disapproval and brainstorm a response. | Employ coaching tools and techniques to increase team motivation. | Add a resource with the same skills to replace the key team member. | Notify the change control board (CCB) and discuss possible ways to resolve the issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Lia is working with team which was all over the globe, few of her team members were based at USA, few in India and rest in Japan. This was implemented in order to have work done concurrently in all planned location. Lia announced a new Bonus Structure for her team, and there seems lot of conflict with the way bonus was structured. Everyone on the team had some or the other issue. Lia called for a meeting and modified the policy based 20% inputs from USA and 20% inputs from India. This did not leave a very nice feeling amongst team member. Which conflict resolution technique did Lia used? | 4 | Continue with the meeting, and ensure that the concerns are added to the risk register after the meeting is finished. | Continue with the scheduled agenda items after reminding the team member of expected meeting etiquette. Then, solicit feedback about the etiquette expectations. | Remember that a project should not go forward when key team members are in disagreement and use the meeting to discuss the member’s concerns. | Make a short comment to acknowledge the team member’s concerns, continue with the meeting, and meet with the member in private to discuss their concerns. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | Project Team listen to your suggestions as you have a proven track record in their field and been awarded various recognitions at national and international levels. This is an example of: | 4 | Let the project sponsor know that an issue with a technical resource may put the project at risk. | Ensure that upper management is aware of the lack of needed resources which may put the project at risk. | Ask the technical resource manager about the availability of technical resources | Work with a third-party vendor to quickly acquire the needed resource. |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 2013-04-26 04:15:26 | N | 4 | [5 empty] | NA | NA
SINGLE | People listened to your suggestions in the IT Department as you have been seen close to the CIO of the company. This is an example of:- | 4 | Creating the project charter | Preparing the scope statement document | Creating a project management plan | Documenting the risk management plan |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA
SINGLE | LocalOil Corporation Ltd is one of world's largest commercial enterprise. The Companies owns and operates 20 refineries and caters to client in aviation, railways, retail by selling the petrol and lubes to aviation, railways and retail outlet clients. The company had issues dealing with order management. One of the IT software company "SAT Soft" got the project to streamline the same after extensive bidding process. The project was won by vertical unit which catered to Oil and Gas. You - the Project Manager, announced rewards to users/customers in order to get feedback on recently launched portal. This is an example of? | 4 | File a change request that includes the agile training that members lack. | Use available funds in the contingency reserve to guarantee training all team members. | Train key team members on main agile topics by hosting virtual training sessions. | Identify the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 2013-09-23 12:25:49 | N | 4 | [5 empty] | NA | NA
SINGLE | LocalOil Corporation Ltd is one of world's largest commercial enterprise. The Companies owns and operates 20 refineries and caters to client in aviation, railways, retail by selling the petrol and lubes to aviation, railways and retail outlet clients. The company had issues dealing with order management. One of the IT software company "SAT Soft" got the project to streamline the same after extensive bidding process. The project was won by vertical unit which catered to Oil and Gas. You- The Project Manager asked your team to fly to one of the client location in order to get user acceptance sign off. This is an example of? | 4 | Create training sessions at the start of the project, so all necessary skills are learned. | List required skills for the project, and organize the project team based on those skills. | Consult with the project sponsor to add training once the lack of a specific skill becomes apparent. | Empower team members to problem solve where skills may be lacking, using the skills they do have. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 2013-09-23 12:29:13 | N | 4 | [5 empty] | NA | NA
SINGLE | LocalOil Corporation Ltd is one of world's largest commercial enterprise. The Companies owns and operates 20 refineries and caters to client in aviation, railways, retail by selling the petrol and lubes to aviation, railways and retail outlet clients. The company had issues dealing with order management. One of the IT software company "SAT Soft" got the project to streamline the same after extensive bidding process. The project was won by vertical unit which catered to Oil and Gas. You- The Project Manager asked your team to work overnights since the team went out for a movie in office time. This is an example of? | 4 | Invite department managers to participate in the team members’ discussions, in order to identify solutions in a business-like manner. | Request shorter discussion time during each standup, leaving more time for working. | Insert a new team member who will manage obstacles and meetings to discuss possible solutions. | Notify team members that they will be required to shorten all standup meetings and improve their method for identifying solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA
SINGLE |  | 4 | Assess the new resource’s communication skills to evaluate their ability to perform acceptably as part of the project team. | Meet with the new resource to discuss their skills and then determine how they can contribute to the project. | Privately ask the program management officer (PMO) to assign a different resource with better skills. | Meet with the functional manager of the new resource to discuss the rumor and see if it is true. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 2013-04-26 04:15:27 | N | 4 | [5 empty] | NA | NA