## Sheet1
id | category_id | sub_category_id | course_id | title | question_type | marks | dificulty_level | explanation | status | assessment_id | created_at | updated_at | silver_set | gold_set
1 | 1 | 2 | 1 | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 16 | 2146990.1313 |  | 1 | 1
2 | 2 | 2 | 1 | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2146990.1313 |  | 1 | 1
3 | 3 | 3 | 1 | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 16 | 2146990.1313
4 | 3 | 3 | 1 | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 16 | 2146990.1313
5 | 2 | 2 | 1 | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2146990.1313
6 | 2 | 2 | 1 | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 16 | 2146990.1313
7 | 2 | 2 | 1 | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 2146990.1313
8 | 2 | 2 | 1 | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2146990.1313
9 | 2 | 2 | 1 | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 16 | 2146990.1313
10 | 2 | 2 | 1 | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2146990.1313
11 | 3 | 3 | 1 | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 16 | 2146990.1313
12 | 3 | 3 | 1 | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 16 | 2146990.1313
13 | 2 | 2 | 1 | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 16 | 2146990.1313
14 | 2 | 2 | 1 | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 16 | 2146990.1313
15 | 1 | 1 | 1 | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 16 | 2146990.1313
16 | 2 | 2 | 1 | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 16 | 2146990.1313
17 | 1 | 1 | 1 | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 16 | 2146990.1313
18 | 2 | 2 | 1 | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 16 | 2146990.1313
19 | 2 | 2 | 1 | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 16 | 2146990.1313
20 | 3 | 3 | 1 | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2146990.1313
21 | 1 | 1 | 1 | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 16 | 2146990.1313
22 | 2 | 2 | 1 | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2146990.1313
23 | 3 | 3 | 1 | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2146990.1313
24 | 3 | 3 | 1 | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 16 | 2146990.1313
25 | 2 | 2 | 1 | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 16 | 2146990.1313
26 | 2 | 2 | 1 | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 16 | 2146990.1313
27 | 3 | 3 | 1 | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 16 | 2146990.1313
28 | 2 | 2 | 1 | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 16 | 2146990.1313
29 | 2 | 2 | 1 | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 16 | 2146990.1313
30 | 3 | 3 | 1 | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 16 | 2146990.1313
31 | 3 | 3 | 1 | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 16 | 2003250.0118
32 | 3 | 3 | 1 | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 16 | 2003250.0118
33 | 3 | 3 | 1 | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 16 | 2003250.0118
34 | 2 | 2 | 1 | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 16 | 2003250.0118
35 | 3 | 3 | 1 | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 16 | 2003250.0118
36 | 1 | 1 | 1 | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 16 | 2003250.0118
37 | 3 | 3 | 1 | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 16 | 2003250.0118
38 | 2 | 2 | 1 | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 16 | 2003250.0118
39 | 3 | 3 | 1 | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 16 | 2003250.0118
40 | 3 | 3 | 1 | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 16 | 2003250.0118
41 | 2 | 2 | 1 | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 16 | 2003250.0118
42 | 2 | 2 | 1 | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2003250.0118
43 | 2 | 2 | 1 | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2003250.0118
44 | 3 | 3 | 1 | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 16 | 2003250.0118
45 | 3 | 3 | 1 | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 16 | 1970-01-01
46 | 2 | 2 | 1 | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 16 | 2201923.0354
47 | 2 | 2 | 1 | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 0289-12-18 00:52:00
48 | 3 | 3 | 1 | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 16 | 1970-01-01
49 | 2 | 2 | 1 | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 16 | 1970-01-01
50 | 2 | 2 | 1 | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 16 | 1970-01-01
51 | 3 | 3 | 1 | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 1970-01-01
52 | 3 | 3 | 1 | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 16 | 1970-01-01
53 | 3 | 3 | 1 | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 16 | 1970-01-01
54 | 3 | 3 | 1 | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 16 | 1970-01-01
55 | 3 | 3 | 1 | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 16 | 1970-01-01
56 | 3 | 3 | 1 | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 1970-01-01
57 | 3 | 3 | 1 | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 1970-01-01
58 | 3 | 3 | 1 | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 16 | 1970-01-01
59 | 3 | 3 | 1 | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 16 | 1970-01-01
60 | 2 | 2 | 1 | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 16 | 1970-01-01
61 | 2 | 2 | 1 | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 16 | 1970-01-01
62 | 2 | 2 | 1 | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 1970-01-01
63 | 3 | 3 | 1 | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 16 | 1970-01-01
64 | 2 | 2 | 1 | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 16 | 1970-01-01
65 | 2 | 2 | 1 | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 16 | 1970-01-01
66 | 2 | 2 | 1 | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 16 | 1970-01-01
67 | 2 | 2 | 1 | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 16 | 1970-01-01
68 | 3 | 3 | 1 | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 16 | 1970-01-01
69 | 3 | 3 | 1 | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 16 | 1970-01-01
70 | 3 | 3 | 1 | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 16 | 1970-01-01
71 | 3 | 3 | 1 | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 1970-01-01
72 | 3 | 3 | 1 | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 16 | 1970-01-01
73 | 3 | 3 | 1 | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 16 | 1970-01-01
74 | 3 | 3 | 1 | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 16 | 1970-01-01
75 | 3 | 3 | 1 | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 16 | 1970-01-01
76 | 3 | 3 | 1 | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 16 | 1970-01-01
77 | 3 | 3 | 1 | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 1970-01-01
78 | 3 | 3 | 1 | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 16 | 1970-01-01
79 | 3 | 3 | 1 | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 16 | 1970-01-01
80 | 3 | 3 | 1 | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 16 | 1970-01-01
81 | 3 | 3 | 1 | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 16 | 1970-01-01
82 | 2 | 2 | 1 | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 1970-01-01
83 | 2 | 2 | 1 | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 16 | 1970-01-01
84 | 2 | 2 | 1 | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 16 | 1970-01-01
85 | 3 | 3 | 1 | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 16 | 1970-01-01
86 | 2 | 2 | 1 | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 16 | 1970-01-01
87 | 3 | 3 | 1 | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 16 | 1970-01-01
88 | 3 | 3 | 1 | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 16 | 1970-01-01
89 | 3 | 3 | 1 | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 1970-01-01
90 | 2 | 2 | 1 | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 16 | 1970-01-01
91 | 3 | 3 | 1 | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 1970-01-01
92 | 3 | 3 | 1 | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 16 | 1970-01-01
93 | 2 | 2 | 1 | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 16 | 1970-01-01
94 | 1 | 1 | 1 | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 16 | 1970-01-01
95 | 3 | 3 | 1 | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 16 | 1970-01-01
96 | 1 | 1 | 1 | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 16 | 1970-01-01
97 | 2 | 2 | 1 | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 1970-01-01
98 | 3 | 3 | 1 | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 16 | 1970-01-01
99 | 2 | 2 | 1 | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 16 | 1970-01-01
100 | 3 | 3 | 1 | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 16 | 1970-01-01
101 | 2 | 2 | 1 | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 16 | 1970-01-01
102 | 3 | 3 | 1 | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 16 | 1970-01-01
103 | 3 | 3 | 1 | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 1970-01-01
104 | 3 | 3 | 1 | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 1970-01-01
105 | 3 | 3 | 1 | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 1970-01-01
106 | 3 | 3 | 1 | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 16 | 1970-01-01
107 | 3 | 3 | 1 | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 1970-01-01
108 | 3 | 3 | 1 | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 1970-01-01
109 | 3 | 3 | 1 | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 1970-01-01
110 | 3 | 3 | 1 | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 16 | 1970-01-01
111 | 1 | 1 | 1 | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 1970-01-01
112 | 1 | 1 | 1 | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 16 | 1970-01-01
113 | 3 | 3 | 1 | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 16 | 1970-01-01
114 | 3 | 3 | 1 | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 1970-01-01
115 | 2 | 2 | 1 | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 16 | 1970-01-01
116 | 3 | 3 | 1 | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 16 | 1970-01-01
117 | 2 | 2 | 1 | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 16 | 1970-01-01
118 | 2 | 2 | 1 | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 16 | 1970-01-01
119 | 2 | 2 | 1 | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 16 | 1970-01-01
120 | 3 | 3 | 1 | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 1970-01-01
121 | 3 | 3 | 1 | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 16 | 1970-01-01
122 | 3 | 3 | 1 | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 16 | 1970-01-01
123 | 2 | 2 | 1 | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 1970-01-01
124 | 3 | 3 | 1 | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 16 | 1970-01-01
125 | 3 | 3 | 1 | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 1970-01-01
126 | 3 | 3 | 1 | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 1970-01-01
127 | 3 | 3 | 1 | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 16 | 1970-01-01
128 | 3 | 3 | 1 | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 16 | 1970-01-01
129 | 2 | 2 | 1 | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 16 | 1970-01-01
130 | 3 | 3 | 1 | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 1970-01-01
131 | 3 | 3 | 1 | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 1970-01-01
132 | 3 | 3 | 1 | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 16 | 1970-01-01
133 | 2 | 2 | 1 | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 16 | 1970-01-01
134 | 3 | 3 | 1 | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 16 | 1970-01-01
135 | 3 | 3 | 1 | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 16 | 1970-01-01
136 | 3 | 3 | 1 | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 1970-01-01
137 | 3 | 3 | 1 | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 16 | 1970-01-01
138 | 3 | 3 | 1 | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 1970-01-01
139 | 3 | 3 | 1 | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 16 | 1970-01-01
140 | 3 | 3 | 1 | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 16 | 1970-01-01
141 | 3 | 3 | 1 | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 16 | 1970-01-01
142 | 3 | 3 | 1 | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 1970-01-01
143 | 3 | 3 | 1 | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 16 | 1970-01-01
144 | 3 | 3 | 1 | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 1970-01-01
145 | 3 | 3 | 1 | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 16 | 1970-01-01
146 | 3 | 3 | 1 | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 16 | 1970-01-01
147 | 3 | 3 | 1 | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 1970-01-01
148 | 2 | 2 | 1 | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 16 | 1970-01-01
149 | 3 | 3 | 1 | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 1970-01-01
150 | 3 | 3 | 1 | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 1970-01-01
151 | 2 | 2 | 1 | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 16 | 1970-01-01
152 | 3 | 3 | 1 | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 16 | 1970-01-01
153 | 3 | 3 | 1 | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 16 | 1970-01-01
154 | 3 | 3 | 1 | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 16 | 1970-01-01
155 | 3 | 3 | 1 | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 16 | 1970-01-01
156 | 3 | 3 | 1 | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 1970-01-01
157 | 2 | 2 | 1 | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 16 | 1970-01-01
158 | 3 | 3 | 1 | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 16 | 1970-01-01
159 | 2 | 2 | 1 | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 16 | 1970-01-01
160 | 3 | 3 | 1 | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 1970-01-01
161 | 3 | 3 | 1 | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 1970-01-01
162 | 3 | 3 | 1 | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 1970-01-01
163 | 3 | 3 | 1 | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 1970-01-01
164 | 3 | 3 | 1 | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 16 | 1970-01-01
165 | 3 | 3 | 1 | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 1970-01-01
166 | 3 | 3 | 1 | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 1970-01-01
167 | 3 | 3 | 1 | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 16 | 1970-01-01
168 | 2 | 2 | 1 | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 1970-01-01
169 | 3 | 3 | 1 | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 16 | 1970-01-01
170 | 3 | 3 | 1 | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 16 | 1970-01-01
171 | 2 | 2 | 1 | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 1970-01-01
172 | 3 | 3 | 1 | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 1970-01-01
173 | 3 | 3 | 1 | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 16 | 1970-01-01
174 | 3 | 3 | 1 | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 16 | 1970-01-01
175 | 2 | 2 | 1 | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 16 | 1970-01-01
176 | 2 | 2 | 1 | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 16 | 1970-01-01
177 | 3 | 3 | 1 | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 16 | 1970-01-01
178 | 3 | 3 | 1 | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 16 | 1970-01-01
179 | 2 | 2 | 1 | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 1970-01-01
180 | 3 | 3 | 1 | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 16 | 1970-01-01
181 | 2 | 2 | 1 | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 16 | 1970-01-01
182 | 2 | 2 | 1 | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 1970-01-01
183 | 3 | 3 | 1 | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 16 | 1970-01-01
184 | 3 | 3 | 1 | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 1970-01-01
185 | 3 | 3 | 1 | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 16 | 1970-01-01
186 | 2 | 2 | 1 | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 16 | 1970-01-01
187 | 3 | 3 | 1 | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 1970-01-01
188 | 3 | 3 | 1 | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 16 | 1970-01-01
189 | 3 | 3 | 1 | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 16 | 1970-01-01
190 | 3 | 3 | 1 | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 16 | 1970-01-01
191 | 3 | 3 | 1 | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 1970-01-01
192 | 2 | 2 | 1 | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 16 | 1970-01-01
193 | 3 | 3 | 1 | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 1970-01-01
194 | 3 | 3 | 1 | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 16 | 1970-01-01
195 | 3 | 3 | 1 | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 16 | 1970-01-01
196 | 3 | 3 | 1 | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 1970-01-01
197 | 2 | 2 | 1 | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 16 | 2003250.0118
198 | 2 | 2 | 1 | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 16 | 1970-01-01
199 | 3 | 3 | 1 | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 16 | 1970-01-01
200 | 3 | 3 | 1 | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 16 | 1970-01-01
201 | 3 | 3 | 1 | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 1970-01-01
202 | 2 | 2 | 1 | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 16 | 1970-01-01
203 | 3 | 3 | 1 | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 16 | 1970-01-01
204 | 2 | 2 | 1 | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 1970-01-01
205 | 3 | 3 | 1 | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 1970-01-01
206 | 3 | 3 | 1 | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 1970-01-01
207 | 3 | 3 | 1 | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 1970-01-01
208 | 3 | 3 | 1 | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 16 | 1970-01-01
209 | 3 | 3 | 1 | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 1970-01-01
210 | 2 | 2 | 1 | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 1970-01-01
211 | 3 | 3 | 1 | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 16 | 1970-01-01
212 | 3 | 3 | 1 | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 16 | 1970-01-01
213 | 3 | 3 | 1 | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 16 | 1970-01-01
214 | 3 | 3 | 1 | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 16 | 1970-01-01
215 | 3 | 3 | 1 | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 16 | 1970-01-01
216 | 3 | 3 | 1 | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 16 | 1970-01-01
217 | 3 | 3 | 1 | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 16 | 1970-01-01
218 | 3 | 3 | 1 | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 16 | 1970-01-01
219 | 3 | 3 | 1 | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 16 | 1970-01-01
220 | 3 | 3 | 1 | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 16 | 1970-01-01
221 | 3 | 3 | 1 | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 16 | 1970-01-01
222 | 3 | 3 | 1 | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 16 | 1970-01-01
223 | 3 | 3 | 1 | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 16 | 1970-01-01
224 | 3 | 3 | 1 | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 16 | 1970-01-01
225 | 3 | 3 | 1 | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 16 | 1970-01-01
226 | 3 | 3 | 1 | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 16 | 1970-01-01
227 | 2 | 2 | 1 | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 16 | 1970-01-01
228 | 2 | 2 | 1 | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 16 | 1970-01-01
229 | 2 | 2 | 1 | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 16 | 1970-01-01
230 | 2 | 2 | 1 | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 16 | 1970-01-01
231 | 2 | 2 | 1 | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 16 | 1970-01-01
232 | 2 | 2 | 1 | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 16 | 1970-01-01
233 | 2 | 2 | 1 | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 16 | 1970-01-01
234 | 2 | 2 | 1 | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 16 | 1970-01-01
235 | 2 | 2 | 1 | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 16 | 1970-01-01
236 | 2 | 2 | 1 | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 16 | 1970-01-01
237 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 16 | 1970-01-01
238 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 16 | 1970-01-01
239 | 2 | 2 | 1 | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 16 | 1970-01-01
240 | 3 | 3 | 1 | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 16 | 1970-01-01
241 | 2 | 2 | 1 | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 16 | 1970-01-01
242 | 2 | 2 | 1 | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 16 | 1970-01-01
243 | 2 | 2 | 1 | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 16 | 1970-01-01
244 | 2 | 2 | 1 | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 16 | 1970-01-01
245 | 3 | 3 | 1 | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 16 | 1970-01-01
246 | 3 | 3 | 1 | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 16 | 1970-01-01
247 | 2 | 2 | 1 | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 16 | 1970-01-01
248 | 2 | 2 | 1 | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 16 | 1970-01-01
249 | 2 | 2 | 1 | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 16 | 1970-01-01
250 | 3 | 3 | 1 | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 16 | 1970-01-01
251 | 3 | 3 | 1 | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 16 | 1970-01-01
252 | 3 | 3 | 1 | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 16 | 1970-01-01
253 | 3 | 3 | 1 | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 16 | 1970-01-01
254 | 3 | 3 | 1 | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 16 | 1970-01-01
255 | 3 | 3 | 1 | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 16 | 1970-01-01
256 | 2 | 2 | 1 | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 16 | 1970-01-01
257 | 2 | 2 | 1 | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 16 | 1970-01-01
258 | 2 | 2 | 1 | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 16 | 1970-01-01
259 | 2 | 2 | 1 | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 16 | 1970-01-01
260 | 2 | 2 | 1 | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 16 | 1970-01-01
261 | 3 | 3 | 1 | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 16 | 1970-01-01
262 | 3 | 3 | 1 | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 16 | 1970-01-01
263 | 3 | 3 | 1 | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 16 | 1970-01-01
264 | 3 | 3 | 1 | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 16 | 1970-01-01
265 | 3 | 3 | 1 | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 16 | 1970-01-01
266 | 3 | 3 | 1 | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 16 | 1970-01-01
267 | 3 | 3 | 1 | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 16 | 1970-01-01
268 | 2 | 2 | 1 | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 16 | 1970-01-01
269 | 2 | 2 | 1 | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 16 | 1970-01-01
270 | 3 | 3 | 1 | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 16 | 1970-01-01
271 | 3 | 3 | 1 | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 16 | 1970-01-01
272 | 3 | 3 | 1 | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 16 | 1970-01-01
273 | 3 | 3 | 1 | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 16 | 1970-01-01
274 | 3 | 3 | 1 | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 16 | 1970-01-01
275 | 3 | 3 | 1 | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 16 | 1970-01-01
276 | 3 | 3 | 1 | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 16 | 1970-01-01
277 | 3 | 3 | 1 | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 16 | 1970-01-01
278 | 3 | 3 | 1 | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 16 | 1970-01-01
279 | 3 | 3 | 1 | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 16 | 1970-01-01
280 | 3 | 3 | 1 | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 16 | 1970-01-01
281 | 3 | 3 | 1 | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 16 | 1970-01-01
282 | 2 | 2 | 1 | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 16 | 1970-01-01
283 | 2 | 2 | 1 | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 16 | 1970-01-01
284 | 2 | 2 | 1 | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 16 | 1970-01-01
285 | 2 | 2 | 1 | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 16 | 1970-01-01
286 | 2 | 2 | 1 | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 16 | 1970-01-01
287 | 2 | 2 | 1 | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 16 | 1970-01-01
288 | 3 | 3 | 1 | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 16 | 1970-01-01
289 | 3 | 3 | 1 | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 16 | 1970-01-01
290 | 3 | 3 | 1 | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 16 | 1970-01-01
291 | 3 | 3 | 1 | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 16 | 1970-01-01
292 | 3 | 3 | 1 | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 16 | 1970-01-01
293 | 3 | 3 | 1 | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 16 | 1970-01-01
294 | 3 | 3 | 1 | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 16 | 1970-01-01
295 | 3 | 3 | 1 | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 16 | 1970-01-01
296 | 3 | 3 | 1 | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 16 | 1970-01-01
297 | 3 | 3 | 1 | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 16 | 1970-01-01
298 | 3 | 3 | 1 | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 16 | 1970-01-01
299 | 3 | 3 | 1 | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 1970-01-01
300 | 3 | 3 | 1 | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 16 | 1970-01-01
301 | 3 | 3 | 1 | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 16 | 1970-01-01
302 | 3 | 3 | 1 | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 1970-01-01
303 | 3 | 3 | 1 | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 16 | 1970-01-01
304 | 3 | 3 | 1 | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 16 | 1970-01-01
305 | 3 | 3 | 1 | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 16 | 1970-01-01
306 | 3 | 3 | 1 | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 16 | 1970-01-01
307 | 3 | 3 | 1 | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 16 | 1970-01-01
308 | 3 | 3 | 1 | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 16 | 1970-01-01
309 | 3 | 3 | 1 | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 16 | 1970-01-01
310 | 3 | 3 | 1 | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 16 | 1970-01-01
311 | 3 | 3 | 1 | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 16 | 1970-01-01
312 | 3 | 3 | 1 | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 16 | 1970-01-01
313 | 3 | 3 | 1 | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 1970-01-01
314 | 3 | 3 | 1 | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 1970-01-01
315 | 3 | 3 | 1 | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 16 | 1970-01-01
316 | 3 | 3 | 1 | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 16 | 1970-01-01
317 | 3 | 3 | 1 | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 16 | 1970-01-01
318 | 3 | 3 | 1 | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 16 | 1970-01-01
319 | 3 | 3 | 1 | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 16 | 1970-01-01
320 | 3 | 3 | 1 | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 16 | 1970-01-01
321 | 3 | 3 | 1 | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 16 | 1970-01-01
322 | 3 | 3 | 1 | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 16 | 1970-01-01
323 | 3 | 3 | 1 | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 16 | 1970-01-01
324 | 3 | 3 | 1 | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 16 | 1970-01-01
325 | 3 | 3 | 1 | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 16 | 1970-01-01
326 | 3 | 3 | 1 | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 16 | 1970-01-01
327 | 3 | 3 | 1 | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 16 | 1970-01-01
328 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 16 | 1970-01-01
329 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 16 | 1970-01-01
330 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 16 | 1970-01-01
331 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 16 | 1970-01-01
332 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 16 | 1970-01-01
333 | 3 | 3 | 1 | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 16 | 1970-01-01
334 | 3 | 3 | 1 | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 16 | 1970-01-01
335 | 3 | 3 | 1 | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 16 | 1970-01-01
336 | 3 | 3 | 1 | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 16 | 1970-01-01
337 | 3 | 3 | 1 | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 16 | 1970-01-01
338 | 3 | 3 | 1 | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 16 | 1970-01-01
339 | 3 | 3 | 1 | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 16 | 1970-01-01
340 | 3 | 3 | 1 | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 16 | 1970-01-01
341 | 3 | 3 | 1 | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 16 | 1970-01-01
342 | 3 | 3 | 1 | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 16 | 1970-01-01
343 | 3 | 3 | 1 | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 16 | 1970-01-01
344 | 3 | 3 | 1 | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 16 | 1970-01-01
345 | 3 | 3 | 1 | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 16 | 1970-01-01
346 | 3 | 3 | 1 | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 16 | 1970-01-01
347 | 3 | 3 | 1 | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 16 | 1970-01-01
348 | 3 | 3 | 1 | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 16 | 1970-01-01
349 | 3 | 3 | 1 | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 16 | 1970-01-01
350 | 3 | 3 | 1 | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 16 | 1970-01-01
351 | 3 | 3 | 1 | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 16 | 1970-01-01
352 | 3 | 3 | 1 | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 16 | 1970-01-01
353 | 3 | 3 | 1 | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 16 | 1970-01-01
354 | 3 | 3 | 1 | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 16 | 1970-01-01
355 | 3 | 3 | 1 | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 16 | 1970-01-01
356 | 3 | 3 | 1 | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 16 | 1970-01-01
357 | 3 | 3 | 1 | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 16 | 1970-01-01
358 | 1 | 1 | 1 | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 16 | 1970-01-01
359 | 3 | 3 | 1 | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 16 | 1970-01-01
360 | 3 | 3 | 1 | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 16 | 1970-01-01
361 | 3 | 3 | 1 | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 16 | 1970-01-01
362 | 3 | 3 | 1 | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 16 | 1970-01-01
363 | 3 | 3 | 1 | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 16 | 1970-01-01
364 | 3 | 3 | 1 | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 16 | 1970-01-01
365 | 3 | 3 | 1 | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 16 | 1970-01-01
366 | 3 | 3 | 1 | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 16 | 1970-01-01
367 | 3 | 3 | 1 | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 16 | 1970-01-01
368 | 2 | 2 | 1 | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 16 | 1970-01-01
369 | 2 | 2 | 1 | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 16 | 1970-01-01
370 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 16 | 1970-01-01
371 | 2 | 2 | 1 | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 16 | 1970-01-01
372 | 2 | 2 | 1 | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 16 | 1970-01-01
373 | 2 | 2 | 1 | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 16 | 1970-01-01
374 | 2 | 2 | 1 | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 16 | 1970-01-01
375 | 2 | 2 | 1 | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 16 | 1970-01-01
376 | 2 | 2 | 1 | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 16 | 1970-01-01
377 | 2 | 2 | 1 | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 16 | 1970-01-01
378 | 2 | 2 | 1 | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 16 | 1970-01-01
379 | 2 | 2 | 1 | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 16 | 1970-01-01
380 | 2 | 2 | 1 | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 16 | 1970-01-01
381 | 2 | 2 | 1 | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 16 | 1970-01-01
382 | 2 | 2 | 1 | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 16 | 1970-01-01
383 | 2 | 2 | 1 | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 16 | 1970-01-01
384 | 2 | 2 | 1 | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 16 | 1970-01-01
385 | 2 | 2 | 1 | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 16 | 1970-01-01
386 | 2 | 2 | 1 | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 16 | 1970-01-01
387 | 2 | 2 | 1 | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 16 | 1970-01-01
388 | 2 | 2 | 1 | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 16 | 1970-01-01
389 | 2 | 2 | 1 | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 16 | 1970-01-01
390 | 2 | 2 | 1 | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 16 | 1970-01-01
391 | 2 | 2 | 1 | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 16 | 1970-01-01
392 | 2 | 2 | 1 | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 16 | 1970-01-01
393 | 2 | 2 | 1 | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 16 | 1970-01-01
394 | 2 | 2 | 1 | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 16 | 1970-01-01
395 | 2 | 2 | 1 | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 16 | 1970-01-01
396 | 2 | 2 | 1 | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 16 | 1970-01-01
397 | 2 | 2 | 1 | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 16 | 1970-01-01
398 | 2 | 2 | 1 | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 16 | 1970-01-01
399 | 2 | 2 | 1 | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 16 | 1970-01-01
400 | 2 | 2 | 1 | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 16 | 1970-01-01
401 | 2 | 2 | 1 | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 16 | 1970-01-01
402 | 2 | 2 | 1 | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 16 | 1970-01-01
403 | 2 | 2 | 1 | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 16 | 1970-01-01
404 | 2 | 2 | 1 | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 16 | 1970-01-01
405 | 2 | 2 | 1 | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 16 | 1970-01-01
406 | 2 | 2 | 1 | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 16 | 1970-01-01
407 | 2 | 2 | 1 | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 16 | 1970-01-01
408 | 2 | 2 | 1 | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 16 | 1970-01-01
409 | 2 | 2 | 1 | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 16 | 1970-01-01
410 | 2 | 2 | 1 | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 16 | 1970-01-01
411 | 2 | 2 | 1 | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 16 | 1970-01-01
412 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 16 | 1970-01-01
413 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 16 | 1970-01-01
414 | 2 | 2 | 1 | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 16 | 1970-01-01
415 | 2 | 2 | 1 | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 16 | 1970-01-01
416 | 2 | 2 | 1 | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 16 | 1970-01-01
417 | 2 | 2 | 1 | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 16 | 1970-01-01
418 | 2 | 2 | 1 | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 16 | 1970-01-01
419 | 2 | 2 | 1 | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 16 | 1970-01-01
420 | 2 | 2 | 1 | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 16 | 1970-01-01
421 | 2 | 2 | 1 | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 16 | 1970-01-01
422 | 2 | 2 | 1 | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 16 | 1970-01-01
423 | 2 | 2 | 1 | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 16 | 1970-01-01
424 | 2 | 2 | 1 | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 16 | 1970-01-01
425 | 2 | 2 | 1 | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 16 | 1970-01-01
426 | 2 | 2 | 1 | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 16 | 1970-01-01
427 | 1 | 1 | 1 | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 16 | 1970-01-01
428 | 3 | 3 | 1 | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 16 | 1970-01-01
429 | 1 | 1 | 1 | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 16 | 1970-01-01
430 | 3 | 3 | 1 | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 16 | 1970-01-01
431 | 1 | 1 | 1 | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 16 | 1970-01-01
432 | 1 | 1 | 1 | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 16 | 1970-01-01
433 | 1 | 1 | 1 | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 16 | 1970-01-01
434 | 3 | 3 | 1 | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 16 | 1970-01-01
435 | 3 | 3 | 1 | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 16 | 1970-01-01
436 | 1 | 1 | 1 | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 16 | 1970-01-01
437 | 1 | 1 | 1 | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 16 | 1970-01-01
438 | 3 | 3 | 1 | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 16 | 1970-01-01
439 | 1 | 1 | 1 | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 16 | 1970-01-01
440 | 1 | 1 | 1 | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 16 | 1970-01-01
441 | 3 | 3 | 1 | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 16 | 1970-01-01
442 | 1 | 1 | 1 | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 16 | 1970-01-01
443 | 1 | 1 | 1 | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 16 | 1970-01-01
444 | 1 | 1 | 1 | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 16 | 1970-01-01
445 | 1 | 1 | 1 | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 16 | 1970-01-01
446 | 1 | 1 | 1 | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 16 | 1970-01-01
447 | 3 | 3 | 1 | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 16 | 1970-01-01
448 | 1 | 1 | 1 | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 16 | 1970-01-01
449 | 3 | 3 | 1 | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 16 | 1970-01-01
450 | 3 | 3 | 1 | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 16 | 1970-01-01
451 | 3 | 3 | 1 | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 16 | 1970-01-01
452 | 3 | 3 | 1 | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 16 | 1970-01-01
453 | 3 | 3 | 1 | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 16 | 1970-01-01
454 | 3 | 3 | 1 | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 16 | 1970-01-01
455 | 2 | 2 | 1 | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 16 | 1970-01-01
456 | 3 | 3 | 1 | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 16 | 1970-01-01
457 | 3 | 3 | 1 | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 16 | 1970-01-01
458 | 3 | 3 | 1 | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 16 | 1970-01-01
459 | 3 | 3 | 1 | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 16 | 1970-01-01
460 | 1 | 1 | 1 | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 16 | 1970-01-01
461 | 3 | 3 | 1 | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 16 | 1970-01-01
462 | 3 | 3 | 1 | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 16 | 1970-01-01
463 | 3 | 3 | 1 | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 16 | 1970-01-01
464 | 3 | 3 | 1 | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 16 | 1970-01-01
465 | 3 | 3 | 1 | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 16 | 1970-01-01
466 | 3 | 3 | 1 | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 16 | 1970-01-01
467 | 3 | 3 | 1 | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 16 | 1970-01-01
468 | 3 | 3 | 1 | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 16 | 1970-01-01
469 | 3 | 3 | 1 | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 16 | 1970-01-01
470 | 3 | 3 | 1 | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 16 | 1970-01-01
471 | 3 | 3 | 1 | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 16 | 1970-01-01
472 | 3 | 3 | 1 | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 16 | 1970-01-01
473 | 3 | 3 | 1 | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 16 | 1970-01-01
474 | 3 | 3 | 1 | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 16 | 1970-01-01
475 | 3 | 3 | 1 | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 16 | 1970-01-01
476 | 3 | 3 | 1 | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 16 | 1970-01-01
477 | 3 | 3 | 1 | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 16 | 1970-01-01
478 | 3 | 3 | 1 | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 16 | 1970-01-01
479 | 3 | 3 | 1 | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 16 | 1970-01-01
480 | 3 | 3 | 1 | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 16 | 1970-01-01
481 | 3 | 3 | 1 | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 16 | 1970-01-01
482 | 3 | 3 | 1 | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 16 | 1970-01-01
483 | 2 | 2 | 1 | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 16 | 1970-01-01
484 | 3 | 3 | 1 | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 16 | 1970-01-01
485 | 3 | 3 | 1 | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 16 | 1970-01-01
486 | 3 | 3 | 1 | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 16 | 1970-01-01
487 | 3 | 3 | 1 | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 16 | 1970-01-01
488 | 3 | 3 | 1 | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 16 | 1970-01-01
489 | 3 | 3 | 1 | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 16 | 1970-01-01
490 | 3 | 3 | 1 | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 16 | 1970-01-01
491 | 3 | 3 | 1 | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 16 | 1970-01-01
492 | 3 | 3 | 1 | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 16 | 1970-01-01
493 | 3 | 3 | 1 | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 16 | 1970-01-01
494 | 3 | 3 | 1 | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 16 | 1970-01-01
495 | 3 | 3 | 1 | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 16 | 1970-01-01
496 | 3 | 3 | 1 | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 16 | 1970-01-01
497 | 2 | 2 | 1 | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 16 | 1970-01-01
498 | 3 | 3 | 1 | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 16 | 1970-01-01
499 | 3 | 3 | 1 | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 16 | 1970-01-01
500 | 3 | 3 | 1 | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 16 | 1970-01-01
501 | 2 | 2 | 1 | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 16 | 1970-01-01
502 | 3 | 3 | 1 | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 16 | 1970-01-01
503 | 3 | 3 | 1 | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 16 | 1970-01-01
504 | 2 | 2 | 1 | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 16 | 1970-01-01
505 | 3 | 3 | 1 | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 16 | 1970-01-01
506 | 3 | 3 | 1 | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 16 | 1970-01-01
507 | 2 | 2 | 1 | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 16 | 1970-01-01
508 | 2 | 2 | 1 | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 16 | 1970-01-01
509 | 2 | 2 | 1 | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 16 | 1970-01-01
510 | 2 | 2 | 1 | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 16 | 1970-01-01
511 | 2 | 2 | 1 | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 16 | 1970-01-01
512 | 3 | 3 | 1 | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 16 | 1970-01-01
513 | 3 | 3 | 1 | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 16 | 1970-01-01
514 | 3 | 3 | 1 | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 16 | 1970-01-01
515 | 3 | 3 | 1 | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 16 | 1970-01-01
516 | 3 | 3 | 1 | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 16 | 1970-01-01
517 | 3 | 3 | 1 | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 16 | 1970-01-01
518 | 3 | 3 | 1 | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 16 | 1970-01-01
519 | 3 | 3 | 1 | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 16 | 1970-01-01
520 | 3 | 3 | 1 | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 16 | 1970-01-01
521 | 3 | 3 | 1 | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 16 | 1970-01-01
522 | 3 | 3 | 1 | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 16 | 1970-01-01
523 | 3 | 3 | 1 | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 16 | 1970-01-01
524 | 3 | 3 | 1 | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 16 | 1970-01-01
525 | 3 | 3 | 1 | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 16 | 1970-01-01
526 | 3 | 3 | 1 | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 16 | 1970-01-01
527 | 3 | 3 | 1 | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 16 | 1970-01-01
528 | 3 | 3 | 1 | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 16 | 1970-01-01
529 | 3 | 3 | 1 | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 16 | 1970-01-01
530 | 3 | 3 | 1 | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 16 | 1970-01-01
531 | 3 | 3 | 1 | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 16 | 1970-01-01
532 | 3 | 3 | 1 | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 16 | 1970-01-01
533 | 3 | 3 | 1 | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 16 | 1970-01-01
534 | 2 | 2 | 1 | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 16 | 1970-01-01
535 | 3 | 3 | 1 | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 16 | 1970-01-01
536 | 3 | 3 | 1 | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 16 | 1970-01-01
537 | 3 | 3 | 1 | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 16 | 1970-01-01
538 | 3 | 3 | 1 | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 16 | 1970-01-01
539 | 3 | 3 | 1 | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 16 | 1970-01-01
540 | 3 | 3 | 1 | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 16 | 1970-01-01
541 | 3 | 3 | 1 | Jack has just taken over a project. He is now currently identifying risks in the project. He gets all Team member in a room and started to pump out ideas. Which among the following information gathering techniques is he using? | 1 | 1 |  | Jack is encouraging all teams members to provide their inputs in identifying risks. He is not masking the identity of the team members as in Delphi technique. He is not conducting 1 on 1s as in interviews. | 0 | 16 | 1970-01-01
542 | 3 | 3 | 1 | You are Project Manager working in IT CORP LTD. You have been assigned a new project of Inventory management System. You are currently identifying risks in your project. You decided to send questionnaires to experts asking about important project risks. Which type of the following information gathering technique is he using? | 1 | 1 |  | You are gathering inputs without other team members knowing the identity of the team member providing inputs which is Delphi technique. | 0 | 16 | 1970-01-01
543 | 3 | 3 | 1 | You are Project Manager working in IT CORP LTD. You have been assigned a new project on Inventory management System. You are currently identifying risks in your project by looking at plans, requirements and documents from your organization process assets. Which type of the identify risk technique you are using? | 1 | 1 |  | You are reviewing historical information of similar past projects to identify potential risks that may be applicable for the current project. You are using "Document Review" technique. You are neither analyzing assumptions/constraints nor doing SWOT analysis not analyzing checklists | 0 | 16 | 1970-01-01
544 | 2 | 2 | 1 | Carrie is a project manager. Two of her team members are engaged in a conflict and they reach out to her for a solution. However, one team member wants them to resolve the conflict on their own. Which conflict resolution Technique did she use? | 1 | 1 | Complex | When one stakeholder wants to resolve the confict any of the techniques can be used. In the current scenario all the others barring Withdrawal need both stakeholders to be engaged. Hence most logical choice is Withdrawal. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 1970-01-01
545 | 1 | 1 | 1 | Project A has a NPV of $1 million and IRR of 4%. Project B hand a NPV of $1.1 million and IRR of $3.9%. Which project should you select? | 1 | 1 | High Complex | Since the IRR are almost similar one should choose the project with greater NPV. Best choice in this situation will be Project B. | 0 | 16 | 1970-01-01
546 | 3 | 3 | 1 | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 1970-01-01
547 | 3 | 3 | 1 | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 16 | 1970-01-01
548 | 3 | 3 | 1 | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 1970-01-01
549 | 2 | 2 | 1 | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 1970-01-01
550 | 2 | 2 | 1 | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 1970-01-01
551 | 3 | 3 | 1 | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 16 | 1970-01-01
552 | 3 | 3 | 1 | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 16 | 1970-01-01
553 | 2 | 2 | 1 | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 1970-01-01
554 | 3 | 3 | 1 | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 16 | 1970-01-01
555 | 2 | 2 | 1 | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 16 | 1970-01-01
556 | 3 | 3 | 1 | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 16 | 1970-01-01
557 | 3 | 3 | 1 | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 16 | 1970-01-01
558 | 1 | 1 | 1 | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 16 | 1970-01-01
559 | 2 | 2 | 1 | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 16 | 1970-01-01
560 | 3 | 3 | 1 | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 16 | 1970-01-01
561 | 1 | 1 | 1 | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 16 | 1970-01-01
562 | 3 | 3 | 1 | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 16 | 1970-01-01
563 | 3 | 3 | 1 | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 16 | 1970-01-01
564 | 3 | 3 | 1 | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 1970-01-01
565 | 3 | 3 | 1 | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 16 | 1970-01-01
566 | 3 | 3 | 1 | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 16 | 1970-01-01
567 | 2 | 2 | 1 | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 16 | 1970-01-01
568 | 3 | 3 | 1 | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 16 | 1970-01-01
569 | 3 | 3 | 1 | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 1970-01-01
570 | 2 | 2 | 1 | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 16 | 1970-01-01
571 | 3 | 3 | 1 | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 1970-01-01
572 | 3 | 3 | 1 | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 16 | 1970-01-01
573 | 3 | 3 | 1 | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 16 | 1970-01-01
574 | 2 | 2 | 1 | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 16 | 1970-01-01
575 | 3 | 3 | 1 | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 1970-01-01
576 | 3 | 3 | 1 | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 16 | 1970-01-01
577 | 3 | 3 | 1 | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 16 | 1970-01-01
578 | 2 | 2 | 1 | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 16 | 1970-01-01
579 | 2 | 2 | 1 | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 16 | 1970-01-01
580 | 3 | 3 | 1 | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 16 | 1970-01-01
581 | 2 | 2 | 1 | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 16 | 1970-01-01
582 | 3 | 3 | 1 | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 16 | 1970-01-01
583 | 3 | 3 | 1 | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 16 | 1970-01-01
584 | 3 | 3 | 1 | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 16 | 1970-01-01
585 | 2 | 2 | 1 | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 1970-01-01
586 | 2 | 2 | 1 | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 16 | 1970-01-01
587 | 3 | 3 | 1 | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 1970-01-01
588 | 3 | 3 | 1 | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 16 | 1970-01-01
589 | 3 | 3 | 1 | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 16 | 1970-01-01
590 | 3 | 3 | 1 | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 16 | 1970-01-01
591 | 3 | 3 | 1 | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 1970-01-01
592 | 3 | 3 | 1 | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 1970-01-01
593 | 3 | 3 | 1 | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 1970-01-01
594 | 3 | 3 | 1 | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 1970-01-01
595 | 2 | 2 | 1 | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 1970-01-01
596 | 3 | 3 | 1 | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 16 | 1970-01-01
597 | 3 | 3 | 1 | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 16 | 1970-01-01
598 | 3 | 3 | 1 | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 16 | 1970-01-01
599 | 3 | 3 | 1 | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 1970-01-01
600 | 2 | 2 | 1 | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 1970-01-01
601 | 3 | 3 | 1 | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 16 | 1970-01-01
602 | 3 | 3 | 1 | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 16 | 1970-01-01
603 | 3 | 3 | 1 | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 16 | 1970-01-01
604 | 3 | 3 | 1 | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 16 | 1970-01-01
605 | 2 | 2 | 1 | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 16 | 1970-01-01
606 | 3 | 3 | 1 | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 1970-01-01
607 | 2 | 2 | 1 | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 16 | 1970-01-01
608 | 2 | 2 | 1 | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 16 | 1970-01-01
609 | 3 | 3 | 1 | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 1970-01-01
610 | 3 | 3 | 1 | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 16 | 1970-01-01
611 | 2 | 2 | 1 | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 16 | 1970-01-01
612 | 2 | 2 | 1 | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 1970-01-01
613 | 3 | 3 | 1 | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 16 | 1970-01-01
614 | 2 | 2 | 1 | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 1970-01-01
615 | 3 | 3 | 1 | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 16 | 1970-01-01
616 | 2 | 2 | 1 | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 16 | 1970-01-01
617 | 2 | 2 | 1 | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 1970-01-01
618 | 3 | 3 | 1 | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 1970-01-01
619 | 2 | 2 | 1 | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 16 | 1970-01-01
620 | 3 | 3 | 1 | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 16 | 1970-01-01
621 | 3 | 3 | 1 | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 16 | 1970-01-01
622 | 2 | 2 | 1 | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 16 | 1970-01-01
623 | 2 | 2 | 1 | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 16 | 1970-01-01
624 | 3 | 3 | 1 | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 16 | 1970-01-01
625 | 3 | 3 | 1 | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 1970-01-01
626 | 2 | 2 | 1 | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 1970-01-01
627 | 2 | 2 | 1 | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 16 | 1970-01-01
628 | 3 | 3 | 1 | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 16 | 1970-01-01
629 | 3 | 3 | 1 | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 1970-01-01
630 | 3 | 3 | 1 | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 16 | 1970-01-01
631 | 2 | 2 | 1 | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 16 | 1970-01-01
632 | 3 | 3 | 1 | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 16 | 1970-01-01
633 | 2 | 2 | 1 | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 16 | 1970-01-01
634 | 3 | 3 | 1 | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 16 | 1970-01-01
635 | 1 | 1 | 1 | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 16 | 1970-01-01
636 | 3 | 3 | 1 | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 16 | 1970-01-01
637 | 2 | 2 | 1 | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 16 | 1970-01-01
638 | 3 | 3 | 1 | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 1970-01-01
639 | 3 | 3 | 1 | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 16 | 1970-01-01
640 | 3 | 3 | 1 | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 16 | 1970-01-01
641 | 3 | 3 | 1 | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 1970-01-01
642 | 3 | 3 | 1 | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 16 | 1970-01-01
643 | 2 | 2 | 1 | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 16 | 1970-01-01
644 | 2 | 2 | 1 | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 16 | 1970-01-01
645 | 3 | 3 | 1 | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 16 | 1970-01-01
646 | 3 | 3 | 1 | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 16 | 1970-01-01
647 | 3 | 3 | 1 | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 16 | 1970-01-01
648 | 2 | 2 | 1 | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 16 | 1970-01-01
649 | 3 | 3 | 1 | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 16 | 1970-01-01
650 | 2 | 2 | 1 | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 16 | 1970-01-01
651 | 2 | 2 | 1 | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 16 | 1970-01-01
652 | 3 | 3 | 1 | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 16 | 1970-01-01
653 | 3 | 3 | 1 | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 16 | 1970-01-01
654 | 1 | 1 | 1 | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 16 | 1970-01-01
655 | 1 | 1 | 1 | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 16 | 1970-01-01
656 | 3 | 3 | 1 | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 16 | 1970-01-01
657 | 3 | 3 | 1 | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 16 | 1970-01-01
658 | 3 | 3 | 1 | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 16 | 1970-01-01
659 | 1 | 1 | 1 | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 16 | 1970-01-01
660 | 2 | 2 | 1 | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 16 | 1970-01-01
661 | 2 | 2 | 1 | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 16 | 1970-01-01
662 | 2 | 2 | 1 | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 16 | 1970-01-01
663 | 1 | 1 | 1 | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 16 | 1970-01-01
664 | 1 | 1 | 1 | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 16 | 1970-01-01
665 | 3 | 3 | 1 | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 16 | 1970-01-01
666 | 2 | 2 | 1 | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 16 | 1970-01-01
667 | 2 | 2 | 1 | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 16 | 1970-01-01
668 | 3 | 3 | 1 | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 16 | 1970-01-01
669 | 3 | 3 | 1 | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 16 | 1970-01-01
670 | 3 | 3 | 1 | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 16 | 1970-01-01
671 | 3 | 3 | 1 | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 16 | 1970-01-01
672 | 2 | 2 | 1 | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 16 | 1970-01-01
673 | 3 | 3 | 1 | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 16 | 1970-01-01
674 | 3 | 3 | 1 | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 16 | 1970-01-01
675 | 2 | 2 | 1 | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 16 | 1970-01-01
676 | 3 | 3 | 1 | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 16 | 1970-01-01
677 | 1 | 1 | 1 | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 16 | 1970-01-01
678 | 2 | 2 | 1 | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 16 | 1970-01-01
679 | 3 | 3 | 1 | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 16 | 1970-01-01
680 | 2 | 2 | 1 | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 16 | 1970-01-01
681 | 1 | 1 | 1 | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 16 | 1970-01-01
682 | 3 | 3 | 1 | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 16 | 1970-01-01
683 | 1 | 1 | 1 | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 16 | 1970-01-01
684 | 3 | 3 | 1 | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 16 | 1970-01-01
685 | 1 | 1 | 1 | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 16 | 1970-01-01
686 | 3 | 3 | 1 | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 16 | 1970-01-01
687 | 2 | 2 | 1 | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 16 | 1970-01-01
688 | 2 | 2 | 1 | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 16 | 1970-01-01 | 2021-04-15 11:57
698 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 16 | 2147021.3813
699 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2147021.3813
700 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 16 | 2147021.3813
701 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 16 | 2147021.3813
702 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2147021.3813
703 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 16 | 2147021.3813
704 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 2147021.3813
705 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2147021.3813
706 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 16 | 2147021.3813
707 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2147021.3813
708 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 16 | 2147021.3813
709 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 16 | 2147021.3813
710 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 16 | 2147021.3813
711 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 16 | 2147021.3813
712 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 16 | 2147021.3813
713 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 16 | 2147021.3813
714 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 16 | 2147021.3813
715 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 16 | 2147021.3813
716 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 16 | 2147021.3813
717 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2147021.3813
718 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 16 | 2147021.3813
719 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2147021.3813
720 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2147021.3813
721 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 16 | 2147021.3813
722 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 16 | 2147021.3813
723 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 16 | 2147021.3813
724 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 16 | 2147021.3813
725 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 16 | 2147021.3813
726 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 16 | 2147021.3813
727 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 16 | 2147021.3813
728 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 16 | 2013-04-26 04:15
729 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 16 | 2013-04-26 04:15
730 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 16 | 2013-04-26 04:15
731 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 16 | 2013-04-26 04:15
732 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 16 | 2013-04-26 04:15
733 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 16 | 2013-04-26 04:15
734 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 16 | 2013-04-26 04:15
735 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 16 | 2013-04-26 04:15
736 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 16 | 2013-04-26 04:15
737 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 16 | 2013-04-26 04:15
738 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 16 | 2013-04-26 04:15
739 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2013-04-26 04:15
740 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2013-04-26 04:15
741 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 16 | 2013-04-26 04:15
742 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 16 | 2013-04-26 04:15
743 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 16 | 2013-09-23 12:26
744 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2013-09-23 12:29
745 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 16 | 2013-04-26 04:15
746 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 16 | 2013-04-26 04:15
747 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 16 | 2021-05-04 15:14
748 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. | 0 | 16 | 2021-05-04 15:14
749 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 16 | 2021-05-04 15:14
750 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 16 | 2021-05-04 15:14
751 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:14
752 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 16 | 2021-05-04 15:14
753 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 2021-05-04 15:14
754 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2021-05-04 15:14
755 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 16 | 2021-05-04 15:14
756 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:14
757 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 16 | 2021-05-04 15:14
758 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 16 | 2021-05-04 15:14
759 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 16 | 2021-05-04 15:14
760 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 16 | 2021-05-04 15:14
761 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 16 | 2021-05-04 15:14
762 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 16 | 2021-05-04 15:14
763 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 16 | 2021-05-04 15:14
764 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 16 | 2021-05-04 15:14
765 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 16 | 2021-05-04 15:14
766 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:14
767 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 16 | 2021-05-04 15:14
768 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:14
769 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:14
770 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 16 | 2021-05-04 15:14
771 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 16 | 2021-05-04 15:14
772 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 16 | 2021-05-04 15:14
773 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 16 | 2021-05-04 15:14
774 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 16 | 2021-05-04 15:14
775 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 16 | 2021-05-04 15:14
776 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 16 | 2021-05-04 15:14
777 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 16 | 2021-05-04 15:14
778 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 16 | 2021-05-04 15:14
779 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 16 | 2021-05-04 15:14
780 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 16 | 2021-05-04 15:14
781 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 16 | 2021-05-04 15:14
782 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 16 | 2021-05-04 15:14
783 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 16 | 2021-05-04 15:14
784 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 16 | 2021-05-04 15:14
785 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 16 | 2021-05-04 15:14
786 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 16 | 2021-05-04 15:14
787 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:14
788 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:14
789 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:14
790 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 16 | 2021-05-04 15:14
791 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 16 | 2021-05-04 15:14
792 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 16 | 2021-05-04 15:14
793 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:14
794 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 16 | 2021-05-04 15:14
795 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 16 | 2021-05-04 15:14
796 | 2 | 2 |  | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 16 | 2021-05-04 15:14
797 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:14
798 | 3 | 3 |  | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 16 | 2021-05-04 15:14
799 | 3 | 3 |  | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 16 | 2021-05-04 15:14
800 | 3 | 3 |  | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 16 | 2021-05-04 15:14
801 | 3 | 3 |  | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 16 | 2021-05-04 15:14
802 | 3 | 3 |  | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:14
803 | 3 | 3 |  | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:14
804 | 3 | 3 |  | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 16 | 2021-05-04 15:14
805 | 3 | 3 |  | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 16 | 2021-05-04 15:14
806 | 2 | 2 |  | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 16 | 2021-05-04 15:14
807 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 16 | 2021-05-04 15:14
808 | 2 | 2 |  | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:14
809 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 16 | 2021-05-04 15:14
810 | 2 | 2 |  | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 16 | 2021-05-04 15:14
811 | 2 | 2 |  | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 16 | 2021-05-04 15:14
812 | 2 | 2 |  | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 16 | 2021-05-04 15:14
813 | 2 | 2 |  | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 16 | 2021-05-04 15:14
814 | 3 | 3 |  | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 16 | 2021-05-04 15:14
815 | 3 | 3 |  | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 16 | 2021-05-04 15:14
816 | 3 | 3 |  | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 16 | 2021-05-04 15:14
817 | 3 | 3 |  | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:14
818 | 3 | 3 |  | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 16 | 2021-05-04 15:14
819 | 3 | 3 |  | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 16 | 2021-05-04 15:14
820 | 3 | 3 |  | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 16 | 2021-05-04 15:14
821 | 3 | 3 |  | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 16 | 2021-05-04 15:14
822 | 3 | 3 |  | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 16 | 2021-05-04 15:14
823 | 3 | 3 |  | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:14
824 | 3 | 3 |  | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 16 | 2021-05-04 15:14
825 | 3 | 3 |  | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 16 | 2021-05-04 15:14
826 | 3 | 3 |  | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 16 | 2021-05-04 15:14
827 | 3 | 3 |  | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 16 | 2021-05-04 15:14
828 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:14
829 | 2 | 2 |  | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 16 | 2021-05-04 15:14
830 | 2 | 2 |  | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 16 | 2021-05-04 15:14
831 | 3 | 3 |  | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 16 | 2021-05-04 15:14
832 | 2 | 2 |  | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 16 | 2021-05-04 15:14
833 | 3 | 3 |  | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 16 | 2021-05-04 15:14
834 | 3 | 3 |  | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 16 | 2021-05-04 15:14
835 | 3 | 3 |  | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:14
836 | 2 | 2 |  | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 16 | 2021-05-04 15:14
837 | 3 | 3 |  | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:14
838 | 3 | 3 |  | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 16 | 2021-05-04 15:14
839 | 2 | 2 |  | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 16 | 2021-05-04 15:14
840 | 1 | 1 |  | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 16 | 2021-05-04 15:14
841 | 3 | 3 |  | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 16 | 2021-05-04 15:14
842 | 1 | 1 |  | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 16 | 2021-05-04 15:14
843 | 2 | 2 |  | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:14
844 | 3 | 3 |  | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 16 | 2021-05-04 15:14
845 | 2 | 2 |  | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 16 | 2021-05-04 15:14
846 | 3 | 3 |  | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 16 | 2021-05-04 15:14
847 | 2 | 2 |  | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 16 | 2021-05-04 15:14
848 | 3 | 3 |  | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 16 | 2021-05-04 15:14
849 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:14
850 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:14
851 | 3 | 3 |  | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:14
852 | 3 | 3 |  | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 16 | 2021-05-04 15:14
853 | 3 | 3 |  | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:14
854 | 3 | 3 |  | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:14
855 | 3 | 3 |  | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:14
856 | 3 | 3 |  | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 16 | 2021-05-04 15:14
857 | 1 | 1 |  | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:14
858 | 1 | 1 |  | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 16 | 2021-05-04 15:14
859 | 3 | 3 |  | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 16 | 2021-05-04 15:14
860 | 3 | 3 |  | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:14
861 | 2 | 2 |  | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 16 | 2021-05-04 15:14
862 | 3 | 3 |  | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 16 | 2021-05-04 15:14
863 | 2 | 2 |  | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 16 | 2021-05-04 15:14
864 | 2 | 2 |  | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 16 | 2021-05-04 15:14
865 | 2 | 2 |  | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 16 | 2021-05-04 15:14
866 | 3 | 3 |  | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:14
867 | 3 | 3 |  | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 16 | 2021-05-04 15:14
868 | 3 | 3 |  | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 16 | 2021-05-04 15:14
869 | 2 | 2 |  | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:14
870 | 3 | 3 |  | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 16 | 2021-05-04 15:14
871 | 3 | 3 |  | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:14
872 | 3 | 3 |  | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:14
873 | 3 | 3 |  | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 16 | 2021-05-04 15:14
874 | 3 | 3 |  | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 16 | 2021-05-04 15:14
875 | 2 | 2 |  | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 16 | 2021-05-04 15:14
876 | 3 | 3 |  | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:14
877 | 3 | 3 |  | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:14
878 | 3 | 3 |  | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 16 | 2021-05-04 15:14
879 | 2 | 2 |  | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 16 | 2021-05-04 15:14
880 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 16 | 2021-05-04 15:14
881 | 3 | 3 |  | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 16 | 2021-05-04 15:14
882 | 3 | 3 |  | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:14
883 | 3 | 3 |  | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 16 | 2021-05-04 15:14
884 | 3 | 3 |  | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:14
885 | 3 | 3 |  | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 16 | 2021-05-04 15:14
886 | 3 | 3 |  | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 16 | 2021-05-04 15:14
887 | 3 | 3 |  | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 16 | 2021-05-04 15:14
888 | 3 | 3 |  | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:14
889 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 16 | 2021-05-04 15:14
890 | 3 | 3 |  | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:14
891 | 3 | 3 |  | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 16 | 2021-05-04 15:14
892 | 3 | 3 |  | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 16 | 2021-05-04 15:14
893 | 3 | 3 |  | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:14
894 | 2 | 2 |  | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 16 | 2021-05-04 15:14
895 | 3 | 3 |  | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:14
896 | 3 | 3 |  | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:14
897 | 2 | 2 |  | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 16 | 2021-05-04 15:14
898 | 3 | 3 |  | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 16 | 2021-05-04 15:14
899 | 3 | 3 |  | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 16 | 2021-05-04 15:14
900 | 3 | 3 |  | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 16 | 2021-05-04 15:14
901 | 3 | 3 |  | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 16 | 2021-05-04 15:14
902 | 3 | 3 |  | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:14
903 | 2 | 2 |  | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 16 | 2021-05-04 15:14
904 | 3 | 3 |  | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 16 | 2021-05-04 15:14
905 | 2 | 2 |  | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 16 | 2021-05-04 15:14
906 | 3 | 3 |  | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:14
907 | 3 | 3 |  | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:14
908 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:14
909 | 3 | 3 |  | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:14
910 | 3 | 3 |  | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 16 | 2021-05-04 15:14
911 | 3 | 3 |  | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:14
912 | 3 | 3 |  | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:14
913 | 3 | 3 |  | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 16 | 2021-05-04 15:14
914 | 2 | 2 |  | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:14
915 | 3 | 3 |  | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 16 | 2021-05-04 15:14
916 | 3 | 3 |  | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 16 | 2021-05-04 15:14
917 | 2 | 2 |  | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:14
918 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:14
919 | 3 | 3 |  | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 16 | 2021-05-04 15:14
920 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 16 | 2021-05-04 15:14
921 | 2 | 2 |  | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 16 | 2021-05-04 15:14
922 | 2 | 2 |  | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 16 | 2021-05-04 15:14
923 | 3 | 3 |  | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 16 | 2021-05-04 15:14
924 | 3 | 3 |  | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 16 | 2021-05-04 15:14
925 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:14
926 | 3 | 3 |  | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 16 | 2021-05-04 15:14
927 | 2 | 2 |  | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 16 | 2021-05-04 15:14
928 | 2 | 2 |  | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:14
929 | 3 | 3 |  | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 16 | 2021-05-04 15:14
930 | 3 | 3 |  | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:14
931 | 3 | 3 |  | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 16 | 2021-05-04 15:14
932 | 2 | 2 |  | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 16 | 2021-05-04 15:14
933 | 3 | 3 |  | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:14
934 | 3 | 3 |  | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 16 | 2021-05-04 15:14
935 | 3 | 3 |  | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 16 | 2021-05-04 15:14
936 | 3 | 3 |  | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 16 | 2021-05-04 15:14
937 | 3 | 3 |  | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:14
938 | 2 | 2 |  | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 16 | 2021-05-04 15:14
939 | 3 | 3 |  | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:14
940 | 3 | 3 |  | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 16 | 2021-05-04 15:14
941 | 3 | 3 |  | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 16 | 2021-05-04 15:14
942 | 3 | 3 |  | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:14
943 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 16 | 2021-05-04 15:14
944 | 2 | 2 |  | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 16 | 2021-05-04 15:14
945 | 3 | 3 |  | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 16 | 2021-05-04 15:14
946 | 3 | 3 |  | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 16 | 2021-05-04 15:14
947 | 3 | 3 |  | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:14
948 | 2 | 2 |  | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 16 | 2021-05-04 15:14
949 | 3 | 3 |  | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 16 | 2021-05-04 15:14
950 | 2 | 2 |  | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:14
951 | 3 | 3 |  | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:14
952 | 3 | 3 |  | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:14
953 | 3 | 3 |  | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:14
954 | 3 | 3 |  | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 16 | 2021-05-04 15:14
955 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:14
956 | 2 | 2 |  | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:14
957 | 3 | 3 |  | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 16 | 2021-05-04 15:14
958 | 3 | 3 |  | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 16 | 2021-05-04 15:14
959 | 3 | 3 |  | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 16 | 2021-05-04 15:14
960 | 3 | 3 |  | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 16 | 2021-05-04 15:14
961 | 3 | 3 |  | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 16 | 2021-05-04 15:14
962 | 3 | 3 |  | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 16 | 2021-05-04 15:14
963 | 3 | 3 |  | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 16 | 2021-05-04 15:14
964 | 3 | 3 |  | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 16 | 2021-05-04 15:14
965 | 3 | 3 |  | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 16 | 2021-05-04 15:14
966 | 3 | 3 |  | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 16 | 2021-05-04 15:14
967 | 3 | 3 |  | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 16 | 2021-05-04 15:14
968 | 3 | 3 |  | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 16 | 2021-05-04 15:14
969 | 3 | 3 |  | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 16 | 2021-05-04 15:14
970 | 3 | 3 |  | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 16 | 2021-05-04 15:14
971 | 3 | 3 |  | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 16 | 2021-05-04 15:14
972 | 3 | 3 |  | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 16 | 2021-05-04 15:14
973 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 16 | 2021-05-04 15:14
974 | 2 | 2 |  | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 16 | 2021-05-04 15:14
975 | 2 | 2 |  | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 16 | 2021-05-04 15:14
976 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 16 | 2021-05-04 15:14
977 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 16 | 2021-05-04 15:14
978 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 16 | 2021-05-04 15:14
979 | 2 | 2 |  | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 16 | 2021-05-04 15:14
980 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 16 | 2021-05-04 15:14
981 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 16 | 2021-05-04 15:14
982 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 16 | 2021-05-04 15:14
983 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 16 | 2021-05-04 15:14
984 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 16 | 2021-05-04 15:14
985 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 16 | 2021-05-04 15:14
986 | 3 | 3 |  | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 16 | 2021-05-04 15:14
987 | 2 | 2 |  | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 16 | 2021-05-04 15:14
988 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 16 | 2021-05-04 15:14
989 | 2 | 2 |  | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 16 | 2021-05-04 15:14
990 | 2 | 2 |  | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 16 | 2021-05-04 15:14
991 | 3 | 3 |  | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 16 | 2021-05-04 15:14
992 | 3 | 3 |  | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 16 | 2021-05-04 15:14
993 | 2 | 2 |  | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 16 | 2021-05-04 15:14
994 | 2 | 2 |  | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 16 | 2021-05-04 15:14
995 | 2 | 2 |  | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 16 | 2021-05-04 15:14
996 | 3 | 3 |  | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 16 | 2021-05-04 15:14
997 | 3 | 3 |  | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 16 | 2021-05-04 15:14
998 | 3 | 3 |  | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 16 | 2021-05-04 15:14
999 | 3 | 3 |  | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 16 | 2021-05-04 15:14
1000 | 3 | 3 |  | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 16 | 2021-05-04 15:14
1001 | 3 | 3 |  | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 16 | 2021-05-04 15:14
1002 | 2 | 2 |  | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 16 | 2021-05-04 15:14
1003 | 2 | 2 |  | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 16 | 2021-05-04 15:14
1004 | 2 | 2 |  | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 16 | 2021-05-04 15:14
1005 | 2 | 2 |  | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 16 | 2021-05-04 15:14
1006 | 2 | 2 |  | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 16 | 2021-05-04 15:14
1007 | 3 | 3 |  | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 16 | 2021-05-04 15:14
1008 | 3 | 3 |  | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 16 | 2021-05-04 15:14
1009 | 3 | 3 |  | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 16 | 2021-05-04 15:14
1010 | 3 | 3 |  | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 16 | 2021-05-04 15:14
1011 | 3 | 3 |  | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 16 | 2021-05-04 15:14
1012 | 3 | 3 |  | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 16 | 2021-05-04 15:14
1013 | 3 | 3 |  | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 16 | 2021-05-04 15:14
1014 | 2 | 2 |  | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 16 | 2021-05-04 15:14
1015 | 2 | 2 |  | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 16 | 2021-05-04 15:14
1016 | 3 | 3 |  | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 16 | 2021-05-04 15:14
1017 | 3 | 3 |  | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 16 | 2021-05-04 15:14
1018 | 3 | 3 |  | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 16 | 2021-05-04 15:14
1019 | 3 | 3 |  | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 16 | 2021-05-04 15:14
1020 | 3 | 3 |  | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 16 | 2021-05-04 15:14
1021 | 3 | 3 |  | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 16 | 2021-05-04 15:14
1022 | 3 | 3 |  | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 16 | 2021-05-04 15:14
1023 | 3 | 3 |  | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 16 | 2021-05-04 15:14
1024 | 3 | 3 |  | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 16 | 2021-05-04 15:14
1025 | 3 | 3 |  | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 16 | 2021-05-04 15:14
1026 | 3 | 3 |  | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 16 | 2021-05-04 15:14
1027 | 3 | 3 |  | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 16 | 2021-05-04 15:14
1028 | 2 | 2 |  | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 16 | 2021-05-04 15:14
1029 | 2 | 2 |  | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 16 | 2021-05-04 15:14
1030 | 2 | 2 |  | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 16 | 2021-05-04 15:14
1031 | 2 | 2 |  | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 16 | 2021-05-04 15:14
1032 | 2 | 2 |  | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 16 | 2021-05-04 15:14
1033 | 2 | 2 |  | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 16 | 2021-05-04 15:14
1034 | 3 | 3 |  | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 16 | 2021-05-04 15:14
1035 | 3 | 3 |  | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 16 | 2021-05-04 15:14
1036 | 3 | 3 |  | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 16 | 2021-05-04 15:14
1037 | 3 | 3 |  | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 16 | 2021-05-04 15:14
1038 | 3 | 3 |  | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 16 | 2021-05-04 15:14
1039 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 16 | 2021-05-04 15:14
1040 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 16 | 2021-05-04 15:14
1041 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 16 | 2021-05-04 15:14
1042 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 16 | 2021-05-04 15:14
1043 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 16 | 2021-05-04 15:14
1044 | 3 | 3 |  | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 16 | 2021-05-04 15:14
1045 | 3 | 3 |  | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:14
1046 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 16 | 2021-05-04 15:14
1047 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 16 | 2021-05-04 15:14
1048 | 3 | 3 |  | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:14
1049 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 16 | 2021-05-04 15:14
1050 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 16 | 2021-05-04 15:14
1051 | 3 | 3 |  | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 16 | 2021-05-04 15:14
1052 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 16 | 2021-05-04 15:14
1053 | 3 | 3 |  | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 16 | 2021-05-04 15:14
1054 | 3 | 3 |  | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 16 | 2021-05-04 15:14
1055 | 3 | 3 |  | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:14
1056 | 3 | 3 |  | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:14
1057 | 3 | 3 |  | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 16 | 2021-05-04 15:14
1058 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 16 | 2021-05-04 15:14
1059 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:14
1060 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:14
1061 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 16 | 2021-05-04 15:14
1062 | 3 | 3 |  | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 16 | 2021-05-04 15:14
1063 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 16 | 2021-05-04 15:14
1064 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 16 | 2021-05-04 15:14
1065 | 3 | 3 |  | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 16 | 2021-05-04 15:14
1066 | 3 | 3 |  | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 16 | 2021-05-04 15:14
1067 | 3 | 3 |  | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 16 | 2021-05-04 15:14
1068 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 16 | 2021-05-04 15:14
1069 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 16 | 2021-05-04 15:14
1070 | 3 | 3 |  | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 16 | 2021-05-04 15:14
1071 | 3 | 3 |  | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 16 | 2021-05-04 15:14
1072 | 3 | 3 |  | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 16 | 2021-05-04 15:14
1073 | 3 | 3 |  | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 16 | 2021-05-04 15:14
1074 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 16 | 2021-05-04 15:14
1075 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 16 | 2021-05-04 15:14
1076 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 16 | 2021-05-04 15:14
1077 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 16 | 2021-05-04 15:14
1078 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 16 | 2021-05-04 15:14
1079 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 16 | 2021-05-04 15:14
1080 | 3 | 3 |  | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 16 | 2021-05-04 15:14
1081 | 3 | 3 |  | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 16 | 2021-05-04 15:14
1082 | 3 | 3 |  | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 16 | 2021-05-04 15:14
1083 | 3 | 3 |  | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 16 | 2021-05-04 15:14
1084 | 3 | 3 |  | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 16 | 2021-05-04 15:14
1085 | 3 | 3 |  | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 16 | 2021-05-04 15:14
1086 | 3 | 3 |  | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 16 | 2021-05-04 15:14
1087 | 3 | 3 |  | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 16 | 2021-05-04 15:14
1088 | 3 | 3 |  | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 16 | 2021-05-04 15:14
1089 | 3 | 3 |  | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 16 | 2021-05-04 15:14
1090 | 3 | 3 |  | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 16 | 2021-05-04 15:14
1091 | 3 | 3 |  | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 16 | 2021-05-04 15:14
1092 | 3 | 3 |  | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 16 | 2021-05-04 15:14
1093 | 3 | 3 |  | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 16 | 2021-05-04 15:14
1094 | 3 | 3 |  | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 16 | 2021-05-04 15:14
1095 | 3 | 3 |  | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 16 | 2021-05-04 15:14
1096 | 3 | 3 |  | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 16 | 2021-05-04 15:14
1097 | 3 | 3 |  | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 16 | 2021-05-04 15:14
1098 | 3 | 3 |  | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 16 | 2021-05-04 15:14
1099 | 3 | 3 |  | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 16 | 2021-05-04 15:14
1100 | 3 | 3 |  | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 16 | 2021-05-04 15:14
1101 | 3 | 3 |  | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 16 | 2021-05-04 15:14
1102 | 3 | 3 |  | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 16 | 2021-05-04 15:14
1103 | 3 | 3 |  | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 16 | 2021-05-04 15:14
1104 | 1 | 1 |  | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 16 | 2021-05-04 15:14
1105 | 3 | 3 |  | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 16 | 2021-05-04 15:14
1106 | 3 | 3 |  | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 16 | 2021-05-04 15:14
1107 | 3 | 3 |  | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 16 | 2021-05-04 15:14
1108 | 3 | 3 |  | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 16 | 2021-05-04 15:14
1109 | 3 | 3 |  | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 16 | 2021-05-04 15:14
1110 | 3 | 3 |  | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 16 | 2021-05-04 15:14
1111 | 3 | 3 |  | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 16 | 2021-05-04 15:14
1112 | 3 | 3 |  | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 16 | 2021-05-04 15:14
1113 | 3 | 3 |  | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 16 | 2021-05-04 15:14
1114 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 16 | 2021-05-04 15:14
1115 | 2 | 2 |  | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 16 | 2021-05-04 15:14
1116 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 16 | 2021-05-04 15:14
1117 | 2 | 2 |  | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 16 | 2021-05-04 15:14
1118 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 16 | 2021-05-04 15:14
1119 | 2 | 2 |  | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 16 | 2021-05-04 15:14
1120 | 2 | 2 |  | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 16 | 2021-05-04 15:14
1121 | 2 | 2 |  | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 16 | 2021-05-04 15:14
1122 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 16 | 2021-05-04 15:14
1123 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 16 | 2021-05-04 15:14
1124 | 2 | 2 |  | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 16 | 2021-05-04 15:14
1125 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 16 | 2021-05-04 15:14
1126 | 2 | 2 |  | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 16 | 2021-05-04 15:14
1127 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 16 | 2021-05-04 15:14
1128 | 2 | 2 |  | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 16 | 2021-05-04 15:14
1129 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 16 | 2021-05-04 15:14
1130 | 2 | 2 |  | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 16 | 2021-05-04 15:14
1131 | 2 | 2 |  | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 16 | 2021-05-04 15:14
1132 | 2 | 2 |  | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 16 | 2021-05-04 15:14
1133 | 2 | 2 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 16 | 2021-05-04 15:14
1134 | 2 | 2 |  | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 16 | 2021-05-04 15:14
1135 | 2 | 2 |  | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 16 | 2021-05-04 15:14
1136 | 2 | 2 |  | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 16 | 2021-05-04 15:14
1137 | 2 | 2 |  | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 16 | 2021-05-04 15:14
1138 | 2 | 2 |  | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 16 | 2021-05-04 15:14
1139 | 2 | 2 |  | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 16 | 2021-05-04 15:14
1140 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 16 | 2021-05-04 15:14
1141 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 16 | 2021-05-04 15:14
1142 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 16 | 2021-05-04 15:14
1143 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 16 | 2021-05-04 15:14
1144 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 16 | 2021-05-04 15:14
1145 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 16 | 2021-05-04 15:14
1146 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 16 | 2021-05-04 15:14
1147 | 2 | 2 |  | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 16 | 2021-05-04 15:14
1148 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 16 | 2021-05-04 15:14
1149 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 16 | 2021-05-04 15:14
1150 | 2 | 2 |  | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 16 | 2021-05-04 15:14
1151 | 2 | 2 |  | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 16 | 2021-05-04 15:14
1152 | 2 | 2 |  | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 16 | 2021-05-04 15:14
1153 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 16 | 2021-05-04 15:14
1154 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 16 | 2021-05-04 15:14
1155 | 2 | 2 |  | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 16 | 2021-05-04 15:14
1156 | 2 | 2 |  | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 16 | 2021-05-04 15:14
1157 | 2 | 2 |  | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 16 | 2021-05-04 15:14
1158 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 16 | 2021-05-04 15:14
1159 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 16 | 2021-05-04 15:14
1160 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 16 | 2021-05-04 15:14
1161 | 2 | 2 |  | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 16 | 2021-05-04 15:14
1162 | 2 | 2 |  | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 16 | 2021-05-04 15:14
1163 | 2 | 2 |  | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 16 | 2021-05-04 15:14
1164 | 2 | 2 |  | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 16 | 2021-05-04 15:14
1165 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 16 | 2021-05-04 15:14
1166 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 16 | 2021-05-04 15:14
1167 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 16 | 2021-05-04 15:14
1168 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 16 | 2021-05-04 15:14
1169 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 16 | 2021-05-04 15:14
1170 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 16 | 2021-05-04 15:14
1171 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 16 | 2021-05-04 15:14
1172 | 2 | 2 |  | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 16 | 2021-05-04 15:14
1173 | 1 | 1 |  | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 16 | 2021-05-04 15:14
1174 | 3 | 3 |  | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 16 | 2021-05-04 15:14
1175 | 1 | 1 |  | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 16 | 2021-05-04 15:14
1176 | 3 | 3 |  | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 16 | 2021-05-04 15:14
1177 | 1 | 1 |  | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 16 | 2021-05-04 15:14
1178 | 1 | 1 |  | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 16 | 2021-05-04 15:14
1179 | 1 | 1 |  | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 16 | 2021-05-04 15:14
1180 | 3 | 3 |  | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 16 | 2021-05-04 15:14
1181 | 3 | 3 |  | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 16 | 2021-05-04 15:14
1182 | 1 | 1 |  | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 16 | 2021-05-04 15:14
1183 | 1 | 1 |  | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 16 | 2021-05-04 15:14
1184 | 3 | 3 |  | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 16 | 2021-05-04 15:14
1185 | 1 | 1 |  | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 16 | 2021-05-04 15:14
1186 | 1 | 1 |  | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 16 | 2021-05-04 15:14
1187 | 3 | 3 |  | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 16 | 2021-05-04 15:14
1188 | 1 | 1 |  | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 16 | 2021-05-04 15:14
1189 | 1 | 1 |  | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 16 | 2021-05-04 15:14
1190 | 1 | 1 |  | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 16 | 2021-05-04 15:14
1191 | 1 | 1 |  | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 16 | 2021-05-04 15:14
1192 | 1 | 1 |  | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 16 | 2021-05-04 15:14
1193 | 3 | 3 |  | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 16 | 2021-05-04 15:14
1194 | 1 | 1 |  | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 16 | 2021-05-04 15:14
1195 | 3 | 3 |  | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 16 | 2021-05-04 15:14
1196 | 3 | 3 |  | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 16 | 2021-05-04 15:14
1197 | 3 | 3 |  | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 16 | 2021-05-04 15:14
1198 | 3 | 3 |  | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 16 | 2021-05-04 15:14
1199 | 3 | 3 |  | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 16 | 2021-05-04 15:14
1200 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 16 | 2021-05-04 15:14
1201 | 2 | 2 |  | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 16 | 2021-05-04 15:14
1202 | 3 | 3 |  | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 16 | 2021-05-04 15:14
1203 | 3 | 3 |  | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 16 | 2021-05-04 15:14
1204 | 3 | 3 |  | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 16 | 2021-05-04 15:14
1205 | 3 | 3 |  | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 16 | 2021-05-04 15:14
1206 | 1 | 1 |  | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 16 | 2021-05-04 15:14
1207 | 3 | 3 |  | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 16 | 2021-05-04 15:14
1208 | 3 | 3 |  | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 16 | 2021-05-04 15:14
1209 | 3 | 3 |  | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 16 | 2021-05-04 15:14
1210 | 3 | 3 |  | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 16 | 2021-05-04 15:14
1211 | 3 | 3 |  | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 16 | 2021-05-04 15:14
1212 | 3 | 3 |  | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 16 | 2021-05-04 15:14
1213 | 3 | 3 |  | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 16 | 2021-05-04 15:14
1214 | 3 | 3 |  | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 16 | 2021-05-04 15:14
1215 | 3 | 3 |  | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 16 | 2021-05-04 15:14
1216 | 3 | 3 |  | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 16 | 2021-05-04 15:14
1217 | 3 | 3 |  | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 16 | 2021-05-04 15:14
1218 | 3 | 3 |  | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 16 | 2021-05-04 15:14
1219 | 3 | 3 |  | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 16 | 2021-05-04 15:14
1220 | 3 | 3 |  | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 16 | 2021-05-04 15:14
1221 | 3 | 3 |  | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 16 | 2021-05-04 15:14
1222 | 3 | 3 |  | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 16 | 2021-05-04 15:14
1223 | 3 | 3 |  | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 16 | 2021-05-04 15:14
1224 | 3 | 3 |  | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 16 | 2021-05-04 15:14
1225 | 3 | 3 |  | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 16 | 2021-05-04 15:14
1226 | 3 | 3 |  | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 16 | 2021-05-04 15:14
1227 | 3 | 3 |  | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 16 | 2021-05-04 15:14
1228 | 3 | 3 |  | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 16 | 2021-05-04 15:14
1229 | 2 | 2 |  | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 16 | 2021-05-04 15:14
1230 | 3 | 3 |  | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 16 | 2021-05-04 15:14
1231 | 3 | 3 |  | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 16 | 2021-05-04 15:14
1232 | 3 | 3 |  | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 16 | 2021-05-04 15:14
1233 | 3 | 3 |  | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 16 | 2021-05-04 15:14
1234 | 3 | 3 |  | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 16 | 2021-05-04 15:14
1235 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 16 | 2021-05-04 15:14
1236 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 16 | 2021-05-04 15:14
1237 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 16 | 2021-05-04 15:14
1238 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 16 | 2021-05-04 15:14
1239 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 16 | 2021-05-04 15:14
1240 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 16 | 2021-05-04 15:14
1241 | 3 | 3 |  | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 16 | 2021-05-04 15:14
1242 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 16 | 2021-05-04 15:14
1243 | 2 | 2 |  | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 16 | 2021-05-04 15:14
1244 | 3 | 3 |  | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 16 | 2021-05-04 15:14
1245 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 16 | 2021-05-04 15:14
1246 | 3 | 3 |  | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 16 | 2021-05-04 15:14
1247 | 2 | 2 |  | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 16 | 2021-05-04 15:14
1248 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 16 | 2021-05-04 15:14
1249 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 16 | 2021-05-04 15:14
1250 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 16 | 2021-05-04 15:14
1251 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 16 | 2021-05-04 15:14
1252 | 3 | 3 |  | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 16 | 2021-05-04 15:14
1253 | 2 | 2 |  | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 16 | 2021-05-04 15:14
1254 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 16 | 2021-05-04 15:14
1255 | 2 | 2 |  | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 16 | 2021-05-04 15:14
1256 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 16 | 2021-05-04 15:14
1257 | 2 | 2 |  | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 16 | 2021-05-04 15:14
1258 | 3 | 3 |  | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 16 | 2021-05-04 15:14
1259 | 3 | 3 |  | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 16 | 2021-05-04 15:14
1260 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 16 | 2021-05-04 15:14
1261 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 16 | 2021-05-04 15:14
1262 | 3 | 3 |  | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 16 | 2021-05-04 15:14
1263 | 3 | 3 |  | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 16 | 2021-05-04 15:14
1264 | 3 | 3 |  | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 16 | 2021-05-04 15:14
1265 | 3 | 3 |  | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 16 | 2021-05-04 15:14
1266 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 16 | 2021-05-04 15:14
1267 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 16 | 2021-05-04 15:14
1268 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 16 | 2021-05-04 15:14
1269 | 3 | 3 |  | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 16 | 2021-05-04 15:14
1270 | 3 | 3 |  | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 16 | 2021-05-04 15:14
1271 | 3 | 3 |  | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 16 | 2021-05-04 15:14
1272 | 3 | 3 |  | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 16 | 2021-05-04 15:14
1273 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 16 | 2021-05-04 15:14
1274 | 3 | 3 |  | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 16 | 2021-05-04 15:14
1275 | 3 | 3 |  | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 16 | 2021-05-04 15:14
1276 | 3 | 3 |  | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 16 | 2021-05-04 15:14
1277 | 3 | 3 |  | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 16 | 2021-05-04 15:14
1278 | 3 | 3 |  | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 16 | 2021-05-04 15:14
1279 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 16 | 2021-05-04 15:14
1280 | 2 | 2 |  | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 16 | 2021-05-04 15:14
1281 | 3 | 3 |  | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 16 | 2021-05-04 15:14
1282 | 3 | 3 |  | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 16 | 2021-05-04 15:14
1283 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 16 | 2021-05-04 15:14
1284 | 3 | 3 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 16 | 2021-05-04 15:14
1285 | 3 | 3 |  | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 16 | 2021-05-04 15:14
1286 | 3 | 3 |  | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 16 | 2021-05-04 15:14
1287 | 3 | 3 |  | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:14
1288 | 3 | 3 |  | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 16 | 2021-05-04 15:14
1289 | 3 | 3 |  | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:14
1290 | 2 | 2 |  | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:14
1291 | 2 | 2 |  | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:14
1292 | 3 | 3 |  | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 16 | 2021-05-04 15:14
1293 | 3 | 3 |  | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 16 | 2021-05-04 15:14
1294 | 2 | 2 |  | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:14
1295 | 3 | 3 |  | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 16 | 2021-05-04 15:14
1296 | 2 | 2 |  | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 16 | 2021-05-04 15:14
1297 | 3 | 3 |  | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 16 | 2021-05-04 15:14
1298 | 3 | 3 |  | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 16 | 2021-05-04 15:14
1299 | 1 | 1 |  | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 16 | 2021-05-04 15:14
1300 | 2 | 2 |  | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 16 | 2021-05-04 15:14
1301 | 3 | 3 |  | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 16 | 2021-05-04 15:14
1302 | 1 | 1 |  | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 16 | 2021-05-04 15:14
1303 | 3 | 3 |  | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 16 | 2021-05-04 15:14
1304 | 3 | 3 |  | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 16 | 2021-05-04 15:14
1305 | 3 | 3 |  | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:14
1306 | 3 | 3 |  | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 16 | 2021-05-04 15:14
1307 | 3 | 3 |  | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 16 | 2021-05-04 15:14
1308 | 2 | 2 |  | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 16 | 2021-05-04 15:14
1309 | 3 | 3 |  | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 16 | 2021-05-04 15:14
1310 | 3 | 3 |  | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:14
1311 | 2 | 2 |  | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 16 | 2021-05-04 15:14
1312 | 3 | 3 |  | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:14
1313 | 3 | 3 |  | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 16 | 2021-05-04 15:14
1314 | 3 | 3 |  | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 16 | 2021-05-04 15:14
1315 | 2 | 2 |  | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 16 | 2021-05-04 15:14
1316 | 3 | 3 |  | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:14
1317 | 3 | 3 |  | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 16 | 2021-05-04 15:14
1318 | 3 | 3 |  | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 16 | 2021-05-04 15:14
1319 | 2 | 2 |  | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 16 | 2021-05-04 15:14
1320 | 2 | 2 |  | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 16 | 2021-05-04 15:14
1321 | 3 | 3 |  | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 16 | 2021-05-04 15:14
1322 | 2 | 2 |  | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 16 | 2021-05-04 15:14
1323 | 3 | 3 |  | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 16 | 2021-05-04 15:14
1324 | 3 | 3 |  | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 16 | 2021-05-04 15:14
1325 | 3 | 3 |  | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 16 | 2021-05-04 15:14
1326 | 2 | 2 |  | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:14
1327 | 2 | 2 |  | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 16 | 2021-05-04 15:14
1328 | 3 | 3 |  | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:14
1329 | 3 | 3 |  | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 16 | 2021-05-04 15:14
1330 | 3 | 3 |  | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 16 | 2021-05-04 15:14
1331 | 3 | 3 |  | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 16 | 2021-05-04 15:14
1332 | 3 | 3 |  | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:14
1333 | 3 | 3 |  | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:14
1334 | 3 | 3 |  | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:14
1335 | 3 | 3 |  | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:14
1336 | 2 | 2 |  | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:14
1337 | 3 | 3 |  | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 16 | 2021-05-04 15:14
1338 | 3 | 3 |  | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 16 | 2021-05-04 15:14
1339 | 3 | 3 |  | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 16 | 2021-05-04 15:14
1340 | 3 | 3 |  | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:14
1341 | 2 | 2 |  | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:14
1342 | 3 | 3 |  | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 16 | 2021-05-04 15:14
1343 | 3 | 3 |  | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 16 | 2021-05-04 15:14
1344 | 3 | 3 |  | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 16 | 2021-05-04 15:14
1345 | 3 | 3 |  | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 16 | 2021-05-04 15:14
1346 | 2 | 2 |  | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 16 | 2021-05-04 15:14
1347 | 3 | 3 |  | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:14
1348 | 2 | 2 |  | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 16 | 2021-05-04 15:14
1349 | 2 | 2 |  | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 16 | 2021-05-04 15:14
1350 | 3 | 3 |  | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:14
1351 | 3 | 3 |  | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 16 | 2021-05-04 15:14
1352 | 2 | 2 |  | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 16 | 2021-05-04 15:14
1353 | 2 | 2 |  | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:14
1354 | 3 | 3 |  | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 16 | 2021-05-04 15:14
1355 | 2 | 2 |  | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:14
1356 | 3 | 3 |  | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 16 | 2021-05-04 15:14
1357 | 2 | 2 |  | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 16 | 2021-05-04 15:14
1358 | 2 | 2 |  | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:14
1359 | 3 | 3 |  | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:14
1360 | 2 | 2 |  | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 16 | 2021-05-04 15:14
1361 | 3 | 3 |  | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 16 | 2021-05-04 15:14
1362 | 3 | 3 |  | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 16 | 2021-05-04 15:14
1363 | 2 | 2 |  | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 16 | 2021-05-04 15:14
1364 | 2 | 2 |  | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 16 | 2021-05-04 15:14
1365 | 3 | 3 |  | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 16 | 2021-05-04 15:14
1366 | 3 | 3 |  | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:14
1367 | 2 | 2 |  | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:14
1368 | 2 | 2 |  | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 16 | 2021-05-04 15:14
1369 | 3 | 3 |  | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 16 | 2021-05-04 15:14
1370 | 3 | 3 |  | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:14
1371 | 3 | 3 |  | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 16 | 2021-05-04 15:14
1372 | 2 | 2 |  | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 16 | 2021-05-04 15:14
1373 | 3 | 3 |  | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 16 | 2021-05-04 15:14
1374 | 2 | 2 |  | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 16 | 2021-05-04 15:14
1375 | 3 | 3 |  | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 16 | 2021-05-04 15:14
1376 | 1 | 1 |  | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 16 | 2021-05-04 15:14
1377 | 3 | 3 |  | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 16 | 2021-05-04 15:14
1378 | 2 | 2 |  | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 16 | 2021-05-04 15:14
1379 | 3 | 3 |  | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:14
1380 | 3 | 3 |  | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 16 | 2021-05-04 15:14
1381 | 3 | 3 |  | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 16 | 2021-05-04 15:14
1382 | 3 | 3 |  | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:14
1383 | 3 | 3 |  | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 16 | 2021-05-04 15:14
1384 | 2 | 2 |  | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 16 | 2021-05-04 15:14
1385 | 2 | 2 |  | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 16 | 2021-05-04 15:14
1386 | 3 | 3 |  | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 16 | 2021-05-04 15:14
1387 | 3 | 3 |  | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 16 | 2021-05-04 15:14
1388 | 3 | 3 |  | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 16 | 2021-05-04 15:14
1389 | 2 | 2 |  | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 16 | 2021-05-04 15:14
1390 | 3 | 3 |  | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 16 | 2021-05-04 15:14
1391 | 2 | 2 |  | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 16 | 2021-05-04 15:14
1392 | 2 | 2 |  | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 16 | 2021-05-04 15:14
1393 | 3 | 3 |  | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 16 | 2021-05-04 15:14
1394 | 3 | 3 |  | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 16 | 2021-05-04 15:14
1395 | 1 | 1 |  | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 16 | 2021-05-04 15:14
1396 | 1 | 1 |  | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 16 | 2021-05-04 15:14
1397 | 3 | 3 |  | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 16 | 2021-05-04 15:14
1398 | 3 | 3 |  | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 16 | 2021-05-04 15:14
1399 | 3 | 3 |  | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 16 | 2021-05-04 15:14
1400 | 1 | 1 |  | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 16 | 2021-05-04 15:14
1401 | 2 | 2 |  | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 16 | 2021-05-04 15:14
1402 | 2 | 2 |  | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 16 | 2021-05-04 15:14
1403 | 2 | 2 |  | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 16 | 2021-05-04 15:14
1404 | 1 | 1 |  | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 16 | 2021-05-04 15:14
1405 | 1 | 1 |  | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 16 | 2021-05-04 15:14
1406 | 3 | 3 |  | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 16 | 2021-05-04 15:14
1407 | 2 | 2 |  | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 16 | 2021-05-04 15:14
1408 | 2 | 2 |  | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 16 | 2021-05-04 15:14
1409 | 3 | 3 |  | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 16 | 2021-05-04 15:14
1410 | 3 | 3 |  | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 16 | 2021-05-04 15:14
1411 | 3 | 3 |  | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 16 | 2021-05-04 15:14
1412 | 3 | 3 |  | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 16 | 2021-05-04 15:14
1413 | 2 | 2 |  | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 16 | 2021-05-04 15:14
1414 | 3 | 3 |  | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 16 | 2021-05-04 15:14
1415 | 3 | 3 |  | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 16 | 2021-05-04 15:14
1416 | 2 | 2 |  | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 16 | 2021-05-04 15:14
1417 | 3 | 3 |  | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 16 | 2021-05-04 15:14
1418 | 1 | 1 |  | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 16 | 2021-05-04 15:14
1419 | 2 | 2 |  | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 16 | 2021-05-04 15:14
1420 | 3 | 3 |  | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 16 | 2021-05-04 15:14
1421 | 2 | 2 |  | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 16 | 2021-05-04 15:14
1422 | 1 | 1 |  | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 16 | 2021-05-04 15:14
1423 | 3 | 3 |  | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 16 | 2021-05-04 15:14
1424 | 1 | 1 |  | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 16 | 2021-05-04 15:14
1425 | 3 | 3 |  | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 16 | 2021-05-04 15:14
1426 | 1 | 1 |  | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 16 | 2021-05-04 15:14
1427 | 3 | 3 |  | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 16 | 2021-05-04 15:14
1428 | 2 | 2 |  | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 16 | 2021-05-04 15:14
1429 | 3 | 3 |  | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 16 | 2021-05-04 15:14
1430 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 16 | 2021-05-04 15:20
1431 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2021-05-04 15:20
1432 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 16 | 2021-05-04 15:20
1433 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 16 | 2021-05-04 15:20
1434 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:20
1435 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 16 | 2021-05-04 15:20
1436 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 2021-05-04 15:20
1437 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2021-05-04 15:20
1438 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 16 | 2021-05-04 15:20
1439 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:20
1440 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 16 | 2021-05-04 15:20
1441 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 16 | 2021-05-04 15:20
1442 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 16 | 2021-05-04 15:20
1443 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 16 | 2021-05-04 15:20
1444 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 16 | 2021-05-04 15:20
1445 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 16 | 2021-05-04 15:20
1446 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 16 | 2021-05-04 15:20
1447 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 16 | 2021-05-04 15:20
1448 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 16 | 2021-05-04 15:20
1449 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:20
1450 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 16 | 2021-05-04 15:20
1451 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:20
1452 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:20
1453 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 16 | 2021-05-04 15:20
1454 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 16 | 2021-05-04 15:20
1455 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 16 | 2021-05-04 15:20
1456 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 16 | 2021-05-04 15:20
1457 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 16 | 2021-05-04 15:20
1458 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 16 | 2021-05-04 15:20
1459 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 16 | 2021-05-04 15:20
1460 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 16 | 2021-05-04 15:20
1461 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 16 | 2021-05-04 15:20
1462 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 16 | 2021-05-04 15:20
1463 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 16 | 2021-05-04 15:20
1464 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 16 | 2021-05-04 15:20
1465 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 16 | 2021-05-04 15:20
1466 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 16 | 2021-05-04 15:20
1467 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 16 | 2021-05-04 15:20
1468 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 16 | 2021-05-04 15:20
1469 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 16 | 2021-05-04 15:20
1470 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:20
1471 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:20
1472 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:20
1473 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 16 | 2021-05-04 15:20
1474 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 16 | 2021-05-04 15:20
1475 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 16 | 2021-05-04 15:20
1476 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:20
1477 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 16 | 2021-05-04 15:20
1478 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 16 | 2021-05-04 15:20
1479 | 2 | 2 |  | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 16 | 2021-05-04 15:20
1480 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:20
1481 | 3 | 3 |  | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 16 | 2021-05-04 15:20
1482 | 3 | 3 |  | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 16 | 2021-05-04 15:20
1483 | 3 | 3 |  | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 16 | 2021-05-04 15:20
1484 | 3 | 3 |  | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 16 | 2021-05-04 15:20
1485 | 3 | 3 |  | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:20
1486 | 3 | 3 |  | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:20
1487 | 3 | 3 |  | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 16 | 2021-05-04 15:20
1488 | 3 | 3 |  | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 16 | 2021-05-04 15:20
1489 | 2 | 2 |  | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 16 | 2021-05-04 15:20
1490 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 16 | 2021-05-04 15:20
1491 | 2 | 2 |  | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:20
1492 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 16 | 2021-05-04 15:20
1493 | 2 | 2 |  | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 16 | 2021-05-04 15:20
1494 | 2 | 2 |  | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 16 | 2021-05-04 15:20
1495 | 2 | 2 |  | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 16 | 2021-05-04 15:20
1496 | 2 | 2 |  | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 16 | 2021-05-04 15:20
1497 | 3 | 3 |  | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 16 | 2021-05-04 15:20
1498 | 3 | 3 |  | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 16 | 2021-05-04 15:20
1499 | 3 | 3 |  | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 16 | 2021-05-04 15:20
1500 | 3 | 3 |  | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:20
1501 | 3 | 3 |  | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 16 | 2021-05-04 15:20
1502 | 3 | 3 |  | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 16 | 2021-05-04 15:20
1503 | 3 | 3 |  | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 16 | 2021-05-04 15:20
1504 | 3 | 3 |  | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 16 | 2021-05-04 15:20
1505 | 3 | 3 |  | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 16 | 2021-05-04 15:20
1506 | 3 | 3 |  | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:20
1507 | 3 | 3 |  | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 16 | 2021-05-04 15:20
1508 | 3 | 3 |  | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 16 | 2021-05-04 15:20
1509 | 3 | 3 |  | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 16 | 2021-05-04 15:20
1510 | 3 | 3 |  | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 16 | 2021-05-04 15:20
1511 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:20
1512 | 2 | 2 |  | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 16 | 2021-05-04 15:20
1513 | 2 | 2 |  | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 16 | 2021-05-04 15:20
1514 | 3 | 3 |  | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 16 | 2021-05-04 15:20
1515 | 2 | 2 |  | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 16 | 2021-05-04 15:20
1516 | 3 | 3 |  | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 16 | 2021-05-04 15:20
1517 | 3 | 3 |  | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 16 | 2021-05-04 15:20
1518 | 3 | 3 |  | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:20
1519 | 2 | 2 |  | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 16 | 2021-05-04 15:20
1520 | 3 | 3 |  | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:20
1521 | 3 | 3 |  | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 16 | 2021-05-04 15:20
1522 | 2 | 2 |  | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 16 | 2021-05-04 15:20
1523 | 1 | 1 |  | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 16 | 2021-05-04 15:20
1524 | 3 | 3 |  | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 16 | 2021-05-04 15:20
1525 | 1 | 1 |  | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 16 | 2021-05-04 15:20
1526 | 2 | 2 |  | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:20
1527 | 3 | 3 |  | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 16 | 2021-05-04 15:20
1528 | 2 | 2 |  | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 16 | 2021-05-04 15:20
1529 | 3 | 3 |  | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 16 | 2021-05-04 15:20
1530 | 2 | 2 |  | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 16 | 2021-05-04 15:20
1531 | 3 | 3 |  | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 16 | 2021-05-04 15:20
1532 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:20
1533 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:20
1534 | 3 | 3 |  | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:20
1535 | 3 | 3 |  | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 16 | 2021-05-04 15:20
1536 | 3 | 3 |  | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:20
1537 | 3 | 3 |  | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:20
1538 | 3 | 3 |  | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:20
1539 | 3 | 3 |  | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 16 | 2021-05-04 15:20
1540 | 1 | 1 |  | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:20
1541 | 1 | 1 |  | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 16 | 2021-05-04 15:20
1542 | 3 | 3 |  | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 16 | 2021-05-04 15:20
1543 | 3 | 3 |  | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:20
1544 | 2 | 2 |  | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 16 | 2021-05-04 15:20
1545 | 3 | 3 |  | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 16 | 2021-05-04 15:20
1546 | 2 | 2 |  | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 16 | 2021-05-04 15:20
1547 | 2 | 2 |  | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 16 | 2021-05-04 15:20
1548 | 2 | 2 |  | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 16 | 2021-05-04 15:20
1549 | 3 | 3 |  | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:20
1550 | 3 | 3 |  | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 16 | 2021-05-04 15:20
1551 | 3 | 3 |  | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 16 | 2021-05-04 15:20
1552 | 2 | 2 |  | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:20
1553 | 3 | 3 |  | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 16 | 2021-05-04 15:20
1554 | 3 | 3 |  | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:20
1555 | 3 | 3 |  | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:20
1556 | 3 | 3 |  | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 16 | 2021-05-04 15:20
1557 | 3 | 3 |  | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 16 | 2021-05-04 15:20
1558 | 2 | 2 |  | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 16 | 2021-05-04 15:20
1559 | 3 | 3 |  | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:20
1560 | 3 | 3 |  | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:20
1561 | 3 | 3 |  | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 16 | 2021-05-04 15:20
1562 | 2 | 2 |  | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 16 | 2021-05-04 15:20
1563 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 16 | 2021-05-04 15:20
1564 | 3 | 3 |  | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 16 | 2021-05-04 15:20
1565 | 3 | 3 |  | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:20
1566 | 3 | 3 |  | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 16 | 2021-05-04 15:20
1567 | 3 | 3 |  | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:20
1568 | 3 | 3 |  | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 16 | 2021-05-04 15:20
1569 | 3 | 3 |  | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 16 | 2021-05-04 15:20
1570 | 3 | 3 |  | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 16 | 2021-05-04 15:20
1571 | 3 | 3 |  | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:20
1572 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 16 | 2021-05-04 15:20
1573 | 3 | 3 |  | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:20
1574 | 3 | 3 |  | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 16 | 2021-05-04 15:20
1575 | 3 | 3 |  | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 16 | 2021-05-04 15:20
1576 | 3 | 3 |  | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:20
1577 | 2 | 2 |  | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 16 | 2021-05-04 15:20
1578 | 3 | 3 |  | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:20
1579 | 3 | 3 |  | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:20
1580 | 2 | 2 |  | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 16 | 2021-05-04 15:20
1581 | 3 | 3 |  | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 16 | 2021-05-04 15:20
1582 | 3 | 3 |  | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 16 | 2021-05-04 15:20
1583 | 3 | 3 |  | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 16 | 2021-05-04 15:20
1584 | 3 | 3 |  | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 16 | 2021-05-04 15:20
1585 | 3 | 3 |  | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:20
1586 | 2 | 2 |  | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 16 | 2021-05-04 15:20
1587 | 3 | 3 |  | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 16 | 2021-05-04 15:20
1588 | 2 | 2 |  | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 16 | 2021-05-04 15:20
1589 | 3 | 3 |  | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:20
1590 | 3 | 3 |  | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:20
1591 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:20
1592 | 3 | 3 |  | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:20
1593 | 3 | 3 |  | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 16 | 2021-05-04 15:20
1594 | 3 | 3 |  | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:20
1595 | 3 | 3 |  | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:20
1596 | 3 | 3 |  | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 16 | 2021-05-04 15:20
1597 | 2 | 2 |  | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:20
1598 | 3 | 3 |  | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 16 | 2021-05-04 15:20
1599 | 3 | 3 |  | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 16 | 2021-05-04 15:20
1600 | 2 | 2 |  | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:20
1601 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:20
1602 | 3 | 3 |  | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 16 | 2021-05-04 15:20
1603 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 16 | 2021-05-04 15:20
1604 | 2 | 2 |  | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 16 | 2021-05-04 15:20
1605 | 2 | 2 |  | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 16 | 2021-05-04 15:20
1606 | 3 | 3 |  | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 16 | 2021-05-04 15:20
1607 | 3 | 3 |  | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 16 | 2021-05-04 15:20
1608 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:20
1609 | 3 | 3 |  | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 16 | 2021-05-04 15:20
1610 | 2 | 2 |  | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 16 | 2021-05-04 15:20
1611 | 2 | 2 |  | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:20
1612 | 3 | 3 |  | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 16 | 2021-05-04 15:20
1613 | 3 | 3 |  | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:20
1614 | 3 | 3 |  | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 16 | 2021-05-04 15:20
1615 | 2 | 2 |  | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 16 | 2021-05-04 15:20
1616 | 3 | 3 |  | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:20
1617 | 3 | 3 |  | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 16 | 2021-05-04 15:20
1618 | 3 | 3 |  | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 16 | 2021-05-04 15:20
1619 | 3 | 3 |  | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 16 | 2021-05-04 15:20
1620 | 3 | 3 |  | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:20
1621 | 2 | 2 |  | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 16 | 2021-05-04 15:20
1622 | 3 | 3 |  | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:20
1623 | 3 | 3 |  | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 16 | 2021-05-04 15:20
1624 | 3 | 3 |  | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 16 | 2021-05-04 15:20
1625 | 3 | 3 |  | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:20
1626 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 16 | 2021-05-04 15:20
1627 | 2 | 2 |  | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 16 | 2021-05-04 15:20
1628 | 3 | 3 |  | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 16 | 2021-05-04 15:20
1629 | 3 | 3 |  | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 16 | 2021-05-04 15:20
1630 | 3 | 3 |  | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:20
1631 | 2 | 2 |  | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 16 | 2021-05-04 15:20
1632 | 3 | 3 |  | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 16 | 2021-05-04 15:20
1633 | 2 | 2 |  | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:20
1634 | 3 | 3 |  | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:20
1635 | 3 | 3 |  | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:20
1636 | 3 | 3 |  | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:20
1637 | 3 | 3 |  | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 16 | 2021-05-04 15:20
1638 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:20
1639 | 2 | 2 |  | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:20
1640 | 3 | 3 |  | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 16 | 2021-05-04 15:20
1641 | 3 | 3 |  | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 16 | 2021-05-04 15:20
1642 | 3 | 3 |  | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 16 | 2021-05-04 15:20
1643 | 3 | 3 |  | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 16 | 2021-05-04 15:20
1644 | 3 | 3 |  | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 16 | 2021-05-04 15:20
1645 | 3 | 3 |  | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 16 | 2021-05-04 15:20
1646 | 3 | 3 |  | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 16 | 2021-05-04 15:20
1647 | 3 | 3 |  | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 16 | 2021-05-04 15:20
1648 | 3 | 3 |  | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 16 | 2021-05-04 15:20
1649 | 3 | 3 |  | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 16 | 2021-05-04 15:20
1650 | 3 | 3 |  | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 16 | 2021-05-04 15:20
1651 | 3 | 3 |  | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 16 | 2021-05-04 15:20
1652 | 3 | 3 |  | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 16 | 2021-05-04 15:20
1653 | 3 | 3 |  | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 16 | 2021-05-04 15:20
1654 | 3 | 3 |  | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 16 | 2021-05-04 15:20
1655 | 3 | 3 |  | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 16 | 2021-05-04 15:20
1656 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 16 | 2021-05-04 15:20
1657 | 2 | 2 |  | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 16 | 2021-05-04 15:20
1658 | 2 | 2 |  | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 16 | 2021-05-04 15:20
1659 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 16 | 2021-05-04 15:20
1660 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 16 | 2021-05-04 15:20
1661 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 16 | 2021-05-04 15:20
1662 | 2 | 2 |  | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 16 | 2021-05-04 15:20
1663 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 16 | 2021-05-04 15:20
1664 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 16 | 2021-05-04 15:20
1665 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 16 | 2021-05-04 15:20
1666 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 16 | 2021-05-04 15:20
1667 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 16 | 2021-05-04 15:20
1668 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 16 | 2021-05-04 15:20
1669 | 3 | 3 |  | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 16 | 2021-05-04 15:20
1670 | 2 | 2 |  | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 16 | 2021-05-04 15:20
1671 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 16 | 2021-05-04 15:20
1672 | 2 | 2 |  | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 16 | 2021-05-04 15:20
1673 | 2 | 2 |  | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 16 | 2021-05-04 15:20
1674 | 3 | 3 |  | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 16 | 2021-05-04 15:20
1675 | 3 | 3 |  | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 16 | 2021-05-04 15:20
1676 | 2 | 2 |  | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 16 | 2021-05-04 15:20
1677 | 2 | 2 |  | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 16 | 2021-05-04 15:20
1678 | 2 | 2 |  | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 16 | 2021-05-04 15:20
1679 | 3 | 3 |  | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 16 | 2021-05-04 15:20
1680 | 3 | 3 |  | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 16 | 2021-05-04 15:20
1681 | 3 | 3 |  | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 16 | 2021-05-04 15:20
1682 | 3 | 3 |  | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 16 | 2021-05-04 15:20
1683 | 3 | 3 |  | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 16 | 2021-05-04 15:20
1684 | 3 | 3 |  | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 16 | 2021-05-04 15:20
1685 | 2 | 2 |  | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 16 | 2021-05-04 15:20
1686 | 2 | 2 |  | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 16 | 2021-05-04 15:20
1687 | 2 | 2 |  | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 16 | 2021-05-04 15:20
1688 | 2 | 2 |  | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 16 | 2021-05-04 15:20
1689 | 2 | 2 |  | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 16 | 2021-05-04 15:20
1690 | 3 | 3 |  | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 16 | 2021-05-04 15:20
1691 | 3 | 3 |  | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 16 | 2021-05-04 15:20
1692 | 3 | 3 |  | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 16 | 2021-05-04 15:20
1693 | 3 | 3 |  | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 16 | 2021-05-04 15:20
1694 | 3 | 3 |  | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 16 | 2021-05-04 15:20
1695 | 3 | 3 |  | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 16 | 2021-05-04 15:20
1696 | 3 | 3 |  | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 16 | 2021-05-04 15:20
1697 | 2 | 2 |  | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 16 | 2021-05-04 15:20
1698 | 2 | 2 |  | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 16 | 2021-05-04 15:20
1699 | 3 | 3 |  | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 16 | 2021-05-04 15:20
1700 | 3 | 3 |  | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 16 | 2021-05-04 15:20
1701 | 3 | 3 |  | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 16 | 2021-05-04 15:20
1702 | 3 | 3 |  | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 16 | 2021-05-04 15:20
1703 | 3 | 3 |  | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 16 | 2021-05-04 15:20
1704 | 3 | 3 |  | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 16 | 2021-05-04 15:20
1705 | 3 | 3 |  | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 16 | 2021-05-04 15:20
1706 | 3 | 3 |  | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 16 | 2021-05-04 15:20
1707 | 3 | 3 |  | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 16 | 2021-05-04 15:20
1708 | 3 | 3 |  | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 16 | 2021-05-04 15:20
1709 | 3 | 3 |  | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 16 | 2021-05-04 15:20
1710 | 3 | 3 |  | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 16 | 2021-05-04 15:20
1711 | 2 | 2 |  | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 16 | 2021-05-04 15:20
1712 | 2 | 2 |  | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 16 | 2021-05-04 15:20
1713 | 2 | 2 |  | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 16 | 2021-05-04 15:20
1714 | 2 | 2 |  | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 16 | 2021-05-04 15:20
1715 | 2 | 2 |  | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 16 | 2021-05-04 15:20
1716 | 2 | 2 |  | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 16 | 2021-05-04 15:20
1717 | 3 | 3 |  | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 16 | 2021-05-04 15:20
1718 | 3 | 3 |  | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 16 | 2021-05-04 15:20
1719 | 3 | 3 |  | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 16 | 2021-05-04 15:20
1720 | 3 | 3 |  | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 16 | 2021-05-04 15:20
1721 | 3 | 3 |  | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 16 | 2021-05-04 15:20
1722 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 16 | 2021-05-04 15:20
1723 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 16 | 2021-05-04 15:20
1724 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 16 | 2021-05-04 15:20
1725 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 16 | 2021-05-04 15:20
1726 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 16 | 2021-05-04 15:20
1727 | 3 | 3 |  | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 16 | 2021-05-04 15:20
1728 | 3 | 3 |  | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:20
1729 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 16 | 2021-05-04 15:20
1730 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 16 | 2021-05-04 15:20
1731 | 3 | 3 |  | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:20
1732 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 16 | 2021-05-04 15:20
1733 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 16 | 2021-05-04 15:20
1734 | 3 | 3 |  | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 16 | 2021-05-04 15:20
1735 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 16 | 2021-05-04 15:20
1736 | 3 | 3 |  | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 16 | 2021-05-04 15:20
1737 | 3 | 3 |  | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 16 | 2021-05-04 15:20
1738 | 3 | 3 |  | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:20
1739 | 3 | 3 |  | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:20
1740 | 3 | 3 |  | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 16 | 2021-05-04 15:20
1741 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 16 | 2021-05-04 15:20
1742 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:20
1743 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:20
1744 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 16 | 2021-05-04 15:20
1745 | 3 | 3 |  | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 16 | 2021-05-04 15:20
1746 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 16 | 2021-05-04 15:20
1747 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 16 | 2021-05-04 15:20
1748 | 3 | 3 |  | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 16 | 2021-05-04 15:20
1749 | 3 | 3 |  | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 16 | 2021-05-04 15:20
1750 | 3 | 3 |  | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 16 | 2021-05-04 15:20
1751 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 16 | 2021-05-04 15:20
1752 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 16 | 2021-05-04 15:20
1753 | 3 | 3 |  | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 16 | 2021-05-04 15:20
1754 | 3 | 3 |  | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 16 | 2021-05-04 15:20
1755 | 3 | 3 |  | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 16 | 2021-05-04 15:20
1756 | 3 | 3 |  | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 16 | 2021-05-04 15:20
1757 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 16 | 2021-05-04 15:20
1758 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 16 | 2021-05-04 15:20
1759 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 16 | 2021-05-04 15:20
1760 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 16 | 2021-05-04 15:20
1761 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 16 | 2021-05-04 15:20
1762 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 16 | 2021-05-04 15:20
1763 | 3 | 3 |  | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 16 | 2021-05-04 15:20
1764 | 3 | 3 |  | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 16 | 2021-05-04 15:20
1765 | 3 | 3 |  | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 16 | 2021-05-04 15:20
1766 | 3 | 3 |  | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 16 | 2021-05-04 15:20
1767 | 3 | 3 |  | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 16 | 2021-05-04 15:20
1768 | 3 | 3 |  | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 16 | 2021-05-04 15:20
1769 | 3 | 3 |  | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 16 | 2021-05-04 15:20
1770 | 3 | 3 |  | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 16 | 2021-05-04 15:20
1771 | 3 | 3 |  | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 16 | 2021-05-04 15:20
1772 | 3 | 3 |  | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 16 | 2021-05-04 15:20
1773 | 3 | 3 |  | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 16 | 2021-05-04 15:20
1774 | 3 | 3 |  | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 16 | 2021-05-04 15:20
1775 | 3 | 3 |  | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 16 | 2021-05-04 15:20
1776 | 3 | 3 |  | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 16 | 2021-05-04 15:20
1777 | 3 | 3 |  | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 16 | 2021-05-04 15:20
1778 | 3 | 3 |  | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 16 | 2021-05-04 15:20
1779 | 3 | 3 |  | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 16 | 2021-05-04 15:20
1780 | 3 | 3 |  | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 16 | 2021-05-04 15:20
1781 | 3 | 3 |  | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 16 | 2021-05-04 15:20
1782 | 3 | 3 |  | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 16 | 2021-05-04 15:20
1783 | 3 | 3 |  | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 16 | 2021-05-04 15:20
1784 | 3 | 3 |  | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 16 | 2021-05-04 15:20
1785 | 3 | 3 |  | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 16 | 2021-05-04 15:20
1786 | 3 | 3 |  | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 16 | 2021-05-04 15:20
1787 | 1 | 1 |  | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 16 | 2021-05-04 15:20
1788 | 3 | 3 |  | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 16 | 2021-05-04 15:20
1789 | 3 | 3 |  | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 16 | 2021-05-04 15:20
1790 | 3 | 3 |  | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 16 | 2021-05-04 15:20
1791 | 3 | 3 |  | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 16 | 2021-05-04 15:20
1792 | 3 | 3 |  | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 16 | 2021-05-04 15:20
1793 | 3 | 3 |  | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 16 | 2021-05-04 15:20
1794 | 3 | 3 |  | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 16 | 2021-05-04 15:20
1795 | 3 | 3 |  | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 16 | 2021-05-04 15:20
1796 | 3 | 3 |  | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 16 | 2021-05-04 15:20
1797 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 16 | 2021-05-04 15:20
1798 | 2 | 2 |  | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 16 | 2021-05-04 15:20
1799 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 16 | 2021-05-04 15:20
1800 | 2 | 2 |  | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 16 | 2021-05-04 15:20
1801 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 16 | 2021-05-04 15:20
1802 | 2 | 2 |  | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 16 | 2021-05-04 15:20
1803 | 2 | 2 |  | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 16 | 2021-05-04 15:20
1804 | 2 | 2 |  | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 16 | 2021-05-04 15:20
1805 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 16 | 2021-05-04 15:20
1806 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 16 | 2021-05-04 15:20
1807 | 2 | 2 |  | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 16 | 2021-05-04 15:20
1808 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 16 | 2021-05-04 15:20
1809 | 2 | 2 |  | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 16 | 2021-05-04 15:20
1810 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 16 | 2021-05-04 15:20
1811 | 2 | 2 |  | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 16 | 2021-05-04 15:20
1812 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 16 | 2021-05-04 15:20
1813 | 2 | 2 |  | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 16 | 2021-05-04 15:20
1814 | 2 | 2 |  | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 16 | 2021-05-04 15:20
1815 | 2 | 2 |  | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 16 | 2021-05-04 15:20
1816 | 2 | 2 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 16 | 2021-05-04 15:20
1817 | 2 | 2 |  | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 16 | 2021-05-04 15:20
1818 | 2 | 2 |  | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 16 | 2021-05-04 15:20
1819 | 2 | 2 |  | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 16 | 2021-05-04 15:20
1820 | 2 | 2 |  | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 16 | 2021-05-04 15:20
1821 | 2 | 2 |  | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 16 | 2021-05-04 15:20
1822 | 2 | 2 |  | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 16 | 2021-05-04 15:20
1823 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 16 | 2021-05-04 15:20
1824 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 16 | 2021-05-04 15:20
1825 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 16 | 2021-05-04 15:20
1826 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 16 | 2021-05-04 15:20
1827 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 16 | 2021-05-04 15:20
1828 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 16 | 2021-05-04 15:20
1829 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 16 | 2021-05-04 15:20
1830 | 2 | 2 |  | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 16 | 2021-05-04 15:20
1831 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 16 | 2021-05-04 15:20
1832 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 16 | 2021-05-04 15:20
1833 | 2 | 2 |  | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 16 | 2021-05-04 15:20
1834 | 2 | 2 |  | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 16 | 2021-05-04 15:20
1835 | 2 | 2 |  | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 16 | 2021-05-04 15:20
1836 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 16 | 2021-05-04 15:20
1837 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 16 | 2021-05-04 15:20
1838 | 2 | 2 |  | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 16 | 2021-05-04 15:20
1839 | 2 | 2 |  | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 16 | 2021-05-04 15:20
1840 | 2 | 2 |  | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 16 | 2021-05-04 15:20
1841 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 16 | 2021-05-04 15:20
1842 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 16 | 2021-05-04 15:20
1843 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 16 | 2021-05-04 15:20
1844 | 2 | 2 |  | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 16 | 2021-05-04 15:20
1845 | 2 | 2 |  | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 16 | 2021-05-04 15:20
1846 | 2 | 2 |  | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 16 | 2021-05-04 15:20
1847 | 2 | 2 |  | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 16 | 2021-05-04 15:20
1848 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 16 | 2021-05-04 15:20
1849 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 16 | 2021-05-04 15:20
1850 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 16 | 2021-05-04 15:20
1851 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 16 | 2021-05-04 15:20
1852 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 16 | 2021-05-04 15:20
1853 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 16 | 2021-05-04 15:20
1854 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 16 | 2021-05-04 15:20
1855 | 2 | 2 |  | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 16 | 2021-05-04 15:20
1856 | 1 | 1 |  | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 16 | 2021-05-04 15:20
1857 | 3 | 3 |  | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 16 | 2021-05-04 15:20
1858 | 1 | 1 |  | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 16 | 2021-05-04 15:20
1859 | 3 | 3 |  | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 16 | 2021-05-04 15:20
1860 | 1 | 1 |  | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 16 | 2021-05-04 15:20
1861 | 1 | 1 |  | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 16 | 2021-05-04 15:20
1862 | 1 | 1 |  | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 16 | 2021-05-04 15:20
1863 | 3 | 3 |  | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 16 | 2021-05-04 15:20
1864 | 3 | 3 |  | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 16 | 2021-05-04 15:20
1865 | 1 | 1 |  | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 16 | 2021-05-04 15:20
1866 | 1 | 1 |  | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 16 | 2021-05-04 15:20
1867 | 3 | 3 |  | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 16 | 2021-05-04 15:20
1868 | 1 | 1 |  | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 16 | 2021-05-04 15:20
1869 | 1 | 1 |  | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 16 | 2021-05-04 15:20
1870 | 3 | 3 |  | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 16 | 2021-05-04 15:20
1871 | 1 | 1 |  | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 16 | 2021-05-04 15:20
1872 | 1 | 1 |  | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 16 | 2021-05-04 15:20
1873 | 1 | 1 |  | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 16 | 2021-05-04 15:20
1874 | 1 | 1 |  | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 16 | 2021-05-04 15:20
1875 | 1 | 1 |  | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 16 | 2021-05-04 15:20
1876 | 3 | 3 |  | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 16 | 2021-05-04 15:20
1877 | 1 | 1 |  | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 16 | 2021-05-04 15:20
1878 | 3 | 3 |  | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 16 | 2021-05-04 15:20
1879 | 3 | 3 |  | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 16 | 2021-05-04 15:20
1880 | 3 | 3 |  | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 16 | 2021-05-04 15:20
1881 | 3 | 3 |  | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 16 | 2021-05-04 15:20
1882 | 3 | 3 |  | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 16 | 2021-05-04 15:20
1883 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 16 | 2021-05-04 15:20
1884 | 2 | 2 |  | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 16 | 2021-05-04 15:20
1885 | 3 | 3 |  | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 16 | 2021-05-04 15:20
1886 | 3 | 3 |  | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 16 | 2021-05-04 15:20
1887 | 3 | 3 |  | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 16 | 2021-05-04 15:20
1888 | 3 | 3 |  | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 16 | 2021-05-04 15:20
1889 | 1 | 1 |  | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 16 | 2021-05-04 15:20
1890 | 3 | 3 |  | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 16 | 2021-05-04 15:20
1891 | 3 | 3 |  | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 16 | 2021-05-04 15:20
1892 | 3 | 3 |  | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 16 | 2021-05-04 15:20
1893 | 3 | 3 |  | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 16 | 2021-05-04 15:20
1894 | 3 | 3 |  | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 16 | 2021-05-04 15:20
1895 | 3 | 3 |  | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 16 | 2021-05-04 15:20
1896 | 3 | 3 |  | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 16 | 2021-05-04 15:20
1897 | 3 | 3 |  | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 16 | 2021-05-04 15:20
1898 | 3 | 3 |  | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 16 | 2021-05-04 15:20
1899 | 3 | 3 |  | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 16 | 2021-05-04 15:20
1900 | 3 | 3 |  | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 16 | 2021-05-04 15:20
1901 | 3 | 3 |  | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 16 | 2021-05-04 15:20
1902 | 3 | 3 |  | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 16 | 2021-05-04 15:20
1903 | 3 | 3 |  | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 16 | 2021-05-04 15:20
1904 | 3 | 3 |  | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 16 | 2021-05-04 15:20
1905 | 3 | 3 |  | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 16 | 2021-05-04 15:20
1906 | 3 | 3 |  | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 16 | 2021-05-04 15:20
1907 | 3 | 3 |  | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 16 | 2021-05-04 15:20
1908 | 3 | 3 |  | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 16 | 2021-05-04 15:20
1909 | 3 | 3 |  | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 16 | 2021-05-04 15:20
1910 | 3 | 3 |  | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 16 | 2021-05-04 15:20
1911 | 3 | 3 |  | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 16 | 2021-05-04 15:20
1912 | 2 | 2 |  | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 16 | 2021-05-04 15:20
1913 | 3 | 3 |  | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 16 | 2021-05-04 15:20
1914 | 3 | 3 |  | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 16 | 2021-05-04 15:20
1915 | 3 | 3 |  | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 16 | 2021-05-04 15:20
1916 | 3 | 3 |  | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 16 | 2021-05-04 15:20
1917 | 3 | 3 |  | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 16 | 2021-05-04 15:20
1918 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 16 | 2021-05-04 15:20
1919 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 16 | 2021-05-04 15:20
1920 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 16 | 2021-05-04 15:20
1921 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 16 | 2021-05-04 15:20
1922 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 16 | 2021-05-04 15:20
1923 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 16 | 2021-05-04 15:20
1924 | 3 | 3 |  | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 16 | 2021-05-04 15:20
1925 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 16 | 2021-05-04 15:20
1926 | 2 | 2 |  | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 16 | 2021-05-04 15:20
1927 | 3 | 3 |  | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 16 | 2021-05-04 15:20
1928 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 16 | 2021-05-04 15:20
1929 | 3 | 3 |  | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 16 | 2021-05-04 15:20
1930 | 2 | 2 |  | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 16 | 2021-05-04 15:20
1931 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 16 | 2021-05-04 15:20
1932 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 16 | 2021-05-04 15:20
1933 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 16 | 2021-05-04 15:20
1934 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 16 | 2021-05-04 15:20
1935 | 3 | 3 |  | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 16 | 2021-05-04 15:20
1936 | 2 | 2 |  | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 16 | 2021-05-04 15:20
1937 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 16 | 2021-05-04 15:20
1938 | 2 | 2 |  | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 16 | 2021-05-04 15:20
1939 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 16 | 2021-05-04 15:20
1940 | 2 | 2 |  | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 16 | 2021-05-04 15:20
1941 | 3 | 3 |  | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 16 | 2021-05-04 15:20
1942 | 3 | 3 |  | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 16 | 2021-05-04 15:20
1943 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 16 | 2021-05-04 15:20
1944 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 16 | 2021-05-04 15:20
1945 | 3 | 3 |  | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 16 | 2021-05-04 15:20
1946 | 3 | 3 |  | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 16 | 2021-05-04 15:20
1947 | 3 | 3 |  | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 16 | 2021-05-04 15:20
1948 | 3 | 3 |  | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 16 | 2021-05-04 15:20
1949 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 16 | 2021-05-04 15:20
1950 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 16 | 2021-05-04 15:20
1951 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 16 | 2021-05-04 15:20
1952 | 3 | 3 |  | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 16 | 2021-05-04 15:20
1953 | 3 | 3 |  | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 16 | 2021-05-04 15:20
1954 | 3 | 3 |  | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 16 | 2021-05-04 15:20
1955 | 3 | 3 |  | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 16 | 2021-05-04 15:20
1956 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 16 | 2021-05-04 15:20
1957 | 3 | 3 |  | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 16 | 2021-05-04 15:20
1958 | 3 | 3 |  | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 16 | 2021-05-04 15:20
1959 | 3 | 3 |  | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 16 | 2021-05-04 15:20
1960 | 3 | 3 |  | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 16 | 2021-05-04 15:20
1961 | 3 | 3 |  | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 16 | 2021-05-04 15:20
1962 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 16 | 2021-05-04 15:20
1963 | 2 | 2 |  | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 16 | 2021-05-04 15:20
1964 | 3 | 3 |  | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 16 | 2021-05-04 15:20
1965 | 3 | 3 |  | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 16 | 2021-05-04 15:20
1966 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 16 | 2021-05-04 15:20
1967 | 3 | 3 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 16 | 2021-05-04 15:20
1968 | 3 | 3 |  | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 16 | 2021-05-04 15:20
1969 | 3 | 3 |  | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 16 | 2021-05-04 15:20
1970 | 3 | 3 |  | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:20
1971 | 3 | 3 |  | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 16 | 2021-05-04 15:20
1972 | 3 | 3 |  | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:20
1973 | 2 | 2 |  | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:20
1974 | 2 | 2 |  | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:20
1975 | 3 | 3 |  | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 16 | 2021-05-04 15:20
1976 | 3 | 3 |  | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 16 | 2021-05-04 15:20
1977 | 2 | 2 |  | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:20
1978 | 3 | 3 |  | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 16 | 2021-05-04 15:20
1979 | 2 | 2 |  | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 16 | 2021-05-04 15:20
1980 | 3 | 3 |  | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 16 | 2021-05-04 15:20
1981 | 3 | 3 |  | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 16 | 2021-05-04 15:20
1982 | 1 | 1 |  | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 16 | 2021-05-04 15:20
1983 | 2 | 2 |  | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 16 | 2021-05-04 15:20
1984 | 3 | 3 |  | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 16 | 2021-05-04 15:20
1985 | 1 | 1 |  | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 16 | 2021-05-04 15:20
1986 | 3 | 3 |  | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 16 | 2021-05-04 15:20
1987 | 3 | 3 |  | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 16 | 2021-05-04 15:20
1988 | 3 | 3 |  | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:20
1989 | 3 | 3 |  | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 16 | 2021-05-04 15:20
1990 | 3 | 3 |  | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 16 | 2021-05-04 15:20
1991 | 2 | 2 |  | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 16 | 2021-05-04 15:20
1992 | 3 | 3 |  | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 16 | 2021-05-04 15:20
1993 | 3 | 3 |  | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:20
1994 | 2 | 2 |  | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 16 | 2021-05-04 15:20
1995 | 3 | 3 |  | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:20
1996 | 3 | 3 |  | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 16 | 2021-05-04 15:20
1997 | 3 | 3 |  | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 16 | 2021-05-04 15:20
1998 | 2 | 2 |  | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 16 | 2021-05-04 15:20
1999 | 3 | 3 |  | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:20
2000 | 3 | 3 |  | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 16 | 2021-05-04 15:20
2001 | 3 | 3 |  | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 16 | 2021-05-04 15:20
2002 | 2 | 2 |  | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 16 | 2021-05-04 15:20
2003 | 2 | 2 |  | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 16 | 2021-05-04 15:20
2004 | 3 | 3 |  | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 16 | 2021-05-04 15:20
2005 | 2 | 2 |  | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 16 | 2021-05-04 15:20
2006 | 3 | 3 |  | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 16 | 2021-05-04 15:20
2007 | 3 | 3 |  | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 16 | 2021-05-04 15:20
2008 | 3 | 3 |  | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 16 | 2021-05-04 15:20
2009 | 2 | 2 |  | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:20
2010 | 2 | 2 |  | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 16 | 2021-05-04 15:20
2011 | 3 | 3 |  | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:20
2012 | 3 | 3 |  | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 16 | 2021-05-04 15:20
2013 | 3 | 3 |  | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 16 | 2021-05-04 15:20
2014 | 3 | 3 |  | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 16 | 2021-05-04 15:20
2015 | 3 | 3 |  | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:20
2016 | 3 | 3 |  | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:20
2017 | 3 | 3 |  | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:20
2018 | 3 | 3 |  | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:20
2019 | 2 | 2 |  | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:20
2020 | 3 | 3 |  | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 16 | 2021-05-04 15:20
2021 | 3 | 3 |  | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 16 | 2021-05-04 15:20
2022 | 3 | 3 |  | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 16 | 2021-05-04 15:20
2023 | 3 | 3 |  | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:20
2024 | 2 | 2 |  | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:20
2025 | 3 | 3 |  | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 16 | 2021-05-04 15:20
2026 | 3 | 3 |  | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 16 | 2021-05-04 15:20
2027 | 3 | 3 |  | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 16 | 2021-05-04 15:20
2028 | 3 | 3 |  | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 16 | 2021-05-04 15:20
2029 | 2 | 2 |  | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 16 | 2021-05-04 15:20
2030 | 3 | 3 |  | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:20
2031 | 2 | 2 |  | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 16 | 2021-05-04 15:20
2032 | 2 | 2 |  | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 16 | 2021-05-04 15:20
2033 | 3 | 3 |  | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:20
2034 | 3 | 3 |  | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 16 | 2021-05-04 15:20
2035 | 2 | 2 |  | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 16 | 2021-05-04 15:20
2036 | 2 | 2 |  | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:20
2037 | 3 | 3 |  | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 16 | 2021-05-04 15:20
2038 | 2 | 2 |  | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:20
2039 | 3 | 3 |  | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 16 | 2021-05-04 15:20
2040 | 2 | 2 |  | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 16 | 2021-05-04 15:20
2041 | 2 | 2 |  | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:20
2042 | 3 | 3 |  | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:20
2043 | 2 | 2 |  | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 16 | 2021-05-04 15:20
2044 | 3 | 3 |  | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 16 | 2021-05-04 15:20
2045 | 3 | 3 |  | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 16 | 2021-05-04 15:20
2046 | 2 | 2 |  | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 16 | 2021-05-04 15:20
2047 | 2 | 2 |  | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 16 | 2021-05-04 15:20
2048 | 3 | 3 |  | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 16 | 2021-05-04 15:20
2049 | 3 | 3 |  | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:20
2050 | 2 | 2 |  | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:20
2051 | 2 | 2 |  | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 16 | 2021-05-04 15:20
2052 | 3 | 3 |  | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 16 | 2021-05-04 15:20
2053 | 3 | 3 |  | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:20
2054 | 3 | 3 |  | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 16 | 2021-05-04 15:20
2055 | 2 | 2 |  | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 16 | 2021-05-04 15:20
2056 | 3 | 3 |  | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 16 | 2021-05-04 15:20
2057 | 2 | 2 |  | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 16 | 2021-05-04 15:20
2058 | 3 | 3 |  | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 16 | 2021-05-04 15:20
2059 | 1 | 1 |  | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 16 | 2021-05-04 15:20
2060 | 3 | 3 |  | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 16 | 2021-05-04 15:20
2061 | 2 | 2 |  | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 16 | 2021-05-04 15:20
2062 | 3 | 3 |  | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:20
2063 | 3 | 3 |  | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 16 | 2021-05-04 15:20
2064 | 3 | 3 |  | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 16 | 2021-05-04 15:20
2065 | 3 | 3 |  | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:20
2066 | 3 | 3 |  | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 16 | 2021-05-04 15:20
2067 | 2 | 2 |  | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 16 | 2021-05-04 15:20
2068 | 2 | 2 |  | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 16 | 2021-05-04 15:20
2069 | 3 | 3 |  | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 16 | 2021-05-04 15:20
2070 | 3 | 3 |  | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 16 | 2021-05-04 15:20
2071 | 3 | 3 |  | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 16 | 2021-05-04 15:20
2072 | 2 | 2 |  | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 16 | 2021-05-04 15:20
2073 | 3 | 3 |  | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 16 | 2021-05-04 15:20
2074 | 2 | 2 |  | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 16 | 2021-05-04 15:20
2075 | 2 | 2 |  | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 16 | 2021-05-04 15:20
2076 | 3 | 3 |  | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 16 | 2021-05-04 15:20
2077 | 3 | 3 |  | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 16 | 2021-05-04 15:20
2078 | 1 | 1 |  | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 16 | 2021-05-04 15:20
2079 | 1 | 1 |  | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 16 | 2021-05-04 15:20
2080 | 3 | 3 |  | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 16 | 2021-05-04 15:20
2081 | 3 | 3 |  | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 16 | 2021-05-04 15:20
2082 | 3 | 3 |  | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 16 | 2021-05-04 15:20
2083 | 1 | 1 |  | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 16 | 2021-05-04 15:20
2084 | 2 | 2 |  | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 16 | 2021-05-04 15:20
2085 | 2 | 2 |  | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 16 | 2021-05-04 15:20
2086 | 2 | 2 |  | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 16 | 2021-05-04 15:20
2087 | 1 | 1 |  | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 16 | 2021-05-04 15:20
2088 | 1 | 1 |  | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 16 | 2021-05-04 15:20
2089 | 3 | 3 |  | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 16 | 2021-05-04 15:20
2090 | 2 | 2 |  | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 16 | 2021-05-04 15:20
2091 | 2 | 2 |  | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 16 | 2021-05-04 15:20
2092 | 3 | 3 |  | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 16 | 2021-05-04 15:20
2093 | 3 | 3 |  | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 16 | 2021-05-04 15:20
2094 | 3 | 3 |  | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 16 | 2021-05-04 15:20
2095 | 3 | 3 |  | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 16 | 2021-05-04 15:20
2096 | 2 | 2 |  | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 16 | 2021-05-04 15:20
2097 | 3 | 3 |  | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 16 | 2021-05-04 15:20
2098 | 3 | 3 |  | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 16 | 2021-05-04 15:20
2099 | 2 | 2 |  | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 16 | 2021-05-04 15:20
2100 | 3 | 3 |  | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 16 | 2021-05-04 15:20
2101 | 1 | 1 |  | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 16 | 2021-05-04 15:20
2102 | 2 | 2 |  | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 16 | 2021-05-04 15:20
2103 | 3 | 3 |  | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 16 | 2021-05-04 15:20
2104 | 2 | 2 |  | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 16 | 2021-05-04 15:20
2105 | 1 | 1 |  | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 16 | 2021-05-04 15:20
2106 | 3 | 3 |  | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 16 | 2021-05-04 15:20
2107 | 1 | 1 |  | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 16 | 2021-05-04 15:20
2108 | 3 | 3 |  | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 16 | 2021-05-04 15:20
2109 | 1 | 1 |  | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 16 | 2021-05-04 15:20
2110 | 3 | 3 |  | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 16 | 2021-05-04 15:20
2111 | 2 | 2 |  | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 16 | 2021-05-04 15:20
2112 | 3 | 3 |  | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 16 | 2021-05-04 15:20
2113 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 16 | 2021-05-04 15:23
2114 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2021-05-04 15:23
2115 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 16 | 2021-05-04 15:23
2116 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 16 | 2021-05-04 15:23
2117 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:23
2118 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 16 | 2021-05-04 15:23
2119 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 16 | 2021-05-04 15:23
2120 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 16 | 2021-05-04 15:23
2121 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 16 | 2021-05-04 15:23
2122 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:23
2123 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 16 | 2021-05-04 15:23
2124 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 16 | 2021-05-04 15:23
2125 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 16 | 2021-05-04 15:23
2126 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 16 | 2021-05-04 15:23
2127 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 16 | 2021-05-04 15:23
2128 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 16 | 2021-05-04 15:23
2129 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 16 | 2021-05-04 15:23
2130 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 16 | 2021-05-04 15:23
2131 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 16 | 2021-05-04 15:23
2132 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:23
2133 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 16 | 2021-05-04 15:23
2134 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:23
2135 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 16 | 2021-05-04 15:23
2136 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 16 | 2021-05-04 15:23
2137 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 16 | 2021-05-04 15:23
2138 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 16 | 2021-05-04 15:23
2139 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 16 | 2021-05-04 15:23
2140 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 16 | 2021-05-04 15:23
2141 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 16 | 2021-05-04 15:23
2142 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 16 | 2021-05-04 15:23
2143 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 16 | 2021-05-04 15:23
2144 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 16 | 2021-05-04 15:23
2145 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 16 | 2021-05-04 15:23
2146 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 16 | 2021-05-04 15:23
2147 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 16 | 2021-05-04 15:23
2148 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 16 | 2021-05-04 15:23
2149 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 16 | 2021-05-04 15:23
2150 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 16 | 2021-05-04 15:23
2151 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 16 | 2021-05-04 15:23
2152 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 16 | 2021-05-04 15:23
2153 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:23
2154 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:23
2155 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 16 | 2021-05-04 15:23
2156 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 16 | 2021-05-04 15:23
2157 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 16 | 2021-05-04 15:23
2158 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 16 | 2021-05-04 15:23
2159 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 16 | 2021-05-04 15:23
2160 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 16 | 2021-05-04 15:23
2161 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 16 | 2021-05-04 15:23
2162 | 2 | 2 |  | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 16 | 2021-05-04 15:23
2163 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:23
2164 | 3 | 3 |  | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 16 | 2021-05-04 15:23
2165 | 3 | 3 |  | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 16 | 2021-05-04 15:23
2166 | 3 | 3 |  | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 16 | 2021-05-04 15:23
2167 | 3 | 3 |  | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 16 | 2021-05-04 15:23
2168 | 3 | 3 |  | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:23
2169 | 3 | 3 |  | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:23
2170 | 3 | 3 |  | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 16 | 2021-05-04 15:23
2171 | 3 | 3 |  | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 16 | 2021-05-04 15:23
2172 | 2 | 2 |  | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 16 | 2021-05-04 15:23
2173 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 16 | 2021-05-04 15:23
2174 | 2 | 2 |  | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 16 | 2021-05-04 15:23
2175 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 16 | 2021-05-04 15:23
2176 | 2 | 2 |  | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 16 | 2021-05-04 15:23
2177 | 2 | 2 |  | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 16 | 2021-05-04 15:23
2178 | 2 | 2 |  | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 16 | 2021-05-04 15:23
2179 | 2 | 2 |  | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 16 | 2021-05-04 15:23
2180 | 3 | 3 |  | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 16 | 2021-05-04 15:23
2181 | 3 | 3 |  | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 16 | 2021-05-04 15:23
2182 | 3 | 3 |  | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 16 | 2021-05-04 15:23
2183 | 3 | 3 |  | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:23
2184 | 3 | 3 |  | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 16 | 2021-05-04 15:23
2185 | 3 | 3 |  | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 16 | 2021-05-04 15:23
2186 | 3 | 3 |  | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 16 | 2021-05-04 15:23
2187 | 3 | 3 |  | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 16 | 2021-05-04 15:23
2188 | 3 | 3 |  | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 16 | 2021-05-04 15:23
2189 | 3 | 3 |  | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:23
2190 | 3 | 3 |  | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 16 | 2021-05-04 15:23
2191 | 3 | 3 |  | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 16 | 2021-05-04 15:23
2192 | 3 | 3 |  | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 16 | 2021-05-04 15:23
2193 | 3 | 3 |  | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 16 | 2021-05-04 15:23
2194 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:23
2195 | 2 | 2 |  | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 16 | 2021-05-04 15:23
2196 | 2 | 2 |  | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 16 | 2021-05-04 15:23
2197 | 3 | 3 |  | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 16 | 2021-05-04 15:23
2198 | 2 | 2 |  | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 16 | 2021-05-04 15:23
2199 | 3 | 3 |  | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 16 | 2021-05-04 15:23
2200 | 3 | 3 |  | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 16 | 2021-05-04 15:23
2201 | 3 | 3 |  | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:23
2202 | 2 | 2 |  | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 16 | 2021-05-04 15:23
2203 | 3 | 3 |  | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:23
2204 | 3 | 3 |  | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 16 | 2021-05-04 15:23
2205 | 2 | 2 |  | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 16 | 2021-05-04 15:23
2206 | 1 | 1 |  | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 16 | 2021-05-04 15:23
2207 | 3 | 3 |  | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 16 | 2021-05-04 15:23
2208 | 1 | 1 |  | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 16 | 2021-05-04 15:23
2209 | 2 | 2 |  | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:23
2210 | 3 | 3 |  | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 16 | 2021-05-04 15:23
2211 | 2 | 2 |  | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 16 | 2021-05-04 15:23
2212 | 3 | 3 |  | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 16 | 2021-05-04 15:23
2213 | 2 | 2 |  | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 16 | 2021-05-04 15:23
2214 | 3 | 3 |  | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 16 | 2021-05-04 15:23
2215 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:23
2216 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 16 | 2021-05-04 15:23
2217 | 3 | 3 |  | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:23
2218 | 3 | 3 |  | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 16 | 2021-05-04 15:23
2219 | 3 | 3 |  | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:23
2220 | 3 | 3 |  | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:23
2221 | 3 | 3 |  | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:23
2222 | 3 | 3 |  | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 16 | 2021-05-04 15:23
2223 | 1 | 1 |  | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:23
2224 | 1 | 1 |  | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 16 | 2021-05-04 15:23
2225 | 3 | 3 |  | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 16 | 2021-05-04 15:23
2226 | 3 | 3 |  | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:23
2227 | 2 | 2 |  | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 16 | 2021-05-04 15:23
2228 | 3 | 3 |  | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 16 | 2021-05-04 15:23
2229 | 2 | 2 |  | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 16 | 2021-05-04 15:23
2230 | 2 | 2 |  | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 16 | 2021-05-04 15:23
2231 | 2 | 2 |  | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 16 | 2021-05-04 15:23
2232 | 3 | 3 |  | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 16 | 2021-05-04 15:23
2233 | 3 | 3 |  | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 16 | 2021-05-04 15:23
2234 | 3 | 3 |  | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 16 | 2021-05-04 15:23
2235 | 2 | 2 |  | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:23
2236 | 3 | 3 |  | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 16 | 2021-05-04 15:23
2237 | 3 | 3 |  | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 16 | 2021-05-04 15:23
2238 | 3 | 3 |  | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 16 | 2021-05-04 15:23
2239 | 3 | 3 |  | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 16 | 2021-05-04 15:23
2240 | 3 | 3 |  | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 16 | 2021-05-04 15:23
2241 | 2 | 2 |  | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 16 | 2021-05-04 15:23
2242 | 3 | 3 |  | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:23
2243 | 3 | 3 |  | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:23
2244 | 3 | 3 |  | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 16 | 2021-05-04 15:23
2245 | 2 | 2 |  | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 16 | 2021-05-04 15:23
2246 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 16 | 2021-05-04 15:23
2247 | 3 | 3 |  | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 16 | 2021-05-04 15:23
2248 | 3 | 3 |  | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 16 | 2021-05-04 15:23
2249 | 3 | 3 |  | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 16 | 2021-05-04 15:23
2250 | 3 | 3 |  | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:23
2251 | 3 | 3 |  | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 16 | 2021-05-04 15:23
2252 | 3 | 3 |  | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 16 | 2021-05-04 15:23
2253 | 3 | 3 |  | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 16 | 2021-05-04 15:23
2254 | 3 | 3 |  | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 16 | 2021-05-04 15:23
2255 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 16 | 2021-05-04 15:23
2256 | 3 | 3 |  | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:23
2257 | 3 | 3 |  | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 16 | 2021-05-04 15:23
2258 | 3 | 3 |  | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 16 | 2021-05-04 15:23
2259 | 3 | 3 |  | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:23
2260 | 2 | 2 |  | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 16 | 2021-05-04 15:23
2261 | 3 | 3 |  | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:23
2262 | 3 | 3 |  | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:23
2263 | 2 | 2 |  | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 16 | 2021-05-04 15:23
2264 | 3 | 3 |  | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 16 | 2021-05-04 15:23
2265 | 3 | 3 |  | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 16 | 2021-05-04 15:23
2266 | 3 | 3 |  | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 16 | 2021-05-04 15:23
2267 | 3 | 3 |  | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 16 | 2021-05-04 15:23
2268 | 3 | 3 |  | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 16 | 2021-05-04 15:23
2269 | 2 | 2 |  | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 16 | 2021-05-04 15:23
2270 | 3 | 3 |  | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 16 | 2021-05-04 15:23
2271 | 2 | 2 |  | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 16 | 2021-05-04 15:23
2272 | 3 | 3 |  | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 16 | 2021-05-04 15:23
2273 | 3 | 3 |  | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:23
2274 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:23
2275 | 3 | 3 |  | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:23
2276 | 3 | 3 |  | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 16 | 2021-05-04 15:23
2277 | 3 | 3 |  | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 16 | 2021-05-04 15:23
2278 | 3 | 3 |  | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:23
2279 | 3 | 3 |  | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 16 | 2021-05-04 15:23
2280 | 2 | 2 |  | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:23
2281 | 3 | 3 |  | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 16 | 2021-05-04 15:23
2282 | 3 | 3 |  | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 16 | 2021-05-04 15:23
2283 | 2 | 2 |  | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:23
2284 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:23
2285 | 3 | 3 |  | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 16 | 2021-05-04 15:23
2286 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 16 | 2021-05-04 15:23
2287 | 2 | 2 |  | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 16 | 2021-05-04 15:23
2288 | 2 | 2 |  | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 16 | 2021-05-04 15:23
2289 | 3 | 3 |  | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 16 | 2021-05-04 15:23
2290 | 3 | 3 |  | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 16 | 2021-05-04 15:23
2291 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:23
2292 | 3 | 3 |  | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 16 | 2021-05-04 15:23
2293 | 2 | 2 |  | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 16 | 2021-05-04 15:23
2294 | 2 | 2 |  | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:23
2295 | 3 | 3 |  | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 16 | 2021-05-04 15:23
2296 | 3 | 3 |  | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:23
2297 | 3 | 3 |  | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 16 | 2021-05-04 15:23
2298 | 2 | 2 |  | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 16 | 2021-05-04 15:23
2299 | 3 | 3 |  | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:23
2300 | 3 | 3 |  | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 16 | 2021-05-04 15:23
2301 | 3 | 3 |  | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 16 | 2021-05-04 15:23
2302 | 3 | 3 |  | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 16 | 2021-05-04 15:23
2303 | 3 | 3 |  | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:23
2304 | 2 | 2 |  | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 16 | 2021-05-04 15:23
2305 | 3 | 3 |  | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 16 | 2021-05-04 15:23
2306 | 3 | 3 |  | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 16 | 2021-05-04 15:23
2307 | 3 | 3 |  | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 16 | 2021-05-04 15:23
2308 | 3 | 3 |  | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 16 | 2021-05-04 15:23
2309 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 16 | 2021-05-04 15:23
2310 | 2 | 2 |  | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 16 | 2021-05-04 15:23
2311 | 3 | 3 |  | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 16 | 2021-05-04 15:23
2312 | 3 | 3 |  | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 16 | 2021-05-04 15:23
2313 | 3 | 3 |  | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 16 | 2021-05-04 15:23
2314 | 2 | 2 |  | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 16 | 2021-05-04 15:23
2315 | 3 | 3 |  | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 16 | 2021-05-04 15:23
2316 | 2 | 2 |  | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 16 | 2021-05-04 15:23
2317 | 3 | 3 |  | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 16 | 2021-05-04 15:23
2318 | 3 | 3 |  | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 16 | 2021-05-04 15:23
2319 | 3 | 3 |  | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 16 | 2021-05-04 15:23
2320 | 3 | 3 |  | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 16 | 2021-05-04 15:23
2321 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 16 | 2021-05-04 15:23
2322 | 2 | 2 |  | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 16 | 2021-05-04 15:23
2323 | 3 | 3 |  | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 16 | 2021-05-04 15:23
2324 | 3 | 3 |  | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 16 | 2021-05-04 15:23
2325 | 3 | 3 |  | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 16 | 2021-05-04 15:23
2326 | 3 | 3 |  | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 16 | 2021-05-04 15:23
2327 | 3 | 3 |  | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 16 | 2021-05-04 15:23
2328 | 3 | 3 |  | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 16 | 2021-05-04 15:23
2329 | 3 | 3 |  | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 16 | 2021-05-04 15:23
2330 | 3 | 3 |  | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 16 | 2021-05-04 15:23
2331 | 3 | 3 |  | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 16 | 2021-05-04 15:23
2332 | 3 | 3 |  | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 16 | 2021-05-04 15:23
2333 | 3 | 3 |  | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 16 | 2021-05-04 15:23
2334 | 3 | 3 |  | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 16 | 2021-05-04 15:23
2335 | 3 | 3 |  | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 16 | 2021-05-04 15:23
2336 | 3 | 3 |  | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 16 | 2021-05-04 15:23
2337 | 3 | 3 |  | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 16 | 2021-05-04 15:23
2338 | 3 | 3 |  | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 16 | 2021-05-04 15:23
2339 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 16 | 2021-05-04 15:23
2340 | 2 | 2 |  | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 16 | 2021-05-04 15:23
2341 | 2 | 2 |  | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 16 | 2021-05-04 15:23
2342 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 16 | 2021-05-04 15:23
2343 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 16 | 2021-05-04 15:23
2344 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 16 | 2021-05-04 15:23
2345 | 2 | 2 |  | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 16 | 2021-05-04 15:23
2346 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 16 | 2021-05-04 15:23
2347 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 16 | 2021-05-04 15:23
2348 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 16 | 2021-05-04 15:23
2349 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 16 | 2021-05-04 15:23
2350 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 16 | 2021-05-04 15:23
2351 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 16 | 2021-05-04 15:23
2352 | 3 | 3 |  | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 16 | 2021-05-04 15:23
2353 | 2 | 2 |  | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 16 | 2021-05-04 15:23
2354 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 16 | 2021-05-04 15:23
2355 | 2 | 2 |  | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 16 | 2021-05-04 15:23
2356 | 2 | 2 |  | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 16 | 2021-05-04 15:23
2357 | 3 | 3 |  | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 16 | 2021-05-04 15:23
2358 | 3 | 3 |  | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 16 | 2021-05-04 15:23
2359 | 2 | 2 |  | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 16 | 2021-05-04 15:23
2360 | 2 | 2 |  | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 16 | 2021-05-04 15:23
2361 | 2 | 2 |  | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 16 | 2021-05-04 15:23
2362 | 3 | 3 |  | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 16 | 2021-05-04 15:23
2363 | 3 | 3 |  | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 16 | 2021-05-04 15:23
2364 | 3 | 3 |  | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 16 | 2021-05-04 15:23
2365 | 3 | 3 |  | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 16 | 2021-05-04 15:23
2366 | 3 | 3 |  | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 16 | 2021-05-04 15:23
2367 | 3 | 3 |  | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 16 | 2021-05-04 15:23
2368 | 2 | 2 |  | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 16 | 2021-05-04 15:23
2369 | 2 | 2 |  | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 16 | 2021-05-04 15:23
2370 | 2 | 2 |  | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 16 | 2021-05-04 15:23
2371 | 2 | 2 |  | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 16 | 2021-05-04 15:23
2372 | 2 | 2 |  | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 16 | 2021-05-04 15:23
2373 | 3 | 3 |  | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 16 | 2021-05-04 15:23
2374 | 3 | 3 |  | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 16 | 2021-05-04 15:23
2375 | 3 | 3 |  | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 16 | 2021-05-04 15:23
2376 | 3 | 3 |  | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 16 | 2021-05-04 15:23
2377 | 3 | 3 |  | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 16 | 2021-05-04 15:23
2378 | 3 | 3 |  | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 16 | 2021-05-04 15:23
2379 | 3 | 3 |  | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 16 | 2021-05-04 15:23
2380 | 2 | 2 |  | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 16 | 2021-05-04 15:23
2381 | 2 | 2 |  | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 16 | 2021-05-04 15:23
2382 | 3 | 3 |  | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 16 | 2021-05-04 15:23
2383 | 3 | 3 |  | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 16 | 2021-05-04 15:23
2384 | 3 | 3 |  | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 16 | 2021-05-04 15:23
2385 | 3 | 3 |  | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 16 | 2021-05-04 15:23
2386 | 3 | 3 |  | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 16 | 2021-05-04 15:23
2387 | 3 | 3 |  | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 16 | 2021-05-04 15:23
2388 | 3 | 3 |  | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 16 | 2021-05-04 15:23
2389 | 3 | 3 |  | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 16 | 2021-05-04 15:23
2390 | 3 | 3 |  | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 16 | 2021-05-04 15:23
2391 | 3 | 3 |  | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 16 | 2021-05-04 15:23
2392 | 3 | 3 |  | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 16 | 2021-05-04 15:23
2393 | 3 | 3 |  | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 16 | 2021-05-04 15:23
2394 | 2 | 2 |  | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 16 | 2021-05-04 15:23
2395 | 2 | 2 |  | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 16 | 2021-05-04 15:23
2396 | 2 | 2 |  | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 16 | 2021-05-04 15:23
2397 | 2 | 2 |  | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 16 | 2021-05-04 15:23
2398 | 2 | 2 |  | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 16 | 2021-05-04 15:23
2399 | 2 | 2 |  | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 16 | 2021-05-04 15:23
2400 | 3 | 3 |  | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 16 | 2021-05-04 15:23
2401 | 3 | 3 |  | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 16 | 2021-05-04 15:23
2402 | 3 | 3 |  | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 16 | 2021-05-04 15:23
2403 | 3 | 3 |  | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 16 | 2021-05-04 15:23
2404 | 3 | 3 |  | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 16 | 2021-05-04 15:23
2405 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 16 | 2021-05-04 15:23
2406 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 16 | 2021-05-04 15:23
2407 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 16 | 2021-05-04 15:23
2408 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 16 | 2021-05-04 15:23
2409 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 16 | 2021-05-04 15:23
2410 | 3 | 3 |  | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 16 | 2021-05-04 15:23
2411 | 3 | 3 |  | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:23
2412 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 16 | 2021-05-04 15:23
2413 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 16 | 2021-05-04 15:23
2414 | 3 | 3 |  | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 16 | 2021-05-04 15:23
2415 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 16 | 2021-05-04 15:23
2416 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 16 | 2021-05-04 15:23
2417 | 3 | 3 |  | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 16 | 2021-05-04 15:23
2418 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 16 | 2021-05-04 15:23
2419 | 3 | 3 |  | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 16 | 2021-05-04 15:23
2420 | 3 | 3 |  | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 16 | 2021-05-04 15:23
2421 | 3 | 3 |  | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:23
2422 | 3 | 3 |  | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 16 | 2021-05-04 15:23
2423 | 3 | 3 |  | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 16 | 2021-05-04 15:23
2424 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 16 | 2021-05-04 15:23
2425 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:23
2426 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 16 | 2021-05-04 15:23
2427 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 16 | 2021-05-04 15:23
2428 | 3 | 3 |  | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 16 | 2021-05-04 15:23
2429 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 16 | 2021-05-04 15:23
2430 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 16 | 2021-05-04 15:23
2431 | 3 | 3 |  | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 16 | 2021-05-04 15:23
2432 | 3 | 3 |  | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 16 | 2021-05-04 15:23
2433 | 3 | 3 |  | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 16 | 2021-05-04 15:23
2434 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 16 | 2021-05-04 15:23
2435 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 16 | 2021-05-04 15:23
2436 | 3 | 3 |  | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 16 | 2021-05-04 15:23
2437 | 3 | 3 |  | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 16 | 2021-05-04 15:23
2438 | 3 | 3 |  | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 16 | 2021-05-04 15:23
2439 | 3 | 3 |  | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 16 | 2021-05-04 15:23
2440 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 16 | 2021-05-04 15:23
2441 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 16 | 2021-05-04 15:23
2442 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 16 | 2021-05-04 15:23
2443 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 16 | 2021-05-04 15:23
2444 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 16 | 2021-05-04 15:23
2445 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 16 | 2021-05-04 15:23
2446 | 3 | 3 |  | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 16 | 2021-05-04 15:23
2447 | 3 | 3 |  | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 16 | 2021-05-04 15:23
2448 | 3 | 3 |  | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 16 | 2021-05-04 15:23
2449 | 3 | 3 |  | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 16 | 2021-05-04 15:23
2450 | 3 | 3 |  | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 16 | 2021-05-04 15:23
2451 | 3 | 3 |  | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 16 | 2021-05-04 15:23
2452 | 3 | 3 |  | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 16 | 2021-05-04 15:23
2453 | 3 | 3 |  | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 16 | 2021-05-04 15:23
2454 | 3 | 3 |  | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 16 | 2021-05-04 15:23
2455 | 3 | 3 |  | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 16 | 2021-05-04 15:23
2456 | 3 | 3 |  | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 16 | 2021-05-04 15:23
2457 | 3 | 3 |  | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 16 | 2021-05-04 15:23
2458 | 3 | 3 |  | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 16 | 2021-05-04 15:23
2459 | 3 | 3 |  | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 16 | 2021-05-04 15:23
2460 | 3 | 3 |  | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 16 | 2021-05-04 15:23
2461 | 3 | 3 |  | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 16 | 2021-05-04 15:23
2462 | 3 | 3 |  | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 16 | 2021-05-04 15:23
2463 | 3 | 3 |  | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 16 | 2021-05-04 15:23
2464 | 3 | 3 |  | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 16 | 2021-05-04 15:23
2465 | 3 | 3 |  | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 16 | 2021-05-04 15:23
2466 | 3 | 3 |  | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 16 | 2021-05-04 15:23
2467 | 3 | 3 |  | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 16 | 2021-05-04 15:23
2468 | 3 | 3 |  | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 16 | 2021-05-04 15:23
2469 | 3 | 3 |  | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 16 | 2021-05-04 15:23
2470 | 1 | 1 |  | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 16 | 2021-05-04 15:23
2471 | 3 | 3 |  | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 16 | 2021-05-04 15:23
2472 | 3 | 3 |  | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 16 | 2021-05-04 15:23
2473 | 3 | 3 |  | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 16 | 2021-05-04 15:23
2474 | 3 | 3 |  | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 16 | 2021-05-04 15:23
2475 | 3 | 3 |  | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 16 | 2021-05-04 15:23
2476 | 3 | 3 |  | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 16 | 2021-05-04 15:23
2477 | 3 | 3 |  | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 16 | 2021-05-04 15:23
2478 | 3 | 3 |  | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 16 | 2021-05-04 15:23
2479 | 3 | 3 |  | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 16 | 2021-05-04 15:23
2480 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 16 | 2021-05-04 15:23
2481 | 2 | 2 |  | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 16 | 2021-05-04 15:23
2482 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 16 | 2021-05-04 15:23
2483 | 2 | 2 |  | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 16 | 2021-05-04 15:23
2484 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 16 | 2021-05-04 15:23
2485 | 2 | 2 |  | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 16 | 2021-05-04 15:23
2486 | 2 | 2 |  | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 16 | 2021-05-04 15:23
2487 | 2 | 2 |  | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 16 | 2021-05-04 15:23
2488 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 16 | 2021-05-04 15:23
2489 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 16 | 2021-05-04 15:23
2490 | 2 | 2 |  | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 16 | 2021-05-04 15:23
2491 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 16 | 2021-05-04 15:23
2492 | 2 | 2 |  | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 16 | 2021-05-04 15:23
2493 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 16 | 2021-05-04 15:23
2494 | 2 | 2 |  | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 16 | 2021-05-04 15:23
2495 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 16 | 2021-05-04 15:23
2496 | 2 | 2 |  | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 16 | 2021-05-04 15:23
2497 | 2 | 2 |  | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 16 | 2021-05-04 15:23
2498 | 2 | 2 |  | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 16 | 2021-05-04 15:23
2499 | 2 | 2 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 16 | 2021-05-04 15:23
2500 | 2 | 2 |  | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 16 | 2021-05-04 15:23
2501 | 2 | 2 |  | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 16 | 2021-05-04 15:23
2502 | 2 | 2 |  | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 16 | 2021-05-04 15:23
2503 | 2 | 2 |  | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 16 | 2021-05-04 15:23
2504 | 2 | 2 |  | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 16 | 2021-05-04 15:23
2505 | 2 | 2 |  | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 16 | 2021-05-04 15:23
2506 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 16 | 2021-05-04 15:23
2507 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 16 | 2021-05-04 15:23
2508 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 16 | 2021-05-04 15:23
2509 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 16 | 2021-05-04 15:23
2510 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 16 | 2021-05-04 15:23
2511 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 16 | 2021-05-04 15:23
2512 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 16 | 2021-05-04 15:23
2513 | 2 | 2 |  | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 16 | 2021-05-04 15:23
2514 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 16 | 2021-05-04 15:23
2515 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 16 | 2021-05-04 15:23
2516 | 2 | 2 |  | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 16 | 2021-05-04 15:23
2517 | 2 | 2 |  | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 16 | 2021-05-04 15:23
2518 | 2 | 2 |  | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 16 | 2021-05-04 15:23
2519 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 16 | 2021-05-04 15:23
2520 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 16 | 2021-05-04 15:23
2521 | 2 | 2 |  | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 16 | 2021-05-04 15:23
2522 | 2 | 2 |  | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 16 | 2021-05-04 15:23
2523 | 2 | 2 |  | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 16 | 2021-05-04 15:23
2524 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 16 | 2021-05-04 15:23
2525 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 16 | 2021-05-04 15:23
2526 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 16 | 2021-05-04 15:23
2527 | 2 | 2 |  | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 16 | 2021-05-04 15:23
2528 | 2 | 2 |  | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 16 | 2021-05-04 15:23
2529 | 2 | 2 |  | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 16 | 2021-05-04 15:23
2530 | 2 | 2 |  | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 16 | 2021-05-04 15:23
2531 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 16 | 2021-05-04 15:23
2532 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 16 | 2021-05-04 15:23
2533 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 16 | 2021-05-04 15:23
2534 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 16 | 2021-05-04 15:23
2535 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 16 | 2021-05-04 15:23
2536 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 16 | 2021-05-04 15:23
2537 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 16 | 2021-05-04 15:23
2538 | 2 | 2 |  | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 16 | 2021-05-04 15:23
2539 | 1 | 1 |  | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 16 | 2021-05-04 15:23
2540 | 3 | 3 |  | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 16 | 2021-05-04 15:23
2541 | 1 | 1 |  | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 16 | 2021-05-04 15:23
2542 | 3 | 3 |  | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 16 | 2021-05-04 15:23
2543 | 1 | 1 |  | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 16 | 2021-05-04 15:23
2544 | 1 | 1 |  | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 16 | 2021-05-04 15:23
2545 | 1 | 1 |  | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 16 | 2021-05-04 15:23
2546 | 3 | 3 |  | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 16 | 2021-05-04 15:23
2547 | 3 | 3 |  | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 16 | 2021-05-04 15:23
2548 | 1 | 1 |  | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 16 | 2021-05-04 15:23
2549 | 1 | 1 |  | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 16 | 2021-05-04 15:23
2550 | 3 | 3 |  | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 16 | 2021-05-04 15:23
2551 | 1 | 1 |  | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 16 | 2021-05-04 15:23
2552 | 1 | 1 |  | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 16 | 2021-05-04 15:23
2553 | 3 | 3 |  | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 16 | 2021-05-04 15:23
2554 | 1 | 1 |  | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 16 | 2021-05-04 15:23
2555 | 1 | 1 |  | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 16 | 2021-05-04 15:23
2556 | 1 | 1 |  | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 16 | 2021-05-04 15:23
2557 | 1 | 1 |  | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 16 | 2021-05-04 15:23
2558 | 1 | 1 |  | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 16 | 2021-05-04 15:23
2559 | 3 | 3 |  | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 16 | 2021-05-04 15:23
2560 | 1 | 1 |  | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 16 | 2021-05-04 15:23
2561 | 3 | 3 |  | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 16 | 2021-05-04 15:23
2562 | 3 | 3 |  | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 16 | 2021-05-04 15:23
2563 | 3 | 3 |  | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 16 | 2021-05-04 15:23
2564 | 3 | 3 |  | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 16 | 2021-05-04 15:23
2565 | 3 | 3 |  | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 16 | 2021-05-04 15:23
2566 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 16 | 2021-05-04 15:23
2567 | 2 | 2 |  | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 16 | 2021-05-04 15:23
2568 | 3 | 3 |  | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 16 | 2021-05-04 15:23
2569 | 3 | 3 |  | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 16 | 2021-05-04 15:23
2570 | 3 | 3 |  | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 16 | 2021-05-04 15:23
2571 | 3 | 3 |  | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 16 | 2021-05-04 15:23
2572 | 1 | 1 |  | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 16 | 2021-05-04 15:23
2573 | 3 | 3 |  | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 16 | 2021-05-04 15:23
2574 | 3 | 3 |  | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 16 | 2021-05-04 15:23
2575 | 3 | 3 |  | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 16 | 2021-05-04 15:23
2576 | 3 | 3 |  | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 16 | 2021-05-04 15:23
2577 | 3 | 3 |  | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 16 | 2021-05-04 15:23
2578 | 3 | 3 |  | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 16 | 2021-05-04 15:23
2579 | 3 | 3 |  | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 16 | 2021-05-04 15:23
2580 | 3 | 3 |  | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 16 | 2021-05-04 15:23
2581 | 3 | 3 |  | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 16 | 2021-05-04 15:23
2582 | 3 | 3 |  | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 16 | 2021-05-04 15:23
2583 | 3 | 3 |  | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 16 | 2021-05-04 15:23
2584 | 3 | 3 |  | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 16 | 2021-05-04 15:23
2585 | 3 | 3 |  | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 16 | 2021-05-04 15:23
2586 | 3 | 3 |  | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 16 | 2021-05-04 15:23
2587 | 3 | 3 |  | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 16 | 2021-05-04 15:23
2588 | 3 | 3 |  | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 16 | 2021-05-04 15:23
2589 | 3 | 3 |  | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 16 | 2021-05-04 15:23
2590 | 3 | 3 |  | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 16 | 2021-05-04 15:23
2591 | 3 | 3 |  | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 16 | 2021-05-04 15:23
2592 | 3 | 3 |  | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 16 | 2021-05-04 15:23
2593 | 3 | 3 |  | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 16 | 2021-05-04 15:23
2594 | 3 | 3 |  | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 16 | 2021-05-04 15:23
2595 | 2 | 2 |  | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 16 | 2021-05-04 15:23
2596 | 3 | 3 |  | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 16 | 2021-05-04 15:23
2597 | 3 | 3 |  | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 16 | 2021-05-04 15:23
2598 | 3 | 3 |  | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 16 | 2021-05-04 15:23
2599 | 3 | 3 |  | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 16 | 2021-05-04 15:23
2600 | 3 | 3 |  | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 16 | 2021-05-04 15:23
2601 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 16 | 2021-05-04 15:23
2602 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 16 | 2021-05-04 15:23
2603 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 16 | 2021-05-04 15:23
2604 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 16 | 2021-05-04 15:23
2605 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 16 | 2021-05-04 15:23
2606 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 16 | 2021-05-04 15:23
2607 | 3 | 3 |  | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 16 | 2021-05-04 15:23
2608 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 16 | 2021-05-04 15:23
2609 | 2 | 2 |  | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 16 | 2021-05-04 15:23
2610 | 3 | 3 |  | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 16 | 2021-05-04 15:23
2611 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 16 | 2021-05-04 15:23
2612 | 3 | 3 |  | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 16 | 2021-05-04 15:23
2613 | 2 | 2 |  | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 16 | 2021-05-04 15:23
2614 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 16 | 2021-05-04 15:23
2615 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 16 | 2021-05-04 15:23
2616 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 16 | 2021-05-04 15:23
2617 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 16 | 2021-05-04 15:23
2618 | 3 | 3 |  | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 16 | 2021-05-04 15:23
2619 | 2 | 2 |  | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 16 | 2021-05-04 15:23
2620 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 16 | 2021-05-04 15:23
2621 | 2 | 2 |  | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 16 | 2021-05-04 15:23
2622 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 16 | 2021-05-04 15:23
2623 | 2 | 2 |  | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 16 | 2021-05-04 15:23
2624 | 3 | 3 |  | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 16 | 2021-05-04 15:23
2625 | 3 | 3 |  | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 16 | 2021-05-04 15:23
2626 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 16 | 2021-05-04 15:23
2627 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 16 | 2021-05-04 15:23
2628 | 3 | 3 |  | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 16 | 2021-05-04 15:23
2629 | 3 | 3 |  | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 16 | 2021-05-04 15:23
2630 | 3 | 3 |  | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 16 | 2021-05-04 15:23
2631 | 3 | 3 |  | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 16 | 2021-05-04 15:23
2632 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 16 | 2021-05-04 15:23
2633 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 16 | 2021-05-04 15:23
2634 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 16 | 2021-05-04 15:23
2635 | 3 | 3 |  | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 16 | 2021-05-04 15:23
2636 | 3 | 3 |  | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 16 | 2021-05-04 15:23
2637 | 3 | 3 |  | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 16 | 2021-05-04 15:23
2638 | 3 | 3 |  | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 16 | 2021-05-04 15:23
2639 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 16 | 2021-05-04 15:23
2640 | 3 | 3 |  | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 16 | 2021-05-04 15:23
2641 | 3 | 3 |  | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 16 | 2021-05-04 15:23
2642 | 3 | 3 |  | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 16 | 2021-05-04 15:23
2643 | 3 | 3 |  | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 16 | 2021-05-04 15:23
2644 | 3 | 3 |  | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 16 | 2021-05-04 15:23
2645 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 16 | 2021-05-04 15:23
2646 | 2 | 2 |  | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 16 | 2021-05-04 15:23
2647 | 3 | 3 |  | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 16 | 2021-05-04 15:23
2648 | 3 | 3 |  | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 16 | 2021-05-04 15:23
2649 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 16 | 2021-05-04 15:23
2650 | 3 | 3 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 16 | 2021-05-04 15:23
2651 | 3 | 3 |  | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 16 | 2021-05-04 15:23
2652 | 3 | 3 |  | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 16 | 2021-05-04 15:23
2653 | 3 | 3 |  | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 16 | 2021-05-04 15:23
2654 | 3 | 3 |  | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 16 | 2021-05-04 15:23
2655 | 3 | 3 |  | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 16 | 2021-05-04 15:23
2656 | 2 | 2 |  | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 16 | 2021-05-04 15:23
2657 | 2 | 2 |  | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 16 | 2021-05-04 15:23
2658 | 3 | 3 |  | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 16 | 2021-05-04 15:23
2659 | 3 | 3 |  | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 16 | 2021-05-04 15:23
2660 | 2 | 2 |  | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 16 | 2021-05-04 15:23
2661 | 3 | 3 |  | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 16 | 2021-05-04 15:23
2662 | 2 | 2 |  | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 16 | 2021-05-04 15:23
2663 | 3 | 3 |  | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 16 | 2021-05-04 15:23
2664 | 3 | 3 |  | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 16 | 2021-05-04 15:23
2665 | 1 | 1 |  | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 16 | 2021-05-04 15:23
2666 | 2 | 2 |  | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 16 | 2021-05-04 15:23
2667 | 3 | 3 |  | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 16 | 2021-05-04 15:23
2668 | 1 | 1 |  | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 16 | 2021-05-04 15:23
2669 | 3 | 3 |  | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 16 | 2021-05-04 15:23
2670 | 3 | 3 |  | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 16 | 2021-05-04 15:23
2671 | 3 | 3 |  | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:23
2672 | 3 | 3 |  | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 16 | 2021-05-04 15:23
2673 | 3 | 3 |  | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 16 | 2021-05-04 15:23
2674 | 2 | 2 |  | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 16 | 2021-05-04 15:23
2675 | 3 | 3 |  | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 16 | 2021-05-04 15:23
2676 | 3 | 3 |  | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 16 | 2021-05-04 15:23
2677 | 2 | 2 |  | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 16 | 2021-05-04 15:23
2678 | 3 | 3 |  | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:23
2679 | 3 | 3 |  | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 16 | 2021-05-04 15:23
2680 | 3 | 3 |  | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 16 | 2021-05-04 15:23
2681 | 2 | 2 |  | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 16 | 2021-05-04 15:23
2682 | 3 | 3 |  | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 16 | 2021-05-04 15:23
2683 | 3 | 3 |  | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 16 | 2021-05-04 15:23
2684 | 3 | 3 |  | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 16 | 2021-05-04 15:23
2685 | 2 | 2 |  | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 16 | 2021-05-04 15:23
2686 | 2 | 2 |  | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 16 | 2021-05-04 15:23
2687 | 3 | 3 |  | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 16 | 2021-05-04 15:23
2688 | 2 | 2 |  | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 16 | 2021-05-04 15:23
2689 | 3 | 3 |  | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 16 | 2021-05-04 15:23
2690 | 3 | 3 |  | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 16 | 2021-05-04 15:23
2691 | 3 | 3 |  | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 16 | 2021-05-04 15:23
2692 | 2 | 2 |  | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 16 | 2021-05-04 15:23
2693 | 2 | 2 |  | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 16 | 2021-05-04 15:23
2694 | 3 | 3 |  | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:23
2695 | 3 | 3 |  | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 16 | 2021-05-04 15:23
2696 | 3 | 3 |  | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 16 | 2021-05-04 15:23
2697 | 3 | 3 |  | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 16 | 2021-05-04 15:23
2698 | 3 | 3 |  | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:23
2699 | 3 | 3 |  | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:23
2700 | 3 | 3 |  | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 16 | 2021-05-04 15:23
2701 | 3 | 3 |  | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 16 | 2021-05-04 15:23
2702 | 2 | 2 |  | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:23
2703 | 3 | 3 |  | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 16 | 2021-05-04 15:23
2704 | 3 | 3 |  | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 16 | 2021-05-04 15:23
2705 | 3 | 3 |  | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 16 | 2021-05-04 15:23
2706 | 3 | 3 |  | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 16 | 2021-05-04 15:23
2707 | 2 | 2 |  | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:23
2708 | 3 | 3 |  | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 16 | 2021-05-04 15:23
2709 | 3 | 3 |  | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 16 | 2021-05-04 15:23
2710 | 3 | 3 |  | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 16 | 2021-05-04 15:23
2711 | 3 | 3 |  | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 16 | 2021-05-04 15:23
2712 | 2 | 2 |  | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 16 | 2021-05-04 15:23
2713 | 3 | 3 |  | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:23
2714 | 2 | 2 |  | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 16 | 2021-05-04 15:23
2715 | 2 | 2 |  | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 16 | 2021-05-04 15:23
2716 | 3 | 3 |  | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 16 | 2021-05-04 15:23
2717 | 3 | 3 |  | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 16 | 2021-05-04 15:23
2718 | 2 | 2 |  | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 16 | 2021-05-04 15:23
2719 | 2 | 2 |  | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 16 | 2021-05-04 15:23
2720 | 3 | 3 |  | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 16 | 2021-05-04 15:23
2721 | 2 | 2 |  | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 16 | 2021-05-04 15:23
2722 | 3 | 3 |  | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 16 | 2021-05-04 15:23
2723 | 2 | 2 |  | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 16 | 2021-05-04 15:23
2724 | 2 | 2 |  | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 16 | 2021-05-04 15:23
2725 | 3 | 3 |  | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 16 | 2021-05-04 15:23
2726 | 2 | 2 |  | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 16 | 2021-05-04 15:23
2727 | 3 | 3 |  | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 16 | 2021-05-04 15:23
2728 | 3 | 3 |  | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 16 | 2021-05-04 15:23
2729 | 2 | 2 |  | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 16 | 2021-05-04 15:23
2730 | 2 | 2 |  | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 16 | 2021-05-04 15:23
2731 | 3 | 3 |  | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 16 | 2021-05-04 15:23
2732 | 3 | 3 |  | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:23
2733 | 2 | 2 |  | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 16 | 2021-05-04 15:23
2734 | 2 | 2 |  | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 16 | 2021-05-04 15:23
2735 | 3 | 3 |  | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 16 | 2021-05-04 15:23
2736 | 3 | 3 |  | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:23
2737 | 3 | 3 |  | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 16 | 2021-05-04 15:23
2738 | 2 | 2 |  | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 16 | 2021-05-04 15:23
2739 | 3 | 3 |  | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 16 | 2021-05-04 15:23
2740 | 2 | 2 |  | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 16 | 2021-05-04 15:23
2741 | 3 | 3 |  | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 16 | 2021-05-04 15:23
2742 | 1 | 1 |  | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 16 | 2021-05-04 15:23
2743 | 3 | 3 |  | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 16 | 2021-05-04 15:23
2744 | 2 | 2 |  | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 16 | 2021-05-04 15:23
2745 | 3 | 3 |  | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 16 | 2021-05-04 15:23
2746 | 3 | 3 |  | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 16 | 2021-05-04 15:23
2747 | 3 | 3 |  | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 16 | 2021-05-04 15:23
2748 | 3 | 3 |  | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 16 | 2021-05-04 15:23
2749 | 3 | 3 |  | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 16 | 2021-05-04 15:23
2750 | 2 | 2 |  | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 16 | 2021-05-04 15:23
2751 | 2 | 2 |  | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 16 | 2021-05-04 15:23
2752 | 3 | 3 |  | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 16 | 2021-05-04 15:23
2753 | 3 | 3 |  | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 16 | 2021-05-04 15:23
2754 | 3 | 3 |  | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 16 | 2021-05-04 15:23
2755 | 2 | 2 |  | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 16 | 2021-05-04 15:23
2756 | 3 | 3 |  | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 16 | 2021-05-04 15:23
2757 | 2 | 2 |  | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 16 | 2021-05-04 15:23
2758 | 2 | 2 |  | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 16 | 2021-05-04 15:23
2759 | 3 | 3 |  | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 16 | 2021-05-04 15:23
2760 | 3 | 3 |  | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 16 | 2021-05-04 15:23
2761 | 1 | 1 |  | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 16 | 2021-05-04 15:23
2762 | 1 | 1 |  | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 16 | 2021-05-04 15:23
2763 | 3 | 3 |  | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 16 | 2021-05-04 15:23
2764 | 3 | 3 |  | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 16 | 2021-05-04 15:23
2765 | 3 | 3 |  | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 16 | 2021-05-04 15:23
2766 | 1 | 1 |  | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 16 | 2021-05-04 15:23
2767 | 2 | 2 |  | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 16 | 2021-05-04 15:23
2768 | 2 | 2 |  | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 16 | 2021-05-04 15:23
2769 | 2 | 2 |  | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 16 | 2021-05-04 15:23
2770 | 1 | 1 |  | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 16 | 2021-05-04 15:23
2771 | 1 | 1 |  | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 16 | 2021-05-04 15:23
2772 | 3 | 3 |  | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 16 | 2021-05-04 15:23
2773 | 2 | 2 |  | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 16 | 2021-05-04 15:23
2774 | 2 | 2 |  | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 16 | 2021-05-04 15:23
2775 | 3 | 3 |  | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 16 | 2021-05-04 15:23
2776 | 3 | 3 |  | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 16 | 2021-05-04 15:23
2777 | 3 | 3 |  | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 16 | 2021-05-04 15:23
2778 | 3 | 3 |  | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 16 | 2021-05-04 15:23
2779 | 2 | 2 |  | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 16 | 2021-05-04 15:23
2780 | 3 | 3 |  | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 16 | 2021-05-04 15:23
2781 | 3 | 3 |  | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 16 | 2021-05-04 15:23
2782 | 2 | 2 |  | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 16 | 2021-05-04 15:23
2783 | 3 | 3 |  | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 16 | 2021-05-04 15:23
2784 | 1 | 1 |  | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 16 | 2021-05-04 15:23
2785 | 2 | 2 |  | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 16 | 2021-05-04 15:23
2786 | 3 | 3 |  | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 16 | 2021-05-04 15:23
2787 | 2 | 2 |  | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 16 | 2021-05-04 15:23
2788 | 1 | 1 |  | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 16 | 2021-05-04 15:23
2789 | 3 | 3 |  | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 16 | 2021-05-04 15:23
2790 | 1 | 1 |  | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 16 | 2021-05-04 15:23
2791 | 3 | 3 |  | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 16 | 2021-05-04 15:23
2792 | 1 | 1 |  | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 16 | 2021-05-04 15:23
2793 | 3 | 3 |  | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 16 | 2021-05-04 15:23
2794 | 2 | 2 |  | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 16 | 2021-05-04 15:23
2795 | 3 | 3 |  | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 16 | 2021-05-04 15:23
2796 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 18 | 2021-05-05 07:20
2797 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 18 | 2021-05-05 07:20
2798 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 18 | 2021-05-05 07:20
2799 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 18 | 2021-05-05 07:20
2800 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 18 | 2021-05-05 07:20
2801 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 18 | 2021-05-05 07:20
2802 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 18 | 2021-05-05 07:20
2803 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 18 | 2021-05-05 07:20
2804 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 18 | 2021-05-05 07:20
2805 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 18 | 2021-05-05 07:20
2806 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 18 | 2021-05-05 07:20
2807 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 18 | 2021-05-05 07:20
2808 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 18 | 2021-05-05 07:20
2809 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 18 | 2021-05-05 07:20
2810 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 18 | 2021-05-05 07:20
2811 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 18 | 2021-05-05 07:20
2812 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 18 | 2021-05-05 07:20
2813 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 18 | 2021-05-05 07:20
2814 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 18 | 2021-05-05 07:20
2815 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 18 | 2021-05-05 07:20
2816 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 18 | 2021-05-05 07:20
2817 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 18 | 2021-05-05 07:20
2818 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 18 | 2021-05-05 07:20
2819 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 18 | 2021-05-05 07:20
2820 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 18 | 2021-05-05 07:20
2821 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 18 | 2021-05-05 07:20
2822 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 18 | 2021-05-05 07:20
2823 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 18 | 2021-05-05 07:20
2824 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 18 | 2021-05-05 07:20
2825 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 18 | 2021-05-05 07:20
2826 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 18 | 2021-05-05 07:20
2827 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 18 | 2021-05-05 07:20
2828 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 18 | 2021-05-05 07:20
2829 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 18 | 2021-05-05 07:20
2830 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 18 | 2021-05-05 07:20
2831 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 18 | 2021-05-05 07:20
2832 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 18 | 2021-05-05 07:20
2833 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 18 | 2021-05-05 07:20
2834 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 18 | 2021-05-05 07:20
2835 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 18 | 2021-05-05 07:20
2836 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 18 | 2021-05-05 07:20
2837 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 18 | 2021-05-05 07:20
2838 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 18 | 2021-05-05 07:20
2839 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 18 | 2021-05-05 07:20
2840 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 18 | 2021-05-05 07:20
2841 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 18 | 2021-05-05 07:20
2842 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 18 | 2021-05-05 07:20
2843 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 18 | 2021-05-05 07:20
2844 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 18 | 2021-05-05 07:20
2845 | 2 | 2 |  | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 18 | 2021-05-05 07:20
2846 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 18 | 2021-05-05 07:20
2847 | 3 | 3 |  | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 18 | 2021-05-05 07:20
2848 | 3 | 3 |  | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 18 | 2021-05-05 07:20
2849 | 3 | 3 |  | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 18 | 2021-05-05 07:20
2850 | 3 | 3 |  | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 18 | 2021-05-05 07:20
2851 | 3 | 3 |  | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 18 | 2021-05-05 07:20
2852 | 3 | 3 |  | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 18 | 2021-05-05 07:20
2853 | 3 | 3 |  | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 18 | 2021-05-05 07:20
2854 | 3 | 3 |  | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 18 | 2021-05-05 07:20
2855 | 2 | 2 |  | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 18 | 2021-05-05 07:20
2856 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 18 | 2021-05-05 07:20
2857 | 2 | 2 |  | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 18 | 2021-05-05 07:20
2858 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 18 | 2021-05-05 07:20
2859 | 2 | 2 |  | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 18 | 2021-05-05 07:20
2860 | 2 | 2 |  | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 18 | 2021-05-05 07:20
2861 | 2 | 2 |  | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 18 | 2021-05-05 07:20
2862 | 2 | 2 |  | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 18 | 2021-05-05 07:20
2863 | 3 | 3 |  | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 18 | 2021-05-05 07:20
2864 | 3 | 3 |  | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 18 | 2021-05-05 07:20
2865 | 3 | 3 |  | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 18 | 2021-05-05 07:20
2866 | 3 | 3 |  | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 18 | 2021-05-05 07:20
2867 | 3 | 3 |  | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 18 | 2021-05-05 07:20
2868 | 3 | 3 |  | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 18 | 2021-05-05 07:20
2869 | 3 | 3 |  | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 18 | 2021-05-05 07:20
2870 | 3 | 3 |  | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 18 | 2021-05-05 07:20
2871 | 3 | 3 |  | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 18 | 2021-05-05 07:20
2872 | 3 | 3 |  | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 18 | 2021-05-05 07:20
2873 | 3 | 3 |  | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 18 | 2021-05-05 07:20
2874 | 3 | 3 |  | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 18 | 2021-05-05 07:20
2875 | 3 | 3 |  | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 18 | 2021-05-05 07:20
2876 | 3 | 3 |  | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 18 | 2021-05-05 07:20
2877 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 18 | 2021-05-05 07:20
2878 | 2 | 2 |  | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 18 | 2021-05-05 07:20
2879 | 2 | 2 |  | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 18 | 2021-05-05 07:20
2880 | 3 | 3 |  | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 18 | 2021-05-05 07:20
2881 | 2 | 2 |  | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 18 | 2021-05-05 07:20
2882 | 3 | 3 |  | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 18 | 2021-05-05 07:20
2883 | 3 | 3 |  | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 18 | 2021-05-05 07:20
2884 | 3 | 3 |  | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 18 | 2021-05-05 07:20
2885 | 2 | 2 |  | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 18 | 2021-05-05 07:20
2886 | 3 | 3 |  | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 18 | 2021-05-05 07:20
2887 | 3 | 3 |  | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 18 | 2021-05-05 07:20
2888 | 2 | 2 |  | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 18 | 2021-05-05 07:20
2889 | 1 | 1 |  | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 18 | 2021-05-05 07:20
2890 | 3 | 3 |  | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 18 | 2021-05-05 07:20
2891 | 1 | 1 |  | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 18 | 2021-05-05 07:20
2892 | 2 | 2 |  | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 18 | 2021-05-05 07:20
2893 | 3 | 3 |  | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 18 | 2021-05-05 07:20
2894 | 2 | 2 |  | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 18 | 2021-05-05 07:20
2895 | 3 | 3 |  | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 18 | 2021-05-05 07:20
2896 | 2 | 2 |  | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 18 | 2021-05-05 07:20
2897 | 3 | 3 |  | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 18 | 2021-05-05 07:20
2898 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 18 | 2021-05-05 07:20
2899 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 18 | 2021-05-05 07:20
2900 | 3 | 3 |  | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 18 | 2021-05-05 07:20
2901 | 3 | 3 |  | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 18 | 2021-05-05 07:20
2902 | 3 | 3 |  | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 18 | 2021-05-05 07:20
2903 | 3 | 3 |  | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 18 | 2021-05-05 07:20
2904 | 3 | 3 |  | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 18 | 2021-05-05 07:20
2905 | 3 | 3 |  | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 18 | 2021-05-05 07:20
2906 | 1 | 1 |  | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 18 | 2021-05-05 07:20
2907 | 1 | 1 |  | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 18 | 2021-05-05 07:20
2908 | 3 | 3 |  | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 18 | 2021-05-05 07:20
2909 | 3 | 3 |  | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 18 | 2021-05-05 07:20
2910 | 2 | 2 |  | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 18 | 2021-05-05 07:20
2911 | 3 | 3 |  | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 18 | 2021-05-05 07:20
2912 | 2 | 2 |  | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 18 | 2021-05-05 07:20
2913 | 2 | 2 |  | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 18 | 2021-05-05 07:20
2914 | 2 | 2 |  | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 18 | 2021-05-05 07:20
2915 | 3 | 3 |  | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 18 | 2021-05-05 07:20
2916 | 3 | 3 |  | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 18 | 2021-05-05 07:20
2917 | 3 | 3 |  | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 18 | 2021-05-05 07:20
2918 | 2 | 2 |  | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 18 | 2021-05-05 07:20
2919 | 3 | 3 |  | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 18 | 2021-05-05 07:20
2920 | 3 | 3 |  | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 18 | 2021-05-05 07:20
2921 | 3 | 3 |  | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 18 | 2021-05-05 07:20
2922 | 3 | 3 |  | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 18 | 2021-05-05 07:20
2923 | 3 | 3 |  | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 18 | 2021-05-05 07:20
2924 | 2 | 2 |  | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 18 | 2021-05-05 07:20
2925 | 3 | 3 |  | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 18 | 2021-05-05 07:20
2926 | 3 | 3 |  | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 18 | 2021-05-05 07:20
2927 | 3 | 3 |  | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 18 | 2021-05-05 07:20
2928 | 2 | 2 |  | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 18 | 2021-05-05 07:20
2929 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 18 | 2021-05-05 07:20
2930 | 3 | 3 |  | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 18 | 2021-05-05 07:20
2931 | 3 | 3 |  | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 18 | 2021-05-05 07:20
2932 | 3 | 3 |  | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 18 | 2021-05-05 07:20
2933 | 3 | 3 |  | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 18 | 2021-05-05 07:20
2934 | 3 | 3 |  | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 18 | 2021-05-05 07:20
2935 | 3 | 3 |  | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 18 | 2021-05-05 07:20
2936 | 3 | 3 |  | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 18 | 2021-05-05 07:20
2937 | 3 | 3 |  | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 18 | 2021-05-05 07:20
2938 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 18 | 2021-05-05 07:20
2939 | 3 | 3 |  | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 18 | 2021-05-05 07:20
2940 | 3 | 3 |  | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 18 | 2021-05-05 07:20
2941 | 3 | 3 |  | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 18 | 2021-05-05 07:20
2942 | 3 | 3 |  | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 18 | 2021-05-05 07:20
2943 | 2 | 2 |  | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 18 | 2021-05-05 07:20
2944 | 3 | 3 |  | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 18 | 2021-05-05 07:20
2945 | 3 | 3 |  | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 18 | 2021-05-05 07:20
2946 | 2 | 2 |  | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 18 | 2021-05-05 07:20
2947 | 3 | 3 |  | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 18 | 2021-05-05 07:20
2948 | 3 | 3 |  | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 18 | 2021-05-05 07:20
2949 | 3 | 3 |  | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 18 | 2021-05-05 07:20
2950 | 3 | 3 |  | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 18 | 2021-05-05 07:20
2951 | 3 | 3 |  | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 18 | 2021-05-05 07:20
2952 | 2 | 2 |  | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 18 | 2021-05-05 07:20
2953 | 3 | 3 |  | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 18 | 2021-05-05 07:20
2954 | 2 | 2 |  | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 18 | 2021-05-05 07:20
2955 | 3 | 3 |  | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 18 | 2021-05-05 07:20
2956 | 3 | 3 |  | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 18 | 2021-05-05 07:20
2957 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 18 | 2021-05-05 07:20
2958 | 3 | 3 |  | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 18 | 2021-05-05 07:20
2959 | 3 | 3 |  | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 18 | 2021-05-05 07:20
2960 | 3 | 3 |  | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 18 | 2021-05-05 07:20
2961 | 3 | 3 |  | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 18 | 2021-05-05 07:20
2962 | 3 | 3 |  | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 18 | 2021-05-05 07:20
2963 | 2 | 2 |  | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 18 | 2021-05-05 07:20
2964 | 3 | 3 |  | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 18 | 2021-05-05 07:20
2965 | 3 | 3 |  | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 18 | 2021-05-05 07:20
2966 | 2 | 2 |  | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 18 | 2021-05-05 07:20
2967 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 18 | 2021-05-05 07:20
2968 | 3 | 3 |  | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 18 | 2021-05-05 07:20
2969 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 18 | 2021-05-05 07:20
2970 | 2 | 2 |  | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 18 | 2021-05-05 07:20
2971 | 2 | 2 |  | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 18 | 2021-05-05 07:20
2972 | 3 | 3 |  | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 18 | 2021-05-05 07:20
2973 | 3 | 3 |  | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 18 | 2021-05-05 07:20
2974 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 18 | 2021-05-05 07:20
2975 | 3 | 3 |  | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 18 | 2021-05-05 07:20
2976 | 2 | 2 |  | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 18 | 2021-05-05 07:20
2977 | 2 | 2 |  | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 18 | 2021-05-05 07:20
2978 | 3 | 3 |  | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 18 | 2021-05-05 07:20
2979 | 3 | 3 |  | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 18 | 2021-05-05 07:20
2980 | 3 | 3 |  | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 18 | 2021-05-05 07:20
2981 | 2 | 2 |  | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 18 | 2021-05-05 07:20
2982 | 3 | 3 |  | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 18 | 2021-05-05 07:20
2983 | 3 | 3 |  | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 18 | 2021-05-05 07:20
2984 | 3 | 3 |  | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 18 | 2021-05-05 07:20
2985 | 3 | 3 |  | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 18 | 2021-05-05 07:20
2986 | 3 | 3 |  | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 18 | 2021-05-05 07:20
2987 | 2 | 2 |  | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 18 | 2021-05-05 07:20
2988 | 3 | 3 |  | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 18 | 2021-05-05 07:20
2989 | 3 | 3 |  | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 18 | 2021-05-05 07:20
2990 | 3 | 3 |  | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 18 | 2021-05-05 07:20
2991 | 3 | 3 |  | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 18 | 2021-05-05 07:20
2992 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 18 | 2021-05-05 07:20
2993 | 2 | 2 |  | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 18 | 2021-05-05 07:20
2994 | 3 | 3 |  | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 18 | 2021-05-05 07:20
2995 | 3 | 3 |  | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 18 | 2021-05-05 07:20
2996 | 3 | 3 |  | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 18 | 2021-05-05 07:20
2997 | 2 | 2 |  | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 18 | 2021-05-05 07:20
2998 | 3 | 3 |  | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 18 | 2021-05-05 07:20
2999 | 2 | 2 |  | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 18 | 2021-05-05 07:20
3000 | 3 | 3 |  | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 18 | 2021-05-05 07:20
3001 | 3 | 3 |  | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 18 | 2021-05-05 07:20
3002 | 3 | 3 |  | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 18 | 2021-05-05 07:20
3003 | 3 | 3 |  | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 18 | 2021-05-05 07:20
3004 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 18 | 2021-05-05 07:20
3005 | 2 | 2 |  | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 18 | 2021-05-05 07:20
3006 | 3 | 3 |  | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 18 | 2021-05-05 07:20
3007 | 3 | 3 |  | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 18 | 2021-05-05 07:20
3008 | 3 | 3 |  | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 18 | 2021-05-05 07:20
3009 | 3 | 3 |  | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 18 | 2021-05-05 07:20
3010 | 3 | 3 |  | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 18 | 2021-05-05 07:20
3011 | 3 | 3 |  | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 18 | 2021-05-05 07:20
3012 | 3 | 3 |  | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 18 | 2021-05-05 07:20
3013 | 3 | 3 |  | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 18 | 2021-05-05 07:20
3014 | 3 | 3 |  | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 18 | 2021-05-05 07:20
3015 | 3 | 3 |  | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 18 | 2021-05-05 07:20
3016 | 3 | 3 |  | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 18 | 2021-05-05 07:20
3017 | 3 | 3 |  | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 18 | 2021-05-05 07:20
3018 | 3 | 3 |  | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 18 | 2021-05-05 07:20
3019 | 3 | 3 |  | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 18 | 2021-05-05 07:20
3020 | 3 | 3 |  | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 18 | 2021-05-05 07:20
3021 | 3 | 3 |  | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 18 | 2021-05-05 07:20
3022 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 18 | 2021-05-05 07:20
3023 | 2 | 2 |  | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 18 | 2021-05-05 07:20
3024 | 2 | 2 |  | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 18 | 2021-05-05 07:20
3025 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 18 | 2021-05-05 07:20
3026 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 18 | 2021-05-05 07:20
3027 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 18 | 2021-05-05 07:20
3028 | 2 | 2 |  | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 18 | 2021-05-05 07:20
3029 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 18 | 2021-05-05 07:20
3030 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 18 | 2021-05-05 07:20
3031 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 18 | 2021-05-05 07:20
3032 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 18 | 2021-05-05 07:20
3033 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 18 | 2021-05-05 07:20
3034 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 18 | 2021-05-05 07:20
3035 | 3 | 3 |  | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 18 | 2021-05-05 07:20
3036 | 2 | 2 |  | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 18 | 2021-05-05 07:20
3037 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 18 | 2021-05-05 07:20
3038 | 2 | 2 |  | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 18 | 2021-05-05 07:20
3039 | 2 | 2 |  | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 18 | 2021-05-05 07:20
3040 | 3 | 3 |  | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 18 | 2021-05-05 07:20
3041 | 3 | 3 |  | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 18 | 2021-05-05 07:20
3042 | 2 | 2 |  | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 18 | 2021-05-05 07:20
3043 | 2 | 2 |  | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 18 | 2021-05-05 07:20
3044 | 2 | 2 |  | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 18 | 2021-05-05 07:20
3045 | 3 | 3 |  | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 18 | 2021-05-05 07:20
3046 | 3 | 3 |  | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 18 | 2021-05-05 07:20
3047 | 3 | 3 |  | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 18 | 2021-05-05 07:20
3048 | 3 | 3 |  | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 18 | 2021-05-05 07:20
3049 | 3 | 3 |  | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 18 | 2021-05-05 07:20
3050 | 3 | 3 |  | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 18 | 2021-05-05 07:20
3051 | 2 | 2 |  | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 18 | 2021-05-05 07:20
3052 | 2 | 2 |  | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 18 | 2021-05-05 07:20
3053 | 2 | 2 |  | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 18 | 2021-05-05 07:20
3054 | 2 | 2 |  | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 18 | 2021-05-05 07:20
3055 | 2 | 2 |  | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 18 | 2021-05-05 07:20
3056 | 3 | 3 |  | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 18 | 2021-05-05 07:20
3057 | 3 | 3 |  | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 18 | 2021-05-05 07:20
3058 | 3 | 3 |  | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 18 | 2021-05-05 07:20
3059 | 3 | 3 |  | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 18 | 2021-05-05 07:20
3060 | 3 | 3 |  | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 18 | 2021-05-05 07:20
3061 | 3 | 3 |  | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 18 | 2021-05-05 07:20
3062 | 3 | 3 |  | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 18 | 2021-05-05 07:20
3063 | 2 | 2 |  | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 18 | 2021-05-05 07:20
3064 | 2 | 2 |  | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 18 | 2021-05-05 07:20
3065 | 3 | 3 |  | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 18 | 2021-05-05 07:20
3066 | 3 | 3 |  | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 18 | 2021-05-05 07:20
3067 | 3 | 3 |  | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 18 | 2021-05-05 07:20
3068 | 3 | 3 |  | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 18 | 2021-05-05 07:20
3069 | 3 | 3 |  | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 18 | 2021-05-05 07:20
3070 | 3 | 3 |  | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 18 | 2021-05-05 07:20
3071 | 3 | 3 |  | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 18 | 2021-05-05 07:20
3072 | 3 | 3 |  | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 18 | 2021-05-05 07:20
3073 | 3 | 3 |  | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 18 | 2021-05-05 07:20
3074 | 3 | 3 |  | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 18 | 2021-05-05 07:20
3075 | 3 | 3 |  | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 18 | 2021-05-05 07:20
3076 | 3 | 3 |  | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 18 | 2021-05-05 07:20
3077 | 2 | 2 |  | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 18 | 2021-05-05 07:20
3078 | 2 | 2 |  | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 18 | 2021-05-05 07:20
3079 | 2 | 2 |  | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 18 | 2021-05-05 07:20
3080 | 2 | 2 |  | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 18 | 2021-05-05 07:20
3081 | 2 | 2 |  | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 18 | 2021-05-05 07:20
3082 | 2 | 2 |  | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 18 | 2021-05-05 07:20
3083 | 3 | 3 |  | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 18 | 2021-05-05 07:20
3084 | 3 | 3 |  | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 18 | 2021-05-05 07:20
3085 | 3 | 3 |  | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 18 | 2021-05-05 07:20
3086 | 3 | 3 |  | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 18 | 2021-05-05 07:20
3087 | 3 | 3 |  | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 18 | 2021-05-05 07:20
3088 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 18 | 2021-05-05 07:20
3089 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 18 | 2021-05-05 07:20
3090 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 18 | 2021-05-05 07:20
3091 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 18 | 2021-05-05 07:20
3092 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 18 | 2021-05-05 07:20
3093 | 3 | 3 |  | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 18 | 2021-05-05 07:20
3094 | 3 | 3 |  | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 18 | 2021-05-05 07:20
3095 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 18 | 2021-05-05 07:20
3096 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 18 | 2021-05-05 07:20
3097 | 3 | 3 |  | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 18 | 2021-05-05 07:20
3098 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 18 | 2021-05-05 07:20
3099 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 18 | 2021-05-05 07:20
3100 | 3 | 3 |  | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 18 | 2021-05-05 07:20
3101 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 18 | 2021-05-05 07:20
3102 | 3 | 3 |  | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 18 | 2021-05-05 07:20
3103 | 3 | 3 |  | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 18 | 2021-05-05 07:20
3104 | 3 | 3 |  | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 18 | 2021-05-05 07:20
3105 | 3 | 3 |  | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 18 | 2021-05-05 07:20
3106 | 3 | 3 |  | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 18 | 2021-05-05 07:20
3107 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 18 | 2021-05-05 07:20
3108 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 18 | 2021-05-05 07:20
3109 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 18 | 2021-05-05 07:20
3110 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 18 | 2021-05-05 07:20
3111 | 3 | 3 |  | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 18 | 2021-05-05 07:20
3112 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 18 | 2021-05-05 07:20
3113 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 18 | 2021-05-05 07:20
3114 | 3 | 3 |  | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 18 | 2021-05-05 07:20
3115 | 3 | 3 |  | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 18 | 2021-05-05 07:20
3116 | 3 | 3 |  | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 18 | 2021-05-05 07:20
3117 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 18 | 2021-05-05 07:20
3118 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 18 | 2021-05-05 07:20
3119 | 3 | 3 |  | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 18 | 2021-05-05 07:20
3120 | 3 | 3 |  | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 18 | 2021-05-05 07:20
3121 | 3 | 3 |  | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 18 | 2021-05-05 07:20
3122 | 3 | 3 |  | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 18 | 2021-05-05 07:20
3123 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 18 | 2021-05-05 07:20
3124 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 18 | 2021-05-05 07:20
3125 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 18 | 2021-05-05 07:20
3126 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 18 | 2021-05-05 07:20
3127 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 18 | 2021-05-05 07:20
3128 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 18 | 2021-05-05 07:20
3129 | 3 | 3 |  | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 18 | 2021-05-05 07:20
3130 | 3 | 3 |  | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 18 | 2021-05-05 07:20
3131 | 3 | 3 |  | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 18 | 2021-05-05 07:20
3132 | 3 | 3 |  | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 18 | 2021-05-05 07:20
3133 | 3 | 3 |  | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 18 | 2021-05-05 07:20
3134 | 3 | 3 |  | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 18 | 2021-05-05 07:20
3135 | 3 | 3 |  | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 18 | 2021-05-05 07:20
3136 | 3 | 3 |  | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 18 | 2021-05-05 07:20
3137 | 3 | 3 |  | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 18 | 2021-05-05 07:20
3138 | 3 | 3 |  | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 18 | 2021-05-05 07:20
3139 | 3 | 3 |  | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 18 | 2021-05-05 07:20
3140 | 3 | 3 |  | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 18 | 2021-05-05 07:20
3141 | 3 | 3 |  | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 18 | 2021-05-05 07:20
3142 | 3 | 3 |  | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 18 | 2021-05-05 07:20
3143 | 3 | 3 |  | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 18 | 2021-05-05 07:20
3144 | 3 | 3 |  | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 18 | 2021-05-05 07:20
3145 | 3 | 3 |  | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 18 | 2021-05-05 07:20
3146 | 3 | 3 |  | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 18 | 2021-05-05 07:20
3147 | 3 | 3 |  | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 18 | 2021-05-05 07:20
3148 | 3 | 3 |  | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 18 | 2021-05-05 07:20
3149 | 3 | 3 |  | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 18 | 2021-05-05 07:20
3150 | 3 | 3 |  | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 18 | 2021-05-05 07:20
3151 | 3 | 3 |  | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 18 | 2021-05-05 07:20
3152 | 3 | 3 |  | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 18 | 2021-05-05 07:20
3153 | 1 | 1 |  | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 18 | 2021-05-05 07:20
3154 | 3 | 3 |  | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 18 | 2021-05-05 07:20
3155 | 3 | 3 |  | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 18 | 2021-05-05 07:20
3156 | 3 | 3 |  | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 18 | 2021-05-05 07:20
3157 | 3 | 3 |  | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 18 | 2021-05-05 07:20
3158 | 3 | 3 |  | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 18 | 2021-05-05 07:20
3159 | 3 | 3 |  | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 18 | 2021-05-05 07:20
3160 | 3 | 3 |  | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 18 | 2021-05-05 07:20
3161 | 3 | 3 |  | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 18 | 2021-05-05 07:20
3162 | 3 | 3 |  | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 18 | 2021-05-05 07:20
3163 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 18 | 2021-05-05 07:20
3164 | 2 | 2 |  | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 18 | 2021-05-05 07:20
3165 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 18 | 2021-05-05 07:20
3166 | 2 | 2 |  | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 18 | 2021-05-05 07:20
3167 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 18 | 2021-05-05 07:20
3168 | 2 | 2 |  | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 18 | 2021-05-05 07:20
3169 | 2 | 2 |  | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 18 | 2021-05-05 07:20
3170 | 2 | 2 |  | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 18 | 2021-05-05 07:20
3171 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 18 | 2021-05-05 07:20
3172 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 18 | 2021-05-05 07:20
3173 | 2 | 2 |  | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 18 | 2021-05-05 07:20
3174 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 18 | 2021-05-05 07:20
3175 | 2 | 2 |  | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 18 | 2021-05-05 07:20
3176 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 18 | 2021-05-05 07:20
3177 | 2 | 2 |  | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 18 | 2021-05-05 07:20
3178 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 18 | 2021-05-05 07:20
3179 | 2 | 2 |  | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 18 | 2021-05-05 07:20
3180 | 2 | 2 |  | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 18 | 2021-05-05 07:20
3181 | 2 | 2 |  | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 18 | 2021-05-05 07:20
3182 | 2 | 2 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 18 | 2021-05-05 07:20
3183 | 2 | 2 |  | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 18 | 2021-05-05 07:20
3184 | 2 | 2 |  | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 18 | 2021-05-05 07:20
3185 | 2 | 2 |  | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 18 | 2021-05-05 07:20
3186 | 2 | 2 |  | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 18 | 2021-05-05 07:20
3187 | 2 | 2 |  | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 18 | 2021-05-05 07:20
3188 | 2 | 2 |  | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 18 | 2021-05-05 07:20
3189 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 18 | 2021-05-05 07:20
3190 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 18 | 2021-05-05 07:20
3191 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 18 | 2021-05-05 07:20
3192 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 18 | 2021-05-05 07:20
3193 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 18 | 2021-05-05 07:20
3194 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 18 | 2021-05-05 07:20
3195 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 18 | 2021-05-05 07:20
3196 | 2 | 2 |  | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 18 | 2021-05-05 07:20
3197 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 18 | 2021-05-05 07:20
3198 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 18 | 2021-05-05 07:20
3199 | 2 | 2 |  | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 18 | 2021-05-05 07:20
3200 | 2 | 2 |  | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 18 | 2021-05-05 07:20
3201 | 2 | 2 |  | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 18 | 2021-05-05 07:20
3202 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 18 | 2021-05-05 07:20
3203 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 18 | 2021-05-05 07:20
3204 | 2 | 2 |  | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 18 | 2021-05-05 07:20
3205 | 2 | 2 |  | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 18 | 2021-05-05 07:20
3206 | 2 | 2 |  | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 18 | 2021-05-05 07:20
3207 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 18 | 2021-05-05 07:20
3208 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 18 | 2021-05-05 07:20
3209 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 18 | 2021-05-05 07:20
3210 | 2 | 2 |  | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 18 | 2021-05-05 07:20
3211 | 2 | 2 |  | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 18 | 2021-05-05 07:20
3212 | 2 | 2 |  | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 18 | 2021-05-05 07:20
3213 | 2 | 2 |  | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 18 | 2021-05-05 07:20
3214 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 18 | 2021-05-05 07:20
3215 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 18 | 2021-05-05 07:20
3216 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 18 | 2021-05-05 07:20
3217 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 18 | 2021-05-05 07:20
3218 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 18 | 2021-05-05 07:20
3219 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 18 | 2021-05-05 07:20
3220 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 18 | 2021-05-05 07:20
3221 | 2 | 2 |  | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 18 | 2021-05-05 07:20
3222 | 1 | 1 |  | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 18 | 2021-05-05 07:20
3223 | 3 | 3 |  | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 18 | 2021-05-05 07:20
3224 | 1 | 1 |  | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 18 | 2021-05-05 07:20
3225 | 3 | 3 |  | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 18 | 2021-05-05 07:20
3226 | 1 | 1 |  | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 18 | 2021-05-05 07:20
3227 | 1 | 1 |  | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 18 | 2021-05-05 07:20
3228 | 1 | 1 |  | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 18 | 2021-05-05 07:20
3229 | 3 | 3 |  | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 18 | 2021-05-05 07:20
3230 | 3 | 3 |  | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 18 | 2021-05-05 07:20
3231 | 1 | 1 |  | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 18 | 2021-05-05 07:20
3232 | 1 | 1 |  | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 18 | 2021-05-05 07:20
3233 | 3 | 3 |  | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 18 | 2021-05-05 07:20
3234 | 1 | 1 |  | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 18 | 2021-05-05 07:20
3235 | 1 | 1 |  | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 18 | 2021-05-05 07:20
3236 | 3 | 3 |  | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 18 | 2021-05-05 07:20
3237 | 1 | 1 |  | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 18 | 2021-05-05 07:20
3238 | 1 | 1 |  | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 18 | 2021-05-05 07:20
3239 | 1 | 1 |  | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 18 | 2021-05-05 07:20
3240 | 1 | 1 |  | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 18 | 2021-05-05 07:20
3241 | 1 | 1 |  | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 18 | 2021-05-05 07:20
3242 | 3 | 3 |  | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 18 | 2021-05-05 07:20
3243 | 1 | 1 |  | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 18 | 2021-05-05 07:20
3244 | 3 | 3 |  | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 18 | 2021-05-05 07:20
3245 | 3 | 3 |  | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 18 | 2021-05-05 07:20
3246 | 3 | 3 |  | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 18 | 2021-05-05 07:20
3247 | 3 | 3 |  | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 18 | 2021-05-05 07:20
3248 | 3 | 3 |  | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 18 | 2021-05-05 07:20
3249 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 18 | 2021-05-05 07:20
3250 | 2 | 2 |  | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 18 | 2021-05-05 07:20
3251 | 3 | 3 |  | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 18 | 2021-05-05 07:20
3252 | 3 | 3 |  | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 18 | 2021-05-05 07:20
3253 | 3 | 3 |  | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 18 | 2021-05-05 07:20
3254 | 3 | 3 |  | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 18 | 2021-05-05 07:20
3255 | 1 | 1 |  | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 18 | 2021-05-05 07:20
3256 | 3 | 3 |  | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 18 | 2021-05-05 07:20
3257 | 3 | 3 |  | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 18 | 2021-05-05 07:20
3258 | 3 | 3 |  | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 18 | 2021-05-05 07:20
3259 | 3 | 3 |  | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 18 | 2021-05-05 07:20
3260 | 3 | 3 |  | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 18 | 2021-05-05 07:20
3261 | 3 | 3 |  | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 18 | 2021-05-05 07:20
3262 | 3 | 3 |  | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 18 | 2021-05-05 07:20
3263 | 3 | 3 |  | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 18 | 2021-05-05 07:20
3264 | 3 | 3 |  | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 18 | 2021-05-05 07:20
3265 | 3 | 3 |  | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 18 | 2021-05-05 07:20
3266 | 3 | 3 |  | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 18 | 2021-05-05 07:20
3267 | 3 | 3 |  | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 18 | 2021-05-05 07:20
3268 | 3 | 3 |  | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 18 | 2021-05-05 07:20
3269 | 3 | 3 |  | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 18 | 2021-05-05 07:20
3270 | 3 | 3 |  | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 18 | 2021-05-05 07:20
3271 | 3 | 3 |  | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 18 | 2021-05-05 07:20
3272 | 3 | 3 |  | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 18 | 2021-05-05 07:20
3273 | 3 | 3 |  | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 18 | 2021-05-05 07:20
3274 | 3 | 3 |  | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 18 | 2021-05-05 07:20
3275 | 3 | 3 |  | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 18 | 2021-05-05 07:20
3276 | 3 | 3 |  | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 18 | 2021-05-05 07:20
3277 | 3 | 3 |  | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 18 | 2021-05-05 07:20
3278 | 2 | 2 |  | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 18 | 2021-05-05 07:20
3279 | 3 | 3 |  | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 18 | 2021-05-05 07:20
3280 | 3 | 3 |  | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 18 | 2021-05-05 07:20
3281 | 3 | 3 |  | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 18 | 2021-05-05 07:20
3282 | 3 | 3 |  | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 18 | 2021-05-05 07:20
3283 | 3 | 3 |  | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 18 | 2021-05-05 07:20
3284 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 18 | 2021-05-05 07:20
3285 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 18 | 2021-05-05 07:20
3286 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 18 | 2021-05-05 07:20
3287 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 18 | 2021-05-05 07:20
3288 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 18 | 2021-05-05 07:20
3289 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 18 | 2021-05-05 07:20
3290 | 3 | 3 |  | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 18 | 2021-05-05 07:20
3291 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 18 | 2021-05-05 07:20
3292 | 2 | 2 |  | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 18 | 2021-05-05 07:20
3293 | 3 | 3 |  | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 18 | 2021-05-05 07:20
3294 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 18 | 2021-05-05 07:20
3295 | 3 | 3 |  | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 18 | 2021-05-05 07:20
3296 | 2 | 2 |  | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 18 | 2021-05-05 07:20
3297 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 18 | 2021-05-05 07:20
3298 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 18 | 2021-05-05 07:20
3299 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 18 | 2021-05-05 07:20
3300 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 18 | 2021-05-05 07:20
3301 | 3 | 3 |  | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 18 | 2021-05-05 07:20
3302 | 2 | 2 |  | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 18 | 2021-05-05 07:20
3303 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 18 | 2021-05-05 07:20
3304 | 2 | 2 |  | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 18 | 2021-05-05 07:20
3305 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 18 | 2021-05-05 07:20
3306 | 2 | 2 |  | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 18 | 2021-05-05 07:20
3307 | 3 | 3 |  | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 18 | 2021-05-05 07:20
3308 | 3 | 3 |  | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 18 | 2021-05-05 07:20
3309 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 18 | 2021-05-05 07:20
3310 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 18 | 2021-05-05 07:20
3311 | 3 | 3 |  | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 18 | 2021-05-05 07:20
3312 | 3 | 3 |  | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 18 | 2021-05-05 07:20
3313 | 3 | 3 |  | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 18 | 2021-05-05 07:20
3314 | 3 | 3 |  | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 18 | 2021-05-05 07:20
3315 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 18 | 2021-05-05 07:20
3316 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 18 | 2021-05-05 07:20
3317 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 18 | 2021-05-05 07:20
3318 | 3 | 3 |  | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 18 | 2021-05-05 07:20
3319 | 3 | 3 |  | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 18 | 2021-05-05 07:20
3320 | 3 | 3 |  | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 18 | 2021-05-05 07:20
3321 | 3 | 3 |  | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 18 | 2021-05-05 07:20
3322 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 18 | 2021-05-05 07:20
3323 | 3 | 3 |  | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 18 | 2021-05-05 07:20
3324 | 3 | 3 |  | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 18 | 2021-05-05 07:20
3325 | 3 | 3 |  | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 18 | 2021-05-05 07:20
3326 | 3 | 3 |  | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 18 | 2021-05-05 07:20
3327 | 3 | 3 |  | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 18 | 2021-05-05 07:20
3328 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 18 | 2021-05-05 07:20
3329 | 2 | 2 |  | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 18 | 2021-05-05 07:20
3330 | 3 | 3 |  | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 18 | 2021-05-05 07:20
3331 | 3 | 3 |  | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 18 | 2021-05-05 07:20
3332 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 18 | 2021-05-05 07:20
3333 | 3 | 3 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 18 | 2021-05-05 07:20
3334 | 3 | 3 |  | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 18 | 2021-05-05 07:20
3335 | 3 | 3 |  | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 18 | 2021-05-05 07:20
3336 | 3 | 3 |  | Jack has just taken over a project. He is now currently identifying risks in the project. He gets all Team member in a room and started to pump out ideas. Which among the following information gathering techniques is he using? | 1 | 1 |  | Jack is encouraging all teams members to provide their inputs in identifying risks. He is not masking the identity of the team members as in Delphi technique. He is not conducting 1 on 1s as in interviews. | 0 | 18 | 2021-05-05 07:20
3337 | 3 | 3 |  | You are Project Manager working in IT CORP LTD. You have been assigned a new project of Inventory management System. You are currently identifying risks in your project. You decided to send questionnaires to experts asking about important project risks. Which type of the following information gathering technique is he using? | 1 | 1 |  | You are gathering inputs without other team members knowing the identity of the team member providing inputs which is Delphi technique. | 0 | 18 | 2021-05-05 07:20
3338 | 3 | 3 |  | You are Project Manager working in IT CORP LTD. You have been assigned a new project on Inventory management System. You are currently identifying risks in your project by looking at plans, requirements and documents from your organization process assets. Which type of the identify risk technique you are using? | 1 | 1 |  | You are reviewing historical information of similar past projects to identify potential risks that may be applicable for the current project. You are using "Document Review" technique. You are neither analyzing assumptions/constraints nor doing SWOT analysis not analyzing checklists | 0 | 18 | 2021-05-05 07:20
3339 | 2 | 2 |  | Carrie is a project manager. Two of her team members are engaged in a conflict and they reach out to her for a solution. However, one team member wants them to resolve the conflict on their own. Which conflict resolution Technique did she use? | 1 | 1 | Complex | When one stakeholder wants to resolve the confict any of the techniques can be used. In the current scenario all the others barring Withdrawal need both stakeholders to be engaged. Hence most logical choice is Withdrawal. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 18 | 2021-05-05 07:20
3340 | 1 | 1 |  | Project A has a NPV of $1 million and IRR of 4%. Project B hand a NPV of $1.1 million and IRR of $3.9%. Which project should you select? | 1 | 1 | High Complex | Since the IRR are almost similar one should choose the project with greater NPV. Best choice in this situation will be Project B. | 0 | 18 | 2021-05-05 07:20
3341 | 3 | 3 |  | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 18 | 2021-05-05 07:20
3342 | 3 | 3 |  | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 18 | 2021-05-05 07:20
3343 | 3 | 3 |  | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 18 | 2021-05-05 07:20
3344 | 2 | 2 |  | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 18 | 2021-05-05 07:20
3345 | 2 | 2 |  | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 18 | 2021-05-05 07:20
3346 | 3 | 3 |  | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 18 | 2021-05-05 07:20
3347 | 3 | 3 |  | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 18 | 2021-05-05 07:20
3348 | 2 | 2 |  | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 18 | 2021-05-05 07:20
3349 | 3 | 3 |  | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 18 | 2021-05-05 07:20
3350 | 2 | 2 |  | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 18 | 2021-05-05 07:20
3351 | 3 | 3 |  | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 18 | 2021-05-05 07:20
3352 | 3 | 3 |  | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 18 | 2021-05-05 07:20
3353 | 1 | 1 |  | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 18 | 2021-05-05 07:20
3354 | 2 | 2 |  | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 18 | 2021-05-05 07:20
3355 | 3 | 3 |  | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 18 | 2021-05-05 07:20
3356 | 1 | 1 |  | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 18 | 2021-05-05 07:20
3357 | 3 | 3 |  | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 18 | 2021-05-05 07:20
3358 | 3 | 3 |  | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 18 | 2021-05-05 07:20
3359 | 3 | 3 |  | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 18 | 2021-05-05 07:20
3360 | 3 | 3 |  | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 18 | 2021-05-05 07:20
3361 | 3 | 3 |  | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 18 | 2021-05-05 07:20
3362 | 2 | 2 |  | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 18 | 2021-05-05 07:20
3363 | 3 | 3 |  | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 18 | 2021-05-05 07:20
3364 | 3 | 3 |  | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 18 | 2021-05-05 07:20
3365 | 2 | 2 |  | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 18 | 2021-05-05 07:20
3366 | 3 | 3 |  | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 18 | 2021-05-05 07:20
3367 | 3 | 3 |  | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 18 | 2021-05-05 07:20
3368 | 3 | 3 |  | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 18 | 2021-05-05 07:20
3369 | 2 | 2 |  | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 18 | 2021-05-05 07:20
3370 | 3 | 3 |  | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 18 | 2021-05-05 07:20
3371 | 3 | 3 |  | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 18 | 2021-05-05 07:20
3372 | 3 | 3 |  | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 18 | 2021-05-05 07:20
3373 | 2 | 2 |  | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 18 | 2021-05-05 07:20
3374 | 2 | 2 |  | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 18 | 2021-05-05 07:20
3375 | 3 | 3 |  | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 18 | 2021-05-05 07:20
3376 | 2 | 2 |  | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 18 | 2021-05-05 07:20
3377 | 3 | 3 |  | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 18 | 2021-05-05 07:20
3378 | 3 | 3 |  | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 18 | 2021-05-05 07:20
3379 | 3 | 3 |  | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 18 | 2021-05-05 07:20
3380 | 2 | 2 |  | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 18 | 2021-05-05 07:20
3381 | 2 | 2 |  | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 18 | 2021-05-05 07:20
3382 | 3 | 3 |  | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 18 | 2021-05-05 07:20
3383 | 3 | 3 |  | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 18 | 2021-05-05 07:20
3384 | 3 | 3 |  | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 18 | 2021-05-05 07:20
3385 | 3 | 3 |  | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 18 | 2021-05-05 07:20
3386 | 3 | 3 |  | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 18 | 2021-05-05 07:20
3387 | 3 | 3 |  | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 18 | 2021-05-05 07:20
3388 | 3 | 3 |  | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 18 | 2021-05-05 07:20
3389 | 3 | 3 |  | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 18 | 2021-05-05 07:20
3390 | 2 | 2 |  | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 18 | 2021-05-05 07:20
3391 | 3 | 3 |  | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 18 | 2021-05-05 07:20
3392 | 3 | 3 |  | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 18 | 2021-05-05 07:20
3393 | 3 | 3 |  | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 18 | 2021-05-05 07:20
3394 | 3 | 3 |  | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 18 | 2021-05-05 07:20
3395 | 2 | 2 |  | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 18 | 2021-05-05 07:20
3396 | 3 | 3 |  | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 18 | 2021-05-05 07:20
3397 | 3 | 3 |  | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 18 | 2021-05-05 07:20
3398 | 3 | 3 |  | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 18 | 2021-05-05 07:20
3399 | 3 | 3 |  | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 18 | 2021-05-05 07:20
3400 | 2 | 2 |  | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 18 | 2021-05-05 07:20
3401 | 3 | 3 |  | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 18 | 2021-05-05 07:20
3402 | 2 | 2 |  | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 18 | 2021-05-05 07:20
3403 | 2 | 2 |  | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 18 | 2021-05-05 07:20
3404 | 3 | 3 |  | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 18 | 2021-05-05 07:20
3405 | 3 | 3 |  | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 18 | 2021-05-05 07:20
3406 | 2 | 2 |  | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 18 | 2021-05-05 07:20
3407 | 2 | 2 |  | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 18 | 2021-05-05 07:20
3408 | 3 | 3 |  | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 18 | 2021-05-05 07:20
3409 | 2 | 2 |  | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 18 | 2021-05-05 07:20
3410 | 3 | 3 |  | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 18 | 2021-05-05 07:20
3411 | 2 | 2 |  | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 18 | 2021-05-05 07:20
3412 | 2 | 2 |  | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 18 | 2021-05-05 07:20
3413 | 3 | 3 |  | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 18 | 2021-05-05 07:20
3414 | 2 | 2 |  | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 18 | 2021-05-05 07:20
3415 | 3 | 3 |  | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 18 | 2021-05-05 07:20
3416 | 3 | 3 |  | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 18 | 2021-05-05 07:20
3417 | 2 | 2 |  | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 18 | 2021-05-05 07:20
3418 | 2 | 2 |  | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 18 | 2021-05-05 07:20
3419 | 3 | 3 |  | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 18 | 2021-05-05 07:20
3420 | 3 | 3 |  | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 18 | 2021-05-05 07:20
3421 | 2 | 2 |  | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 18 | 2021-05-05 07:20
3422 | 2 | 2 |  | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 18 | 2021-05-05 07:20
3423 | 3 | 3 |  | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 18 | 2021-05-05 07:20
3424 | 3 | 3 |  | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 18 | 2021-05-05 07:20
3425 | 3 | 3 |  | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 18 | 2021-05-05 07:20
3426 | 2 | 2 |  | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 18 | 2021-05-05 07:20
3427 | 3 | 3 |  | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 18 | 2021-05-05 07:20
3428 | 2 | 2 |  | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 18 | 2021-05-05 07:20
3429 | 3 | 3 |  | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 18 | 2021-05-05 07:20
3430 | 1 | 1 |  | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 18 | 2021-05-05 07:20
3431 | 3 | 3 |  | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 18 | 2021-05-05 07:20
3432 | 2 | 2 |  | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 18 | 2021-05-05 07:20
3433 | 3 | 3 |  | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 18 | 2021-05-05 07:20
3434 | 3 | 3 |  | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 18 | 2021-05-05 07:20
3435 | 3 | 3 |  | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 18 | 2021-05-05 07:20
3436 | 3 | 3 |  | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 18 | 2021-05-05 07:20
3437 | 3 | 3 |  | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 18 | 2021-05-05 07:20
3438 | 2 | 2 |  | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 18 | 2021-05-05 07:20
3439 | 2 | 2 |  | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 18 | 2021-05-05 07:20
3440 | 3 | 3 |  | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 18 | 2021-05-05 07:20
3441 | 3 | 3 |  | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 18 | 2021-05-05 07:20
3442 | 3 | 3 |  | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 18 | 2021-05-05 07:20
3443 | 2 | 2 |  | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 18 | 2021-05-05 07:20
3444 | 3 | 3 |  | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 18 | 2021-05-05 07:20
3445 | 2 | 2 |  | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 18 | 2021-05-05 07:20
3446 | 2 | 2 |  | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 18 | 2021-05-05 07:20
3447 | 3 | 3 |  | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 18 | 2021-05-05 07:20
3448 | 3 | 3 |  | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 18 | 2021-05-05 07:20
3449 | 1 | 1 |  | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 18 | 2021-05-05 07:20
3450 | 1 | 1 |  | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 18 | 2021-05-05 07:20
3451 | 3 | 3 |  | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 18 | 2021-05-05 07:20
3452 | 3 | 3 |  | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 18 | 2021-05-05 07:20
3453 | 3 | 3 |  | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 18 | 2021-05-05 07:20
3454 | 1 | 1 |  | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 18 | 2021-05-05 07:20
3455 | 2 | 2 |  | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 18 | 2021-05-05 07:20
3456 | 2 | 2 |  | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 18 | 2021-05-05 07:20
3457 | 2 | 2 |  | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 18 | 2021-05-05 07:20
3458 | 1 | 1 |  | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 18 | 2021-05-05 07:20
3459 | 1 | 1 |  | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 18 | 2021-05-05 07:20
3460 | 3 | 3 |  | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 18 | 2021-05-05 07:20
3461 | 2 | 2 |  | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 18 | 2021-05-05 07:20
3462 | 2 | 2 |  | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 18 | 2021-05-05 07:20
3463 | 3 | 3 |  | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 18 | 2021-05-05 07:20
3464 | 3 | 3 |  | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 18 | 2021-05-05 07:20
3465 | 3 | 3 |  | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 18 | 2021-05-05 07:20
3466 | 3 | 3 |  | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 18 | 2021-05-05 07:20
3467 | 2 | 2 |  | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 18 | 2021-05-05 07:20
3468 | 3 | 3 |  | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 18 | 2021-05-05 07:20
3469 | 3 | 3 |  | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 18 | 2021-05-05 07:20
3470 | 2 | 2 |  | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 18 | 2021-05-05 07:20
3471 | 3 | 3 |  | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 18 | 2021-05-05 07:20
3472 | 1 | 1 |  | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 18 | 2021-05-05 07:20
3473 | 2 | 2 |  | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 18 | 2021-05-05 07:20
3474 | 3 | 3 |  | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 18 | 2021-05-05 07:20
3475 | 2 | 2 |  | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 18 | 2021-05-05 07:20
3476 | 1 | 1 |  | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 18 | 2021-05-05 07:20
3477 | 3 | 3 |  | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 18 | 2021-05-05 07:20
3478 | 1 | 1 |  | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 18 | 2021-05-05 07:20
3479 | 3 | 3 |  | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 18 | 2021-05-05 07:20
3480 | 1 | 1 |  | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 18 | 2021-05-05 07:20
3481 | 3 | 3 |  | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 18 | 2021-05-05 07:20
3482 | 2 | 2 |  | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 18 | 2021-05-05 07:20
3483 | 3 | 3 |  | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 18 | 2021-05-05 07:20
3484 | 2 | 2 |  | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 1 | 1 | Complex | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 0 | 19 | 2021-05-07 08:30
3485 | 2 | 2 |  | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 1 | 1 | Complex | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 19 | 2021-05-07 08:30
3486 | 3 | 3 |  | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 1 | 1 | Complex | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 0 | 19 | 2021-05-07 08:30
3487 | 3 | 3 |  | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 1 | 1 | Complex | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 0 | 19 | 2021-05-07 08:30
3488 | 2 | 2 |  | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 1 | 1 | Complex | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 19 | 2021-05-07 08:30
3489 | 2 | 2 |  | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 0 | 19 | 2021-05-07 08:30
3490 | 2 | 2 |  | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 1 | 1 | Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 19 | 2021-05-07 08:30
3491 | 2 | 2 |  | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 0 | 19 | 2021-05-07 08:30
3492 | 2 | 2 |  | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 1 | 1 | Medium | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 0 | 19 | 2021-05-07 08:30
3493 | 2 | 2 |  | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 19 | 2021-05-07 08:30
3494 | 3 | 3 |  | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 1 | 1 | Simple | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 0 | 19 | 2021-05-07 08:30
3495 | 3 | 3 |  | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 1 | 1 | Medium | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 0 | 19 | 2021-05-07 08:30
3496 | 2 | 2 |  | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 1 | 1 | Complex | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 0 | 19 | 2021-05-07 08:30
3497 | 2 | 2 |  | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 1 | 1 | High Complex | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 0 | 19 | 2021-05-07 08:30
3498 | 1 | 1 |  | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 1 | 1 | Complex | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 0 | 19 | 2021-05-07 08:30
3499 | 2 | 2 |  | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 1 | 1 | Complex | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 0 | 19 | 2021-05-07 08:30
3500 | 1 | 1 |  | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 1 | 1 | Medium | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 0 | 19 | 2021-05-07 08:30
3501 | 2 | 2 |  | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 1 | 1 | Medium | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 0 | 19 | 2021-05-07 08:30
3502 | 2 | 2 |  | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 1 | 1 | Complex | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 0 | 19 | 2021-05-07 08:30
3503 | 3 | 3 |  | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 1 | 1 | High Complex | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 19 | 2021-05-07 08:30
3504 | 1 | 1 |  | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 1 | 1 | Complex | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 0 | 19 | 2021-05-07 08:30
3505 | 2 | 2 |  | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 1 | 1 | Medium | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 19 | 2021-05-07 08:30
3506 | 3 | 3 |  | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 1 | 1 | Complex | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 0 | 19 | 2021-05-07 08:30
3507 | 3 | 3 |  | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 1 | 1 | Medium | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 0 | 19 | 2021-05-07 08:30
3508 | 2 | 2 |  | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 1 | 1 | Medium | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 0 | 19 | 2021-05-07 08:30
3509 | 2 | 2 |  | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 1 | 1 | Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 0 | 19 | 2021-05-07 08:30
3510 | 3 | 3 |  | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 1 | 1 | Complex | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 0 | 19 | 2021-05-07 08:30
3511 | 2 | 2 |  | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 1 | 1 | Complex | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 0 | 19 | 2021-05-07 08:30
3512 | 2 | 2 |  | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 1 | 1 | Complex | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 0 | 19 | 2021-05-07 08:30
3513 | 3 | 3 |  | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 1 | 1 | Complex | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 0 | 19 | 2021-05-07 08:30
3514 | 3 | 3 |  | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 1 | 1 | Medium | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 0 | 19 | 2021-05-07 08:30
3515 | 3 | 3 |  | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 1 | 1 | Medium | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 0 | 19 | 2021-05-07 08:30
3516 | 3 | 3 |  | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 1 | 1 | Complex | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 0 | 19 | 2021-05-07 08:30
3517 | 2 | 2 |  | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 1 | 1 | Complex | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 0 | 19 | 2021-05-07 08:30
3518 | 3 | 3 |  | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 1 | 1 | Complex | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 0 | 19 | 2021-05-07 08:30
3519 | 1 | 1 |  | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 1 | 1 | Complex | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 0 | 19 | 2021-05-07 08:30
3520 | 3 | 3 |  | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 1 | 1 | Simple | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 0 | 19 | 2021-05-07 08:30
3521 | 2 | 2 |  | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 1 | 1 | Complex | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 0 | 19 | 2021-05-07 08:30
3522 | 3 | 3 |  | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 1 | 1 | Complex | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 0 | 19 | 2021-05-07 08:30
3523 | 3 | 3 |  | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 1 | 1 | Complex | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 0 | 19 | 2021-05-07 08:30
3524 | 2 | 2 |  | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 1 | 1 | Complex | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 0 | 19 | 2021-05-07 08:30
3525 | 2 | 2 |  | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 1 | 1 | Complex | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 19 | 2021-05-07 08:30
3526 | 2 | 2 |  | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 1 | 1 | High Complex | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 0 | 19 | 2021-05-07 08:30
3527 | 3 | 3 |  | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 1 | 1 | High Complex | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 0 | 19 | 2021-05-07 08:30
3528 | 3 | 3 |  | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 1 | 1 | Medium | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 0 | 19 | 2021-05-07 08:30
3529 | 2 | 2 |  | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 1 | 1 | Complex | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 0 | 19 | 2021-05-07 08:30
3530 | 2 | 2 |  | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 1 | 1 | Complex | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 0 | 19 | 2021-05-07 08:30
3531 | 3 | 3 |  | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 1 | 1 | High Complex | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 0 | 19 | 2021-05-07 08:30
3532 | 2 | 2 |  | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 1 | 1 | High Complex | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 0 | 19 | 2021-05-07 08:30
3533 | 2 | 2 |  | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 1 | 1 | Complex | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 0 | 19 | 2021-05-07 08:30
3534 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Simple | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 19 | 2021-05-07 08:30
3535 | 3 | 3 |  | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 1 | 1 | Medium | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 0 | 19 | 2021-05-07 08:30
3536 | 3 | 3 |  | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 1 | 1 | Complex | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 0 | 19 | 2021-05-07 08:30
3537 | 3 | 3 |  | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 1 | 1 | Complex | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 0 | 19 | 2021-05-07 08:30
3538 | 3 | 3 |  | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 1 | 1 | Simple | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 0 | 19 | 2021-05-07 08:30
3539 | 3 | 3 |  | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 19 | 2021-05-07 08:30
3540 | 3 | 3 |  | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 1 | 1 | Simple | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 19 | 2021-05-07 08:30
3541 | 3 | 3 |  | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 1 | 1 | Simple | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 0 | 19 | 2021-05-07 08:30
3542 | 3 | 3 |  | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 1 | 1 | Medium | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 0 | 19 | 2021-05-07 08:30
3543 | 2 | 2 |  | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 1 | 1 | Complex | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 0 | 19 | 2021-05-07 08:30
3544 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 1 | 1 | Complex | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 0 | 19 | 2021-05-07 08:30
3545 | 2 | 2 |  | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 1 | 1 | Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 0 | 19 | 2021-05-07 08:30
3546 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 1 | 1 | High Complex | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 0 | 19 | 2021-05-07 08:30
3547 | 2 | 2 |  | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 1 | 1 | Complex | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 0 | 19 | 2021-05-07 08:30
3548 | 2 | 2 |  | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 1 | 1 | High Complex | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 0 | 19 | 2021-05-07 08:30
3549 | 2 | 2 |  | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 1 | 1 | Complex | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 0 | 19 | 2021-05-07 08:30
3550 | 2 | 2 |  | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 1 | 1 | High Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 0 | 19 | 2021-05-07 08:30
3551 | 3 | 3 |  | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 1 | 1 | Medium | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 0 | 19 | 2021-05-07 08:30
3552 | 3 | 3 |  | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 1 | 1 | Medium | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 0 | 19 | 2021-05-07 08:30
3553 | 3 | 3 |  | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 1 | 1 | Complex | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 0 | 19 | 2021-05-07 08:30
3554 | 3 | 3 |  | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 1 | 1 | Complex | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 19 | 2021-05-07 08:30
3555 | 3 | 3 |  | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 1 | 1 | High Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 0 | 19 | 2021-05-07 08:30
3556 | 3 | 3 |  | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 0 | 19 | 2021-05-07 08:30
3557 | 3 | 3 |  | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 1 | 1 | Complex | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 0 | 19 | 2021-05-07 08:30
3558 | 3 | 3 |  | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 0 | 19 | 2021-05-07 08:30
3559 | 3 | 3 |  | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 0 | 19 | 2021-05-07 08:30
3560 | 3 | 3 |  | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 19 | 2021-05-07 08:30
3561 | 3 | 3 |  | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 1 | 1 | Simple | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 0 | 19 | 2021-05-07 08:30
3562 | 3 | 3 |  | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 1 | 1 | High Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 0 | 19 | 2021-05-07 08:30
3563 | 3 | 3 |  | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | Medium | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 0 | 19 | 2021-05-07 08:30
3564 | 3 | 3 |  | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 1 | 1 | Complex | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 0 | 19 | 2021-05-07 08:30
3565 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 19 | 2021-05-07 08:30
3566 | 2 | 2 |  | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 1 | 1 | Complex | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 0 | 19 | 2021-05-07 08:30
3567 | 2 | 2 |  | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 1 | 1 | Medium | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 0 | 19 | 2021-05-07 08:30
3568 | 3 | 3 |  | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 0 | 19 | 2021-05-07 08:30
3569 | 2 | 2 |  | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 0 | 19 | 2021-05-07 08:30
3570 | 3 | 3 |  | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 1 | 1 | Simple | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 0 | 19 | 2021-05-07 08:30
3571 | 3 | 3 |  | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | Simple | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 0 | 19 | 2021-05-07 08:30
3572 | 3 | 3 |  | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 1 | 1 | Complex | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 19 | 2021-05-07 08:30
3573 | 2 | 2 |  | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 1 | 1 | Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 0 | 19 | 2021-05-07 08:30
3574 | 3 | 3 |  | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 1 | 1 | Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 19 | 2021-05-07 08:30
3575 | 3 | 3 |  | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 1 | 1 | Complex | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 0 | 19 | 2021-05-07 08:30
3576 | 2 | 2 |  | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 1 | 1 | Simple | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 0 | 19 | 2021-05-07 08:30
3577 | 1 | 1 |  | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 0 | 19 | 2021-05-07 08:30
3578 | 3 | 3 |  | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 0 | 19 | 2021-05-07 08:30
3579 | 1 | 1 |  | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 1 | 1 | Medium | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 0 | 19 | 2021-05-07 08:30
3580 | 2 | 2 |  | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 1 | 1 | Complex | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 19 | 2021-05-07 08:30
3581 | 3 | 3 |  | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 1 | 1 | High Complex | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 0 | 19 | 2021-05-07 08:30
3582 | 2 | 2 |  | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 1 | 1 | High Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 0 | 19 | 2021-05-07 08:30
3583 | 3 | 3 |  | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 1 | 1 | High Complex | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 0 | 19 | 2021-05-07 08:30
3584 | 2 | 2 |  | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 1 | 1 | High Complex | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 0 | 19 | 2021-05-07 08:30
3585 | 3 | 3 |  | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 1 | 1 | Complex | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 0 | 19 | 2021-05-07 08:30
3586 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 19 | 2021-05-07 08:30
3587 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 0 | 19 | 2021-05-07 08:30
3588 | 3 | 3 |  | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 1 | 1 | Complex | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 19 | 2021-05-07 08:30
3589 | 3 | 3 |  | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 1 | 1 | Simple | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 0 | 19 | 2021-05-07 08:30
3590 | 3 | 3 |  | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 1 | 1 | Complex | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 19 | 2021-05-07 08:30
3591 | 3 | 3 |  | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 1 | 1 | Medium | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 19 | 2021-05-07 08:30
3592 | 3 | 3 |  | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 1 | 1 | Complex | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 19 | 2021-05-07 08:30
3593 | 3 | 3 |  | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 1 | 1 | Complex | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 0 | 19 | 2021-05-07 08:30
3594 | 1 | 1 |  | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 1 | 1 | Medium | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 19 | 2021-05-07 08:30
3595 | 1 | 1 |  | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 1 | 1 | Complex | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 0 | 19 | 2021-05-07 08:30
3596 | 3 | 3 |  | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 1 | 1 | Medium | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 0 | 19 | 2021-05-07 08:30
3597 | 3 | 3 |  | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 1 | 1 | Complex | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 19 | 2021-05-07 08:30
3598 | 2 | 2 |  | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 1 | 1 | Complex | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 0 | 19 | 2021-05-07 08:30
3599 | 3 | 3 |  | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 1 | 1 | Simple | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 0 | 19 | 2021-05-07 08:30
3600 | 2 | 2 |  | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 1 | 1 | High Complex | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 0 | 19 | 2021-05-07 08:30
3601 | 2 | 2 |  | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 1 | 1 | High Complex | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 0 | 19 | 2021-05-07 08:30
3602 | 2 | 2 |  | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 1 | 1 | Complex | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 0 | 19 | 2021-05-07 08:30
3603 | 3 | 3 |  | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 1 | 1 | Complex | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 0 | 19 | 2021-05-07 08:30
3604 | 3 | 3 |  | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 1 | 1 | Medium | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 0 | 19 | 2021-05-07 08:30
3605 | 3 | 3 |  | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 1 | 1 | Complex | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 0 | 19 | 2021-05-07 08:30
3606 | 2 | 2 |  | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 1 | 1 | High Complex | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 19 | 2021-05-07 08:30
3607 | 3 | 3 |  | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 1 | 1 | Complex | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 0 | 19 | 2021-05-07 08:30
3608 | 3 | 3 |  | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 1 | 1 | Medium | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 0 | 19 | 2021-05-07 08:30
3609 | 3 | 3 |  | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 1 | 1 | Simple | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 0 | 19 | 2021-05-07 08:30
3610 | 3 | 3 |  | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 1 | 1 | Complex | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 0 | 19 | 2021-05-07 08:30
3611 | 3 | 3 |  | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 1 | 1 | Complex | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 0 | 19 | 2021-05-07 08:30
3612 | 2 | 2 |  | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 1 | 1 | High Complex | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 0 | 19 | 2021-05-07 08:30
3613 | 3 | 3 |  | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 1 | 1 | Medium | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 19 | 2021-05-07 08:30
3614 | 3 | 3 |  | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 1 | 1 | High Complex | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 19 | 2021-05-07 08:30
3615 | 3 | 3 |  | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 1 | 1 | Simple | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 0 | 19 | 2021-05-07 08:30
3616 | 2 | 2 |  | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 1 | 1 | Complex | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 0 | 19 | 2021-05-07 08:30
3617 | 3 | 3 |  | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 1 | 1 | Complex | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 0 | 19 | 2021-05-07 08:30
3618 | 3 | 3 |  | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 1 | 1 | High Complex | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 0 | 19 | 2021-05-07 08:30
3619 | 3 | 3 |  | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 1 | 1 | Complex | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 0 | 19 | 2021-05-07 08:30
3620 | 3 | 3 |  | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 1 | 1 | Complex | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 0 | 19 | 2021-05-07 08:30
3621 | 3 | 3 |  | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 19 | 2021-05-07 08:30
3622 | 3 | 3 |  | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 1 | 1 | High Complex | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 0 | 19 | 2021-05-07 08:30
3623 | 3 | 3 |  | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 1 | 1 | Complex | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 0 | 19 | 2021-05-07 08:30
3624 | 3 | 3 |  | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 1 | 1 | High Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 0 | 19 | 2021-05-07 08:30
3625 | 3 | 3 |  | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 1 | 1 | High Complex | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 0 | 19 | 2021-05-07 08:30
3626 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 1 | 1 | High Complex | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 0 | 19 | 2021-05-07 08:30
3627 | 3 | 3 |  | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 1 | 1 | High Complex | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 19 | 2021-05-07 08:30
3628 | 3 | 3 |  | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 1 | 1 | High Complex | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 0 | 19 | 2021-05-07 08:30
3629 | 3 | 3 |  | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 1 | 1 | Medium | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 0 | 19 | 2021-05-07 08:30
3630 | 3 | 3 |  | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 1 | 1 | High Complex | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 19 | 2021-05-07 08:30
3631 | 2 | 2 |  | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 1 | 1 | High Complex | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 0 | 19 | 2021-05-07 08:30
3632 | 3 | 3 |  | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 1 | 1 | Complex | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 19 | 2021-05-07 08:30
3633 | 3 | 3 |  | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 1 | 1 | High Complex | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 19 | 2021-05-07 08:30
3634 | 2 | 2 |  | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 1 | 1 | Complex | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 0 | 19 | 2021-05-07 08:30
3635 | 3 | 3 |  | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 1 | 1 | High Complex | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 0 | 19 | 2021-05-07 08:30
3636 | 3 | 3 |  | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 1 | 1 | High Complex | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 0 | 19 | 2021-05-07 08:30
3637 | 3 | 3 |  | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 1 | 1 | High Complex | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 0 | 19 | 2021-05-07 08:30
3638 | 3 | 3 |  | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 1 | 1 | Simple | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 0 | 19 | 2021-05-07 08:30
3639 | 3 | 3 |  | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 1 | 1 | Complex | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 0 | 19 | 2021-05-07 08:30
3640 | 2 | 2 |  | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 1 | 1 | High Complex | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 0 | 19 | 2021-05-07 08:30
3641 | 3 | 3 |  | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 1 | 1 | Complex | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 0 | 19 | 2021-05-07 08:30
3642 | 2 | 2 |  | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 1 | 1 | Complex | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 0 | 19 | 2021-05-07 08:30
3643 | 3 | 3 |  | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 1 | 1 | Medium | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 0 | 19 | 2021-05-07 08:30
3644 | 3 | 3 |  | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 19 | 2021-05-07 08:30
3645 | 3 | 3 |  | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 1 | 1 | High Complex | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 19 | 2021-05-07 08:30
3646 | 3 | 3 |  | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 1 | 1 | Complex | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 19 | 2021-05-07 08:30
3647 | 3 | 3 |  | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 1 | 1 | High Complex | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 0 | 19 | 2021-05-07 08:30
3648 | 3 | 3 |  | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 1 | 1 | Complex | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 0 | 19 | 2021-05-07 08:30
3649 | 3 | 3 |  | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 1 | 1 | Complex | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 19 | 2021-05-07 08:30
3650 | 3 | 3 |  | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 1 | 1 | High Complex | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 0 | 19 | 2021-05-07 08:30
3651 | 2 | 2 |  | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 1 | 1 | High Complex | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 19 | 2021-05-07 08:30
3652 | 3 | 3 |  | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 1 | 1 | High Complex | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 0 | 19 | 2021-05-07 08:30
3653 | 3 | 3 |  | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 1 | 1 | Complex | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 0 | 19 | 2021-05-07 08:30
3654 | 2 | 2 |  | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 1 | 1 | High Complex | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 19 | 2021-05-07 08:30
3655 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Medium | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 19 | 2021-05-07 08:30
3656 | 3 | 3 |  | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 1 | 1 | Complex | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 0 | 19 | 2021-05-07 08:30
3657 | 3 | 3 |  | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 1 | 1 | High Complex | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 0 | 19 | 2021-05-07 08:30
3658 | 2 | 2 |  | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 1 | 1 | Complex | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 0 | 19 | 2021-05-07 08:30
3659 | 2 | 2 |  | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 1 | 1 | High Complex | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 0 | 19 | 2021-05-07 08:30
3660 | 3 | 3 |  | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 1 | 1 | Complex | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 0 | 19 | 2021-05-07 08:30
3661 | 3 | 3 |  | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 1 | 1 | High Complex | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 0 | 19 | 2021-05-07 08:30
3662 | 2 | 2 |  | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 1 | 1 | Complex | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 19 | 2021-05-07 08:30
3663 | 3 | 3 |  | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 1 | 1 | High Complex | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 0 | 19 | 2021-05-07 08:30
3664 | 2 | 2 |  | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 1 | 1 | High Complex | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 0 | 19 | 2021-05-07 08:30
3665 | 2 | 2 |  | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 1 | 1 | Simple | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 19 | 2021-05-07 08:30
3666 | 3 | 3 |  | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 1 | 1 | Complex | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 0 | 19 | 2021-05-07 08:30
3667 | 3 | 3 |  | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 1 | 1 | High Complex | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 19 | 2021-05-07 08:30
3668 | 3 | 3 |  | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 1 | 1 | Complex | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 0 | 19 | 2021-05-07 08:30
3669 | 2 | 2 |  | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 1 | 1 | Complex | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 0 | 19 | 2021-05-07 08:30
3670 | 3 | 3 |  | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 1 | 1 | Complex | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 19 | 2021-05-07 08:30
3671 | 3 | 3 |  | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 1 | 1 | Medium | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 0 | 19 | 2021-05-07 08:30
3672 | 3 | 3 |  | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 1 | 1 | Complex | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 0 | 19 | 2021-05-07 08:30
3673 | 3 | 3 |  | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 1 | 1 | High Complex | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 0 | 19 | 2021-05-07 08:30
3674 | 3 | 3 |  | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 1 | 1 | High Complex | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 19 | 2021-05-07 08:30
3675 | 2 | 2 |  | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 1 | 1 | High Complex | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 0 | 19 | 2021-05-07 08:30
3676 | 3 | 3 |  | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 1 | 1 | Complex | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 0 | 19 | 2021-05-07 08:30
3677 | 3 | 3 |  | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 1 | 1 | Complex | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 0 | 19 | 2021-05-07 08:30
3678 | 3 | 3 |  | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 1 | 1 | High Complex | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 0 | 19 | 2021-05-07 08:30
3679 | 3 | 3 |  | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 1 | 1 | Simple | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 0 | 19 | 2021-05-07 08:30
3680 | 2 | 2 |  | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 0 | 19 | 2021-05-07 08:30
3681 | 2 | 2 |  | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 1 | 1 | Complex | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 0 | 19 | 2021-05-07 08:30
3682 | 3 | 3 |  | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 1 | 1 | High Complex | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 0 | 19 | 2021-05-07 08:30
3683 | 3 | 3 |  | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 1 | 1 | Complex | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 0 | 19 | 2021-05-07 08:30
3684 | 3 | 3 |  | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 1 | 1 | Medium | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 0 | 19 | 2021-05-07 08:30
3685 | 2 | 2 |  | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 1 | 1 | High Complex | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 0 | 19 | 2021-05-07 08:30
3686 | 3 | 3 |  | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 1 | 1 | High Complex | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 0 | 19 | 2021-05-07 08:30
3687 | 2 | 2 |  | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 1 | 1 | Medium | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 0 | 19 | 2021-05-07 08:30
3688 | 3 | 3 |  | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 1 | 1 | High Complex | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 0 | 19 | 2021-05-07 08:30
3689 | 3 | 3 |  | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 1 | 1 | Complex | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 0 | 19 | 2021-05-07 08:30
3690 | 3 | 3 |  | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 1 | 1 | High Complex | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 0 | 19 | 2021-05-07 08:30
3691 | 3 | 3 |  | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 1 | 1 | High Complex | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 0 | 19 | 2021-05-07 08:30
3692 | 3 | 3 |  | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 1 | 1 | Complex | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 0 | 19 | 2021-05-07 08:30
3693 | 2 | 2 |  | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 1 | 1 | Simple | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 0 | 19 | 2021-05-07 08:30
3694 | 3 | 3 |  | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 1 | 1 |  | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off | 0 | 19 | 2021-05-07 08:30
3695 | 3 | 3 |  | What is the correct order of performing the processes? | 1 | 1 |  | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation | 0 | 19 | 2021-05-07 08:30
3696 | 3 | 3 |  | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 1 | 1 |  | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required | 0 | 19 | 2021-05-07 08:30
3697 | 3 | 3 |  | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 1 | 1 |  | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits | 0 | 19 | 2021-05-07 08:30
3698 | 3 | 3 |  | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 1 | 1 |  | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance" | 0 | 19 | 2021-05-07 08:30
3699 | 3 | 3 |  | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 1 | 1 |  | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit. | 0 | 19 | 2021-05-07 08:30
3700 | 3 | 3 |  | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 1 | 1 |  | Force Majeure clause covers earth quakes, flash floods, landslides, etc. | 0 | 19 | 2021-05-07 08:30
3701 | 3 | 3 |  | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 1 | 1 |  | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen | 0 | 19 | 2021-05-07 08:30
3702 | 3 | 3 |  | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 1 | 1 |  | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete | 0 | 19 | 2021-05-07 08:30
3703 | 3 | 3 |  | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 1 | 1 |  | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000 | 0 | 19 | 2021-05-07 08:30
3704 | 3 | 3 |  | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 1 | 1 |  | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms | 0 | 19 | 2021-05-07 08:30
3705 | 3 | 3 |  | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 1 | 1 |  | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure | 0 | 19 | 2021-05-07 08:30
3706 | 3 | 3 |  | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 1 | 1 |  | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use | 0 | 19 | 2021-05-07 08:30
3707 | 3 | 3 |  | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 1 | 1 |  | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed | 0 | 19 | 2021-05-07 08:30
3708 | 3 | 3 |  | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 1 | 1 |  | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature) | 0 | 19 | 2021-05-07 08:30
3709 | 3 | 3 |  | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 1 | 1 |  | Project / work requirements are part of Contract terms & conditions | 0 | 19 | 2021-05-07 08:30
3710 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 1 | 1 |  | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible | 0 | 19 | 2021-05-07 08:30
3711 | 2 | 2 |  | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 1 | 1 |  | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions | 0 | 19 | 2021-05-07 08:30
3712 | 2 | 2 |  | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 1 | 1 |  | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving | 0 | 19 | 2021-05-07 08:30
3713 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 1 | 1 |  | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at | 0 | 19 | 2021-05-07 08:30
3714 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 1 | 1 |  | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties | 0 | 19 | 2021-05-07 08:30
3715 | 2 | 2 |  | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 1 | 1 |  | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation | 0 | 19 | 2021-05-07 08:30
3716 | 2 | 2 |  | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 1 | 1 |  | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue | 0 | 19 | 2021-05-07 08:30
3717 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 1 | 1 |  | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict | 0 | 19 | 2021-05-07 08:30
3718 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 1 | 1 |  | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation | 0 | 19 | 2021-05-07 08:30
3719 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 1 | 1 |  | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation | 0 | 19 | 2021-05-07 08:30
3720 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 1 | 1 |  | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work | 0 | 19 | 2021-05-07 08:30
3721 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 1 | 1 |  | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception | 0 | 19 | 2021-05-07 08:30
3722 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 1 | 1 |  | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option | 0 | 19 | 2021-05-07 08:30
3723 | 3 | 3 |  | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 1 | 1 |  | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required | 0 | 19 | 2021-05-07 08:30
3724 | 2 | 2 |  | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 1 | 1 |  | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory | 0 | 19 | 2021-05-07 08:30
3725 | 2 | 2 |  | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 1 | 1 |  | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing | 0 | 19 | 2021-05-07 08:30
3726 | 2 | 2 |  | In the communication model, the "Decoder" is different from the "Receiver" because: | 1 | 1 |  | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense | 0 | 19 | 2021-05-07 08:30
3727 | 2 | 2 |  | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 1 | 1 |  | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop | 0 | 19 | 2021-05-07 08:30
3728 | 3 | 3 |  | Communication between Project Manager and team members takes place best: | 1 | 1 |  | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication | 0 | 19 | 2021-05-07 08:30
3729 | 3 | 3 |  | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 1 | 1 |  | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop | 0 | 19 | 2021-05-07 08:30
3730 | 2 | 2 |  | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 1 | 1 |  | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted | 0 | 19 | 2021-05-07 08:30
3731 | 2 | 2 |  | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 1 | 1 |  | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication | 0 | 19 | 2021-05-07 08:30
3732 | 2 | 2 |  | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 1 | 1 |  | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial | 0 | 19 | 2021-05-07 08:30
3733 | 3 | 3 |  | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 1 | 1 |  | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project | 0 | 19 | 2021-05-07 08:30
3734 | 3 | 3 |  | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 1 | 1 |  | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions | 0 | 19 | 2021-05-07 08:30
3735 | 3 | 3 |  | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 1 | 1 |  | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects | 0 | 19 | 2021-05-07 08:30
3736 | 3 | 3 |  | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 1 | 1 |  | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive | 0 | 19 | 2021-05-07 08:30
3737 | 3 | 3 |  | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 1 | 1 |  | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue | 0 | 19 | 2021-05-07 08:30
3738 | 3 | 3 |  | Of the following which one is not a form of project communications? | 1 | 1 |  | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form | 0 | 19 | 2021-05-07 08:30
3739 | 2 | 2 |  | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. All other options are valid except option#2 | 0 | 19 | 2021-05-07 08:30
3740 | 2 | 2 |  | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 1 | 1 |  | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word. | 0 | 19 | 2021-05-07 08:30
3741 | 2 | 2 |  | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers | 0 | 19 | 2021-05-07 08:30
3742 | 2 | 2 |  | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 1 | 1 |  | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages. | 0 | 19 | 2021-05-07 08:30
3743 | 2 | 2 |  | To achieve consensus all of the following can be used EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts | 0 | 19 | 2021-05-07 08:30
3744 | 3 | 3 |  | A communications management plan should include all of the following, EXCEPT: | 1 | 1 |  | The Comms Management plan does not include Risk Register. It includes all the other options | 0 | 19 | 2021-05-07 08:30
3745 | 3 | 3 |  | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 1 | 1 |  | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer | 0 | 19 | 2021-05-07 08:30
3746 | 3 | 3 |  | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members | 0 | 19 | 2021-05-07 08:30
3747 | 3 | 3 |  | Status coordination and reporting is the PRIME focus of: | 1 | 1 |  | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project | 0 | 19 | 2021-05-07 08:30
3748 | 3 | 3 |  | The best method of resolving conflict in a project is: | 1 | 1 |  | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy | 0 | 19 | 2021-05-07 08:30
3749 | 3 | 3 |  | The sender in the communication model is responsible for: | 1 | 1 |  | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver | 0 | 19 | 2021-05-07 08:30
3750 | 3 | 3 |  | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 1 | 1 |  | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting | 0 | 19 | 2021-05-07 08:30
3751 | 2 | 2 |  | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are | 0 | 19 | 2021-05-07 08:30
3752 | 2 | 2 |  | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 1 | 1 |  | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression | 0 | 19 | 2021-05-07 08:30
3753 | 3 | 3 |  | The presence of communication barriers most likely leads to: | 1 | 1 |  | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers | 0 | 19 | 2021-05-07 08:30
3754 | 3 | 3 |  | The most common communication problem that occurs during negotiation is that: | 1 | 1 |  | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention | 0 | 19 | 2021-05-07 08:30
3755 | 3 | 3 |  | Which of the following tools or techniques are used in the Manage Communication Process? | 1 | 1 |  | This is ITTO question. Information management system & communication methods are the TTs | 0 | 19 | 2021-05-07 08:30
3756 | 3 | 3 |  | In an Agile project, an example of work performance data is: | 1 | 1 |  | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report | 0 | 19 | 2021-05-07 08:30
3757 | 3 | 3 |  | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 1 | 1 |  | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process | 0 | 19 | 2021-05-07 08:30
3758 | 3 | 3 |  | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 1 | 1 |  | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation) | 0 | 19 | 2021-05-07 08:30
3759 | 3 | 3 |  | All of the following statements are true about defect repairs EXCEPT: | 1 | 1 |  | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages | 0 | 19 | 2021-05-07 08:30
3760 | 3 | 3 |  | Inputs to Perform Integrated Change Control include: | 1 | 1 |  | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process | 0 | 19 | 2021-05-07 08:30
3761 | 3 | 3 |  | Most effective power which a Project Manager can have is: | 1 | 1 |  | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power | 0 | 19 | 2021-05-07 08:30
3762 | 3 | 3 |  | Least effective power is: | 1 | 1 |  | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective | 0 | 19 | 2021-05-07 08:30
3763 | 3 | 3 |  | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 1 | 1 |  | All other options EXCEPT Dictator is are forms of power | 0 | 19 | 2021-05-07 08:30
3764 | 3 | 3 |  | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 1 | 1 |  | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields | 0 | 19 | 2021-05-07 08:30
3765 | 2 | 2 |  | Punishment power is also known as: | 1 | 1 |  | Punishment includes both Coercion & penalty | 0 | 19 | 2021-05-07 08:30
3766 | 2 | 2 |  | Referent power is: | 1 | 1 |  | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power | 0 | 19 | 2021-05-07 08:30
3767 | 2 | 2 |  | Among the following which of the roles is LEAST appropriate for the Project Manager? | 1 | 1 |  | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles | 0 | 19 | 2021-05-07 08:30
3768 | 2 | 2 |  | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 1 | 1 |  | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid | 0 | 19 | 2021-05-07 08:30
3769 | 2 | 2 |  | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 1 | 1 |  | Refer to Maslow's pyramid: Humans have 5 basic needs | 0 | 19 | 2021-05-07 08:30
3770 | 2 | 2 |  | Where do successful project managers generally spend their maximum time? | 1 | 1 |  | The PM spends most of the time in communication (>80%) | 0 | 19 | 2021-05-07 08:30
3771 | 3 | 3 |  | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 1 | 1 |  | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria | 0 | 19 | 2021-05-07 08:30
3772 | 3 | 3 |  | Which of the following BEST describes the main purpose of the project charter? | 1 | 1 |  | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct | 0 | 19 | 2021-05-07 08:30
3773 | 3 | 3 |  | Which of the following is TRUE about iterative approach? | 1 | 1 |  | In iterative approach, uncertain environment & rapid changes can be effectively managed | 0 | 19 | 2021-05-07 08:30
3774 | 3 | 3 |  | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 1 | 1 |  | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next | 0 | 19 | 2021-05-07 08:30
3775 | 3 | 3 |  | "Statement of Work" is input to? | 1 | 1 |  | SoW is the clear input to the Charter. SoW is clearly not an input to other options | 0 | 19 | 2021-05-07 08:30
3776 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 1 | 1 |  | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part | 0 | 19 | 2021-05-07 08:30
3777 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 1 | 1 |  | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs) | 0 | 19 | 2021-05-07 08:30
3778 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 1 | 1 |  | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable | 0 | 19 | 2021-05-07 08:30
3779 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility analysis | 0 | 19 | 2021-05-07 08:30
3780 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis | 0 | 19 | 2021-05-07 08:30
3781 | 3 | 3 |  | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 1 | 1 |  | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives | 0 | 19 | 2021-05-07 08:30
3782 | 3 | 3 |  | Project Initiation's main objective is: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 19 | 2021-05-07 08:30
3783 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 1 | 1 |  | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification | 0 | 19 | 2021-05-07 08:30
3784 | 3 | 3 |  | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 1 | 1 |  | RFP/RFB & all associated contract documents should be referred whilst creating the SoW | 0 | 19 | 2021-05-07 08:30
3785 | 3 | 3 |  | Project Initiation's main objective is to: | 1 | 1 |  | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning | 0 | 19 | 2021-05-07 08:30
3786 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 1 | 1 |  | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME | 0 | 19 | 2021-05-07 08:30
3787 | 3 | 3 |  | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 1 | 1 |  | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process | 0 | 19 | 2021-05-07 08:30
3788 | 3 | 3 |  | In a project you are presented with the following four options. Which project should you select? | 1 | 1 |  | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project | 0 | 19 | 2021-05-07 08:30
3789 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 1 | 1 |  | "Initial requirement" is the key word here. Project Charter outlines this need | 0 | 19 | 2021-05-07 08:30
3790 | 3 | 3 |  | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 1 | 1 |  | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question | 0 | 19 | 2021-05-07 08:30
3791 | 3 | 3 |  | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 1 | 1 |  | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it | 0 | 19 | 2021-05-07 08:30
3792 | 3 | 3 |  | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 1 | 1 |  | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options | 0 | 19 | 2021-05-07 08:30
3793 | 3 | 3 |  | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 1 | 1 |  | Rick is creating the project charter. It has all the sections outlined in the first three options | 0 | 19 | 2021-05-07 08:30
3794 | 3 | 3 |  | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 1 | 1 |  | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company | 0 | 19 | 2021-05-07 08:30
3795 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286 | 0 | 19 | 2021-05-07 08:30
3796 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 19 | 2021-05-07 08:30
3797 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3 | 0 | 19 | 2021-05-07 08:30
3798 | 3 | 3 |  | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284 | 0 | 19 | 2021-05-07 08:30
3799 | 3 | 3 |  | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500 | 0 | 19 | 2021-05-07 08:30
3800 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30% | 0 | 19 | 2021-05-07 08:30
3801 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 1 | 1 |  | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5% | 0 | 19 | 2021-05-07 08:30
3802 | 3 | 3 |  | Your project has a CPI of 0.59. Which statement is TRUE? | 1 | 1 |  | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned | 0 | 19 | 2021-05-07 08:30
3803 | 3 | 3 |  | Your project has an SPI of 0.59. Which statement is TRUE? | 1 | 1 |  | SPI (Schedule Performance Index) measures the timeline percentage of project progress. | 0 | 19 | 2021-05-07 08:30
3804 | 3 | 3 |  | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 1 | 1 |  | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500 | 0 | 19 | 2021-05-07 08:30
3805 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 1 | 1 |  | EV=SV+PV=297500 CV=EV-AC=-127500 | 0 | 19 | 2021-05-07 08:30
3806 | 3 | 3 |  | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 1 | 1 |  | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000 | 0 | 19 | 2021-05-07 08:30
3807 | 3 | 3 |  | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 1 | 1 |  | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI | 0 | 19 | 2021-05-07 08:30
3808 | 3 | 3 |  | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 1 | 1 |  | Tracking & monitoring project budget is done in controlling process | 0 | 19 | 2021-05-07 08:30
3809 | 3 | 3 |  | Tools and techniques for performance reporting include all of the following EXCEPT: | 1 | 1 |  | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools | 0 | 19 | 2021-05-07 08:30
3810 | 3 | 3 |  | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 1 | 1 |  | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer | 0 | 19 | 2021-05-07 08:30
3811 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 1 | 1 |  | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either | 0 | 19 | 2021-05-07 08:30
3812 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 1 | 1 |  | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices | 0 | 19 | 2021-05-07 08:30
3813 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc. | 0 | 19 | 2021-05-07 08:30
3814 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 1 | 1 |  | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good. | 0 | 19 | 2021-05-07 08:30
3815 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 1 | 1 |  | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision | 0 | 19 | 2021-05-07 08:30
3816 | 3 | 3 |  | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 1 | 1 |  | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better | 0 | 19 | 2021-05-07 08:30
3817 | 3 | 3 |  | Which of the following is NOT a part of Control Procurements? | 1 | 1 |  | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements | 0 | 19 | 2021-05-07 08:30
3818 | 3 | 3 |  | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 1 | 1 |  | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process | 0 | 19 | 2021-05-07 08:30
3819 | 3 | 3 |  | What is/are the main difference(s) between Performance Review and an Inspection? | 1 | 1 |  | Both options 1 & 2 outline the major differences between performance reviews & audits | 0 | 19 | 2021-05-07 08:30
3820 | 3 | 3 |  | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 1 | 1 |  | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next | 0 | 19 | 2021-05-07 08:30
3821 | 3 | 3 |  | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 1 | 1 |  | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation | 0 | 19 | 2021-05-07 08:30
3822 | 3 | 3 |  | When should one use Inspection and Audit? | 1 | 1 |  | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard | 0 | 19 | 2021-05-07 08:30
3823 | 3 | 3 |  | When should one use Performance Review? | 1 | 1 |  | Performance reviews are done to ensure that the performance of the seller is as per the contract | 0 | 19 | 2021-05-07 08:30
3824 | 3 | 3 |  | Why is Performance Reporting necessary at Control Procurement process? | 1 | 1 |  | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller | 0 | 19 | 2021-05-07 08:30
3825 | 3 | 3 |  | Which of the following is TRUE? | 1 | 1 |  | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten | 0 | 19 | 2021-05-07 08:30
3826 | 3 | 3 |  | Payments to sellers should always be made according to the _______. | 1 | 1 |  | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties | 0 | 19 | 2021-05-07 08:30
3827 | 3 | 3 |  | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 1 | 1 |  | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing | 0 | 19 | 2021-05-07 08:30
3828 | 3 | 3 |  | Which one of the following techniques explains the effects of risk interdependencies? | 1 | 1 |  | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks | 0 | 19 | 2021-05-07 08:30
3829 | 3 | 3 |  | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 1 | 1 |  | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here | 0 | 19 | 2021-05-07 08:30
3830 | 3 | 3 |  | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 1 | 1 |  | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here | 0 | 19 | 2021-05-07 08:30
3831 | 3 | 3 |  | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 1 | 1 |  | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified | 0 | 19 | 2021-05-07 08:30
3832 | 3 | 3 |  | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 1 | 1 |  | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement. | 0 | 19 | 2021-05-07 08:30
3833 | 3 | 3 |  | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 1 | 1 |  | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks | 0 | 19 | 2021-05-07 08:30
3834 | 3 | 3 |  | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 1 | 1 |  | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis | 0 | 19 | 2021-05-07 08:30
3835 | 3 | 3 |  | Which of the following is NOT done at Control Risks? | 1 | 1 |  | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling | 0 | 19 | 2021-05-07 08:30
3836 | 3 | 3 |  | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 1 | 1 |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives | 0 | 19 | 2021-05-07 08:30
3837 | 3 | 3 |  | A project is considered complete when the : | 1 | 1 |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed. | 0 | 19 | 2021-05-07 08:30
3838 | 3 | 3 |  | Each project phase is marked by completion of one or more: | 1 | 1 |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases. | 0 | 19 | 2021-05-07 08:30
3839 | 3 | 3 |  | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 1 | 1 |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled. | 0 | 19 | 2021-05-07 08:30
3840 | 3 | 3 |  | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 1 | 1 |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM | 0 | 19 | 2021-05-07 08:30
3841 | 1 | 1 |  | Historical records during close-out are useful to __________ and ____________ for future projects: | 1 | 1 |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions | 0 | 19 | 2021-05-07 08:30
3842 | 3 | 3 |  | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 1 | 1 |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off | 0 | 19 | 2021-05-07 08:30
3843 | 3 | 3 |  | Which of the following would be the most appropriate thing to do during the closing process group? | 1 | 1 |  | Project performance reviews are done during closure. All other options are done during monitor & control domain | 0 | 19 | 2021-05-07 08:30
3844 | 3 | 3 |  | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 1 | 1 |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action | 0 | 19 | 2021-05-07 08:30
3845 | 3 | 3 |  | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 1 | 1 |  | Project status is incomplete till all the activities / processes are completed | 0 | 19 | 2021-05-07 08:30
3846 | 3 | 3 |  | All the following are always part of the close project/phase process EXCEPT: | 1 | 1 |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure | 0 | 19 | 2021-05-07 08:30
3847 | 3 | 3 |  | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 1 | 1 |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point" | 0 | 19 | 2021-05-07 08:30
3848 | 3 | 3 |  | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 1 | 1 |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase | 0 | 19 | 2021-05-07 08:30
3849 | 3 | 3 |  | All the following are required to bring a project to closure except:- | 1 | 1 |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending | 0 | 19 | 2021-05-07 08:30
3850 | 3 | 3 |  | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 1 | 1 |  | All work outlined in the SoW is completed, hence the contract is considered to be completed | 0 | 19 | 2021-05-07 08:30
3851 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 1 | 1 |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise | 0 | 19 | 2021-05-07 08:30
3852 | 2 | 2 |  | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 1 | 1 |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects | 0 | 19 | 2021-05-07 08:30
3853 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 1 | 1 |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only | 0 | 19 | 2021-05-07 08:30
3854 | 2 | 2 |  | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 1 | 1 |  | All other documents are NOT produced during this process. This is a direct ITTO question | 0 | 19 | 2021-05-07 08:30
3855 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 1 | 1 |  | Interpersonal skills are always considered soft skills as they are not core technical skills | 0 | 19 | 2021-05-07 08:30
3856 | 2 | 2 |  | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 1 | 1 |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills | 0 | 19 | 2021-05-07 08:30
3857 | 2 | 2 |  | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 1 | 1 |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together. | 0 | 19 | 2021-05-07 08:30
3858 | 2 | 2 |  | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 1 | 1 |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members. | 0 | 19 | 2021-05-07 08:30
3859 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 1 | 1 |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning | 0 | 19 | 2021-05-07 08:30
3860 | 2 | 2 |  | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 1 | 1 |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming) | 0 | 19 | 2021-05-07 08:30
3861 | 2 | 2 |  | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 1 | 1 |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase | 0 | 19 | 2021-05-07 08:30
3862 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 1 | 1 |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage | 0 | 19 | 2021-05-07 08:30
3863 | 2 | 2 |  | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 1 | 1 |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage | 0 | 19 | 2021-05-07 08:30
3864 | 2 | 2 |  | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 1 | 1 |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules | 0 | 19 | 2021-05-07 08:30
3865 | 2 | 2 |  | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 1 | 1 |  | Co-location is the most effective technique to develop teams from different geographical locations | 0 | 19 | 2021-05-07 08:30
3866 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 1 | 1 |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique | 0 | 19 | 2021-05-07 08:30
3867 | 2 | 2 |  | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 1 | 1 |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts | 0 | 19 | 2021-05-07 08:30
3868 | 2 | 2 |  | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 1 | 1 |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment | 0 | 19 | 2021-05-07 08:30
3869 | 2 | 2 |  | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 1 | 1 |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique | 0 | 19 | 2021-05-07 08:30
3870 | 2 | 2 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 1 | 1 |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart | 0 | 19 | 2021-05-07 08:30
3871 | 2 | 2 |  | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 1 | 1 |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit. | 0 | 19 | 2021-05-07 08:30
3872 | 2 | 2 |  | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 1 | 1 |  | Team development is the effective tool to keep higher motivation levels and bump up team morale | 0 | 19 | 2021-05-07 08:30
3873 | 2 | 2 |  | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 1 | 1 |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members | 0 | 19 | 2021-05-07 08:30
3874 | 2 | 2 |  | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 1 | 1 |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway) | 0 | 19 | 2021-05-07 08:30
3875 | 2 | 2 |  | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 1 | 1 |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects | 0 | 19 | 2021-05-07 08:30
3876 | 2 | 2 |  | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 1 | 1 |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet. | 0 | 19 | 2021-05-07 08:30
3877 | 2 | 2 |  | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 1 | 1 |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power | 0 | 19 | 2021-05-07 08:30
3878 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 1 | 1 |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO | 0 | 19 | 2021-05-07 08:30
3879 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 1 | 1 |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance. | 0 | 19 | 2021-05-07 08:30
3880 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 1 | 1 |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done. | 0 | 19 | 2021-05-07 08:30
3881 | 2 | 2 |  | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 1 | 1 |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power | 0 | 19 | 2021-05-07 08:30
3882 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 1 | 1 |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation | 0 | 19 | 2021-05-07 08:30
3883 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 1 | 1 |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option | 0 | 19 | 2021-05-07 08:30
3884 | 2 | 2 |  | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X | 0 | 19 | 2021-05-07 08:30
3885 | 2 | 2 |  | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 1 | 1 |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle. | 0 | 19 | 2021-05-07 08:30
3886 | 2 | 2 |  | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 1 | 1 |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors | 0 | 19 | 2021-05-07 08:30
3887 | 2 | 2 |  | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 1 | 1 |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development | 0 | 19 | 2021-05-07 08:30
3888 | 2 | 2 |  | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 1 | 1 |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed. | 0 | 19 | 2021-05-07 08:30
3889 | 2 | 2 |  | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 1 | 1 |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence | 0 | 19 | 2021-05-07 08:30
3890 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 1 | 1 |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance. | 0 | 19 | 2021-05-07 08:30
3891 | 2 | 2 |  | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 1 | 1 |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns | 0 | 19 | 2021-05-07 08:30
3892 | 2 | 2 |  | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 1 | 1 |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations | 0 | 19 | 2021-05-07 08:30
3893 | 2 | 2 |  | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 1 | 1 |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans | 0 | 19 | 2021-05-07 08:30
3894 | 2 | 2 |  | As per Herzberg's theory, which of the following is not a motivating agent? | 1 | 1 |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents | 0 | 19 | 2021-05-07 08:30
3895 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 1 | 1 |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option | 0 | 19 | 2021-05-07 08:30
3896 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 1 | 1 |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management | 0 | 19 | 2021-05-07 08:30
3897 | 2 | 2 |  | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 1 | 1 |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs | 0 | 19 | 2021-05-07 08:30
3898 | 2 | 2 |  | When should a Project Manager get involved in resolving a conflict? | 1 | 1 |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her | 0 | 19 | 2021-05-07 08:30
3899 | 2 | 2 |  | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 1 | 1 |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique. | 0 | 19 | 2021-05-07 08:30
3900 | 2 | 2 |  | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 1 | 1 |  | Involving staff in decision making process is the democratic management style | 0 | 19 | 2021-05-07 08:30
3901 | 2 | 2 |  | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 1 | 1 |  | All options but "Avoid" is not a conflict management/resolution technique | 0 | 19 | 2021-05-07 08:30
3902 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 1 | 1 |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together. | 0 | 19 | 2021-05-07 08:30
3903 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 1 | 1 |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations | 0 | 19 | 2021-05-07 08:30
3904 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 1 | 1 |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus | 0 | 19 | 2021-05-07 08:30
3905 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 1 | 1 |  | The conflicting parties are retreating or withdrawing from the conflicting situation. | 0 | 19 | 2021-05-07 08:30
3906 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 1 | 1 |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal. | 0 | 19 | 2021-05-07 08:30
3907 | 2 | 2 |  | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 1 | 1 |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force. | 0 | 19 | 2021-05-07 08:30
3908 | 2 | 2 |  | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 1 | 1 |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution | 0 | 19 | 2021-05-07 08:30
3909 | 2 | 2 |  | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 1 | 1 |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best | 0 | 19 | 2021-05-07 08:30
3910 | 1 | 1 |  | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 1 | 1 |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter. | 0 | 19 | 2021-05-07 08:30
3911 | 3 | 3 |  | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 1 | 1 |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements | 0 | 19 | 2021-05-07 08:30
3912 | 1 | 1 |  | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 1 | 1 |  | Project giving maximum returns (i.e. IRR) is considered to be better | 0 | 19 | 2021-05-07 08:30
3913 | 3 | 3 |  | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 1 | 1 |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward | 0 | 19 | 2021-05-07 08:30
3914 | 1 | 1 |  | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 1 | 1 |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options | 0 | 19 | 2021-05-07 08:30
3915 | 1 | 1 |  | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 1 | 1 |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM | 0 | 19 | 2021-05-07 08:30
3916 | 1 | 1 |  | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 1 | 1 |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back. | 0 | 19 | 2021-05-07 08:30
3917 | 3 | 3 |  | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 1 | 1 |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter | 0 | 19 | 2021-05-07 08:30
3918 | 3 | 3 |  | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 1 | 1 |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy | 0 | 19 | 2021-05-07 08:30
3919 | 1 | 1 |  | Which of the following is true regarding IRR? | 1 | 1 |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero. | 0 | 19 | 2021-05-07 08:30
3920 | 1 | 1 |  | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 1 | 1 |  | This is pure business need of the CPO. It is neither legal or customer requirement. | 0 | 19 | 2021-05-07 08:30
3921 | 3 | 3 |  | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 1 | 1 |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off | 0 | 19 | 2021-05-07 08:30
3922 | 1 | 1 |  | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 1 | 1 |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined | 0 | 19 | 2021-05-07 08:30
3923 | 1 | 1 |  | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 1 | 1 |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A. | 0 | 19 | 2021-05-07 08:30
3924 | 3 | 3 |  | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 1 | 1 |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question. | 0 | 19 | 2021-05-07 08:30
3925 | 1 | 1 |  | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 1 | 1 |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months | 0 | 19 | 2021-05-07 08:30
3926 | 1 | 1 |  | Which of the following is the most complex type of project selection method? | 1 | 1 |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized | 0 | 19 | 2021-05-07 08:30
3927 | 1 | 1 |  | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 1 | 1 |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost | 0 | 19 | 2021-05-07 08:30
3928 | 1 | 1 |  | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 1 | 1 |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months. | 0 | 19 | 2021-05-07 08:30
3929 | 1 | 1 |  | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 1 | 1 |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money | 0 | 19 | 2021-05-07 08:30
3930 | 3 | 3 |  | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 1 | 1 |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked. | 0 | 19 | 2021-05-07 08:30
3931 | 1 | 1 |  | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 1 | 1 |  | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs | 0 | 19 | 2021-05-07 08:30
3932 | 3 | 3 |  | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 1 | 1 |  | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones | 0 | 19 | 2021-05-07 08:30
3933 | 3 | 3 |  | Which of the following is the logical flow of any project? | 1 | 1 |  | This is very straight forward. IPECC is the natural flow of domains in the project flow | 0 | 19 | 2021-05-07 08:30
3934 | 3 | 3 |  | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 1 | 1 |  | Both the processes happen simultaneously as both include minimizing scope creep & gold plating | 0 | 19 | 2021-05-07 08:30
3935 | 3 | 3 |  | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 1 | 1 |  | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index) | 0 | 19 | 2021-05-07 08:30
3936 | 3 | 3 |  | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 1 | 1 |  | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data) | 0 | 19 | 2021-05-07 08:30
3937 | 3 | 3 |  | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 1 | 1 |  | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000 | 0 | 19 | 2021-05-07 08:30
3938 | 2 | 2 |  | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 1 | 1 |  | This is more moral & ethical that does not meet or exceed PM's quality standard. | 0 | 19 | 2021-05-07 08:30
3939 | 3 | 3 |  | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 1 | 1 |  | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits | 0 | 19 | 2021-05-07 08:30
3940 | 3 | 3 |  | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 1 | 1 |  | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope | 0 | 19 | 2021-05-07 08:30
3941 | 3 | 3 |  | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 1 | 1 |  | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA | 0 | 19 | 2021-05-07 08:30
3942 | 3 | 3 |  | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 1 | 1 |  | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details | 0 | 19 | 2021-05-07 08:30
3943 | 1 | 1 |  | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 1 | 1 |  | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy | 0 | 19 | 2021-05-07 08:30
3944 | 3 | 3 |  | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 1 | 1 |  | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied | 0 | 19 | 2021-05-07 08:30
3945 | 3 | 3 |  | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 1 | 1 |  | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product. | 0 | 19 | 2021-05-07 08:30
3946 | 3 | 3 |  | Which of the following is NOT true about configuration management ? | 1 | 1 |  | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management | 0 | 19 | 2021-05-07 08:30
3947 | 3 | 3 |  | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 1 | 1 |  | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work | 0 | 19 | 2021-05-07 08:30
3948 | 3 | 3 |  | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 1 | 1 |  | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative | 0 | 19 | 2021-05-07 08:30
3949 | 3 | 3 |  | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 1 | 1 |  | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management | 0 | 19 | 2021-05-07 08:30
3950 | 3 | 3 |  | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 1 | 1 |  | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options | 0 | 19 | 2021-05-07 08:30
3951 | 3 | 3 |  | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 1 | 1 |  | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process. | 0 | 19 | 2021-05-07 08:30
3952 | 3 | 3 |  | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 1 | 1 |  | Nobody can prevent changes from occurring. We can only react when a change event has occurred. | 0 | 19 | 2021-05-07 08:30
3953 | 3 | 3 |  | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 1 | 1 |  | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor | 0 | 19 | 2021-05-07 08:30
3954 | 3 | 3 |  | In all of the following form change requests can occur EXCEPT: | 1 | 1 |  | Except is key word that should not be missed. CRs cannot be informal | 0 | 19 | 2021-05-07 08:30
3955 | 3 | 3 |  | Which of the following BEST describes the impact of scope change requests? | 1 | 1 |  | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking) | 0 | 19 | 2021-05-07 08:30
3956 | 3 | 3 |  | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 1 | 1 |  | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform. | 0 | 19 | 2021-05-07 08:30
3957 | 3 | 3 |  | Which of the following statements are FALSE regarding Monte Carlo analysis? | 1 | 1 |  | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed. | 0 | 19 | 2021-05-07 08:30
3958 | 3 | 3 |  | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 1 | 1 |  | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines. | 0 | 19 | 2021-05-07 08:30
3959 | 3 | 3 |  | Variance analysis , trend analysis and earned value management techniques are:- | 1 | 1 |  | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management | 0 | 19 | 2021-05-07 08:30
3960 | 3 | 3 |  | What should the project manager be most concerned before moving to the final phase? | 1 | 1 |  | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase. | 0 | 19 | 2021-05-07 08:30
3961 | 3 | 3 |  | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 1 | 1 |  | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time. | 0 | 19 | 2021-05-07 08:30
3962 | 3 | 3 |  | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 1 | 1 |  | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take. | 0 | 19 | 2021-05-07 08:30
3963 | 3 | 3 |  | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 1 | 1 |  | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines | 0 | 19 | 2021-05-07 08:30
3964 | 3 | 3 |  | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 1 | 1 |  | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources | 0 | 19 | 2021-05-07 08:30
3965 | 3 | 3 |  | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 1 | 1 |  | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks) | 0 | 19 | 2021-05-07 08:30
3966 | 2 | 2 |  | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 1 | 1 |  | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique | 0 | 19 | 2021-05-07 08:30
3967 | 3 | 3 |  | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 1 | 1 |  | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies | 0 | 19 | 2021-05-07 08:30
3968 | 3 | 3 |  | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 1 | 1 |  | NOT is the keywork here. We do all other options except changing the project schedule | 0 | 19 | 2021-05-07 08:30
3969 | 3 | 3 |  | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 1 | 1 |  | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule | 0 | 19 | 2021-05-07 08:30
3970 | 3 | 3 |  | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 1 | 1 |  | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns) | 0 | 19 | 2021-05-07 08:30
3971 | 3 | 3 |  | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500 | 0 | 19 | 2021-05-07 08:30
3972 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7 | 0 | 19 | 2021-05-07 08:30
3973 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875 | 0 | 19 | 2021-05-07 08:30
3974 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget | 0 | 19 | 2021-05-07 08:30
3975 | 3 | 3 |  | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 1 | 1 |  | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget | 0 | 19 | 2021-05-07 08:30
3976 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned is more than planned, we are clearly ahead of schedule | 0 | 19 | 2021-05-07 08:30
3977 | 3 | 3 |  | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 1 | 1 |  | As we have earned less than what was planned, we are clearly behind schedule | 0 | 19 | 2021-05-07 08:30
3978 | 3 | 3 |  | Which of the following statement is NOT true about CPI and SPI? | 1 | 1 |  | "NOT true" is the key word. CPI & SPI cannot be less than 0 | 0 | 19 | 2021-05-07 08:30
3979 | 3 | 3 |  | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 1 | 1 |  | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off) | 0 | 19 | 2021-05-07 08:30
3980 | 2 | 2 |  | Which of the following shows roles and responsibilities on your project? | 1 | 1 |  | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities) | 0 | 19 | 2021-05-07 08:30
3981 | 3 | 3 |  | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 1 | 1 |  | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration | 0 | 19 | 2021-05-07 08:30
3982 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 1 | 1 |  | Option 3 is operation (ongoing task). Both options 1 & 2 define the project | 0 | 19 | 2021-05-07 08:30
3983 | 3 | 3 |  | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 1 | 1 |  | Michael does not have full authority over the project & his primary role is to track the project progress | 0 | 19 | 2021-05-07 08:30
3984 | 2 | 2 |  | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 1 | 1 |  | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project | 0 | 19 | 2021-05-07 08:30
3985 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 1 | 1 |  | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer | 0 | 19 | 2021-05-07 08:30
3986 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 1 | 1 |  | Activities are created & sequenced in Schedule Management KA | 0 | 19 | 2021-05-07 08:30
3987 | 2 | 2 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 1 | 1 |  | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization | 0 | 19 | 2021-05-07 08:30
3988 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 1 | 1 |  | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false | 0 | 19 | 2021-05-07 08:30
3989 | 3 | 3 |  | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 1 | 1 |  | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase | 0 | 19 | 2021-05-07 08:30
3990 | 2 | 2 |  | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 1 | 1 |  | All the three options outline the characteristics of functional organization | 0 | 19 | 2021-05-07 08:30
3991 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 1 | 1 |  | In projectized organization, all decisions are taken by the PM and PM has maximum authority | 0 | 19 | 2021-05-07 08:30
3992 | 2 | 2 |  | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 1 | 1 |  | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority | 0 | 19 | 2021-05-07 08:30
3993 | 2 | 2 |  | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 1 | 1 |  | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE") | 0 | 19 | 2021-05-07 08:30
3994 | 2 | 2 |  | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 1 | 1 |  | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities | 0 | 19 | 2021-05-07 08:30
3995 | 3 | 3 |  | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 1 | 1 |  | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to. | 0 | 19 | 2021-05-07 08:30
3996 | 3 | 3 |  | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 1 | 1 |  | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur | 0 | 19 | 2021-05-07 08:30
3997 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 1 | 1 |  | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk | 0 | 19 | 2021-05-07 08:30
3998 | 3 | 3 |  | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 1 | 1 |  | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. | 0 | 19 | 2021-05-07 08:30
3999 | 3 | 3 |  | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 1 | 1 |  | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies) | 0 | 19 | 2021-05-07 08:30
4000 | 3 | 3 |  | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 1 | 1 |  | Risks are accepted if the impact is within the threshold that is also known as risk tolerance | 0 | 19 | 2021-05-07 08:30
4001 | 3 | 3 |  | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 1 | 1 |  | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed | 0 | 19 | 2021-05-07 08:30
4002 | 3 | 3 |  | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 1 | 1 |  | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process | 0 | 19 | 2021-05-07 08:30
4003 | 3 | 3 |  | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 1 | 1 |  | Entire project team is involved in identifying risks. | 0 | 19 | 2021-05-07 08:30
4004 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 1 | 1 |  | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project | 0 | 19 | 2021-05-07 08:30
4005 | 3 | 3 |  | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 1 | 1 |  | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline | 0 | 19 | 2021-05-07 08:30
4006 | 3 | 3 |  | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 1 | 1 |  | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed. | 0 | 19 | 2021-05-07 08:30
4007 | 3 | 3 |  | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 1 | 1 |  | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability | 0 | 19 | 2021-05-07 08:30
4008 | 3 | 3 |  | To come out with staffing requirement , Project Manager first needs:- | 1 | 1 |  | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it | 0 | 19 | 2021-05-07 08:30
4009 | 3 | 3 |  | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 1 | 1 |  | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique | 0 | 19 | 2021-05-07 08:30
4010 | 3 | 3 |  | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 1 | 1 |  | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis | 0 | 19 | 2021-05-07 08:30
4011 | 3 | 3 |  | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 1 | 1 |  | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45 | 0 | 19 | 2021-05-07 08:30
4012 | 3 | 3 |  | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 1 | 1 |  | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21 | 0 | 19 | 2021-05-07 08:30
4013 | 3 | 3 |  | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 1 | 1 |  | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added | 0 | 19 | 2021-05-07 08:30
4014 | 3 | 3 |  | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 1 | 1 |  | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question) | 0 | 19 | 2021-05-07 08:30
4015 | 3 | 3 |  | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 1 | 1 |  | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping | 0 | 19 | 2021-05-07 08:30
4016 | 3 | 3 |  | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 1 | 1 |  | NOT is the key. Project is not ongoing as operations | 0 | 19 | 2021-05-07 08:30
4017 | 2 | 2 |  | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 1 | 1 |  | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question | 0 | 19 | 2021-05-07 08:30
4018 | 3 | 3 |  | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 1 | 1 |  | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow | 0 | 19 | 2021-05-07 08:30
4019 | 3 | 3 |  | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 1 | 1 |  | All risk responses have to be considered in this case | 0 | 19 | 2021-05-07 08:30
4020 | 3 | 3 |  | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation | 0 | 19 | 2021-05-07 08:30
4021 | 3 | 3 |  | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact) | 0 | 19 | 2021-05-07 08:30
4022 | 3 | 3 |  | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 1 | 1 |  | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV) | 0 | 19 | 2021-05-07 08:30
4023 | 3 | 3 |  | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 1 | 1 |  | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered | 0 | 19 | 2021-05-07 08:30
4024 | 3 | 3 |  | Jack has just taken over a project. He is now currently identifying risks in the project. He gets all Team member in a room and started to pump out ideas. Which among the following information gathering techniques is he using? | 1 | 1 |  | Jack is encouraging all teams members to provide their inputs in identifying risks. He is not masking the identity of the team members as in Delphi technique. He is not conducting 1 on 1s as in interviews. | 0 | 19 | 2021-05-07 08:30
4025 | 3 | 3 |  | You are Project Manager working in IT CORP LTD. You have been assigned a new project of Inventory management System. You are currently identifying risks in your project. You decided to send questionnaires to experts asking about important project risks. Which type of the following information gathering technique is he using? | 1 | 1 |  | You are gathering inputs without other team members knowing the identity of the team member providing inputs which is Delphi technique. | 0 | 19 | 2021-05-07 08:30
4026 | 3 | 3 |  | You are Project Manager working in IT CORP LTD. You have been assigned a new project on Inventory management System. You are currently identifying risks in your project by looking at plans, requirements and documents from your organization process assets. Which type of the identify risk technique you are using? | 1 | 1 |  | You are reviewing historical information of similar past projects to identify potential risks that may be applicable for the current project. You are using "Document Review" technique. You are neither analyzing assumptions/constraints nor doing SWOT analysis not analyzing checklists | 0 | 19 | 2021-05-07 08:30
4027 | 2 | 2 |  | Carrie is a project manager. Two of her team members are engaged in a conflict and they reach out to her for a solution. However, one team member wants them to resolve the conflict on their own. Which conflict resolution Technique did she use? | 1 | 1 | Complex | When one stakeholder wants to resolve the confict any of the techniques can be used. In the current scenario all the others barring Withdrawal need both stakeholders to be engaged. Hence most logical choice is Withdrawal. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 0 | 19 | 2021-05-07 08:30
4028 | 1 | 1 |  | Project A has a NPV of $1 million and IRR of 4%. Project B hand a NPV of $1.1 million and IRR of $3.9%. Which project should you select? | 1 | 1 | High Complex | Since the IRR are almost similar one should choose the project with greater NPV. Best choice in this situation will be Project B. | 0 | 19 | 2021-05-07 08:30
4029 | 3 | 3 |  | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 1 | 1 | Medium | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 0 | 19 | 2021-05-07 08:30
4030 | 3 | 3 |  | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 1 | 1 | Complex | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 0 | 19 | 2021-05-07 08:30
4031 | 3 | 3 |  | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 1 | 1 | Complex | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 0 | 19 | 2021-05-07 08:30
4032 | 2 | 2 |  | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 1 | 1 | Complex | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 0 | 19 | 2021-05-07 08:30
4033 | 2 | 2 |  | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 1 | 1 | High Complex | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 0 | 19 | 2021-05-07 08:30
4034 | 3 | 3 |  | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 1 | 1 | Simple | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 0 | 19 | 2021-05-07 08:30
4035 | 3 | 3 |  | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 1 | 1 | High Complex | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 0 | 19 | 2021-05-07 08:30
4036 | 2 | 2 |  | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 1 | 1 | Complex | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 0 | 19 | 2021-05-07 08:30
4037 | 3 | 3 |  | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 1 | 1 | Complex | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 0 | 19 | 2021-05-07 08:30
4038 | 2 | 2 |  | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 1 | 1 | Complex | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 0 | 19 | 2021-05-07 08:30
4039 | 3 | 3 |  | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 1 | 1 | Medium | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 0 | 19 | 2021-05-07 08:30
4040 | 3 | 3 |  | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 1 | 1 | Complex | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 0 | 19 | 2021-05-07 08:30
4041 | 1 | 1 |  | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 1 | 1 | High Complex | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 0 | 19 | 2021-05-07 08:30
4042 | 2 | 2 |  | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 1 | 1 | Complex | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 0 | 19 | 2021-05-07 08:30
4043 | 3 | 3 |  | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 1 | 1 | Simple | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 0 | 19 | 2021-05-07 08:30
4044 | 1 | 1 |  | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 1 | 1 | Simple | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 0 | 19 | 2021-05-07 08:30
4045 | 3 | 3 |  | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 1 | 1 | Complex | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 0 | 19 | 2021-05-07 08:30
4046 | 3 | 3 |  | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 1 | 1 | High Complex | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 0 | 19 | 2021-05-07 08:30
4047 | 3 | 3 |  | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 1 | 1 | Complex | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 19 | 2021-05-07 08:30
4048 | 3 | 3 |  | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 1 | 1 | High Complex | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 0 | 19 | 2021-05-07 08:30
4049 | 3 | 3 |  | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 1 | 1 | Complex | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 0 | 19 | 2021-05-07 08:30
4050 | 2 | 2 |  | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 1 | 1 | Simple | PM is responsible to perform CCB process. Best choice is option A. | 0 | 19 | 2021-05-07 08:30
4051 | 3 | 3 |  | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 1 | 1 | Complex | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 0 | 19 | 2021-05-07 08:30
4052 | 3 | 3 |  | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 1 | 1 | Complex | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 0 | 19 | 2021-05-07 08:30
4053 | 2 | 2 |  | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 1 | 1 | High Complex | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 0 | 19 | 2021-05-07 08:30
4054 | 3 | 3 |  | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 1 | 1 | Medium | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 19 | 2021-05-07 08:30
4055 | 3 | 3 |  | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 1 | 1 | Complex | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 0 | 19 | 2021-05-07 08:30
4056 | 3 | 3 |  | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 1 | 1 | Complex | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 0 | 19 | 2021-05-07 08:30
4057 | 2 | 2 |  | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 1 | 1 | High Complex | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 0 | 19 | 2021-05-07 08:30
4058 | 3 | 3 |  | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 1 | 1 | Complex | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 0 | 19 | 2021-05-07 08:30
4059 | 3 | 3 |  | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 1 | 1 | Complex | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 0 | 19 | 2021-05-07 08:30
4060 | 3 | 3 |  | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 1 | 1 | Medium | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 0 | 19 | 2021-05-07 08:30
4061 | 2 | 2 |  | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 1 | 1 | High Complex | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 0 | 19 | 2021-05-07 08:30
4062 | 2 | 2 |  | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 1 | 1 | High Complex | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 0 | 19 | 2021-05-07 08:30
4063 | 3 | 3 |  | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 1 | 1 | High Complex | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 0 | 19 | 2021-05-07 08:30
4064 | 2 | 2 |  | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 1 | 1 | Complex | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 0 | 19 | 2021-05-07 08:30
4065 | 3 | 3 |  | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 1 | 1 | High Complex | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 0 | 19 | 2021-05-07 08:30
4066 | 3 | 3 |  | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 1 | 1 | Complex | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 0 | 19 | 2021-05-07 08:30
4067 | 3 | 3 |  | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 1 | 1 | Simple | Lowest level item in WBS are the deliverables. Best choice is A. | 0 | 19 | 2021-05-07 08:30
4068 | 2 | 2 |  | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 1 | 1 | Complex | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 0 | 19 | 2021-05-07 08:30
4069 | 2 | 2 |  | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 1 | 1 | High Complex | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 0 | 19 | 2021-05-07 08:30
4070 | 3 | 3 |  | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 1 | 1 | High Complex | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 19 | 2021-05-07 08:30
4071 | 3 | 3 |  | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 1 | 1 | Complex | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 0 | 19 | 2021-05-07 08:30
4072 | 3 | 3 |  | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 1 | 1 | Complex | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 0 | 19 | 2021-05-07 08:30
4073 | 3 | 3 |  | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 1 | 1 | High Complex | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 0 | 19 | 2021-05-07 08:30
4074 | 3 | 3 |  | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 1 | 1 | High Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 19 | 2021-05-07 08:30
4075 | 3 | 3 |  | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 19 | 2021-05-07 08:30
4076 | 3 | 3 |  | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 1 | 1 | Complex | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 0 | 19 | 2021-05-07 08:30
4077 | 3 | 3 |  | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 1 | 1 | Complex | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 0 | 19 | 2021-05-07 08:30
4078 | 2 | 2 |  | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 1 | 1 | High Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 19 | 2021-05-07 08:30
4079 | 3 | 3 |  | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 1 | 1 | Medium | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 0 | 19 | 2021-05-07 08:30
4080 | 3 | 3 |  | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 1 | 1 | Complex | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 0 | 19 | 2021-05-07 08:30
4081 | 3 | 3 |  | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 1 | 1 | Medium | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 0 | 19 | 2021-05-07 08:30
4082 | 3 | 3 |  | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 1 | 1 | High Complex | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 0 | 19 | 2021-05-07 08:30
4083 | 2 | 2 |  | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 1 | 1 | High Complex | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 19 | 2021-05-07 08:30
4084 | 3 | 3 |  | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 1 | 1 | Complex | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 0 | 19 | 2021-05-07 08:30
4085 | 3 | 3 |  | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 1 | 1 | High Complex | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 0 | 19 | 2021-05-07 08:30
4086 | 3 | 3 |  | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 1 | 1 | Complex | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 0 | 19 | 2021-05-07 08:30
4087 | 3 | 3 |  | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 1 | 1 | Complex | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 0 | 19 | 2021-05-07 08:30
4088 | 2 | 2 |  | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 1 | 1 | Medium | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 0 | 19 | 2021-05-07 08:30
4089 | 3 | 3 |  | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 1 | 1 | Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 19 | 2021-05-07 08:30
4090 | 2 | 2 |  | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 1 | 1 | Complex | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 0 | 19 | 2021-05-07 08:30
4091 | 2 | 2 |  | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 1 | 1 | Complex | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 0 | 19 | 2021-05-07 08:30
4092 | 3 | 3 |  | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 1 | 1 | High Complex | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 0 | 19 | 2021-05-07 08:30
4093 | 3 | 3 |  | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 1 | 1 | Complex | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 0 | 19 | 2021-05-07 08:30
4094 | 2 | 2 |  | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 1 | 1 | High Complex | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 0 | 19 | 2021-05-07 08:30
4095 | 2 | 2 |  | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 1 | 1 | Complex | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 0 | 19 | 2021-05-07 08:30
4096 | 3 | 3 |  | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 1 | 1 | Complex | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 0 | 19 | 2021-05-07 08:30
4097 | 2 | 2 |  | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 1 | 1 | High Complex | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 0 | 19 | 2021-05-07 08:30
4098 | 3 | 3 |  | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 1 | 1 | High Complex | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 0 | 19 | 2021-05-07 08:30
4099 | 2 | 2 |  | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 1 | 1 | Complex | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 0 | 19 | 2021-05-07 08:30
4100 | 2 | 2 |  | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 1 | 1 | Complex | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 0 | 19 | 2021-05-07 08:30
4101 | 3 | 3 |  | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 1 | 1 | High Complex | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 0 | 19 | 2021-05-07 08:30
4102 | 2 | 2 |  | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 1 | 1 | High Complex | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 0 | 19 | 2021-05-07 08:30
4103 | 3 | 3 |  | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 1 | 1 | Medium | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 0 | 19 | 2021-05-07 08:30
4104 | 3 | 3 |  | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 1 | 1 | Medium | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 0 | 19 | 2021-05-07 08:30
4105 | 2 | 2 |  | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 1 | 1 | Complex | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 0 | 19 | 2021-05-07 08:30
4106 | 2 | 2 |  | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 1 | 1 | Complex | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 0 | 19 | 2021-05-07 08:30
4107 | 3 | 3 |  | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 1 | 1 | Complex | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 0 | 19 | 2021-05-07 08:30
4108 | 3 | 3 |  | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 19 | 2021-05-07 08:30
4109 | 2 | 2 |  | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 1 | 1 | Complex | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 0 | 19 | 2021-05-07 08:30
4110 | 2 | 2 |  | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 1 | 1 | Complex | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 0 | 19 | 2021-05-07 08:30
4111 | 3 | 3 |  | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 1 | 1 | Complex | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 0 | 19 | 2021-05-07 08:30
4112 | 3 | 3 |  | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 1 | 1 | Medium | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 19 | 2021-05-07 08:30
4113 | 3 | 3 |  | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 1 | 1 | Medium | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 0 | 19 | 2021-05-07 08:30
4114 | 2 | 2 |  | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 1 | 1 | Complex | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 0 | 19 | 2021-05-07 08:30
4115 | 3 | 3 |  | A project manager using probability distributions to display data is most likely to use which of the following: | 1 | 1 | Complex | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 0 | 19 | 2021-05-07 08:30
4116 | 2 | 2 |  | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 1 | 1 | Complex | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 0 | 19 | 2021-05-07 08:30
4117 | 3 | 3 |  | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 1 | 1 | High Complex | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 0 | 19 | 2021-05-07 08:30
4118 | 1 | 1 |  | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 1 | 1 | High Complex | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 0 | 19 | 2021-05-07 08:30
4119 | 3 | 3 |  | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 1 | 1 | Complex | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 0 | 19 | 2021-05-07 08:30
4120 | 2 | 2 |  | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 1 | 1 | High Complex | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 0 | 19 | 2021-05-07 08:30
4121 | 3 | 3 |  | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 1 | 1 | High Complex | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 0 | 19 | 2021-05-07 08:30
4122 | 3 | 3 |  | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 1 | 1 | Complex | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 0 | 19 | 2021-05-07 08:30
4123 | 3 | 3 |  | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 1 | 1 | High Complex | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 0 | 19 | 2021-05-07 08:30
4124 | 3 | 3 |  | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 1 | 1 | Complex | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 0 | 19 | 2021-05-07 08:30
4125 | 3 | 3 |  | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 1 | 1 | Complex | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 0 | 19 | 2021-05-07 08:30
4126 | 2 | 2 |  | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 1 | 1 | High Complex | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 0 | 19 | 2021-05-07 08:30
4127 | 2 | 2 |  | You have been tasked with creating the project charter for your new project. Who are you? | 1 | 1 | Simple | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 0 | 19 | 2021-05-07 08:30
4128 | 3 | 3 |  | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 1 | 1 | Complex | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 0 | 19 | 2021-05-07 08:30
4129 | 3 | 3 |  | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 1 | 1 | Medium | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 0 | 19 | 2021-05-07 08:30
4130 | 3 | 3 |  | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 1 | 1 | Complex | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 0 | 19 | 2021-05-07 08:30
4131 | 2 | 2 |  | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 1 | 1 | Medium | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 0 | 19 | 2021-05-07 08:30
4132 | 3 | 3 |  | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 1 | 1 | Complex | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 0 | 19 | 2021-05-07 08:30
4133 | 2 | 2 |  | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 1 | 1 | Complex | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 0 | 19 | 2021-05-07 08:30
4134 | 2 | 2 |  | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 1 | 1 | Complex | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 0 | 19 | 2021-05-07 08:30
4135 | 3 | 3 |  | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 1 | 1 | Complex | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 0 | 19 | 2021-05-07 08:30
4136 | 3 | 3 |  | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 1 | 1 | Complex | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 0 | 19 | 2021-05-07 08:30
4137 | 1 | 1 |  | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 1 | 1 | Medium | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 0 | 19 | 2021-05-07 08:30
4138 | 1 | 1 |  | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 1 | 1 | Complex | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 0 | 19 | 2021-05-07 08:30
4139 | 3 | 3 |  | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 1 | 1 | Complex | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 0 | 19 | 2021-05-07 08:30
4140 | 3 | 3 |  | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 1 | 1 | Complex | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 0 | 19 | 2021-05-07 08:30
4141 | 3 | 3 |  | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 1 | 1 | Complex | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 0 | 19 | 2021-05-07 08:30
4142 | 1 | 1 |  | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 1 | 1 | Complex | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 0 | 19 | 2021-05-07 08:30
4143 | 2 | 2 |  | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 1 | 1 | High Complex | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 0 | 19 | 2021-05-07 08:30
4144 | 2 | 2 |  | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 1 | 1 | High Complex | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 0 | 19 | 2021-05-07 08:30
4145 | 2 | 2 |  | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 1 | 1 | Medium | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 0 | 19 | 2021-05-07 08:30
4146 | 1 | 1 |  | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 1 | 1 | High Complex | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 0 | 19 | 2021-05-07 08:30
4147 | 1 | 1 |  | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 1 | 1 | Medium | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 0 | 19 | 2021-05-07 08:30
4148 | 3 | 3 |  | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 1 | 1 | Medium | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 0 | 19 | 2021-05-07 08:30
4149 | 2 | 2 |  | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 1 | 1 | High Complex | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 0 | 19 | 2021-05-07 08:30
4150 | 2 | 2 |  | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 1 | 1 | Complex | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 0 | 19 | 2021-05-07 08:30
4151 | 3 | 3 |  | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 1 | 1 | Medium | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 0 | 19 | 2021-05-07 08:30
4152 | 3 | 3 |  | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 1 | 1 | Simple | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 0 | 19 | 2021-05-07 08:30
4153 | 3 | 3 |  | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 1 | 1 | Simple | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 0 | 19 | 2021-05-07 08:30
4154 | 3 | 3 |  | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 1 | 1 | High Complex | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 0 | 19 | 2021-05-07 08:30
4155 | 2 | 2 |  | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 1 | 1 | Simple | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 0 | 19 | 2021-05-07 08:30
4156 | 3 | 3 |  | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 1 | 1 | Complex | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 0 | 19 | 2021-05-07 08:30
4157 | 3 | 3 |  | Which of the following statement is true with respect to a typical project scenario? | 1 | 1 | Complex | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 0 | 19 | 2021-05-07 08:30
4158 | 2 | 2 |  | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 1 | 1 | Medium | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 0 | 19 | 2021-05-07 08:30
4159 | 3 | 3 |  | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 1 | 1 | Complex | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 0 | 19 | 2021-05-07 08:30
4160 | 1 | 1 |  | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 1 | 1 | High Complex | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 0 | 19 | 2021-05-07 08:30
4161 | 2 | 2 |  | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 1 | 1 | Medium | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 0 | 19 | 2021-05-07 08:30
4162 | 3 | 3 |  | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 1 | 1 | Complex | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 0 | 19 | 2021-05-07 08:30
4163 | 2 | 2 |  | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 1 | 1 | High Complex | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 0 | 19 | 2021-05-07 08:30
4164 | 1 | 1 |  | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 1 | 1 | Complex | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 0 | 19 | 2021-05-07 08:30
4165 | 3 | 3 |  | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 1 | 1 | High Complex | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 0 | 19 | 2021-05-07 08:30
4166 | 1 | 1 |  | Making small, incremental improvements within a product or process is known as: | 1 | 1 | Complex | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 0 | 19 | 2021-05-07 08:30
4167 | 3 | 3 |  | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 1 | 1 | Complex | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 0 | 19 | 2021-05-07 08:30
4168 | 1 | 1 |  | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 1 | 1 | High Complex | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 0 | 19 | 2021-05-07 08:30
4169 | 3 | 3 |  | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 1 | 1 | Complex | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 0 | 19 | 2021-05-07 08:30
4170 | 2 | 2 |  | Within Agile, a “T” shaped person refers to what? | 1 | 1 | High Complex | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 0 | 19 | 2021-05-07 08:30
4171 | 3 | 3 |  | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 1 | 1 | Complex | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 0 | 19 | 2021-05-07 08:30