## all_permeter_sheet_new_only
QuestionID | QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Question Category | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
1 | SINGLE | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? | 4 | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and require standup attendance. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction.In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 43933.9653 | N | 4 | [5 empty] | NA | NA
2 | SINGLE | Project team members are concerned that a new resource does not seem suitable for an assigned task. How should the project manager respond to this concern? | 4 | Contact senior management to discuss the possibility of reassigning the new resource to a different project. | Schedule time to chat with the new resource to assess their skills and understand their strength level. | Ask the team members to document task-related deficiencies displayed by the resource. | Contact the project sponsor to highlight these concerns and decide on an appropriate response. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A project manager should not take action by just listening to other member’s feedback. He should talk to the new member to find out about his strength and make some evaluation later. PMBOK® Guide Sixth Edition (2018) PMI, 9. Project Resource Management / 9.4 Develop team, p338 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 43933.9653
3 | SINGLE | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? | 4 | Work with key stakeholders to identify project requirements that could be reduced. | Immediately ask project team members to increase the pace of each task within the project. | Ensure that substantial scope creep is included in the original project schedule, so that revised deadlines can be met. | Meet individually with project team members to discuss how aspects of the project can be completed more quickly than planned. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 43933.9653
4 | SINGLE | During an iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? | 4 | Meet with both teams separately, and ask them to figure out a way to meet the required deadlines and complete the project on time. | Meet with the product owner to reprioritize the iteration backlog, so that it does not impact other teams or obligations. | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule. | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in lessons learned. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 43933.9653
5 | SINGLE | The project manager schedules an iteration review and learns that a few key stakeholders do not approve of how a feature has been developed. What should the project manager do first in order to address this issue? | 4 | Invite project team members to a brainstorming session to identify an appropriate response. | Address the issue only after evaluating why these stakeholders are concerned. | Determine the impact of the conflict by listing the pros and cons of the situation. | Ask the project sponsor to act as a neutral party in negotiation with those stakeholders who are dissatisfied. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | One of the required abilities of Project Managers is to identify when the conflict escalates. If it happens, the Project Manager should help to facilitate a satisfactory solution, addressing conflict early, in private an using a direct and collaborative approach. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 43933.9653
6 | SINGLE | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | 4 | Discuss the conflict with the project sponsor and formulate a response. | Replace the key team member with a new resource who has the same skills. | Meet with the change control board (CCB) to discuss the requested change. | Engage in the change management process to resolve the resource issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 43933.9653
7 | SINGLE | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The Project manager is surprised because the team is in the process of executing an important component of the project and the concern has not been raised before. What steps should the project manager take? | 4 | Update the risk register to document the concerns, then continue with the meeting’s scheduled agenda items. | Recognize that the concern must be fully discussed and resolved prior to continuing with the meeting’s agenda items. | Address the team with a generic reminder about meeting etiquette, then ask if the team wants to use the time to fully discuss the concerns raised during the meeting. | Immediately acknowledge the team member’s concern, continue with the scheduled agenda, then privately meet with the team member to fully understand the concerns expressed. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 43933.9653
8 | SINGLE | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | 4 | Notify the project sponsor about the lack of a technical resource. | Immediately escalate the issue to decision makers in the organization. | Check with the technical resource manager to see if there is an available technical resource. | Since time is short, hire an outside party to meet the need for a technical resource. |  |  | 3 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 43933.9653
9 | SINGLE | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, there are team members who have not had the appropriate agile training. How should the project manager respond to the lack of agile training? | 4 | Include agile training for these team members in a change request. | Ensure the project’s contingency reserve can cover agile training for all team members. | Create virtual training sessions for key team members, covering the main agile topics. | Identify and implement the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Medium | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018) 9. Project resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities, 37 | 43933.9653
10 | SINGLE | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? | 4 | Offer more skill-specific training throughout the project. | Identify required strengths, and organize the team based on those strengths. | Meet with the project sponsor and team members to assign training for specific skills. | Empower team members to problem solve in situations where skills may be lacking. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 43933.9653
11 | SINGLE | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? | 4 | Ask team members to invite their managers to standup sessions, in order to find solutions more quickly. | Explain to team members that long discussions take time away from actual work on the project. | Insert a new team member who will manage obstacles and schedule additional meetings to discuss possible solutions. | Tell the team members that they are required to shorten the standup meetings and improve on finding solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Agile Hybrid | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 43933.9653
12 | SINGLE | A customer is not satisfied with the delivered product, saying that it was not what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | 4 | Required team sign off for each of the constant changes to the requirements | Set aside more resources for product testing after changes are made | Made sure that the customer was aware of the value of demos | Ensured that the team fully participated in developing the project scope |  |  | 3 | 1 | PMP | Process | Project Stakeholder Management |  |  | Medium | Predictive Approach | The customer was not engaged enough in the project. The iteration review is the best mechanism for the team to demonstrate working software and for the customer to give feedback to ensure that their expectations are met. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement,524 ¦ The Agile Practice Guide (No Date), 5 Implementing Agile: Delivering in and Agile Environment / 5.2.5 Demonstrations/Reviews, 55 | 43933.9653
13 | SINGLE | A project manager's team has been efficiently delivering expected results in an environment where budget and scope are fixed. Now, there is an increased demand for new skills due to changes in the market. What can the project manager do to meet this new demand? | 4 | Meet the new demand by adding new resources with the required skills. | Hire a third-party vendor who can provide resources with the needed skills. | Change the distribution of partially dedicated resources with the needed skills. | Meet the new demand by upgrading the existing team members' skills. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop Team: Identifying and assessing skills is the key responsibility of a Project Manager and accordingly upgrading the team's skill and competencies to meet the project demand. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, pp 336-338 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1.4 Consider These Servant Leader Responsibilities, pp 36-37 | 43933.9653
14 | SINGLE | A project team is small and the team members have known each other for a long time. The team's project is in the execution phase. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | 4 | Preview the current stakeholder engagement plan for the way to resolve the difficulty. | Schedule a mandatory team meeting which will lead to the creation of a new social contract. | Notify team members that they should submit anonymous recommendations for a new social contract. | Send a survey to team members, requesting suggestions for dealing with the dissatisfaction. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - While this may help in addressing the situation, it will not help to rectify any existing damage done to the team as a result of the situation. B) Yes - This is the best solution. It encourages every team member to particulate and results in a clear set of guidelines for the team. C) No - This is not the best answer. While this will create a set of guidelines, they may not be the best ones for the team. D) No - This is not the best solution as it does not encourage team cohesion and self leadership. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 Team Charter, 319 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In AN Agile Environment / 5.1 Charter The Project And The Team p50 | 43933.9653
15 | SINGLE | During a highly-regulated project, the project sponsor and a high-level executive have asked for changes that appear to disregard legal requirements. What should be the first step in the project manager's response? | 4 | Immediately schedule a meeting with the stakeholders to review the situation. | Send the change control board (CCB) a change request. | Check with the organization's relevant legal practitioner for guidance. | Review the organization's lessons learned database for precedents and direction. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | A) No - This is not the best response as you may not fully understand the situation. B) No - This is necessary but is not the first step C) Yes - This is the best FIRST step before going to the CCB because this is a highly regulated industry D) No - While this may provide guidance, this is not ultimately your decision to decide. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.3 Linking Organizational Governance and Project Governance PMI, p545 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 6. Project Initiation and Execution / 6.3 Legal Considerations and Execution | 43933.9653 | N | 4 | [5 empty] | NA | NA
16 | SINGLE | A project manager has multiple projects. One project has new team members and is in its early stages. Unfortunately, the project manager will be very busy executing other projects over the next few weeks. How can the project manager develop the new project team over the next few weeks? | 4 | Help the team create a social contract that will encourage team cohesion. | Suggest that the team engage in multiple team-building events to normalize the team. | Keep the team informed by sending short daily project status updates. | Engage in face-to-face personal conversations with each team member to build relationships. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) Yes - This will allow the team to normalize themselves and be self-servicing when you are unavailable. B) No - This may be productive, but it is a one-time activity and does not encourage self-servicing when you are unavailable. C) No - This does not encourage the team to get to know each other and become self-servicing. D) No - While this may result in deeper relationships, there is not enough time for this and it does not encourage the team to get to know each other. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 1.5 The Project Lifecycle, pp 547-548 | 43933.9653 | N | 4 | [5 empty] | NA | NA
17 | SINGLE | A project manager needs to ensure that the team delivers business value within the required timelines. The manager recently learned that key stakeholders are worried that the current release plan will not meet urgent business needs. What can the project manager do to effectively respond to the stakeholder concerns? | 4 | Renegotiate scope with the project sponsor after examining the work breakdown structure (WBS). | In consultation with the stakeholders and team members, identify the minimum viable product needed for launch. | Determine the schedule performance index (SPI), then escalate the schedule risk to the project sponsor. | Monitor progress using a burndown chart after modifying the schedule baseline to meet stakeholder requirements. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Medium | Predictive Approach | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Essential Scrum: A Practical Guide to the Most Popular Agile Process (No Date) Kenneth S. Rubin, Chapter 17 Envisioning (Product Planning) / Product Roadmap Definition ¦ The Agile Practice Guide (2017), 3. Life Cycle Section / 3.1.3 Characteristics of Incremental Life Cycles,p23 | 43933.9653 | N | 4 | [5 empty] | NA | NA
18 | SINGLE | A key stakeholder voices a concern during the planning stage about whether the available resources are sufficient to meet the objectives of the project. The project manager believes that the stakeholder is right. How should the project manager handle this stakeholder's concern? | 4 | Review the bounds of the negotiations for agreement. | Determine the project's ultimate objectives after carefully evaluating project priorities. | Engage in agreement negotiations for better resources. | Ensure that the impact of the unavailability of required resources is fully documented. |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Medium | Predictive Approach | Acquire and manage project resources by following the human resource and procurement management plans in order to meet project requirements. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.3 Acquire Resources, p330 | 43933.9653 | N | 4 | [5 empty] | NA | NA
19 | SINGLE | A project manager notices that one team member seems increasingly unhappy during team meetings. The team member is not making progress on a key work package, and this lack of progress is now impacting the critical path. The team member feels that they are not in the correct role within the project team. What should the project manager do? | 4 | Reassure the team member about their abilities by reminding them that they were chosen for a reason. | Meet with the team member to discuss where they can contribute, based on their strengths. | Enroll the team member in targeted training to acquire the needed skills for their assigned role. | Schedule weekly touchpoints with the team member to discuss barriers that may impact their work. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is positive reinforcement, but it may be unwarranted. B) Yes - This is the best response. The individual may truly be right. As a Servant Leader, you can help them find the correct role. C) No - This is helpful, but it doesn't address the core of their concern. D) No - This creates a false sense of momentum that doesn't address the core of their concern. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management 1. Introduction 1.7 Role of the Project Manager, p552 ¦ The Agile Practice Guide (2017), 4. Implementing Agile: Creating An Agile Environment / 4.2.1 Servant Leader Responsibilities 34 | 43933.9653 | N | 4 | [5 empty] | NA | NA
20 | SINGLE | A project owner repeatedly complains, saying that a function developed by the development team does not seem to align with the original design. What will help to solve this issue? | 4 | Ask the product owner to sit in on the next iteration review meeting to learn more about the development status for the product. | Ask the quality assurance team to identify any mismatches in functionality compared to the initial design. | Ask the development team to rewrite the function so that it matches with the project scope. | Schedule time during the next retrospective session to discuss all corrective actions and ask the project owner to participate in the session. |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Agile Hybrid | Retrospective can discuss the product release status, whether the team reaches any other milestone. It can be used by project manage to survey all necessary parties to reach consensus and build understanding PMBOK® Guide Sixth Edition (2018), 8 Project Quality Management / 8.3.2.6 Meetings, p305 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 43933.9653 | N | 4 | [5 empty] | NA | NA
21 | SINGLE | A customer indicates that they would like to add functionality. Although this request is made during the execution phase of the project, the project manager finds that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | 4 | Agree that the functionality would offer a great opportunity, but the proposed addition is out of scope. | Schedule a meeting with the company's management team, and present the customer's request for additional functionality as a good opportunity. | Move forward, using the project's management reserve to add the requested functionality. | Identify an already-developed feature that could be combined with the new functionality and use the combination to meet the customer's request. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | By building a small increment and then testing and reviewing it, the team can add value in terms of new functionalities or additional awarded projects. Important factor for a successful implementation and value capture is the response time of the team PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.4.1 Project and Development Life Cycles, p19 | 43933.9653 | N | 4 | [5 empty] | NA | NA
22 | SINGLE | A customer requests a change in the technical approach for a product currently in development. The project manager learns about this request during a reoccurring project review. What should the project manager do in response to the customer's request? | 4 | Work with team members to immediately implement the new approach. | Have the team decide on the appropriate approach, giving them authority to implement their decision and validating their decision in talks with stakeholders. | Discuss the pros and cons of the proposed approach with stakeholders, then select the approach that is best for the team and notify team members. | In order to obtain sponsor buy-in, have the team to benchmark the approach. |  |  | 2 | 1 | PMP | People | Project Integration Management |  |  | Medium | Agile Hybrid | As a technical issue the project management should address the team to assess and select the best options to solve, empower then and improving engagement. The Agile Practice Guide (2017), 2 An Introduction To Agile / Figure 2-2 The Twelve Principles Behind the Agile Manifesto, p9 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 43933.9653 | N | 4 | [5 empty] | NA | NA
23 | SINGLE | A project manager realizes during the third iteration of product development that the template used for the project management plan is not showing updates. Which action should the project manager take? | 4 | Assign one team member to update the project management plan template and document any risk. | Rank the need to update the template according to the business value for the upcoming iterations. | Avoid adding to team distraction by fixing the issue independently. | Document the issue as a new project risk and propose a solution. |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  | Complex | Agile Hybrid | In a hybrid approach a project manager should work to protect the team against impediment around the product building. This question addresses administrative work that doesn't require technical knowledge. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, p33 | 43933.9653 | N | 4 | [5 empty] | NA | NA
24 | SINGLE | During a challenging shareholder meeting, the customer indicates that they will reject an iteration's deliverable. What should the project manager do? | 4 | Send a request to the project sponsor, asking them to update the project charter then reassign the responsibilities and authorities. | Meet with the project team to add new and improved features to replace the features that were rejected. | Work with stakeholders to create a shared approach that will address the issues of concern. | File a change request with the change control board (CCB) in order to add budget to the baseline. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Agile Hybrid | Before initiate any action the project manager should work with the team to identify the root cause of the problem and build an approach to conduct the project for the next iterations. As a hybrid approach a retrospective ceremonial can be a good option to solve this situation. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 5. Monitoring and Controlling Process Group / 5.1 Monitoring and Controlling Project Work, p 615 | 43933.9653 | N | 4 | [5 empty] | NA | NA
25 | SINGLE | During work on a government project, stakeholders pressure the project manager to submit to their preferred actions. While the project manager must coordinate and plan with multiple stakeholders, the project manager must also deal with complex relations and frequently changing scenarios. What should the project manager consider doing? | 4 | Use the Salience model of categorization. | Use the Transformation model of categorization. | Use the Transaction model of categorization. | Use the Collaboration method of categorization. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | Salience model needs to be used to categorize for government contracts especially when the scenario is for frequently changing, complex relationships with multiple representatives involved PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 Data Representation, p513 | 43933.9653 | N | 4 | [5 empty] | NA | NA
26 | SINGLE | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | 4 | Assess the new resource’s ability to perform the necessary work by testing their communication skills with the current project team. | Evaluate the skills of the new resource to see how the resource can provide value to the project. | File a request with the project management office (PMO) manager in order to obtain a better resource. | Address the rumor with the new resource’s functional manager to mitigate any conflict within the project team. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.3.2.1 Decision Making, p332 | 43933.9653 | N | 4 | [5 empty] | NA | NA
27 | SINGLE | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | 4 | Plan a database development specification, then regularly check to ensure the developer aligns with the specification. | Arrange for review of the data security status on a quarterly basis, and recommend remedial steps if noncompliance is found. | Tell the database developer to submit documentation of data security items and the steps they take to correct items that do not meet specifications. | Add a quality assurance specialist resource to the project team, who will be responsible for monitoring the data security quality of the project. |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The project review is the best opportunity to formally review compliance. These reviews should be scheduled quarterly or at significant milestones PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / Tailoring Considerations, p276 ¦ PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.1.6 Enterprise Environmental Factors, p301 | 43933.9653 | N | 4 | [5 empty] | NA | NA
28 | SINGLE | Several successor activities are behind schedule because a project team member has not been at work for the past week. This impacts the critical path. How should the project manager respond to this problem? | 4 | Obtain a new resource to complete the needed tasks, resulting in less impact on the critical path. | Discuss the situation with the team member, and work with them to identify a practical solution. | Remind the team member that they needed to complete the work package in the agreed-upon timeframe. | Ask the functional manager for assistance communicating with the absent team member. |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.2 Manage Communication / 10.2.2.6 Interpersonal and Team Skills, p386 ¦ PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills / Conflict Management, p348 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.2.1 Servant Leader Responsibilities, p34 | 43933.9653 | N | 4 | [5 empty] | NA | NA
29 | SINGLE | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | 4 | Contract with a third-party company that specializes in helping businesses define scope of work on large projects. | Work with project stakeholders to recommend an iterative approach that will then help to define the project's scope. | Construct a project management plan that provides extra time within the schedule, then seek to revise the scope of work. | Suspend final delivery dates for the project in order to have time to revise the schedule once there is clarity on the scope of work |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Although most of the distractors are not bad ideas for the project manager, the key is the first correct action the they must perform. Introducing adaptive steps in a heavily predictive environment is never easy and also, the stakeholders will be the ones heavily involved in the 3 weeks interaction phase. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3 Manage Stakeholder Engagement, p524 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.6 Planning for Iteration-Base Agile, p55 | 43933.9653 | N | 4 | [5 empty] | NA | NA
30 | SINGLE | After six iterations, significant variations have occurred to project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager wants to suggest a new approach to the next iteration to avoid possible delays. What should the project manager do first? | 4 | Rank the importance of each improvement item, then implement actions identified during the last retrospective. | Engage in a cost-benefit analysis that can help predict the profits that could be realized through the use of new technology for the next phase. | Research new technology trends and management tools that have been successful on similar projects. | Use a backlog refinement meeting and include the customer's change requests in the discussion. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | The retrospective is used to review lessons learned and suggest corrective actions for the next iterations. Essential Scrum: A Practical Guide to the Most Popular Agile Process (2012), Chapter 22. Sprint Retrospective / Overview ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering In An Agile Environment / 5.2.1. Retrospectives, pp 50-51 | 43933.9653 | N | 4 | [5 empty] | NA | NA
31 | SINGLE | All team members on a new project want to gain the customer's trust by delivering value as quickly as possible. The project manager learns that one resource has worked with the sponsor on other projects. The resource seems to be using personal influence, working with a project sponsor to increase the project's benefits realization. At which stage in the project should the project manager address this concern to optimize cost effectiveness? | 4 | At the start of the team's performing stage | Immediately after the first benefit realization | During the next retrospective ceremony | During the next resource performance review |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Medium | Agile Hybrid | The retrospective would be the event to address this concern. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2. Control Quality: Tools and Technics / 8.3.2.6 Meetings, p305 ¦ PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.4.2.6 Meetings, p535 | 41390.1774 | N | 4 | [5 empty] | NA | NA
32 | SINGLE | A project team learns that there is a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after project charter is completed and the project sponsor has signed. How should the project manager proceed? | 4 | Research the requirement and possible consequences, then give the sponsor a recommendation. | Address the requirement through the creation of a quality management plan. | Decline to address the issue, as the new requirement is not part of the project's documented scope. | Ensure that the requirement is documented in the risk register, then ask for further guidance from all stakeholders. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | The context of this scenario demands the Project Manager to influence the organization (sponsor) and recommend next steps after reviewing and understanding compliance requirements and consequences. PMBOK® Guide Sixth Edition (2018),4. Project Integration Management / 4.1.1.3 Enterprise Environmental Factors p78 | 41390.1774 | N | 4 | [5 empty] | NA | NA
33 | SINGLE | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has not yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | 4 | The functionality was formally approved, so initiate the change management process. | Schedule a meeting to discuss and brainstorm the functionality with the project team and business representative. | Ensure that the issue is addressed by escalating it to the project sponsor, who should discuss it with the representative. | Continue with the current sprint, recognizing that the issue will be identified during the testing phase. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | As the functionality has not been built the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, this way avoiding re-work. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project Manager / 3.4.4 Leadership Skills ¦ The Agile Practice Guide (2017) 3 Life Cycle Selection / 3.1.10 - Hybrid life cycles as Fit-For-Purpose, p29 | 41390.1774 | N | 4 | [5 empty] | NA | NA
34 | SINGLE | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is not completing the planned story points, and the change control board (CCB) is becoming passive. The project manager is concerned and wants to improve productivity. What should the project manager do? | 4 | Provide team training, so the team can do a better job of estimating story points. | Speed up the project by reducing the backlog. | Gain the needed time for story point completion by adding more iterations to the project. | Use burndown charts to evaluate team performance. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Training should add more skills and abilities for the team, as a long-term solution PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management /9.4.3.1 Team Performance Assessments, p343 | 41390.1774 | N | 4 | [5 empty] | NA | NA
35 | SINGLE | During one daily standup meeting, team members indicate that they are having to engage in rework because there seems to be too much up-front work. How should the project manager respond to this concern? | 4 | Try using a Kanban board for reviews. | Request that team members implement shorter iterations. | Request that the project owner maximizes the product value. | Engage in a process to manage a reduction in the product backlog. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | Shorter iterations allow for managing functionalities more closely. Should the team keep working on a minimum Viable Product. The Agile Practice Guide (2017), Implementing Agile: Delivering In An Agile Environment / 5.3 Troubleshooting Agile Project Challenges / Table 5-1, p59 | 41390.1774 | N | 4 | [5 empty] | NA | NA
36 | SINGLE | A project manager from a traditional project management organization is assigned to an ongoing project. Recently, the organization has started to use agile methodologies in its projects. The project manager hears that some team members feel like key subject matter expertise is missing and there is insufficient collaboration within the team. How should the project manager respond to these team members' concerns? | 4 | Employ third-party specialists to fill the knowledge gap. | Add additional resources via a request to the sponsor. | Add cross-functional internal resources. | Where possible, reduce the sprint backlog. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Agile Hybrid | Being an organization that is moving from Predictive to Agile Project Management, it is necessary to include Agile methodologies. The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.2 Agile Teams, pp 40-41 | 41390.1774 | N | 4 | [5 empty] | NA | NA
37 | SINGLE | A contractor has sent an email request for urgent payment of their last installment on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | 4 | Negotiate payment terms through a meeting with procurement and the contractor. | Authorize the payment by notifying accounts payable and follow up to ensure it was made. | Act according to the agreed upon commitments in the procurement management plan. | Authorize payment only after reviewing forecast spend versus actual spend to see if the actual status allows it. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Even an inexperienced project manager should understand that terms and conditions should be agreed before engaging a contractor to actually do project work. The procurement plan holds all data re contracts and is the single source to guide payment activities PMBOK® Guide Sixth Edition (2018), 4, Project Integration Management / 4.7.1 Close Projects or Phase: Inputs, pp124-125 ¦ The Agile Practice Guide (2017), 6 Organizational Considerations For Project Agility / 6.3 Procurement and Contracts p77 | 41390.1774 | N | 4 | [5 empty] | NA | NA
38 | SINGLE | A team member expresses concern about a team behavior issue during a retrospective meeting. The member says that group morale is affected by two team members who continuously criticize the high amount of requirements in each iteration. Match each conflict resolution technique with the project manager's possible resolution for this issue. | 4 | Smooth/accommodate Recognize the team members’ feelings regarding the high level of requirements. | Compromise/reconcile Reconsider the distribution of work among the whole team to ensure that the work is equably distributed. | Force/direct Since all requirements were evaluated and organized by the full team, remind the team that the decisions were theirs. | Collaborate/problem solve Meet with the full team in order to discuss requirement allocation and the planning methodology. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The success of project managers in managing their project teams depends on their ability to resolve conflict. Different project managers may use different conflict resolutions methods and techniques for resolving conflict. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, pp348-349 | 41390.1774 | N | 4 | [5 empty] | NA | NA
39 | SINGLE | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20 month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 12 weeks. What should be the first step in the project manager’s response? | 4 | Meet with key stakeholders to discuss ways to reduce some project requirements. | Add team members to work more quickly just this one time in order to satisfy stakeholder requirements. | Refuse to modify the timeline, explaining that scope creep should be discouraged. | Identify agreed-upon tasks in the original project and assign additional duties as needed to meet the new, shorter timeline. |  |  | 1 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Consistent with executing the project with urgency, working with stakeholders to reduce requirements is the best option listed to reduce delivery time. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / Trends and Emerging Practices in Project Schedule Management, p177 | 41390.1774 | N | 4 | [5 empty] | NA | NA
40 | SINGLE | During an iteration, a project team encounters problems that may cause a delay in task completion. Another team within the same project needs the task to be completed on time in order to meet their schedule. What can the project manager do to resolve this problem? | 4 | Insist that the project team work a bit harder to complete on time, in order to avoid delaying the work of other teams. | Work with the product owner to reprioritize the iteration backlog, so that it does not delay work by other teams. | Increase the iteration length, and add additional resources to the project team, so that they can meet the appropriate deadlines. | am members to perform to the best of their abilities during the iteration, and engage in a retrospective after completion of the iteration. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Agile Hybrid | May cause a delay does not mean the task completion will be delayed, To improve probability of success, reprioritizing the backlog may improve the probability for success more than the other options. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, pp 222-224 ¦ The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.3 Backlog Refinement, p52 | 41390.1774 | N | 4 | [5 empty] | NA | NA
41 | SINGLE | Certain key stakeholders are dissatisfied with how a key feature of a project has been developed. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | 4 | Gather the project team for a brainstorming session and identify a solution. | Identify the reasons why there are issues with the feature, then address the issue. | Create a list of the pros and cons of the situation to define the impact of the conflict. | Add a neutral party, such as the project sponsor, to function as a negotiator with stakeholders. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Identifying the source of conflict is a key initial step in conflict management. PMBOK® Guide Sixth Edition (2018), 9. Project Resource management / 9.5.2 Manage Team Tools and Techniques, p348 | 41390.1774 | N | 4 | [5 empty] | NA | NA
42 | SINGLE | During a technical project, a key project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | 4 | Notify the project sponsor regarding the team’s disapproval and brainstorm a response. | Employ coaching tools and techniques to increase team motivation. | Add a resource with the same skills to replace the key team member. | Notify the change control board (CCB) and discuss possible ways to resolve the issue. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5 Manage Team, p345 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 41390.1774 | N | 4 | [5 empty] | NA | NA
43 | SINGLE | A key team member is unhappy with the overall approach documented in a project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting during the execution phase of the project. How should the project manager address the team member’s concerns? | 4 | Continue with the meeting, and ensure that the concerns are added to the risk register after the meeting is finished. | Continue with the scheduled agenda items after reminding the team member of expected meeting etiquette. Then, solicit feedback about the etiquette expectations. | Remember that a project should not go forward when key team members are in disagreement and use the meeting to discuss the member’s concerns. | Make a short comment to acknowledge the team member’s concerns, continue with the meeting, and meet with the member in private to discuss their concerns. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Conflict should be addressed in private, first, to better understand the concern being raised. Exploring the concern after the meeting gives the PM an opportunity to verify the concern and determine needed next steps without disrupting the meeting with all meeting attendees. PMBOK® Guide Sixth Edition (2018) //9 Project Resource Management / 9.5.2 Manage Team: Tools and Techniques, p348 | 41390.1774 | N | 4 | [5 empty] | NA | NA
44 | SINGLE | A project manager is faced with an updated schedule that requires delivering a business result under a far more aggressive timeline. The project’s technical resource manager has worked with the project manager on previous projects. Still, a team member indicates that the company does not have technical resources that could be added to the project to meet the new timeline. What should be the project manager's next step? | 4 | Let the project sponsor know that an issue with a technical resource may put the project at risk. | Ensure that upper management is aware of the lack of needed resources which may put the project at risk. | Ask the technical resource manager about the availability of technical resources | Work with a third-party vendor to quickly acquire the needed resource. |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) 10. Project Communication Management / 10.2 Manage Communication, p381 ¦ The Agile Practice Guide (2017), 2 An Introduction To Agile / 2.2 The Agile Manifest and Mindset, p8 | 41390.1774 | N | 4 | [5 empty] | NA | NA
45 | SINGLE | A project manager has been asked to conduct a risk analysis that is based on a high-level scope. As part of the analysis, the project manager must use expert judgment to prepare a document. Which document-based action is being performed? | 4 | Creating the project charter | Preparing the scope statement document | Creating a project management plan | Documenting the risk management plan |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | Expert judgment is one of the tools and techniques for developing the project charter. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management 4.2.1 Develop Project Charter, p79 | 41390.1774 | N | 4 | [5 empty] | NA | NA
46 | SINGLE | An agile approach meets the needs of the next phase in a team’s project. As the team discusses the phase it becomes clear that some team members have not received appropriate training in the agile model. How should the project manager respond to this issue? | 4 | File a change request that includes the agile training that members lack. | Use available funds in the contingency reserve to guarantee training all team members. | Train key team members on main agile topics by hosting virtual training sessions. | Identify the most cost-effective agile training for the team members. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | If project team members training results in added skills that could be useful for future phases or future projects, schedule training lessons and related costs could be evaluated to be included in resource management plan and cost management plan. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.6 Training, p342 ¦ The Agile Practice Guide (2017), 3 Life Cycle Selection / 3.3 Project Factors That Influence Tailoring p32 | 41540.5179 | N | 4 | [5 empty] | NA | NA
47 | SINGLE | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How could the project manager avoid this type of situation in the future? | 4 | Create training sessions at the start of the project, so all necessary skills are learned. | List required skills for the project, and organize the project team based on those skills. | Consult with the project sponsor to add training once the lack of a specific skill becomes apparent. | Empower team members to problem solve where skills may be lacking, using the skills they do have. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.3 Develop Team: Outputs, p343 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating An Agile Environment / 4.3.3 Generalizing Specialists, p42 | 41540.5203 | N | 4 | [5 empty] | NA | NA
48 | SINGLE | A projects’ daily standups are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | 4 | Invite department managers to participate in the team members’ discussions, in order to identify solutions in a business-like manner. | Request shorter discussion time during each standup, leaving more time for working. | Insert a new team member who will manage obstacles and meetings to discuss possible solutions. | Notify team members that they will be required to shorten all standup meetings and improve their method for identifying solutions. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | Most of project manager think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.4 Daily Standups, p53 | 41390.1774 | N | 4 | [5 empty] | NA | NA
49 | SINGLE | A new resource is assigned to fill in for a resource who is leaving. The new resource will be working on a small project that is critical to a larger program milestone. Unfortunately, there is a rumor that the new resource may be a problem, due to a lack of skills. How should the program manager respond to this rumor? | 4 | Assess the new resource’s communication skills to evaluate their ability to perform acceptably as part of the project team. | Meet with the new resource to discuss their skills and then determine how they can contribute to the project. | Privately ask the program management officer (PMO) to assign a different resource with better skills. | Meet with the functional manager of the new resource to discuss the rumor and see if it is true. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | A) No - This is not the best use of time, and unfairly makes presumptions on the candidate. B) Yes - This is the best answer. Without seeing performance first-hand, there is no available proof to the hearsay. C) No - This assumes that hearsay is fact, which may create a strained relationship between the Project Manager and functional manager. D) No - While this may give solace to the Project Manager, this is inappropriate and unwarranted. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team pp336-338 | 41390.1774 | N | 4 | [5 empty] | NA | NA
50 | SINGLE | A team member could not be reached by email or phone during the week that they were absent. The team member had not notified anyone on the team prior to their absence. Due to the absence, several successor activities are behind schedule, impacting the project’s critical path. How should the project manager respond to this situation? | 4 | Add a new resource who can complete the work package in a professional manner. | Discuss the situation with the team member, and work with them to identify a workable solution. | Require that the team member complete the work package more quickly when they return. | Ask the functional manager for additional support on the project, including assignment of a new resource. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Agile Hybrid | Key Rationale A) No - This is premature and will most likely take longer than attempting to rectify the situation. B) Yes - A Project Manager also has the ability to be a coach. Servant Leadership encourages listening and serving, and therefore it may be possible to compromise with the team member. C) No - This does not address the situation and is in direct contradiction to the coaching role of a Project Manager. D) No - This does not address the situation directly and offsets blame to a third party. PMBOK® Guide Sixth Edition (2018), 10 Project Communications Management, p363 ¦ The Agile Practice Guide (2017), Implementing Agile: Creating An Agile Environment / 4.2 Servant Leadership Empowers The Team, pp33-34 | 41390.1774 | N | 4 | [5 empty] | NA | NA
51 | SINGLE | A project that should have been 90 percent complete by now is only 65 percent complete. The total project budget is US$120,000 and the actual cost of work performed (ACWP) is US$80,000. What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 4 | The SPI is 0.72, and the CPI is 0.98. | The SPI is 1.38, and the CPI is 1.2. | The SPI is 0.94, and the CPI is 1.04. | The SPI is 0.80, and the CPI is 0.91. |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  | Simple | Predictive Approach | EV = %compl * budget. 75% * $100,000 = $75,000. AC = $72,000 CPI = EV/AC = 1.04 A CPI over 1 means the project is under budget. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 41390.1774 | N | 4 | [5 empty] | NA | NA
52 | SINGLE | A project has the following characteristics: -US$3 million budget -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about the current status of the project? | 4 | The project is ahead of schedule and under budget. | The project is behind schedule and over budget. | The project is ahead of schedule and over budget. | The project is behind schedule and under budget. |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  | Medium | Predictive Approach | CV = EV - AC; 540-650 = -110 SV = EV - PV; 540-630 = -90. Negative cost variance means over budget Negative schedule variance means behind schedule. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4.2.2 Data Analysis, p262 | 41390.1774 | N | 4 | [5 empty] | NA | NA
53 | SINGLE | A project manager is working with a customer who repeatedly submits new feature requests for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? | 4 | Hold a meeting with the product manager to request that the number of new requests be reduced. | Define project boundaries immediately with the sponsor. | Organize a meeting with the stakeholders to set expectations. | Analyze the scope management plan and iterate it through the scope definition process. |  |  | 4 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | The scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. The key benefit of this document is that it provides guidance and direction on how scope will be managed throughout the project. PMBOK® Guide Sixth Edition (2018), 5. Project Scope management / 5.1.3.1 Scope Management Plan, p137 | 41390.1774 | N | 4 | [5 empty] | NA | NA
54 | SINGLE | A project manager receives the following for a new project: -assumptions -restrictions -preliminary scope After receiving this information, what should the project manager do first? | 4 | Review and understand the business case and project goals. | Put together the project team and assign project tasks. | Build the project schedule and determine the critical path. | Ensure project charter approval is obtained from the sponsor. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The business case and project goals need to be understood first before a charter can be written. Building a team and a schedule come later in the process. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6.1 Project Business Case, p30-32 | 41390.1774 | N | 4 | [5 empty] | NA | NA
55 | SINGLE | A project manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines During planning, what should the project manager do to avoid any scope creep and keep the team focused on delivering a product that meets requirements? | 4 | Put any changes to scope through the formal approval process. | Hold daily stand-ups with all development teams. | Ask that all development team leads prepare detailed requirements. | Disallow stakeholders from directly interacting with the development team leads. |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Simple | Predictive Approach | Scope creep can be avoided by adherence to the agreed upon change management process. Project Manager's Portable Handbook, 3rd Ed (2010), 6 Project / 6.4.2 Getting Started | 41390.1774 | N | 4 | [5 empty] | NA | NA
56 | SINGLE | A project is delayed. To obtain the desired quality level of the deliverables, a change is required. First, the project manager issues a formal change request and communicates the change to all stakeholders. Then, the project manager learns that this communications approach did not meet stakeholders' expectations. What should the project manager do next? | 4 | Refer to the communications management and stakeholder engagement plans. | Provide a change request to include stakeholders' expectations in the project management plan. | Organize a meeting with the project sponsor to better understand stakeholders' expectations. | Review the communications management plan, follow it, and issue a status report. |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  | High Complex | Predictive Approach | The Monitoring of the communications process may result in improved effectiveness of communication through additional and possibly amended communications plans and activities. Such iterations illustrate the continuous nature of the Project Communications Management processes. Issues or key performance indicators, risks, or conﬂicts may trigger an immediate revision. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 41390.1774 | N | 4 | [5 empty] | NA | NA
57 | SINGLE | A project sponsor asks the project manager to change production materials because these materials could cause health problems to consumers. What is an appropriate step for the project manager to take? | 4 | Follow the project change control process to thoroughly investigate the matter. | Immediately implement the change and submit a change request for formal documentation. | End the current work and enact the change control process. | Reject the change because the request is outside of scope. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 41390.1774 | N | 4 | [5 empty] | NA | NA
58 | SINGLE | A project is in the execution phase. Three necessary changes are brought to the attention of the team. The team members all have differing opinions regarding how to implement the changes. What should the project manager do? | 4 | Confirm that all team members and stakeholders understand and follow the change management plan. | Hold a meeting with the board and project sponsor to address the issue. | Organize a meeting with team members to review the issues and request changes where needed. | Ensure all requested changes are applied to the project and communicate directly with all team members. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | The team and project manager must follow the documented and agreed upon change management processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.3.1 Project Management Plan -Additional Components, p88 ¦ PMBOK® Guide Sixth Edition (2018), 3. The Role of The Project Manager / 3.1 Overview, p51 | 41390.1774 | N | 4 | [5 empty] | NA | NA
59 | SINGLE | After a project ends, the project manager and project team members are still being asked to do the following: -Evaluate new requirements -Make minor modifications -Solve technical issues The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | 4 | Complete the handover of the project. | Review the acceptance criteria and get acceptance. | Formally disband the project team and find a new project. | Continue to fulfill the requests as the product is still being developed. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | Project closure and hand-off will ensure knowledge transfer to production and/or operations. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 Close Project or Phase, pp121-123 | 41390.1774 | N | 4 | [5 empty] | NA | NA
60 | SINGLE | The initial draft of a project management plan is completed. The project manager plans to show the draft to stakeholders who are located around the globe for approval. The project manager has limited time to gain approval, and the project management plan is lengthy. The project manager needs to ensure that the review of the plan is completed on time. Which action should the project manager take? | 4 | Send the plan for the stakeholders to review, and then meet with the all of them to discuss it. | Have each stakeholder review the plan individually, adding their comments, and then update the document accordingly. | Ask select stakeholders to review particular sections of the plan based on their areas of expertise. | Organize individual meetings with only the key stakeholders to walk them through the plan. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | By sending the project management plan to the attendees in advance, the PM can insure that the meeting is most productive. PMBOK® Guide Sixth Edition (2018), 3. The Role of the Project manager / 3.4.4.3 Politics, Power, and Getting Things Done, pp62-63 ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2 Project Communications | 41390.1774 | N | 4 | [5 empty] | NA | NA
61 | SINGLE | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realized there are many differing opinions about how to address technical decisions. Team members did not respect each other's ideas, and the environment was becoming counterproductive. However, now the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | 4 | Storming | Forming | Norming | Performing |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Storming often starts where there is a conflict between team members' natural working styles. People may work in different ways for all sorts of reasons but, if differing working styles cause unforeseen problems, they may become frustrated. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p338 | 41390.1774 | N | 4 | [5 empty] | NA | NA
62 | SINGLE | A planned task for a project does not get completed due to an issue that appeared three days ago but did not get resolved. The project manager wants to prevent this type of situation in the future. What should the project manager do? | 4 | During the retrospective, examine the issue. | In the demo, address the issue. | During the next iteration planning meeting, discuss the issue. | In the next daily standup meeting, review the issue. |  |  | 1 | 1 | PMP | People | Project Schedule Management |  |  | Complex | Agile Hybrid | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvements. Retrospectives are a primary tool to manage project knowledge and develop the team through discussions of what is working well and team-based problem solving. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, p224 ¦ Agile Practice Guide (2017), 5 Implementing Agile: Delivering In An Agile Environment / 5.2.1 Retrospectives, pp50-51 | 41390.1774 | N | 4 | [5 empty] | NA | NA
63 | SINGLE | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 1 5 B 4 4 C 2 5 D 2 2 Based on the table, in what order should the project manager rank these risks for management purposes? | 4 | B, A, D, C | B, C, A, D | B, A, C, D | C, D, A, B |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | Risk severity is the product of probability and impact; the higher the product, the higher the risk is rated. PMBOK® Guide, Figure 11-5 Example Probability and Impact Matrix with Scoring Scheme A=0.08, B=0.28, C-0.24, D= 0.03, "BCAD" Project Manager's Handbook, Risk Ranking by Intersection, A=5, B=7, C=6, D=3 "BCAD" PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.9/ ¦ Project Manager's Portable Handbook, 3rd Ed (2010), Section 7, Project Planning and Control / 7.5.5 Risk Quantification, Figure 7.8 Risk ranking by intersection | 41390.1774 | N | 4 | [5 empty] | NA | NA
64 | SINGLE | A project manager needs to successfully lead a project that has diverse, globally dispersed team members. What should the project manager do to develop cultural sensitivity? | 4 | Be aware of local customs, remain flexible when working with team members, and recognize that culture is learned. | Seek help from the human resource department to obtain formal training in this area. | Travel to each team member's geographic location to gain awareness of their culture and meet face-to-face. | Explore each team member's culture in-depth for several weeks to be sensitive to their needs. |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | The project manager needs to be proactive and learn what he can while also maintaining flexibility. Project Manager's Portable Handbook, 3rd Ed (2010), Section 9. Project Communications / 9.2.4 Role of Informal Communications | 41390.1774 | N | 4 | [5 empty] | NA | NA
65 | SINGLE | On a project, three critical risks with a high-impact are identified. The project manager must find a solution to address these risks immediately. Three specific resources are required to address the risks; however, they are already committed to another project with critical deliverables. Which action should the project manager take? | 4 | Option A 1. Check with the functional manager regarding the resources' availability 2. Negotiate task crashing or rescheduling with the functional manager. | Option B 1. Hire outside resources. 2. Assign these resources to handle the tasks. | Option C 1. Assume the risks. 2. Control these risks often to reduce potential impact. | Option D 1. Generate a contingency reserve to solve the potential schedule delay. 2. Mitigate the possible impact. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The functional manager is the person who will be able to reschedule, reassign or replace resources. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6.2.3 Interpersonal and Team Skills, p357 | 41390.1774 | N | 4 | [5 empty] | NA | NA
66 | SINGLE | Schedule performance issues are occurring on a project. After assessing the issue, the project manager determines that the cause is the expertise levels of project resources. Specifically, a few of the senior-level resources check irrelevant details, and some inexperienced resources take too much time to complete tasks. The project manager needs to enhance team performance. Which action is appropriate to take? | 4 | Implement training where necessary and create a checklist for all team members. | Request that the senior-level resources help the inexperienced resources. | Advise the senior-level resources and replace the junior-level resources. | Design and conduct training for the junior-level staff. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The PM must train the junior members and supply a checklist so that all are checking all and only what they are supposed to be checking. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4 Develop Team, p342 | 41390.1774 | N | 4 | [5 empty] | NA | NA
67 | SINGLE | Multiple new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do not have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | 4 | Ask the original team members to provide support and training, and schedule a second kick-off meeting for new team members. | Assure all new team members that they should feel comfortable asking for help from both the long-term members and project manager. | Revise the team, so that the newer resources are moved to other projects and resources with relevant experience are added, then log lessons learned. | Recognize that this is a common occurrence when teams experience change, and revise the schedule to allow for the slight decrease in productivity. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.4.2.4 Interpersonal and Team Skills, p341 | 41390.1774 | N | 4 | [5 empty] | NA | NA
68 | SINGLE | A project’s single sponsor has been replaced by a steering committee due to a significant increase in project size. How should the project manager approach this change? | 4 | Tailor communications to the new steering committee, recognizing that there has been a change in stakeholder structure. | Follow the initial project plan, recognizing that the stakeholder group now includes the steering committee members. | Schedule a low-key introductory meeting with the new steering committee and the team, while continuing to follow the initial project plan. | Ensure that the new steering committee members receive the project’s current status report. |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  | Medium | Predictive Approach | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / 10.1.2.2 Communications Requirements Analysis, p369-370 | 41390.1774 | N | 4 | [5 empty] | NA | NA
69 | SINGLE | Prior to preparing a monthly project status report, a project manager identifies three new risks. All of these risks could impact critical key milestones. The project manager wants to reference additional information before presenting this new risk information. To which sources should the project manager refer? | 4 | Risk register and risk report | Risk register and organizational process assets | Risk management plan and risk report | Lessons learned repository and risk report |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Medium | Predictive Approach | The project manager must check the risk register and risk report to see if this is indeed a new risk and to see if there was action already planned around it. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, pp409-411 | 41390.1774 | N | 4 | [5 empty] | NA | NA
70 | SINGLE | A week prior to the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of how complex the project deliverables are. The resource expresses concern and worry regarding the deliverables. What should the project manager do to ensure that the deliverables are realistic? | 4 | Perform a feasibility study, and then assess the results. | Discuss the resource's concerns with the sponsor, and modify the project charter. | Note the concerns in the issue log to review at a later date. | Identify threats and preventive actions by conducting a risk assessment. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | To ensure that the deliverable are realistic, the project manager needs to conduct a feasibility study and then evaluate the results. none of the other choices will ensure this. PMBOK® Guide Sixth Edition (2018), 1. Introduction / 1.2.6 Project Management Business Documents, p29 | 41390.1774 | N | 4 | [5 empty] | NA | NA
71 | SINGLE | During user testing a client agreed to a final product. A few days later the client is reconsidering their agreement What should the project manager do? | 4 | Review the project’s acceptance criteria. | Refer to the project’s quality management plan. | Review the requirements documentation. | Refer to the project's project charter. |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | The deﬁnition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 41390.1774 | N | 4 | [5 empty] | NA | NA
72 | SINGLE | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project’s success. What should the project manager do first? | 4 | Engage in identification of project risks, then assess those risks. | Ask the project sponsor for additional funding to cover project planning. | Schedule a meeting with the functional manager to address the potential impact of unplanned risks. | Execute the project as planned, recognizing that additional project funds must be requested at a later point in the project. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.1.2.1 Expert Judgement, p 404 | 41390.1774 | N | 4 | [5 empty] | NA | NA
73 | SINGLE | A large project includes functional groups in four countries. It is close to completion, so the project manager must prepare the closeout documents. How should the project manager obtain appropriate signoff on the acceptance of project deliverables? | 4 | The project sponsor should be asked to sign off. | The steering committee should be asked to sign off. | The director of the project manager’s business unit should be asked to sign off. | The four managers from the four countries should be asked to sign off. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.1.4 Accepted Deliverables, p125 | 41390.1774 | N | 4 | [5 empty] | NA | NA
74 | SINGLE | A project has the following characteristics: -A quality management plan is in place. -The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. -Four deliverables have missed this quality requirement. What is an appropriate step for the project manager to take? | 4 | Use a cause-and-effect diagram for root cause analysis. | Modify the quality management plan to conform to project practices. | Request that the project to undergo an internal audit. | Reach out to the project sponsor for their input. |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | By understanding the root cause of the issue, the project manager may avoid this type of problem later on in this and other projects. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.3 Decision Making, p293 | 41390.1774 | N | 4 | [5 empty] | NA | NA
75 | SINGLE | A company wants to reduce costs by installing solar panels. Their local government provides subsidies for specific energy-efficient projects. After project start, the program manager learns that solar panels may not qualify for the energy-efficiency subsidy. How should the program manger address this issue? | 4 | Increase the risk level for the project. | Ensure the issue log is updated. | Make use of the contingency reserve. | File a change request. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018), 11. Project risk management / Key Concepts For Project Risk Management, pp397-398 | 41390.1774 | N | 4 | [5 empty] | NA | NA
76 | SINGLE | Three parts of a single project are being completed by three project teams. The three parts are highly dependent on each other. The team leader worries that this might create conflicts when the outputs from the three teams are combined and asks for advice. What advice should the project manager provide? | 4 | Identify potential conflicts, and then arrange for a weekly joint meeting with the members of the three teams to monitor each other’s work. | Decide which team’s work should be prioritized, then delay the work from the other two teams to ensure there are no conflicts. | Document conflicts as they occur, and take action to remedy any problems that arise. | Continue to let all three teams work simultaneously, recognizing that conflicts can be addressed at the testing phase. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.4.4.2 Qualities and Skills Of A Leader, p61 | 41390.1774 | N | 4 | [5 empty] | NA | NA
77 | SINGLE | In response to slippage on some scheduled tasks, the project manager reprioritized a number of subsequent tasks in order to fix the problem. The reprioritization did not put the project back on track, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, what should the project manager do first? | 4 | Refer to the communications management plan. | Review the stakeholder engagement plan. | Refer to the change management plan. | Review the risk management plan. |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  | Complex | Predictive Approach | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 41390.1774 | N | 4 | [5 empty] | NA | NA
78 | SINGLE | A project is in the execution phase. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | 4 | Control procurement | Statistical sampling | Process audit | Quality assurance |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Simple | Predictive Approach | B Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2 Quality Control: Tools and Technics, pp302-303 | 41390.1774 | N | 4 | [5 empty] | NA | NA
79 | SINGLE | Because a deliverable does not meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable does not meet expectations because there is a problem with vendor-provided parts. The vendor says that they will not correct the problem. Before deciding on next steps, what should the project manager do? | 4 | Check the service level agreement (SLA) established with the vendor. | Review the procurement management plan and contract agreements. | Check the internal quality assurance reports. | Review the resource management plan and document lessons learned. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. Project Manager's Portable Handbook, 3rd Ed (2015), Section 6 Project Initiation and Execution / 6.8 Contract Negotiations and Administration | 41390.1774 | N | 4 | [5 empty] | NA | NA
80 | SINGLE | Several team members have been transferred to another project, so the project manager needs additional resource support from a new supplier. The project manager is concerned about the cost risk of using a new supplier at this stage of the project. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 4 | Recommend a fixed price incentive fee (FPIF) contract. | Recommend a time and material (TM) contract. | Recommend a cost plus incentive fee (CPIF) contract. | Recommend a firm fixed price (FFP) contract. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | Medium | Predictive Approach | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.1.1.6 Organizational Process Assets p472 | 41390.1774 | N | 4 | [5 empty] | NA | NA
81 | SINGLE | A previously identified technical issue has been resolved and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should be done first when responding to this warning? | 4 | Ensure that the issue log is updated. | Create a risk report and keep the report current. | Notify the project sponsor about the warning. . | Ensure that the lessons learned register is updated |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The issue log will help the project manager effectively track and manage issues, ensuring that they are investigated and resolved. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.3 Issue Log, p96 | 41390.1774 | N | 4 | [5 empty] | NA | NA
82 | SINGLE | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 4 | Meet with the team member’s manager, and negotiate for an alternative time to complete the other task. | Ask the team member to focus on the critical task, and obtain an additional resource from another department | Send a report to the project sponsor, documenting noncompliance from the member’s manager. | Tell the team member’s manger to release the team member from outside activities until the scheduled project activity is complete. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 41390.1774 | N | 4 | [5 empty] | NA | NA
83 | SINGLE | The project manager receives a progress report during a demo and review meeting. The report shows that the agile project is not on track. Since all work was purposely selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication in an agile project? | 4 | Support self organization for the project team and help them provide buy-in for the project. | Ensure that there is a contingency reserve to cover these issues. | Ensure that the team is trained to use the agile process reporting system. | Provide early training and ongoing mentoring about the agile approach for the project team. |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Complex | Agile Hybrid | For Agile projects, rather than a project manager selecting and sequencing work, higher-level objectives are explained and the team members are empowered to self-organize specific tasks as a group to best meet those objectives. This leads to the creation of practical plans with high levels of buy-in from the team members. PMBOK® Guide Sixth Edition (2018), Appendix 3 / X3.3.3 Executing Process Group, p670 | 41390.1774 | N | 4 | [5 empty] | NA | NA
84 | SINGLE | As part of effective leadership, project managers help team members grow and keep them motivated throughout each project. What is one step that supports this effective leadership? | 4 | Stand up for the team’s beliefs and be assertive. | Challenge the team by delegating project tasks. | Use daily discussion sessions to solicit and respond to the team’s concerns. | Provide a team reward for each successfully completed task. |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | Medium | Predictive Approach | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018), 3. The Role Of The Project Manager / 3.1 Overview, pp51-52 | 41390.1774 | N | 4 | [5 empty] | NA | NA
85 | SINGLE | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 4 | Meet with the senior project manager to identify established plans and processes. Then, ask for assistance in selecting the appropriate standards. | Schedule a meeting with the customer to collect requirements and obtain benchmarking samples. | Obtain the necessary benchmarking samples and cost-benefit analyses from the sponsor. | Postpone the development of the quality management plan until quality metrics and quality checklists are created. |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.1.3.1 Quality Management Plan, p286 | 41390.1774 | N | 4 | [5 empty] | NA | NA
86 | SINGLE | A small group of users complain during a project’s user acceptance stage. The users say that their expectations are not met. Which action could help avoid this issue on future projects? | 4 | Make use of stakeholder feedback during the project. | Engage in risk assessments throughout the project. | Make use of conflict management techniques. | Create a professional relationship with users. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.3.2.2 Communication Skills, p527 | 41390.1774 | N | 4 | [5 empty] | NA | NA
87 | SINGLE | The project sponsor requires a project team composed of resources that live in four different time zones, working in four different locations. The project sponsor did not consider the implications of this requirement, and believes that the dispersion will provide an ideal project team that will save costs. Where should this be documented in the project charter? | 4 | In the overall project risks | In the key stakeholder list | As part of high-level requirements | As part of the resource management plan |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Having a dispersed project team does not come without risks. These risks need to be identified in the risk for the project. Develop Project Charter: Tools and Techniques, Expert judgement risk identification PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2 Develop Project Charter: Tools and Techniques, p79 | 41390.1774 | N | 4 | [5 empty] | NA | NA
88 | SINGLE | A governmental agency becomes a key stakeholder on a complex project due to regulatory changes. In light of the change, the project manager needs to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 4 | Schedule meetings with the new stakeholders. | Update the assumption log. | Revise the stakeholder engagement plan. | Share the benefits management plan with the new stakeholders. |  |  | 1 | 1 | PMP | Process | Project Stakeholder Management |  |  | Simple | Predictive Approach | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.5 Meetings, p514 | 41390.1774 | N | 4 | [5 empty] | NA | NA
89 | SINGLE | The project requires the development of a human resource system (HRIS) to centrally manage human resources and payroll. The project sponsor is a multinational company. The project manager reviews historical data on the company’s human resources practices and considers the regulatory framework of the project. Still, there are concerns about project risks. What should the project manager do in response to these concerns? | 4 | Recognize high-level project risks. | Calculate and quantify project risks. | Formulate a risk mitigation plan. | Engage in regular risk reviews. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The project manager must first identify the risks before you can quantify them, develop risk mitigation plans or review them. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 41390.1774 | N | 4 | [5 empty] | NA | NA
90 | SINGLE | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is finding it hard to obtain consistent input due to lack of participation. How can the project manager boost stakeholder input? | 4 | Make use of political awareness techniques. | Review risk management tools and techniques. | Engage in effective meeting management techniques. | Use effective facilitation techniques. |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  | Complex | Predictive Approach | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.2.3 Interpersonal and Team Skills, p80 | 42011.3713 | N | 4 | [5 empty] | NA | NA
91 | SINGLE | The project manager reviews the issues log and sees that three tasks assigned to three team members are significantly behind schedule. How should the project manager handle this issue? | 4 | Meet with the relevant team members to review the tasks and determine a strategy for resolving the issue. | Contact the project sponsor and escalate the issue in order to reduce delays. | Ask those who are responsible for the reason for the delays and their plans for next steps. | Inform the team to quickly bring the tasks up to date, so that the project is not at risk. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018), 4. Project Risk Management / 11.2 Identify Risks, pp409-411 | 41390.1774 | N | 4 | [5 empty] | NA | NA
92 | SINGLE | Project team members are spending a lot of time helping maintenance and operations staff with a recently commissioned project component. The project manager needs to validate that the component was signed off and ownership transferred. Which three documents should the project manager use for this decision? | 4 | Final report, organizational process assets updates, and procurement agreements | Procurement agreements, project document updates, and organizational process assets updates | Procurement agreements, stakeholder engagement plan, and organizational process assets updates | Final report, project document updates, and organizational process assets updates |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and that the project has met its objectives. The project documents are updated accordingly. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7.3 Close Project or Phase: Outputs, pp127-128 | 41390.1774 | N | 4 | [5 empty] | NA | NA
93 | SINGLE | A global organization sponsors a project that involves six different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | 4 | Update the stakeholder engagement plan. | Revise the project charter. | Update the stakeholder register. | Revise the project management plan. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Simple | Predictive Approach | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.2.3 Plan Stakeholder Engagement: Outputs, p522 | 41390.1774 | N | 4 | [5 empty] | NA | NA
94 | SINGLE | A new law is expected within the next four-to-five months that will affect the business’ type of products. The next product launch is starting and should be completed within three months. Unfortunately, the new product would not meet the requirements of the proposed law. How should the project manager respond to this potential problem? | 4 | Option A 1. Schedule a meeting with the sponsor and key stakeholders to discuss risks. 2. Using the results of the meeting, revise the assumption log and project charter. | Option B 1. Revise the risk management plan. 2. Move ahead with planning the project. | Option C 1. Move ahead with the project; following the plan. 2. Ensure on-time completion, so that the product will not be affected by any possible rule change. | Option D 1. Schedule a meeting with the sponsor and key stakeholders to warn them about the law. 2. Advise them to cancel the project until the legislation is finalized. |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Predictive Approach | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3 Develop Project Charter: Outputs, p81 | 41390.1774 | N | 4 | [5 empty] | NA | NA
95 | SINGLE | A project manager implemented an approved change to manage a risk. Three months after the implemented change, the project manager learns that the change did not produce the desired result, and there are adverse consequences. What can the project manager do to avoid this problem on future projects? | 4 | Follow up to verify that a risk response is performing as expected. | Revisit or change existing assumptions after reviewing the assumption log. | Update the lessons learned register with the risk information. | Update the probability and impact matrix after assessing any new risks. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), /Risk Process 82/203 | 41390.1774 | N | 4 | [5 empty] | NA | NA
96 | SINGLE | During a conversation with a friend, a project manager hears that a possible union action will occur within the next two weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. How should the project manager respond to this issue? | 4 | Notify relevant stakeholders and add the new risks to the risk register. | Get more information through informal discussions, and use what is found to decide on next steps. | Plan to reward those who do not participate and identify possible disciplinary actions for those who do participate. | Schedule a meeting with the union’s leader in order to resolve any outstanding conflicts. |  |  | 1 | 1 | PMP | Business Environment | Project Risk Management |  |  | Medium | Predictive Approach | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.7 Monitor Risks, p453-454 | 41390.1774 | N | 4 | [5 empty] | NA | NA
97 | SINGLE | A project team has set up an unofficial online communications platform to enhance communication. The project manager was not aware that this platform existed until recently, after learning that it was being used inappropriately. Which action should the project manager take? | 4 | Have the project team stop using the platform, and then review the communications management plan. | Report the issue to the compliance office after disciplining the individuals involved. | Since it is not part of the communications management plan, terminate the platform. | Delegate an administrator to monitor communications on this platform. |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | Since this platform was not part of the original communications plan, it should not be used. The project manager needs to refer the team members back to the approved project communications plan. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 41390.1774 | N | 4 | [5 empty] | NA | NA
98 | SINGLE | A project has the following characteristics: -To determine what product should be created, a feasibility study has been conducted. -A change request has now been approved to develop another product that contradicts the original requirements. -Data analysis was conducted before the change request was approved. Which action should the project manager take? | 4 | Execute the change request. | Decline the change request. | Ask for a detailed report of the data analysis. | Ask for a feasibility study of the new product. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Approved change requests can require new or revised cost estimates, activity sequences, schedule dates, resource requirements, and/or analysis of risk response alternatives. These changes can require adjustments to the project management plan and other project documents. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6.2 Perform Integrated Change Control: Tools and Techniques, pp118-119 | 41390.1774 | N | 4 | [5 empty] | NA | NA
99 | SINGLE | A technology development project has the following characteristics: -It requires a highly skilled resource that is unavailable locally. -The project manager has identified a resource who can work on site, but the resource lives in a different country and requires a work visa. -The work visa process is taking more time than anticipated. What should the project manager do? | 4 | Assign the existing team overtime work. | Have the project's scope reduced. | Delay the project by an equivalent duration. | Request that the resource work remotely. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be deﬁned as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3 Acquire Resources, pp328-330 | 41390.1774 | N | 4 | [5 empty] | NA | NA
100 | SINGLE | A contractor is late with a critical project deliverable due to resource challenges. There is a 22% buffer in the budget for cost overruns. What is the first thing a project manager should to mitigate this issue? | 4 | Look into alternative vendors that can assist with project deliverables despite resource constraints. | Hire a new vendor to replace the current vendor; ask the new vendor to send a contract. | Hold a discussion with the vendor regarding the legal implications of this slippage. | Update the project schedule after first accepting the cost overrun. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | Realizing that project delivery is the prime focus, the project manager needs to assess alternatives without concern for the potential budget impact. Once a viable alternative is identified, they can present their case to the sponsor for a decision. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / Tailoring Considerations, p465 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 26. Human Resource Planning | 41390.1774 | N | 4 | [5 empty] | NA | NA
101 | SINGLE | There is an unresolved conflict between a member of a third-party vendor's team and a member of a project team. The issue is escalated to the project manager. What is the first thing the project manager should do? | 4 | Meet in-person with the vendor to discuss the issue. | Call the vendor on the phone to discuss the issue. | Draft and send a contractual letter to the vendor. | Send an email to the vendor to discuss the issue. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The project manager wants to resolve this issue quickly. A face to face meeting is the best choice to resolve this conflict. Any other communication choice would involve noise that would hinder resolution. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 Interpersonal and Team Skills, p86 ¦ PMBOK® Guide Sixth Edition (2018), Appendix X4 Summary of Key Concepts for Knowledge Areas / X4.10 Key Concepts for Project Stakeholder Management, p678 | 41390.1774 | N | 4 | [5 empty] | NA | NA
102 | SINGLE | A customer's resources have not completed the required training. The project manager has to consider the risk it poses to the timely completion of the project. Customer resource training is a required project deliverable. Which action should the project manager perform? | 4 | Communicate with the project stakeholders to address the risk. | Revise the risk register and discuss it at the next project status meeting. | Dedicate additional post-implementation support to mitigate the risk. | Modify the project schedule to account for the training delay. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Since the customer is a key stakeholder, the project manager should engage with them to address this risk. PMBOK® Guide Sixth Edition (2018), 11 Project Risk management / 11.5.2.9 Decision Making, p446 | 41390.1774 | N | 4 | [5 empty] | NA | NA
103 | SINGLE | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 4 | 20 | 40 | 60 | 30 |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Simple | Predictive Approach | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 41390.1774 | N | 4 | [5 empty] | NA | NA
104 | SINGLE | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 29 days. The second group identifies some risks that could make the duration up to 46 days. The third group proposes a new development method that can shorten the time to 18 days. What is the estimated development duration for the new product? | 4 | 28 | 30 | 32 | 36 |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Simple | Predictive Approach | Using 3 point, PERT, or average delivers an estimate of 40 PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.4.2.4 Three-point Estimating, p201 | 41390.1774 | N | 4 | [5 empty] | NA | NA
105 | SINGLE | A project manager realizes that sponsor expectations are NOT being met, specifically regarding project deliverables. To address this issue, which action should the project manager take? | 4 | Create a risk register. | Develop a stakeholder engagement plan. | Develop a communications management plan. | Create a work breakdown structure (WBS). |  |  | 2 | 1 | PMP | Process | Project Stakeholder Management |  |  | Complex | Predictive Approach | The stakeholder engagement plan is a component of the project management plan that identifies the strategies and actions required to promote productive involvement of stakeholders in decision making and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 41390.1774 | N | 4 | [5 empty] | NA | NA
106 | SINGLE | A customer is contemplating adding new features to the project deliverable. Before a project team member starts working on these new features, what is a mandatory step? | 4 | Gain approval from the project manager. | Ensure the change control board (CCB) approves. | Gain approval from the project sponsor. | Ensure key subject matter experts (SMEs) approve. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | The Change control board is a formally chartered group responsible for reviewing, evaluating, approving, deferring, or rejecting changes to the project and for recording and communicating such decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.1.3/93 | 41390.1774 | N | 4 | [5 empty] | NA | NA
107 | SINGLE | A project is at the multi-functional planning phase. The project manager realizes that producing a complex application is not feasible with the current number of resources and decides to hire more resources for the production of the application. The project manager identifies temporary resources and signs a service level agreement (SLA) with them. Which risk response strategy does this scenario exemplify? | 4 | Mitigate | Transfer | Accept | Avoid |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The risk to the project was posed by insufficient resources. The risk was Avoided by hiring additional resources. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 41390.1774 | N | 4 | [5 empty] | NA | NA
108 | SINGLE | A project manager has completed the following steps: -Finished a major IT deployment project. -Confirmed with the release manager that all systems are working. -Confirmed that functionality has been verified by the quality assurance team. -Informed the customer. What is the next step the project manager should take? | 4 | Add the lessons learned to the organization knowledge base. | Update the risk register, stakeholders, and team members. | Ensure that the procurement plan is closed out. | Review, verify, and complete the release documentation. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | During project close out, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 41390.1774 | N | 4 | [5 empty] | NA | NA
109 | SINGLE | After realizing that there are insufficient resources on a project that has an increasingly high workload, management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | 4 | Review the communications management plan | Revise the procurement management plan | Escalate to the project sponsor | Prepare an organizational chart |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | The Procurement Management Plan is where the process of documenting project procurement decisions, specifying the approach and identifying potential sellers is captured. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 41390.1774 | N | 4 | [5 empty] | NA | NA
110 | SINGLE | A project has the following need: 900 resource hours must be outsourced. Because of internal policies, all providers must comprehend the requirements. Which action should the project manager take to ensure this? | 4 | Hold direct negotiations with each provider. | Conduct a bidder conference with the providers. | Ensure the procurement management plan is sent to each provider. | Have each of the providers added to the stakeholder register. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | A bidder conference is a meeting between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3/487 | 41390.1774 | N | 4 | [5 empty] | NA | NA
111 | SINGLE | A company has a goal of increasing customer satisfaction within 4 months. A project is initiated to meet this goal. The project manager needs to identify best practices. What should the project manager utilize to accomplish this? | 4 | Benchmarking | Focus groups | Facilitation | Affinity diagram |  |  | 1 | 1 | PMP | Business Environment | Project Quality Management |  |  | Medium | Predictive Approach | Benchmarking involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 41390.1774 | N | 4 | [5 empty] | NA | NA
112 | SINGLE | A new product is released. When a customer identifies performance issues with this product, the project manager realizes that cost of quality (COQ) should have been used to estimate this cost. Which category of COQ should the project manager have used? | 4 | Prevention costs | External failure costs | Appraisal costs | Cost-benefit analysis |  |  | 2 | 1 | PMP | Business Environment | Project Quality Management |  |  | Complex | Predictive Approach | External Failure Costs are those failures found by the customer. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.3/321 | 41390.1774 | N | 4 | [5 empty] | NA | NA
113 | SINGLE | A project manager is doing the following: -conducting a risk analysis based on a high-level scope, and -using expert judgement to prepare a document. What is the project manager doing, based on the description of the activity? | 4 | Creating a project charter | Preparing a project scope statement | Creating the project management plan | Preparing a risk management plan |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | The other options require a more detailed project scope PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/113 | 41390.1774 | N | 4 | [5 empty] | NA | NA
114 | SINGLE | A project is started based on the approved scope. As the project design is being implemented, a team member says that the product will not meet the requirements in certain situations. Correcting the issue will not only cause an increase in scope and costs, but the project will also miss the deadline. The project sponsors do not have additional funding to support the project. Considering this information, what should the project manager do? | 4 | Conduct a risk analysis and update the project sponsor. | Enact the Perform Integrated Change Control process. | Resolve the issue to satisfy the customer. | Contact the customer and negotiate for risk acceptance. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 41390.1774 | N | 4 | [5 empty] | NA | NA
115 | SINGLE | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager needs to align this stakeholder's expectations. What should the project manager do to accomplish this goal? | 4 | Produce a stakeholder engagement plan. | Convey the stakeholder engagement plan. | Gain consensus on project objectives by meeting with all stakeholders. . | Ensure that the stakeholder register is complete and updated |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2/516 | 41390.1774 | N | 4 | [5 empty] | NA | NA
116 | SINGLE | A medium-sized company is expanding into a new market. However, the company does not have previous experience in that market. A project manager needs to collect requirements. Which tool or technique should the project manager use? | 4 | Prototypes | Expert judgment | Product analysis | Create requirements traceability matrix |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Simple | Predictive Approach | Prototyping is a method of obtaining early feedback on requirements by providing a model of the expected product before actually building it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.8/147 | 41390.1774 | N | 4 | [5 empty] | NA | NA
117 | SINGLE | A project manager has local and virtual team members for a project. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which statement is true about this scenario? | 4 | It demonstrates the Smooth/Accommodate conflict resolution technique. | It is an example of the Collaborate/Problem Solve conflict resolution technique. | It demonstrates the Force/Direct conflict resolution technique. | It is an example of the Compromise/Reconcile conflict resolution technique. |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Collaborate/problem solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5.2.1/349 | 41390.1774 | N | 4 | [5 empty] | NA | NA
118 | SINGLE | A high-level manager in an organization would like to use a critical project resource for a new project. Which action should the project manager take? | 4 | Contact the program manager to resolve the issue. | Request that the high-level manager provides a replacement. | Use the Legitimate form of power to deny the request | Tell the team and reassign that resource's responsibilities to other team members. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The project management team’s ability to inﬂuence others plays an important role in negotiating resource allocation, as does the politics of the organizations involved. If getting to an agreement is not possible, the issue needs to be escalated for resolution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.3/52 | 41390.1774 | N | 4 | [5 empty] | NA | NA
119 | SINGLE | What should the project manager do to gain a stakeholder's approval if the stakeholder believes a project's deliverables were not achieved? | 4 | Review the project scope while analyzing the stakeholder's needs and expectations. | Review the project charter thoroughly with this stakeholder on a conference call. | Ensure that the stakeholder understands the quality management plan. | Perform a risk analysis after obtaining the stakeholder's new requirements. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Monitor Stakeholder Engagement is the process of monitoring project stakeholder relationships and tailoring strategies for engaging stakeholders through modification of engagement strategies and plans. The key benefit of this process is that it maintains or increases the efficiency and effectiveness of stakeholder engagement activities as the project evolves and its environment changes. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.4/530 | 41390.1774 | N | 4 | [5 empty] | NA | NA
120 | SINGLE | A client's employee asks the project manager for an additional, new product feature during a status meeting. To what document should the project manager first refer to find out who has the authority to approve this request? | 4 | Change log | Change management plan | Responsible, accountable, consult, and inform (RACI) matrix | Change request document |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The change management plan describes the process for submitting, evaluating and implementing changes to the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1/87 | 41390.1774 | N | 4 | [5 empty] | NA | NA
121 | SINGLE | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is Step 3? | 4 | The project manager should update the bid documents. | The project manager should obtain stakeholder acceptance. | The project manager should reassign the project team. | The project manager should reallocate the unused funds. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | Deliverables that meet the acceptance criteria are formally signed off and approved by the customer or sponsor. Formal documentation received from the customer or sponsor acknowledging formal stakeholder acceptance of the project’s deliverables is forwarded to the Close Project process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.5.3.1/166 | 41390.1774 | N | 4 | [5 empty] | NA | NA
122 | SINGLE | Review the following project characteristics: -The project is in its initiation phase. -Due to lack of funding, the project gets terminated. -The project manager must close the project. What is the first action the project manager should take? | 4 | Rely on the communications management plan to properly inform all stakeholders. | Examine the organization's project closure guidelines. | Determine the potential impact of terminating the project by performing a risk analysis. | Close all project procurement processes. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Project closure guidelines or requirements will contain the organization's procedures to follow. PMBOK® Guide Sixth Edition (2018) PMI/PMI/2.3.1/41 | 41390.1774 | N | 4 | [5 empty] | NA | NA
123 | SINGLE | A project has the following characteristics: -A functional manager is also a project stakeholder. -The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. -The new stakeholder is not attending meetings. The project manager needs to engage this new stakeholder. What should the project manager do? | 4 | Examine the project charter with the new stakeholder and assess their level of engagement. | Present the project schedule and the specific, assigned tasks to the new stakeholder. | Request that the functional manager briefs this new stakeholder and ask that they send them to all relevant meetings. | Ask the new stakeholder to pair with a more experienced stakeholder to learn responsibilities. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | The ﬁrst version of the stakeholder engagement plan is developed after the initial stakeholder community has been identified by the Identify Stakeholder process. The stakeholder engagement plan is updated regularly to reﬂect changes to the stakeholder community. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 41390.1774 | N | 4 | [5 empty] | NA | NA
124 | SINGLE | A project manager is attending a periodic review with stakeholders. The project sponsor asks the project manager how deliverables will be verified for accuracy and accepted. In which project document is this information found? | 4 | Scope management plan | Requirements management plan | Quality management plan | Work performance reports |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The quality management plan identifies the quality requirements and/or standards for the project and its deliverables, and documenting how the project will demonstrate compliance with quality requirements and/ or standards. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.1/324 | 41390.1774 | N | 4 | [5 empty] | NA | NA
125 | SINGLE | A project is being planned in a remote area with limited access to vehicles and equipment. The project manager proposes that the company deliver all heavy equipment themselves despite the significant expense. The project manager will take full responsibility for this activity. What type of risk response is the project manager demonstrating? | 4 | Transfer | Mitigate | Accept | Avoid |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  | Medium | Predictive Approach | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5.2.4/443 | 41390.1774 | N | 4 | [5 empty] | NA | NA
126 | SINGLE | A project manager begins to prepare the project management plan after receiving the project charter. There is currently no historical information in the project management office (PMO). What is the next step the project manager should take in this scenario? | 4 | Utilize analogous estimating. | Seek advice from experts in the field. | Organize an initial kick-off call. | Request that the project sponsor provides input. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | If there is no historical information available, then consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.2.2/281 | 41390.1774 | N | 4 | [5 empty] | NA | NA
127 | SINGLE | A marketing team is developing a new website and has agreed upon a target audience. Now the marketing team needs to identify the target audience's style preferences. What is an appropriate tool or technique to use for this situation? | 4 | Focus groups | Brainstorming | Product analysis | Benchmarking |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | Focus groups bring together prequalified stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.2.2.2/180 | 41390.1774 | N | 4 | [5 empty] | NA | NA
128 | SINGLE | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | 4 | Verify with the stakeholders to see if these missed deliverables should be added. | Ask that the project management office (PMO) approve additional funds for this work. | Include the work in the WBS, per the 100% rule, and recalculate the total project cost. | Determine whether these deliverables are necessary by verifying with experts in the field. |  |  | 3 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | The WBS is a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. The WBS organizes and deﬁnes the total scope of the project and represents the work specified in the current approved project scope statement. This must always reflect the complete and accurate scope of work. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.4.2.2/161 | 41390.1774 | N | 4 | [5 empty] | NA | NA
129 | SINGLE | A project manager is working with three key stakeholders. Each stakeholder has a different vision regarding the project and its goal. They each feel strongly about their opinion. The project manager needs to obtain approval of the project charter. What should the project manager do? | 4 | Conduct a stakeholder analysis. | Use negotiation to ensure the three stakeholders are in agreement. | Request that the project sponsor resolve the conflict. | Use the project kick-off meeting to settle the project goals. |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Projects experiencing a high degree of change require active engagement and participation with project stakeholders. To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.5/488 | 41390.1774 | N | 4 | [5 empty] | NA | NA
130 | SINGLE | Review the following project characteristics: -A sponsor approves a project. -The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. -The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | 4 | Milestone list | Work breakdown structure (WBS) dictionary | Scope management plan | Requirements management plan |  |  | 3 | 1 | PMP | Process | Project Scope Management |  |  | Medium | Predictive Approach | The scope management plan is a component of the project management plan that describes how the scope will be deﬁned, developed, monitored, controlled, and validated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 41390.1774 | N | 4 | [5 empty] | NA | NA
131 | SINGLE | A project is in the development stage. During this stage, there will be sensitive client data to handle. The compliance manager raises an issue of project non-compliance. What is the first document the project manager should review? | 4 | Statement of work (SOW) | Issue log | Business case | Risk register |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | After a new issue is raised, the issue log should be reviewed prior to taking action PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 41390.1774 | N | 4 | [5 empty] | NA | NA
132 | SINGLE | A project is underway and is 50% completed. An essential project team member requests 1.5 months leave for personal matters. What should the project manager do first? | 4 | Check with this team member to see if the leave can be postponed. | Discuss the issue with the functional manager and request a replacement. | Assess how the leave will impact on the project. | Refer to the resource management plan. |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  | Simple | Predictive Approach | The FIRST thing the project manager needs to do is to understand what impact (if any) this absence will have on the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.3/461 | 41390.1774 | N | 4 | [5 empty] | NA | NA
133 | SINGLE | A project manager works for a company that is preparing to develop a new product. The new product will require currently unavailable skills. To initiate this project, what should the project manager do? | 4 | Develop detailed project requirements | Focus on quality control | Focus on the assessment of high-level risks | Develop a competitor analysis |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | If you plan to deliver a product and do not possess the skills required, this is a risk. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1.1.4/441 | 41390.1774 | N | 4 | [5 empty] | NA | NA
134 | SINGLE | A project manager is uncertain about the duration of a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 25 days. The second group identifies some risks that could make the duration up to 40 days. The third group proposes a new development method that can shorten the time to 10 days. What is the estimated development duration for the new product? | 4 | 23 days | 25 days | 27 days | 30 days |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Using the PERT formula: [10 + 4(25) + 40]/6 = 25 PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.2.2.5/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
135 | SINGLE | A new product development project has the following characteristics: -There are three main tasks. -Task A must be delivered 4 weeks before task C starts. -Once task B is finished; task C will start. What is the relationship between tasks A and B? | 4 | Finish-to-start (FS) | Finish-to-finish (FF) | Start-to-start (SS) | Start-to-finish (SF) |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Predictive Approach | While there is no DIRECT relationship between A and B, both must be completed before C can start, so, of the choices, the only response that makes sense is FF PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.3.2.1/190 | 41390.1774 | N | 4 | [5 empty] | NA | NA
136 | SINGLE | A product deliverable is undergoing acceptance testing. A senior-level stakeholder raises concern that an essential product feature for their department was not developed. The project manager wants to avoid this issue in the future. What is one way to accomplish this goal? | 4 | Properly manage stakeholder expectations. | Prepare a change management plan. | Ensure a scope management plan gets approved. | Hold a product demo with stakeholders. |  |  | 3 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | A scope management plan documents how the project and product scope will be deﬁned, validated, and controlled. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.1.3.1/137 | 41390.1774 | N | 4 | [5 empty] | NA | NA
137 | SINGLE | A skincare company reports that customers are increasingly complaining that a product is underweight. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | 4 | Scatter diagram | Affinity diagram | Control chart | Histogram |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Control charts are used to determine whether or not a process is stable or has predictable performance. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2.5/304 | 41390.1774 | N | 4 | [5 empty] | NA | NA
138 | SINGLE | A product passes 96% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have been done differently to avoid this. What should the project manager have done? | 4 | Assessed and evaluated the test management plan | Created the work breakdown structure (WBS) | Ensured that the quality metrics were defined | Reviewed the requirements documentation |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 41390.1774 | N | 4 | [5 empty] | NA | NA
139 | SINGLE | A project manager is working on a data center migration project and is developing the schedule management plan. Per the project sponsor's request, the schedule must plan for all tasks as soon as possible. Additionally, the project manager is presented with possible network paths that will not violate schedule constraints. The project manager needs to select the appropriate leads and lags relationship for this situation. Which type should the project manager choose? | 4 | Early start is smaller than the late start in all activities. | Early start equals the late start in some activities. | Early start equals the late start in all activities. | Early start is smaller than the late start in some activities. |  |  | 3 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Predictive Approach | If the ES = LS on all tasks, they will be scheduled with no float or slack and will require all tasks to begin ASAP. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.2/210 | 41390.1774 | N | 4 | [5 empty] | NA | NA
140 | SINGLE | A project manager is preparing the charter for a project. The project aims to automate 30 percent of product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is uncooperative because they believe that the project will lead to downsizing in their department. What should the project manager do first? | 4 | Have a meeting with the test department manager to review the statement of work (SOW). | Request for the project sponsor to provide a rationale for test automation. | Present data-driven, cost-benefit evidence of test automation to the test department manager. | Raise the risk that the senior testing engineers will be unavailable for the testing. |  |  | 1 | 1 | PMP | Process | Project Stakeholder Management |  |  | Complex | Predictive Approach | The FIRST thing the PM need to do is to make sure the project goals are clearly understood by the stakeholders. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/523 | 41390.1774 | N | 4 | [5 empty] | NA | NA
141 | SINGLE | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | 4 | Analogous | Three-point | Bottom-up | Parametric |  |  | 3 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Predictive Approach | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.4.2.5/202 | 41390.1774 | N | 4 | [5 empty] | NA | NA
142 | SINGLE | A project has the following characteristics: -It is in the planning phase. -A key stakeholder will be unavailable for 2.5 weeks during the project. The project manager must decide what to do first, after learning about the key stakeholder's unavailability. What is the correct step to take? | 4 | Ensure that the issue log is updated and inform the other stakeholders. | Request that the finance department provide a replacement during the stakeholder's absence. | Organize a meeting with the sponsor to evaluate the situation and identify alternatives. | Continue with planning and acknowledge the impact the change may have on the project schedule. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | The FIRST thing the PM needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.3/487 | 41390.1774 | N | 4 | [5 empty] | NA | NA
143 | SINGLE | A project has the following characteristics: -It is in the execution phase. -A regulatory law has recently been approved that mandates immediate compliance. -This law will impact the project's scope, schedule, and cost. The project manager needs to determine what to do first. What is the correct step to take? | 4 | Initiate mitigation of the risk. | Ensure the project management plan is updated. | Escalate the issue to senior management. | Begin the change request process. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Since compliance is mandatory, a change request needs to be submitted. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3.3.4/96 | 41390.1774 | N | 4 | [5 empty] | NA | NA
144 | SINGLE | A project's deliverable on the critical path is lagging behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. What happens to the project? | 4 | There will be activities performed in parallel. | There will be a revised scope. | There will be an increase in costs and risks. | There will be rework. |  |  | 3 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Predictive Approach | Crashing a project will increase both costs and risks. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 41390.1774 | N | 4 | [5 empty] | NA | NA
145 | SINGLE | An intricate project has key stakeholders located in the United States, France, and China. The project manager discovers that a senior manager asked a team member for project information. Which step is appropriate to take next? | 4 | Rely on the information in the stakeholder register. | Refer to the project management information system (PMIS). | Ensure that the senior manager attends the next team meeting. | Read the communications management plan. |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  | High Complex | Predictive Approach | A communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377 | 41390.1774 | N | 4 | [5 empty] | NA | NA
146 | SINGLE | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What is the next step that the project manager should take? | 4 | Issue a change request for cost re-baselining. | Ask for additional resources. | Crash the project schedule. | Utilize the management reserve. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | Medium | Predictive Approach | Since the project is over budget and the trend analysis show that will continue, the best course of action is to re-baseline the cost of the project and manage to that. PMBOK® Guide Sixth Edition (2018) PMI/PMI/7.3.3.1/254 | 41390.1774 | N | 4 | [5 empty] | NA | NA
147 | SINGLE | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. What is the appropriate action for the project manager to take? | 4 | Anticipate risk responses and modify the risk register accordingly. | Use forecasting methods. | Plan to use the contingency reserve and update the risk mitigation plan. | Utilize methods such as earned value management (EVM). |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | These new requirements may pose additional risks. These risks need to be documented and appropriate responses need to be identified. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 41390.1774 | N | 4 | [5 empty] | NA | NA
148 | SINGLE | A project is in the execution phase. Due to the demand for a quick turnaround time, the project manager needs to rapidly assign resources to build the team and meet project requirements. Which action should the project manager take next? | 4 | Build library services. | Deliver workshops. | Train the new team. | Host a webinar. |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Develop Team is the process of improving competences, team member interaction, and overall team environment to enhance project performance. Training is a Tool & Technique of the Develop Project Team process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.5/602 | 41390.1774 | N | 4 | [5 empty] | NA | NA
149 | SINGLE | A project manager leaves the company and is replaced. The new project manager wants to start guiding the team toward project success. What should the new project manager do? | 4 | Look over the project charter to identify goals and deliverables. | Review the project diary and look for notes made by the former project manager. | Modify the project schedule, adding a new activity related to the knowledge transfer process. | Revisit the project budget to determine if extra time is required. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | In order to successfully lead a project, the PM must first understand the purpose of the project and what the goals and deliverables are. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 41390.1774 | N | 4 | [5 empty] | NA | NA
150 | SINGLE | Project team members are busier than usual. They indicate that they do not have the time to update the lessons learned because of other project responsibilities. How should the project manager respond to this issue? | 4 | Require submission of lessons learned documentation after each project deliverable is accepted by the customer. | Ensure there is an agenda item for discussion of lessons learned from project activities as part of all project meetings. | File a change request to the project management office (PMO) to change how often lessons learned is collected. | Bring in a consultant to assist with collecting lessons learned to help reduce the burden on project team. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | The lessons learned collection must be present throughout the project, using different facilitating techniques. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 41390.1774 | N | 4 | [5 empty] | NA | NA
151 | SINGLE | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across multiple geographic regions who will be working on a global project. How can the project manager work to ensure that the stakeholders are engaged? | 4 | Create slides for the kick-off meeting to address stakeholder involvement. | Survey stakeholders' preferred meeting dates and times to accommodate the teams in different time zones. | Verify that all required participants or their delegates will be available to attend. | Review the kick-off session agenda and materials for overall clarity and concision. |  |  | 3 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | None of the other options are viable without ensuring that all stakeholders are attending the project kick off meeting PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3/503 | 41390.1774 | N | 4 | [5 empty] | NA | NA
152 | SINGLE | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly, until the new manager learns that a critical component has failed during testing. What is the appropriate first step when responding to this issue? | 4 | Review the risk management plan to identify whether this risk and accompanying response strategies have been captured. | Check with other local team project managers to see how they would respond to the issue. | Revise the timeline to account for slippage due to the additional time needed to implement mitigation. | Communicate with stakeholders, describing the issue, proposed costs, and potential changes to delivery dates related to the project. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | Risk responses to identified risks should be outlined as part of the risk management plan PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.5/437 | 41390.1774 | N | 4 | [5 empty] | NA | NA
153 | SINGLE | A team member has taken an unplanned leave during the execution phase of a project. In response, the project team rescheduled some tasks. The result is that critical activities are now occurring at the same time. What is the first thing that the project manager should do? | 4 | Assess the newly introduced risks with the project team. | Mitigate risks by reverting to the original schedule. | Revise the risk register and then rank the project's risks. | Identify suitable responses for the newly introduced risks. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | PM should first involve the project team in the risk assessment. PM should also update risk register, prioritize risks and plan the response but first the newly discovered risk should be evaluated with the project team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2/409 | 41390.1774 | N | 4 | [5 empty] | NA | NA
154 | SINGLE | There are three deliverables in the project manager's IT transformation project: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. The project manager expects that Deliverable 3 will see quickly changing requirements during development. Which lifecycle model should be used to meet the project's requirements? | 4 | A. Select a fully agile project model, with a common user story and three-week sprints. | B. Select a waterfall project model for deliverables, with firm milestones and change control procedures. | C. Select a hybrid project model, where Deliverable 2 is positioned as single agile sprint embedded in an overall waterfall project. | Select a hybrid project model, where Deliverable 2 is positioned as a single waterfall phase embedded in an overall agile project. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | In this project two deliverables have unknown durations or changing requirement sets appropriate for Agile. The migration deliverable 2 requires tight schedule control and external dependencies appropriate for waterfall. PMBOK® Guide Sixth Edition (2018) PMI/PMI/1/19 ¦ The Agile Practice Guide (No Date) PMI/PMI/3.1.9/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
155 | SINGLE | A project manager is uncertain about the duration of a new product development project and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 14 days. The second group identifies some risks that could make the duration up to 32 days. The third group proposes a new development method that can shorten the time to 8 days. What is the estimated development duration for the new product? | 4 | 12 | 16 | 18 | 20 |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Simple | Predictive Approach | PERT Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (8 + (4*14) + 32)/6 = 16 days PMBOK® Guide Sixth Edition (2018) /PMI/7.2.2.5/244 | 41390.1774 | N | 4 | [5 empty] | NA | NA
156 | SINGLE | A product passes 99% percent of the functional requirements defined in the scope. A customer is unwilling to accept the product since it did not pass 100%. A project manager is assessing what could have done differently to avoid this. What should the project manager have done? | 4 | Properly evaluated the test management plan | Produced the work breakdown structure (WBS) | Defined and communicated the quality metrics | Verified the requirements documentation |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Quality metrics are a description of a project or product attribute and how to measure it. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1.3.2/287 | 41390.1774 | N | 4 | [5 empty] | NA | NA
157 | SINGLE | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are not able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | 4 | Face-to-face | Phone | Contractual letter | Email |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Predictive Approach | Face-to-face interaction is usually the most effective way to build the trusting relationships that are needed to manage knowledge. Once relationships are established, virtual interaction can be used to maintain the relationship. PMBOK® Guide Sixth Edition (2018) //13/506 ¦ PMBOK® Guide Sixth Edition (2018) //4.7/605 ¦ PMBOK® Guide Sixth Edition (2018) //X4.10/678 | 41390.1774 | N | 4 | [5 empty] | NA | NA
158 | SINGLE | A software vendor is behind on a key project deliverable. There is a 21% buffer in the budget for cost overruns. The project manager needs to mitigate the issue. Which action should the project manager take next? | 4 | Evaluate alternative software vendors that can help project deliverables despite resource constraints. | Remove the current vendor and have the new vendor send a contract. | Ask the vendor to meet to discuss legal issues regarding the slippage. | Accept the cost overrun and update the project schedule. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | The first step is analysis and evaluation of alternate options. After that, specific and appropriate action can be taken. PMBOK® Guide Sixth Edition (2018) /PMI/12.3/492 | 41390.1774 | N | 4 | [5 empty] | NA | NA
159 | SINGLE | A project needs a specialized resource. A resource that fits the needs of the project is identified, and can work onsite, but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | 4 | Ask the existing team to work overtime. | Place a limit on the project's scope. | Put the project on hold by an equivalent duration. | Request that the resource work virtually. |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The globalization of projects has promoted the need for virtual teams that work on the same project, but are not collocated. PMBOK® Guide Sixth Edition (2018) //9/311 | 41390.1774 | N | 4 | [5 empty] | NA | NA
160 | SINGLE | To determine which product to create, a project feasibility study was conducted. However, a change request was recently approved to develop another product that contradicts the original requirements. Data specialists conducted an analysis before the change request was approved. What is an appropriate action for the project manager to take? | 4 | Perform the change request. | Do not accept the change request. | Review a detailed report of the data analysis. | Review a feasibility study of the new product. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | After a change request has been approved, it should be executed. If the new requirements did not contradict the original ones, a change request would likely not be needed in the first place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6/113 | 41390.1774 | N | 4 | [5 empty] | NA | NA
161 | SINGLE | A project that should have been 70 percent complete by now is only 55 percent complete. The total project budget is US$210,000, and the actual cost of work performed (ACWP) is US$162,000 What is the scheduled performance index (SPI) and cost performance index (CPI) of this project? | 4 | A. The SPI is 0.79, and the CPI is .71. | B. The SPI is 1.27, and the CPI is 0.98. | C. The SPI is 0.82, and the CPI is 1.05. | D. The SPI is 0.99, and the CPI is 0.96. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | EV = Actual% * BAC = 0.55*$210,000 = $115,500 PV = Plan% * BAC = 0.70*$210,000 = $147,000 AC = $162,000 (given) SPI = EV/PV = $115,500/$147,000 = 0.79 CPI = EV/AC = $115,500/$162,000 = 0.71 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 41390.1774 | N | 4 | [5 empty] | NA | NA
162 | SINGLE | A project that should have been 90 percent complete by now is only 84 percent complete. The total project budget is US$110,000 and the actual cost of work performed (ACWP) is US$82,000. What is the schedule performance index (SPI) and cost performance index (CPI) for this project? | 4 | The SPI is 0.93, and the CPI is 1.13. | The SPI is 1.07, and the CPI is 0.99. | The SPI is 1.15, and the CPI of .93. | The SPI is 0.96, and the CPI is 1.18. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | High Complex | Predictive Approach | EV = Actual% * BAC = 0.84*$110,000 = $92,400 PV = Plan% * BAC = 0.90*$110,000 = $99,000 AC = $82,000 (given) SPI = EV/PV = $92,400/$99,000 = 0.93 CPI = EV/AC = $92,400/$82,000 = 1.13 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 41390.1774 | N | 4 | [5 empty] | NA | NA
163 | SINGLE | A project that should have been 95 percent complete by now is only 80 percent complete. The total project budget is US$140,000 and the actual cost of work performed (ACWP) is US$95,000. What is the schedule performance index (SPI) and a cost performance index (CPI) of the project? | 4 | The SPI is 0.84, and the CPI is 1.17 | The SPI is 1.19, and the CPI is 0.96. | The SPI is 0.86, and the CPI is 1.14. | The SPI is 0.94, and the CPI is 1.16. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | EV = Actual% * BAC = 0.80*$140,000 = $112,000 PV = Plan% * BAC = 0.95*$140,000 = $133,000 AC = $95,000 (given) SPI = EV/PV = $112,000/$133,000 = 0.84 CPI = EV/AC = $112,000/$95,000 = 1.17 PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 41390.1774 | N | 4 | [5 empty] | NA | NA
164 | SINGLE | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | 4 | Ask to meet with the product manager and discuss reducing the number of new requests. | Meet with the sponsor immediately to discuss project boundaries. | Meet face-to-face with stakeholders to set expectations. | Assess the scope management plan and iterate it through the scope definition process. |  |  | 4 | 1 | PMP | Process | Project Scope Management |  |  | High Complex | Predictive Approach | The scope management plan is needed to help control the scope of the project PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.6/167 | 41390.1774 | N | 4 | [5 empty] | NA | NA
165 | SINGLE | A project has the following budgetary features: -Total budget of US$3 million -Planned cost of US$630,000 -Actual cost of US$650,000 -Earned value of US$540,000 Which statement is true about this project? | 4 | It is under budget, and ahead of schedule. | It is over budget and behind schedule. | It is over budget and ahead of schedule. | It is under budget and behind schedule. |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | CPI = EV/AC = $540,000/$650,000 = less than 1 = over budget SPI = EV/PV = $540,000/$630,000 = less than 1 = behind schedule PMBOK® Guide Sixth Edition (2018) /PMI/7.4.2.2/263 | 41390.1774 | N | 4 | [5 empty] | NA | NA
166 | SINGLE | A project manager receives the following information for a new project: -assumptions -preliminary scope -restrictions After receiving this information, what is the first step the project manager should take? | 4 | Discern the project goals as well as the business case. | Determine the project team and provide the team with tasks. | Decide on the project schedule and determine the critical path. | Seek approval for the project charter from the sponsor. |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | The project charter will require a list of assumptions, the preliminary scope, and some of the restrictions. Additionally, the project goals and business case will also be needed. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 41390.1774 | N | 4 | [5 empty] | NA | NA
167 | SINGLE | A project manager recently joined a new project. This project has the following characteristics: -Deadlines that are tight -Global team that works virtually -Fixed budget The project manager is in the planning phase, and wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. What should the project manager do to achieve this goal? | 4 | Ensure that any changes to scope go through the formal approval process. | Ensure that daily stand-ups occur, with all development teams. | Ensure that the development team leads generate detailed requirements. | Ensure that stakeholders do not directly interact with the development team leads. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Following the formal approval process is the best way to control unnecessary project changes. PMBOK® Guide Sixth Edition (2018) //5.2/616 | 41390.1774 | N | 4 | [5 empty] | NA | NA
168 | SINGLE | After a project delay, the project manager determines that a change is needed to the product deliverables in order to ensure quality. The project manager takes the following steps: 1. A formal change request is issued. 2. The project manager communicates the change to all stakeholders. 3. The project manager receives feedback that the communications approach did not meet stakeholders' expectations. What should the project manager do next? | 4 | Use the communications management and stakeholder engagement plans. | Ensure stakeholders' expectations are included in the project management plan by issuing a change request. | Hold a meeting with the project sponsor to better understand stakeholders' expectations. | Refer to the communications management plan and issue a status report. |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Predictive Approach | These two plans help establish how communication will be managed and how the stakeholders will be engaged. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 41390.1774 | N | 4 | [5 empty] | NA | NA
169 | SINGLE | The project sponsor reports that an element of a product could lead to moderate health issues in customers. Therefore, the sponsor asks to modify production materials. Which action should the project manager take? | 4 | Refer to the Perform Integrated Change Control process to examine the issue further. | Promptly implement the change and submit a change request for formal documentation. | Halt current production and initiate the Perform Integrated Change Control process. | Do not fulfill the request because it will lead to scope creep. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Always investigate an issue first before taking action. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.6 (Integrated Change Control)/112 | 41390.1774 | N | 4 | [5 empty] | NA | NA
170 | SINGLE | There are necessary changes being requested to a project; however, team members are not in agreement regarding how to implement the changes. The project manager needs to address this issue. Which action should the project manager take? | 4 | Use the change management plan and ensure all team members and stakeholders understand and follow it. | Schedule an in-person meeting with the project sponsor and the board to address the issue. | Hold a meeting with team members to assess the issues and request changes where needed. | Ensure all requested changes are applied to the project and communicate face-to-face with all team members. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.2.3.1 (Integrated Change Control)/88 | 41390.1774 | N | 4 | [5 empty] | NA | NA
171 | SINGLE | A project manager with limited experience managing globally-distributed team members receives a project that has team members from five countries, spanning three continents. To successfully manage this project, the project manager needs to develop cultural sensitivity. What should the project manager do? | 4 | Be flexible when working with team members, recognize that culture is learned, and be aware of local customs. | Seek guidance from the human resource department, and request to be certified in this topic. | Request for another project manager to lead the project and follow behind this person to gain necessary skills. | Gather requisite learning material to better understand every detail of each team member's culture to be sensitive to their needs. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The project management team should capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 41390.1774 | N | 4 | [5 empty] | NA | NA
172 | SINGLE | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probability Impact A 3 5 B 4 2 C 3 3 D 2 2 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 4 | A, C, B, D | B, A, D, C | D, A, C, B | C, D, A, B |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Medium | Predictive Approach | Probability * Impact provides the risk ranking from highest to lowest. A = 3*5 = 15 B = 4*2 = 8 C = 3*3 = 9 D = 2*2 = 4 Therefore the risks should be ranked in the following order: A, C, B, D PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 41390.1774 | N | 4 | [5 empty] | NA | NA
173 | SINGLE | A project is completed, but the project manager and project team members are being asked to do the following: -Troubleshoot and resolve technical issues -Evaluate new requirements -Make minor adjustments The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | 4 | Execute the project hand off. | Procure project acceptance. | Contact the project team, dismiss them from the project, and find a new project. . | Since the product is still under development, continue to fulfill the requests |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | At project close, the final product, service, or result can be transitioned to a production support team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3.2/127 | 41390.1774 | N | 4 | [5 empty] | NA | NA
174 | SINGLE | A project has the following characteristics: -It is in the execution phase. -500 products have been developed based on the originally-approved blueprint. -The project team randomly selected 50 products to evaluate against the quality plan. What is occurring in this scenario? | 4 | The project team is performing inspections. | The project team is utilizing statistical sampling. | The project team is conducting audits. | The project team is undertaking a quality control measure. |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Predictive Approach | Statistical sampling involves choosing part of a population of interest for inspection. The sample is taken to measure controls and verify quality. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.3.2/302 | 41390.1774 | N | 4 | [5 empty] | NA | NA
175 | SINGLE | A project manager has the following situation: -A very long project management plan is drafted. -Stakeholders on the project are spread across three continents. -The project manager needs the stakeholders to approve the plan in as short of time as possible. What is an appropriate course of action for the project manager to take? | 4 | Option A 1. Arrange a meeting with all stakeholders. 2. Have the stakeholders review the plan before the meeting. | Option B 1. Send the plan to each stakeholder individually. 2. Ask them to add their comments and return it for updating. | Option C 1. Divide the plan into sections. 2. Based on their areas of expertise, ask select stakeholders to review particular portions. | Option D 1. Schedule individual meetings. 2. Invite only the key stakeholders and walk them through the plan. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | This option will require the least follow up discussions. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60-63/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
176 | SINGLE | A project manager has identified the following: -Four critical risks with a high-impact. -Four specific resources necessary for addressing the risks. -The resources are committed to another project with critical deliverables. The project manager must find a solution to address these risks immediately. Which actions should the project manager take? | 4 | Option A 1. Contact the functional manager. 2. Evaluate the resources' availability to negotiate task crashing or rescheduling. | Option B 1. Contract a third-party vendor. 2. Assign this vendor to these tasks. | Option C 1. Accept the risks. 2. Monitor these risks often to reduce potential impact. | Option D 1. Create a contingency reserve to solve the potential schedule delay. 2. Mitigate the possible impact. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Negotiation is an important tool and technique of the Control Resources process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
177 | SINGLE | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least 5 business days before the deadline. Four deliverables have missed this quality requirement. What should the project manager do? | 4 | Generate a cause-and-effect diagram for analysis. | Re-write relevant portions of the quality management plan. | Inquire regarding the feasibility of an internal audit of the project. | Contact the project sponsor, and request advice. |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Cause-and-effect diagrams break down the causes of the problem into discrete branches, helping to identify the main or root cause. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.2.2.4/293 | 41390.1774 | N | 4 | [5 empty] | NA | NA
178 | SINGLE | Several team members frequently spend their time helping operations and maintenance staff with a project feature that was just commissioned. The project manager needs to ensure that the feature was signed off on and that ownership was transferred. Which documents should the project manager rely on for this purpose? | 4 | Procurement agreements, organizational process assets updates, and final report | Procurement agreements, organizational process assets updates, and project document updates | Stakeholder engagement plan, organizational process assets updates, and procurement agreements | Project document updates, organizational process assets updates, and final report |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Project document updates, organizational process assets updates, and final report are outputs of the close project or phase process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7.3/127 | 41390.1774 | N | 4 | [5 empty] | NA | NA
179 | SINGLE | A project manager joins a project as a replacement on a project team. During initial meetings, the project manager realizes there are many differing opinions about how to address technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and is now working smoothly and productively on the project, without conflict or interruption. In what phase of development is the team? | 4 | Storming | Norming | Forming | Performing |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Complex | Predictive Approach | During Storming, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 41390.1774 | N | 4 | [5 empty] | NA | NA
180 | SINGLE | A project manager is presented with the following situation: -An iteration just ended. -A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? | 4 | During the retrospective | In the demo | During the next iteration planning meeting | In the next daily standup meeting |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | The retrospective allows issues with the execution approach to be identified and discussed in a timely fashion along with ideas for improvement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/Appendix X3/X3.3.3 | 41390.1774 | N | 4 | [5 empty] | NA | NA
181 | SINGLE | A project has the following characteristics: -Schedule performance issues are occurring due to expertise levels of project resources. -Highly-experienced resources are reviewing unnecessary details. -Junior-level resources are not completing tasks in a timely manner. The project manager needs to enhance team performance. What should the project manager do? | 4 | Where necessary, implement training, and design a checklist for all team members. | Where necessary, have the senior-level resources help the inexperienced resources. | Where necessary, replace specific junior-level resources, and advise the senior-level resources. | Where necessary, conduct training for the junior-level staff members. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Project managers should attempt to resolve issues via the tools and techniques available to them prior to changing the plan or escalations PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/336 | 41390.1774 | N | 4 | [5 empty] | NA | NA
182 | SINGLE | An informal and unofficial blog was set up to enhance communication and morale among project team members. The project manager was not previously aware of the blog but has discovered that team members are using it inappropriately. What should the project manager do? | 4 | Tell the project team to stop using the blog, and then assess the communications management plan. | Reprimand all individuals involved and report the issue to the compliance office. | Close down the blog, as it is not part of the communications management plan. | Identify an administrator who can monitor communications on the blog. |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | Simple | Predictive Approach | Communications outside of those covered by the communications management plan can lead to additional risks and issues. However, since the team was using the blog, the project manager should assess the communications management plan for any gaps. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
183 | SINGLE | A key project resource is discussing the complexity of project deliverables with the project manager 1.5 weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | 4 | Implement a feasibility study and then assess and review the results. | Hold a meeting with the project sponsor to discuss the resource's concern and revise the project charter. . | Ensure that the concerns are documented in the issue log for later review. | Start to identify threats and preventive actions by performing a risk assessment |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The feasibility study will support the business case to begin a new project PMBOK® Guide Sixth Edition (2018) PMI/PMI/1.2.6.1/30 | 41390.1774 | N | 4 | [5 empty] | NA | NA
184 | SINGLE | Four new risks for a project are identified while the project manager is preparing the monthly project status report. These four risks could affect vital key milestones. What should the project manager do before presenting this new risk information? | 4 | Refer to the risk register as well as the risk report. | Review the organizational process assets and risk register. | Refer to the risk management plan and the risk report. | Review the risk report and lessons learned repository. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | The first step will be to analyze the new risks. Reviewing the current risk register and risk report will be the best starting point. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 41390.1774 | N | 4 | [5 empty] | NA | NA
185 | SINGLE | A project that is nearing completion has the following characteristics: -It is very large. -It contains functional groups in five different countries. -Closeout documents are being prepared. The project manager needs to gain acceptance of the project deliverables. What should the project manager do? | 4 | Seek the project sponsor's sign off. | Contact the steering committee for sign off. | Seek sign off from the director of the project manager's business unit. | Contact managers from the five countries involved in the project for sign off. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 | 41390.1774 | N | 4 | [5 empty] | NA | NA
186 | SINGLE | During a kick-off, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do not have the same level of understanding. How should the project manager respond to this challenge? | 4 | Ask current team members to provide training and support and hold a second kick-off meeting for new team members. | Tell the newer team members to ask for help from the long-term members when they run into things they do not understand. | Add new members who have the relevant experience, reassign the newer team members, and log turnover issues in the lessons learned register. | Recognize that this is a natural project progression and revise the schedule to allow for the slight decrease in productivity. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | It is the PM's responsibility to make sure that the new members are adequately trained. This approach provides that training. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4.2.4/341 | 41390.1774 | N | 4 | [5 empty] | NA | NA
187 | SINGLE | A project has increased in size. As a result, the project's single sponsor is replaced by a steering committee. What should the project manager do to accommodate this new development? | 4 | Ensure that communications are tailored to the steering committee, since there has been a change in stakeholder structure. | Ensure that the initial project plan is followed, since the new stakeholders will focus on the project’s progress to date. | Introduce the steering committee to the team and continue to follow the initial project plan in order to meet project deadlines. | Make sure that the new steering committee members are included when sending the current status report for the project. |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  | Complex | Predictive Approach | The project manager needs to be proactive and respond to this change. The same communication that was planned for a single sponsor will not necessarily work for this steering committee. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
188 | SINGLE | During user testing, a client agrees to the final product. One day later the client indicates that the final product may not be acceptable. What should be the project manager’s first step for resolving this issue? | 4 | Review the project’s requirements documentation. | Review the project's quality management plan. | Consult the project’s acceptance criteria. | Refer to the project charter and lessons learned log. |  |  | 3 | 1 | PMP | Process | Project Scope Management |  |  | Medium | Predictive Approach | The definition of acceptance criteria may significantly increase or decrease quality costs and, therefore, project costs. Satisfying all acceptance criteria implies the needs of the stakeholders have been met. PMBOK® Guide Sixth Edition (2018) PMI/PMI/5.3.3.1/154 | 41390.1774 | N | 4 | [5 empty] | NA | NA
189 | SINGLE | Both the project sponsor and project team assure a project manager that the new project has a realistic schedule and an adequate budget. The project manager worries that unplanned events could threaten the project’s success. How should the project manager respond to this concern? | 4 | List and assess any project risks. | Ask for additional funding to cover project planning. | Schedule a meeting with the functional manager to address the potential impact of unplanned risks. | Review the original project plan and focus on completing the plan on schedule |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The project manager needs to be proactive and to familiarize himself with the identified risks and their mitigation strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.1/401 | 41390.1774 | N | 4 | [5 empty] | NA | NA
190 | SINGLE | The project manager has a large project with functional groups in four countries. Now that the project is close to completion, the project manager needs to obtain the correct signoff on the acceptance of project deliverables. What should be done to obtain the appropriate signoff on this project? | 4 | Ask for signoff from the managers of the four countries involved in the project. | Ask the director of the project manager's business unit to sign off. | Ask the steering committee to sign off. | Ask the project sponsor to sign off. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Since the sponsor provided the resources for the project, it is their responsibility to officially sign off on the project deliverables. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.7/121 ¦ Project Management: A Systems Approach to Planning, Scheduling, and Controlling (2013) Harold Kerzner/John Wiley/Wiley/10/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
191 | SINGLE | After the start of a project, the project manager learns that an expected governmental subsidy may not be available. What should the project manager do to address this issue? | 4 | Raise the project’s risk level. | Make sure that the information is added to the issue log. | Make up any project deficit using the contingency reserve. | Make a change request. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | The risk level on this issue must be raised as an expected monetary result might not be achieved. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 41390.1774 | N | 4 | [5 empty] | NA | NA
192 | SINGLE | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. The project manager needs to provide guidance to the team lead. What guidance should be offered? | 4 | The team lead should document conflicts as they occur, and take action to remedy any problems that arise. | The team lead should decide which team’s work should be prioritized, then delay the work from the other two teams to ensure there are no conflicts. | The team lead should identify potential conflicts and arrange for a weekly joint meeting with the members of the three teams to monitor each other’s work. | The team lead should tell all three teams to continue to work simultaneously, recognizing that conflicts can be addressed at the testing phase. |  |  | 3 | 1 | PMP | People | Project Integration Management |  |  | High Complex | Predictive Approach | Before deciding to act, the project manager needs to determine the potential conflicts and monitor progress. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2.3/80 | 41390.1774 | N | 4 | [5 empty] | NA | NA
193 | SINGLE | A project was not meeting scheduled dates for some tasks, so the project manager reprioritized a number of subsequent tasks to try to get the project back on track. The reprioritization did not fix the problem, and now the project manager needs to escalate the issue to project stakeholders. To escalate the issue, to which plan should the project manager refer? | 4 | Baselines for scope plan | Change management plan | Stakeholder engagement plan | Communications management plan |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  | Complex | Predictive Approach | The communications management plan is developed to ensure that the appropriate messages are communicated to stakeholders in various formats and various means as deﬁned by the communication strategy. PMBOK® Guide Sixth Edition (2018) PMI/PMI/10.1.3.1/377/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
194 | SINGLE | A deliverable does not meet the agreed-upon quality specifications and is rejected by the customer. After investigation, the project team finds that there is a fault with the vendor-provided parts, and this fault caused the issue. The vendor says that they cannot correct the situation. What should be reviewed before deciding on next steps? | 4 | The service level agreement (SLA) established with the vendor | The procurement management plan and contract agreements | The internal quality assurance reports | The resource management plan |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | A contract is a mutually binding agreement that obligates the seller to provide the speciﬁed products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.3/492 | 41390.1774 | N | 4 | [5 empty] | NA | NA
195 | SINGLE | 1 There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the project manager requires resource support from an external supplier. The project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | 4 | Suggest a fixed price incentive fee (FPIF) contract. | Recommend a time and material (TM) contract. | Suggest a cost plus incentive fee (CPIF) contract. | Recommend a firm fixed price (FFP) contract. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as deﬁned by the contract), and the seller can earn an additional amount if the seller meets deﬁned performance criteria. FPIF contracts are the most risk averse. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.1/472 | 41390.1774 | N | 4 | [5 empty] | NA | NA
196 | SINGLE | Although a previously identified technical issue has been resolved, the project manager is warned that the same issue is likely to occur on similar projects in the future. Which document should be part of the first step in responding to the warning? | 4 | The issue log | A risk report | A communication for the project sponsor | The lessons learned register |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | The lessons learned register can be used for future projects to help avoid past project issues PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.4.3.1/104 | 41390.1774 | N | 4 | [5 empty] | NA | NA
197 | SINGLE | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | 4 | Schedule a meeting with the team member’s manager to negotiate for additional time to complete the other task. | Replace the team member with a new resource from another department. | Notify the project sponsor, documenting the conflict caused by the member’s manager. | Notify the team member’s manager of project needs and require the release of the member until the project activity is completed. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.6/352 | 41390.1774 | N | 4 | [5 empty] | NA | NA
198 | SINGLE | Successful project leaders nurture team members’ skills and knowledge, and keep members motivated throughout the project. Which action helps to promote successful project leadership? | 4 | Be assertive, and stand up for the team’s needs, concerns, and beliefs. | Promote team challenges by delegating project tasks. | Schedule daily sessions where team members can voice concerns and receive a response. | Create a team reward for each successfully completed task. |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Complex | Predictive Approach | The primary goal of a project manager in relation to the project team is to ensure that the team has the time and resources to do their job and to remove any barriers they may encounter. By standing up for the team's beliefs the project manager is demonstrating their support for the team. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4/60 | 41390.1774 | N | 4 | [5 empty] | NA | NA
199 | SINGLE | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | 4 | Schedule a meeting with the sponsor to obtain benchmarking samples and cost-benefit analyses. | Schedule a meeting with the customer to collect requirements and obtain benchmarking samples. | Obtain established quality processes and plans from the senior project manager. Then, ask them for guidance in selecting the appropriate standards. | Postpone the development of the quality management plan by submitting a change request. Only proceed when quality metrics and quality checklists have been created. |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Predictive Approach | The new project manager needs to consult with the senior project manager to find out what practices and processes are already in place. PMBOK® Guide Sixth Edition (2018) PMI/PMI/8.1/277 | 41390.1774 | N | 4 | [5 empty] | NA | NA
200 | SINGLE | Two users complain during the project’s user acceptance stage, saying that their expectations were not met. What could the project manager use to avoid this issue in the future? | 4 | Risk assessments | Conflict management techniques | A professional relationship with the users | A. Stakeholder feedback |  |  | 4 | 1 | PMP | Process | Project Stakeholder Management |  |  | Complex | Predictive Approach | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2/526 | 41390.1774 | N | 4 | [5 empty] | NA | NA
201 | SINGLE | A new project sponsor asks for a project team that includes resources working in three different time zones and locations. The project sponsor did not consider the implications of this requirement and believes that the request will save costs while creating the ideal project team. Where should the project manager document this request in the project charter? | 4 | Overall project risks | Key stakeholder list | High-level requirements | Resource management plan |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Medium | Predictive Approach | Having a dispersed project team does not come without risks. These risks need to be identified in the risk log for the project. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.2/418 | 41390.1774 | N | 4 | [5 empty] | NA | NA
202 | SINGLE | As a result of multiple regulatory changes, a governmental agency is added as a key stakeholder on a complex project. The project manager wants to develop an understanding of this new stakeholder and identify any new high-level risks that may result from the change. What should the project manager do? | 4 | High-level requirements | Identify needed changes to the assumption log. | Meet with the new stakeholders. | Resource management plan |  |  | 3 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Meetings are used to develop an understanding of significant project stakeholders. They can take the form of facilitation workshops, small group guided discussions, and virtual groups using electronics or social media technologies to share ideas and analyze data. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.3.2.5/528/ | 41390.1774 | N | 4 | [5 empty] | NA | NA
203 | SINGLE | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify strategic and operational assumptions and constraints. How can the project manager improve stakeholder input? | 4 | Use political awareness techniques. | Institute checklist policies. | Research effective meeting management techniques. | Make use of effective facilitation techniques. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures that there is effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achieved are appropriately dealt with afterward. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1.2/80 | 41390.1774 | N | 4 | [5 empty] | NA | NA
204 | SINGLE | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager is informed that one stakeholder is experiencing difficulties and cannot provide their former level of involvement. Which action should the project manager perform? | 4 | Update the stakeholder engagement plan. | Revise the project charter. | Update the stakeholder register. | Revise the project management plan. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | The stakeholder engagement plan is updated to reﬂect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution. PMBOK® Guide Sixth Edition (2018) PMI/PMI/13.2.3.1/522 | 41390.1774 | N | 4 | [5 empty] | NA | NA
205 | SINGLE | A company’s products will be affected by a new law that might be passed in the next four months. A new product launch is starting, and should be completed within three months. If the proposed law is passed, the new product will not meet the new requirements. How should the project manager address to this potential problem? | 4 | Option A 1. Warn the sponsor and key stakeholders about the implications of the possible law. 2. Advise them to put the project on hold until the legislation is passed. | Option B 1. Move forward with the project and project planning. 2. Meet all deadlines, ensuring that the product will be complete prior to potential change in the law. | Option C 1. Update the risk management plan. 2. Move ahead with project planning. | Option D 1. Discuss risks with the sponsor and key stakeholders. 2. Using the results of the discussion, update the assumption log and project charter. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions and a possible charter change. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.1/75 | 41390.1774 | N | 4 | [5 empty] | NA | NA
206 | SINGLE | An approved change was implemented to manage a risk. Three months later, the project manager finds that the change did not yield the desired result. In fact, the change led to adverse consequences. What should the project manager do to avoid this issue in the future? | 4 | Update the risk information to the lessons learned register. | Review the assumption log to revisit or change current assumptions. | Confirm that an implemented risk response is effective. | Evaluate new risks and update the probability and impact matrix. |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.7/453 | 41390.1774 | N | 4 | [5 empty] | NA | NA
207 | SINGLE | A project manager overhears a conversation in a cafeteria. The speaker says that a possible union action will occur within the next two weeks. The project manager knows that any union action will affect the project team, and at this stage of the project, any project delays will cause substantial harm to both budget and schedule. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. What should the project manager do? | 4 | Inform relevant stakeholders and update the risk register with the new risk. | Ask stakeholders for additional information regarding the likelihood of the union action, then act on what is heard. | Set up an information session for the project team, letting them know of possible disciplinary sanctions for those who participate in the union action. | Meet with union members and the union leader to resolve this conflict. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | The project manager needs to proactively approach this. By updating the risk register and by communicating this development to the appropriate stakeholders, they will be achieving this. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.2.3.1/417 | 41390.1774 | N | 4 | [5 empty] | NA | NA
208 | SINGLE | While reviewing the issues log, the project manager notices that tasks assigned to two team members are quite a bit behind schedule. What should be done? | 4 | Document the issue, escalate to the project sponsor, and ask for how they would like it resolved. | Work with the relevant team members to review the delayed tasks and decide on strategies for resolution. | Tell the team members who are behind schedule that they should explain why tasks were delayed and how they will get back on schedule. | Notify the responsible team members of the need to complete the overdue tasks quickly in order to avoid introducing extra project risks. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | The project manager needs to be proactive and review the activities with the team and to identify resolution strategies. PMBOK® Guide Sixth Edition (2018) PMI/PMI/3.4.4.2/61 | 41390.1774 | N | 4 | [5 empty] | NA | NA
209 | SINGLE | A project sponsor is risk averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale, 1 being the lowest and 5 being the highest. Risk Probabilit Impact A 2 3 B 2 5 C 3 4 D 4 4 Based on the table, in what order should the project manager rank these risks for risk management purposes? | 4 | B, A, D, C | B, C, A, D | D, C, B, A | C, D, A, B |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | C Probability * Impact provides the risk ranking from highest to lowest. A = 2*3 = 6 B = 2*5 = 10 C = 3*4 = 12 D = 4*4 = 16 Therefore the risks should be ranked in the following order: D, C, B, A PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.4/428 | 41390.1774 | N | 4 | [5 empty] | NA | NA
210 | SINGLE | A project manager has put together a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have not been told the specific details of the project. In what phase of development is the team? | 4 | Storming | Norming | Forming | Performing |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Simple | Predictive Approach | The Forming phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.4/338 | 41390.1774 | N | 4 | [5 empty] | NA | NA
211 | SINGLE | The procurement statement of work (SOW) is completed on a project. However, the customer is not happy because she wants additional work to be completed. what should the PM do first? | 4 | Begin the close contract process, and sign a new agreement for additional work. | Raise a Change Request. | Raise Objection. | Include the work in the same PO. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | As all the work outlined in the SOW is completed, raising a CR is not an option. A new SOW outlining the additional work has to be drafted and signed off
212 | SINGLE | What is the correct order of performing the processes? | 4 | Control Quality, Close Project or Phase, Close Procurements | Validate Scope, Control Quality, Close Project or Phase, Close Procurements | Control Quality, Validate Scope, Close Project or Phase | Validate Scope, Control Quality, Close Procurements |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Scope is validated only after QC. Project or the phase is closed after scope is validated. (Project cannot be closed without scope validation
213 | SINGLE | The Sprint goal cannot deliver the intended business value because of the extreme change in business priorities. Who can terminate the Sprint (Iteration)? | 4 | Product Owner | Scum Master | Functional Manager | Customer |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Agile | Product Owner is authorized to terminate the Sprint if it is determined that a drastic change in direction is required
214 | SINGLE | You are a Project Manager for Xansa Consulting. Your latest project includes the upgrade of an organization's operating system on 215 servers. You are doing this project under contract. You are in the Contract Closure Process & have reviewed the contracting process to identify lessons learned. What is the name of the tool and technique that you will use to perform the above function? | 4 | Performance Audits | Performance Reviews | Procurement Audits | Procurement Reviews |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | "Project under contract" is the key sentence. Contracting processes are reviewed lessons learned are documented during Procurement Audits
215 | SINGLE | You are a Project Manager for XtraMind Consulting. Your current project involves the upgrade of an organization's operating system on 220 servers. You are doing this project under contract. You are in the penultimate sprint & closing the contract & know that you should document which of the following? | 4 | Formal Acceptance | Administrative Closure Procedures | Contract Closure Procedures | Product Verification |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Agile | The project is being delivered under contract (contract type is immaterial). You cannot close the contract without the "Formal Acceptance"
216 | SINGLE | You are working on a construction project. Everyone in your team and your senior manager feel that the work is complete except one of your stakeholders who disagrees, and feels that one deliverable is not acceptable. What is the BEST way to handle this conflict? | 4 | Renegotiate the contract. | Consult the contract and follow its Claims Administration Procedure. | File a lawsuit to force the stakeholder to accept the deliverable. | Follow the administrative and contract closure procedures. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Key is looking for the BEST solution. All stakeholders are bound by the terms of the contract, hence it has to be consulted & followed in letter & spirit.
217 | SINGLE | You are managing a project to build a new wing in a local school over a summer break. One day, the school & your construction site are destroyed by an earthquake. Your client stresses that you continue work despite the disaster, but you consult the contract and find a clause that states that you are not responsible for any more work. This is referred to as: | 4 | Mitigation | An "act of God" clause | A force majeure clause | An ex parte communication |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Force Majeure clause covers earth quakes, flash floods, landslides, etc.
218 | SINGLE | You have just finished the project for a client to implement a business software solution. All deliverables have been handed over & are already, in use by the client. However, there is still a minor payment to be made by the client on contract closure. You believe that it is now high time to finally close the contract with the client & then, close the project. You approached the client this morning and found that they are somewhat reluctant to close the contract. But you do not exactly understand the reason. What should you NOT do? | 4 | Based on the contract and all documents which are relevant for the formal relationship with the customer, write a close-out report describing what was contractually required and what was obtained. | Focus on your next project and leave the customer the time to get familiar with the software. They will come back to you anyway after some weeks to close the contract and make the last payment. | Update all documents related to the project and the product so that they reflect the final specifications and the status of both the project and the product. Organize them in a fashion for easy access. | Make sure that there are no active purchase orders against the contract or any other pending obligations, requests or claims from either party which need to be resolved. Then insist on formal contract closure. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | NOT do is the key. You cannot leave the stakeholder alone & expect things to get normal. This is never going to happen
219 | SINGLE | You are currently working on an e-commerce project to develop a new user interface for a legacy mainframe banking application. You are under a Time & Material contract to develop an e-commerce based interface for this application. You had a release plan of 10 sprints, but delivered all the user stories in 8 sprints. This means that the profit of your company will decrease. What should you do? | 4 | You should inform the customer that your project is complete. | You should add activities to the project to increase the number of billable hours. | You should tell the customer that you will be adding more requirements to the project in order to meet profit estimates. | You should invoice the customer for the expected billable amount, as allowed by the provisions of your contract. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Agile | As a certified professional you are expected to be exhibit integrity & transparency over profits. Hence inform the customer & mark the project as complete
220 | SINGLE | The seller delivers a fixed price plus incentive fee project at a cost of $90,000. The terms of the contract are a ceiling price of $120,000, a target cost of $100,000, a target profit of $10,000, and a target price of $110,000. The share ratio is 70/30. The final price (your total reimbursement) is: | 4 | 93000 | 96000 | 97000 | 103000 |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Target Cost = $100,000 Ceiling = $120,000 BSR=0.3 Final Fee=((Target cost-Actual Cost) * Seller ratio) + Target Fee = ($100,000-$90,000)0.3 + $10,000 = $13,000. Final price = Cost + Final Fee = $90,000+$13,000 = $103000
221 | SINGLE | A contract has just been signed with a construction company to complete a renovation project within 4 months. Due to "force majeure", the project will be delayed by an additional 3 months. The construction company has asked for an early termination of the contract. What is the MOST appropriate thing to do in above situation? | 4 | Seek legal advice. | Complete administrative closure. | Complete contract closure. | Re-negotiate the contract. |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | As the Force Majeure clause is invoked (considered part of contract terms), the contract has to be closed as per the terms
222 | SINGLE | During project closure a project sponsor complains that the project did not enhance the department's knowledge of Android programming and therefore, the project is not complete. The customer has accepted the project. The project manager confirms that all stated objectives and deliverables have been met. He does not find evidence that Android programming knowledge enhancement was an objective for the project. A review of project correspondence shows no mention of the deliverable. The project manager should:- | 4 | Begin project closure. | Re-plan the project to include the new objective. | Meet with the team to discuss the issue and find a resolution. | Get the project stakeholders involved to help resolve the issue. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | As "Android programming knowledge enhancement" was not captured as deliverable or a stakeholder requirement, you are not contractually bound to deliver it. Proceed with project closure
223 | SINGLE | A project manager for a large international bank has a project team that just executed an electronic funds project involving 4 large vendors. The project manager struggled through every phase of the procurement process since the bank had a pathetic internal contracts department. What would be the MOST appropriate thing to do to ensure the problems are resolved for future projects? | 4 | Document all of the issues in a memo and schedule a meeting with the head of the contract office. | Include an agenda item in the project closedown to discuss these issues in a non-threatening manner. | Address this through contract change control. | Conduct a procurement audit. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Procurement audits will unearth the reasons behind procurement process delays & lessons learned are documented for further use
224 | SINGLE | You are a project manager at a Construction company that develops and manages residential, retail and commercial properties in Dubai. As the company continues to grow, the company's IT infrastructure is unable to meet business needs of the organization. Specifically, you have been assigned to upgrade the company's IT infrastructure. Your team has been asked to implement a corporate general ledger system, improve accounting and real estate processes, develop & implement lease tracking system & implement HR & payroll systems. You are also required to perform diagnostics and monthly closures. You are closing out a minor contract on the project phase when you discover that a deliverable has not been received. Your manager wants the problem resolved as soon as possible without much trouble. What should you do? | 4 | Deduct the cost of the deliverable from payments. | Deduct the deliverable from the cost of the project | Deduct the deliverable from the scope of work | Require that the deliverable be done & submitted. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | AS your Manager has requested you to resolve the issuer asap & you cannot close the contract or the project without the missing deliverable, best option is to get the missing deliverable completed
225 | SINGLE | You are about to complete all work associated with a new, systems integration project when the seller comes to you with detailed procedures for closure of the contract. The contract you had signed earlier included different closure procedures. The seller is insisting to use the revised procedures for contract closure. What should you do? | 4 | Revise the closure procedures after getting management's approval. | Get a change order from the Change Control Board. | Assess the quality of the seller's new detailed procedures, and if they are better than the current procedures, use them. | Create new procedures altogether. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | All changes after baselining has to be approved by the CCB. Here the seller is proposing changes after contract signature (contract terms were baselined on contract signature)
226 | SINGLE | While you are working on the project closeout documents, you begin to review the project deliverables & develop checklist of project requirements. You can usually find the requirements for formal contract closeout in the: | 4 | Project plan | Contract terms and conditions | Work breakdown structure | Project Charter |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Project / work requirements are part of Contract terms & conditions
227 | SINGLE | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in the process of designing a new two-wheeler. He is managing a big team and hence needs to handle number of conflicts. Which of the following is the most ineffective way of conflict resolution? | 4 | Problem Solving | Compromising | Forcing | Withdrawal |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Out of all the conflict resolution techniques, Forcing creates Win-Lose situation. PMs should strive to create Win-Win solution as far as possible
228 | SINGLE | Ramie is working as a Project Manager in a Four-Wheeler CORP LTD located in Japan. He finds a conflict between two of his team members. He is not able to confront the problem. What is the next best conflict resolution technique from the following? | 4 | Compromising | Forcing | Withdrawal | Smoothing |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | As the PM is unable to confront the conflicting problem, Compromising is the next best option. Forcing & Withdrawal are not good options as they bring create Win-Lose & Lose-Lose solutions
229 | SINGLE | Philip is working as a Scrum Master for AUTOCARS PVT LTD. He is managing a 20 Scrum member team. For conflict resolution he always try to use confronting first. Confronting conflict resolution method is also known as: | 4 | Forcing | Withdrawal | Problem-Solving | Smoothing |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Most effective way to resolve a conflict is to confront the problem head-on & trying to get a solution. This creates a Win-Win solution known as Problem-Solving
230 | SINGLE | Two team members of your Scrum team Philip and Ramie was having a conflict. In one of the Sprints, you used problem solving conflict resolution technique. Problem Solving is : | 4 | A Win-Win situation | A Win-Lose Situation | A Lose-Lose Situation | Delaying the solution |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Problem-solving always leads to creating a Win-Win situation as the conflicting problem (bone of contention) is confronted & a resolution is arrived at
231 | SINGLE | Two team members of your Scrum team Philip and Ramie were having a conflict. You used Compromising conflict resolution technique. Compromising is : | 4 | A Win-Win situation | A Win-Lose Situation | A Lose-Lose Situation | Delaying the solution |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | You did not confront the conflicting problem, but tried to create a Lose-Lose situation by compromising among the conflicting parties
232 | SINGLE | Two team members of your Scrum team Philip and Ramie was having a conflict. You used Forcing Conflict Resolution technique. Forcing is : | 4 | A Win-Win situation | A Win-Lose Situation | A Lose-Lose Situation | Delaying the solution |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Forcing creates Win-Lose solution as the forcing person will be in winning situation & the person being forced will be in losing situation
233 | SINGLE | You have been given the responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. Two of your team members are having a conflict over a technical issue. What is the first thing you should do? | 4 | Check technical documentation | Meet the team members and find what is causing conflict | Ask them to resolve themselves | Put one of them in some other project |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Always look at the problem that is causing the conflict, which is a technical issue in this case. So the very first thing you do is to meet the conflicting parties & try to understand the conflicting issue
234 | SINGLE | Philip and Ricky are having an argument over a technical issue in one of the Sprints. Philip tells Ricky that his views are not going to work, on listening this Ricky storms out of the room even though he knew his views about the problem were better than Philip's. Which type of conflict resolution is this? | 4 | Withdrawal | Problem Solving | Smoothing | Forcing |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Ricky is walking out of the conflict (potential conflict), hence he is withdrawing from the conflict
235 | SINGLE | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them and conclude that both agree on certain things and they should concentrate on the grounds they agree. Which type of conflict resolution is this? | 4 | Withdrawal | Problem Solving | Smoothing | Forcing |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | The conflicting parties agree on some of the points. They are not completely against the conflicting issues & are agreeing on the common grounds. This is Smoothing situation
236 | SINGLE | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master to resolve the problem. He listens to both of them, however due to his busy schedule he says that he will listen to them in detail a week later. Which type of conflict resolution is this? | 4 | Withdrawal | Confronting | Compromising | Forcing |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | The Scrum Master is neither confronting the problem nor trying to find a resolution. He is withdrawing (procrastinating) from the conflicting situation
237 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He keeps a watch on each of his team member and reviews each document prepared by them. Which kind of manager is Russell? | 4 | Theory X | Theory Y | Theory Z | None of the above |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | In Theory X, the Manager micro-manages the project. He usually mistrusts the team members & reviews all the work
238 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He keeps faith on his team and occasionally reviews the documents prepared by his team members. Which kind of manager is Russell? | 4 | Theory X | Theory Y | Theory Z | None of the above |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | unlike in Theory-X, Theory-Y Managers completely trust the team members. They do not micro-manage & always manage by exception
239 | SINGLE | Ronaldo has just finished his project and has been assigned new project that needs working on a new technology which has never been used by the company before for any of the projects. He is currently executing the project and finds that he is slightly behind the schedule. Therefore, he announces INR 5,000 reward for any of the team member who would work overtime and help him to meet deadlines. Which type of power is he using? | 4 | Legitimate | Reward | Referent | Expert |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | By announcing INR 5,000 reward, Ronaldo is using the rewarding power. All other options do not use the reward option
240 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. You recently heard a word War-Room from one of your colleague. A War-Room is a: | 4 | Place where decisions are made. | Place or room where conflicts are resolved | Place where team can sit together and get closer communication | A power of manager |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | War-room is a command center wherein entire team operates from a single location where high degree of communication & coordination among the team members is required
241 | SINGLE | Renée is a working as a Project Manager in Muddy Pharmaceutical Pvt Company. She sets up a reward for team members completing work in a defined period of time. But she finds that the team is less motivated than before. She checks and finds that it is impossible to complete the work in that defined time. Which motivational theory does this demonstrates? | 4 | Maslow's Hierarchy of Needs | McGregor's Theory of X and Y | Herzberg's Hygiene Theory | Expectancy Theory |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | The team is less motivated in spite of the reward being announced. This means that the team is expecting something different for motivation as proposed by Vroom's Expectancy theory
242 | SINGLE | Philip and Ricky are having an argument over a technical issue in one of the Sprints. So they went to the Scrum Master. He listened to Philip's views and then without listening Ricky's views he concludes that Philip is correct. Which conflict resolution technique did the manager used? | 4 | Problem Solving | Smoothing | Forcing | Compromise |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Agile | Philip's views are being forced on Ricky & creating a Win-Lose solution. This is Forcing
243 | SINGLE | In the communication model, the "Decoder" is different from the "Receiver" because: | 4 | The decoder evaluates, uses assumptions to translate message back into meaningful thoughts or ideas while the receiver sees or hears | The decoder interprets based on his or her frame of reference | Receiver is used to convey message. | Both A & B |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Receiver just receives the encoded communication, where as Decoder decrypts & converts the encoded messages into a communication that makes sense
244 | SINGLE | In a one-on-one communication process, the sender is the one who transmits the signals, while the receiver ________ the signals. | 4 | Interpret | Accepts | Intercept | Rejects |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | The receiver receives the encoded message, decrypts & interprets the message. Then the receiver acknowledges the receipt & interpretation of the message which completes the communication loop
245 | SINGLE | Communication between Project Manager and team members takes place best: | 4 | through daily status report | through approved documented forms | through formal chain of command | through written and oral communication |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Status reports or formal chain of command leads to one-way communication most of the time. We are looking for BEST solution here which is written & oral communication
246 | SINGLE | A Rosy Cloud club at New Delhi is going through a critical phase. To understand the reason of this the club did an analysis and found that their employees are not able to understand their foreigner client's message properly. To resolve this problem, the club issued a notice saying while communicating with the client every employee should use ________ as a means of giving feedback to the speaker by rephrasing the speaker's words to ensure their level of understanding. | 4 | Cross check | Active listening | Give back | Double talk |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Interpreting the communication depends upon the listening / understanding ability of the receiver. Active listening & requesting para-phrasing is the effective method to improve the communication loop
247 | SINGLE | Individuals send two messages when they speak in face-to-face communication. The two message aspects are content and command. The first contains that part of the message about which two or more persons can agree, and the second contains ________. | 4 | That portion of communication that imposes behavior and the relationship between the parties | That portion of communication which is intentionally meant to be misunderstood | Reinforcement of prior messages | Random information that does not contribute to the message content |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | In face to face communication, relationship between the communication parties plays a role in how messages are sent, received, and interpreted
248 | SINGLE | While managing a project, a project manager spends major part of his time in communicating. Thus, striving to improve the communications within the project team as well as with external elements is of prime importance. The project manager can improve communications by removing ________ of the information. | 4 | Distortion, redundancy and blockage | Some portion of information that, you as a project manager feels, is not important | Haste and waste | All of the above |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Filtering the communication & removing distortion, redundancy and blockage leads to improved communication. All of the above is not the option here is haste & waste is not used to improve communication. The question is about improving communication
249 | SINGLE | As a Project Manager you want to ensure your team member understands the work to be accomplished. You can be more assured of the effectiveness of your communication by ________. | 4 | Obtaining feedback and using active listening | Obtaining feedback and evaluating the end result of the work | Restating the directive and communicating the expected commitment from all your team members | Emphasizing the importance of the work and restating the directive |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Effective method of assigning work is to get feedback & evaluate the work deliverable. Other options are redundant or superficial
250 | SINGLE | Scrum meetings (or Standup meetings) are integral part of Agile projects. It facilitates the communication of information among individuals. A legitimate reason for assembling the project team in a meeting includes ________. | 4 | Giving team members a chance to know each other and befriend so as to make them create a better team environment and be an effective team | Resolving all the team conflicts | Exhibiting the project information and making further decisions on project direction | Discussing the project experience among team members |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  |  | Agile | Meetings among all the team members are the most effective way of discussing project information/status & deciding further course of the project
251 | SINGLE | Effective communication has always been an important need in Project Management. In a communication model where everyone is permitted to talk to anyone, essential communication ___. | 4 | Changes the context in which complex issues are delivered as compared to formal written communications | Loses its importance because of confusion in communication responsibility | Becomes non essential communication because of the lack of emphasis given to the verbal message | Can be done through the shorter route from the sender to the intended stakeholder |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | In one-to-many communication model, finding the shortest communication route is most effective. The question is about essential communication, hence other options are not the best solutions
252 | SINGLE | In the course of managing the project, the Project Manager must communicate with several different people . His/her sole purpose for sending a message is to ________. | 4 | Convey positive image of project progress | Impress people | Convey information or an action | Have a motivating impact |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | The basic purpose (as being asked in the question) of effective communication is to convey the information. It is not to impress people or to promote only positive aspects
253 | SINGLE | There are various types of communication a project manager can perform. The most difficult and costly type of communication performed by the project manager is ________. | 4 | One to One counseling | Emails | Formal reports or letters | Meeting or conference |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | All the meeting attendees' time has to be considered in meeting, hence making it expensive. Emails or types of communication are less expensive
254 | SINGLE | The project manager of Kite Sky project is called for an information meeting with the customer. In the meeting a problem is raised which has major implications for the project manager's company. The customer wants to pursue a solution at the meeting. The project manager should ________. | 4 | Collect as much information on the problem without committing his/her company to a solution | Tell the customer that the problem is not sufficiently defined to determine the appropriate action | Tell the customer that he/she will not address any problems because this is only an information exchange meeting | Give the customer a range of solutions that might be acceptable to his/her company |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | As the PM's company will be affected by the issue raised by the customer, the PM should gather as much information as possible that will help him/her to analyze. PM should not jump into making commitments without thorough analysis of the issue
255 | SINGLE | Of the following which one is not a form of project communications? | 4 | Professional journals and magazines | Telephone logs | Correspondence | Handwritten memos |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | All other options are a type of project communication expect telephone logs. Remember in question we have to identify NOT a communication form
256 | SINGLE | In Matrix and Projectised environments communication barriers are a more frequent source of conflict, than in functional organizations. Following could be the reason of it EXCEPT: | 4 | Team members are often physically separated in a matrix or project environment | Communication is the prime focus of an expediter type of project manager | There are increased numbers of levels of authority in a Matrix or Projectised environment | Team members with differing skills and backgrounds can be asked to contribute to project results |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Do not forget that EXCEPT is the key word. All other options are valid except option#2
257 | SINGLE | For active and effective communication the listening ability plays an important role. Following could be the ways of improving the listening ability EXCEPT: | 4 | Listening and giving Feedback | Working on another activity while listening | Allow the speaker to complete his message. | Focusing on concepts and ideas |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Working on another activity OR multi-tasking is not an effective communication method. Do not forget that EXCEPT is the key word.
258 | SINGLE | The project manager of Wi-Sky project is planning for his project. While planning he needs to communicate with several stakeholders. While communicating he faces various communication barriers. These barriers can include the following EXCEPT: | 4 | Unclear expectation | Shared assumptions | Cultural differences | Environment circumstances |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Do not forget that EXCEPT is the key word. Shared assumptions does not lead to a communication barrier. All other options lead to communication barriers
259 | SINGLE | Statements such as "It's never been done before" or "It will cost a fortune" are examples of: | 4 | Imposing | Feedback | Conflict generators | Communication blockers |  |  | 4 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Making sweeping statements like "It's never been done before" or "It will cost a fortune" leads to communication blockages. All other options do not lead to communication blockages.
260 | SINGLE | To achieve consensus all of the following can be used EXCEPT: | 4 | Avoiding self-oriented behavior | Looking for facts | Giving focus to problem and try solving it | Avoiding conflict |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Do not forget that EXCEPT is the key word. We cannot achieve consensus by running away or avoiding conflicts
261 | SINGLE | A communications management plan should include all of the following, EXCEPT: | 4 | Glossary of Common Terminology | Escalation List/Contacts | Person that will issue weekly reports | Risk Register |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | The Comms Management plan does not include Risk Register. It includes all the other options
262 | SINGLE | Most project managers spend about ___________ of their work time spent in communicating and engaging with stakeholders. | 4 | 0.7 | 0.4 | 0.8 | 0.9 |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Remember the question includes BOTH communicating & engaging with the stakeholders, hence 90% is the right answer
263 | SINGLE | All of the following are important for the project manager to effectively manage communications within the project team EXCEPT: | 4 | Promoting harmony and trust between team members | Ensuring that feedback occurs in both directions | Formalizing and controlling communication among the team members | Recognizing the importance of the interpersonal communication network |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Do not forget that EXCEPT is the key word. The PM cannot control the communication among the team members
264 | SINGLE | Status coordination and reporting is the PRIME focus of: | 4 | Portfolio Manager | Program Manager | Manager in a Projectized organization | Project Expediter |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Project Expediter is mostly involved in project status reporting rather than having complete authority or ownership over managing the project
265 | SINGLE | The best method of resolving conflict in a project is: | 4 | Withdrawal | Smoothing | Problem Solving | Compromise |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | Do not forget that BEST method is the key word. Problem solving leads to Win-Win solution that is long lasting & all the conflicting parties are happy
266 | SINGLE | The sender in the communication model is responsible for: | 4 | Exhibiting message in a favorable way | Ensuring the receiver agrees with the message | Making sure that the message is understood by receiver | Decoding message |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | Senders accountability is to ensure that the sent message is received & UNDERSTOOD by the receiver
267 | SINGLE | Existing contractor has withdrawn from the project after 3 sprints due to technical difficulties. A new contractor and his team have assembled in a conference room for an introductory meeting. What is the basic purpose of the communication? | 4 | Establishing a line of command | Outlining behavior and ground rules to new team | Introduction with teams on either side | Clarifying project goals and release plan |  |  | 4 | 1 | PMP | Process | Project Communications Management |  |  |  | Agile | As the new contractor has been on-boarded project goals & release plan has to be clarified in the introductory meeting
268 | SINGLE | Communication is a very integral part of Agile Project Management approach. A Scrum Master should try to remove all the barriers that can affect communication. Following are barriers to communication except: | 4 | Team members are on a planned leave | Clear communication channels are not available | Environmental factor is distracting | Difficulties with technical language |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  |  | Agile | Do not forget that EXCEPT is the key word. Planned leave is not a communication barrier whereas all other options are
269 | SINGLE | In High Fly Pvt Ltd the strict norms has led to the strong pressures within a group. The groups are impelled to conform to group norms at the expense of critical and innovative thinking. Which of the following terms best describes this pressure? | 4 | Groupthink | Group oppression | Group speak | Group grope |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  |  | Predictive | Compliance to the strict norms is creating extra pressure on the groups. This leads to curbing of innovative or critical thinking that leads to oppression
270 | SINGLE | The presence of communication barriers most likely leads to: | 4 | Increased conflicts | Reduced productivity | Increased stress | Low morale |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | More the communication barriers more conflicts can be expected. Team members do not get a chance to clear their inhibitions due to communication barriers
271 | SINGLE | The most common communication problem that occurs during negotiation is that: | 4 | Parties are trying to confront their personal interests | Either side may not be paying attention | Either of the side thinks that other is not enough knowledgeable | Parties has come for the negotiation with withdrawal attitude |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | We are looking for the MOST common communication issue. This usually happens when both the parties or one of them are not listening or paying attention
272 | SINGLE | Which of the following tools or techniques are used in the Manage Communication Process? | 4 | Communication skills, work results, and status reports | Performance reviews, performance reports, and project plan | Information management systems and communication methods | Communication management plan, project plan, and information distribution system |  |  | 3 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive | This is ITTO question. Information management system & communication methods are the TTs
273 | SINGLE | In an Agile project, an example of work performance data is: | 4 | Status of deliverables | Implementation status for change requests | Forecasted estimates to complete | Sprint Start Date |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Agile | Sprint Start date is the raw data (work performance data) where as other options are processed data that is work performance information or report
274 | SINGLE | A Project Manager, while working through activities and producing products, inevitably comes upon things that needs to be changed. These changes are recorded as: | 4 | Project Management Plan Updates | Change Requests | Work Performance Information | Project Document Updates |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Any deviations from signed off baseline that have to be initiated whilst producing project deliverables are recorded as Change Requests. These CRs will go through the change management process
275 | SINGLE | During project implementation the client interprets a clause in the contract to mean that he is entitled to a substantial refund for work recently completed. You review the clause and disagree with the client's conclusion. As the Project Manager which of the following actions should be taken? | 4 | Disregard the customer's conclusion and continue to process invoices interpretations and disputes | Advise the customer that ambiguous information in contract is always interpreted in favor of the contractor | Immediately correct the clause to remove any possible misinterpretation by the customer | Document the dispute and refer to the provisions of the contract that addresses the same |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | First action to take during a conflicting point of view is to document the dispute and analyze the situation (by referring to the signed-off documentation)
276 | SINGLE | All of the following statements are true about defect repairs EXCEPT: | 4 | Defect repairing is done when a project component does not meet the requirements or specifications | All the defect repairs must be documented in change log | Defects might be discovered while conducting quality audits | Defect repairs can result due to the scope change at later stages |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  |  | Predictive | Do not forget that EXCEPT is the key word. Defect repairs are required as defects may occur despite quality assurance activities & they have to be kept out of customer's deliverables. Their cause is not due to scope creep at later stages
277 | SINGLE | Inputs to Perform Integrated Change Control include: | 4 | Project plan, performance reports and lessons learned | Project plan, project reports and change request | Product plan, performance reports and change request | Project plan, work performance reports and change request |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | This is ITTO question. Refer to Inputs of Perform Integrated Change Control process
278 | SINGLE | Most effective power which a Project Manager can have is: | 4 | Reward and expert power | Expert and referent power | Legitimate and reward power | Legitimate and coercive power |  |  | 1 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | Project Manager has to earn the respect of the team which can be achieved through expert power & combining that with ability to reward good work leads to most effective power
279 | SINGLE | Least effective power is: | 4 | Reward Power | Expert Power | Coercive power | Legitimate Power |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | Coercive power is used when the team members are forced or coerced into doing the work. This is least effective
280 | SINGLE | Leaders, managers, and project managers use power to convince others to do task in a specific way. Which of the following is NOT the form of power? | 4 | Punishment Power | Legitimate Power | Referent Power | Dictator |  |  | 4 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | All other options EXCEPT Dictator is are forms of power
281 | SINGLE | Ramjet Pal is a Project Manager in Friendly Access Bank. He is responsible to handle an IT project in the bank. He notices that a team member of a project always try to dominate people and distract them by his comments. Which power can be used here by him? | 4 | Expert Power | Reward Power | Legitimate Power | Referent Power |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  |  | Predictive | Ramjet Patel has to use his power as the PM and let the team member to mend his way failing which leads to insubordination to the PM. This is a legitimate power the PM wields
282 | SINGLE | Punishment power is also known as: | 4 | Coercive power | Penalty Power | Formal Power | a and b |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Punishment includes both Coercion & penalty
283 | SINGLE | Referent power is: | 4 | Exerted when power comes about as a result of the influencer's position | Obtained by the influence obtained by association with higher authority | Exerted when employees are threatened with consequences if expectations are not met | Exerted when influencer is knowledgeable about the subject or has special abilities that make him expert |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Referent power is obtained by the association with people with higher authority. All other options are not associated with referent power
284 | SINGLE | Among the following which of the roles is LEAST appropriate for the Project Manager? | 4 | Communicator | Team leader | Integrator | Technical consultant |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive | LEAST is the keyword. Technical consulting is the role of a SME (Subject Matter Expert) & all other are project manager roles
285 | SINGLE | Which of the following are relatevely higher motivation factors in Motivation Hiereachy? | 4 | Salary | Recognition | Personal aspirations | Working conditions |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Recognition is the highest motivation element among all the options. Refer to Maslow's pyramid
286 | SINGLE | Abraham Maslow, in Maslow's hierarchy of needs, has theorized that humans have ___ basic needs. | 4 | 5 | 7 | 4 | 6 |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive | Refer to Maslow's pyramid: Humans have 5 basic needs
287 | SINGLE | Where do successful project managers generally spend their maximum time? | 4 | Updating the Project Management Plan | Communicating | Working Scheduled Activities | Managing Risks |  |  | 2 | 1 | PMP | People | Project Stakeholder Management |  |  |  | Predictive | The PM spends most of the time in communication (>80%)
288 | SINGLE | A number of deliverables were submitted to the buyer as part of the project. Where would the project manager find documentation on the requirements for formal deliverable acceptance and how non-conforming deliverables can be addressed? | 4 | In the SOW. | In the lessons learnt document. | In the deliverable release note. | In the contract. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Key word here is BUYER. Hence there has to be contract that outlines deliverables & their acceptance criteria
289 | SINGLE | Which of the following BEST describes the main purpose of the project charter? | 4 | It authorizes the project manager to work on the project | It identifies the sponsor and describes his or her role on the project | It contains a list of all activities to be performed | It describes the initial scope of the work |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | This basic definition of the Project Charter is outlined in option # 1. We have to select the BEST option though other options may be partially correct
290 | SINGLE | Which of the following is TRUE about iterative approach? | 4 | Shrilly has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. | In a project environment which is very uncertain or where there is a lot of rapid change, this approach is BEST recommended. | None of the above |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Agile | In iterative approach, uncertain environment & rapid changes can be effectively managed
291 | SINGLE | James is working as a program manager in Earth Construction Pvt. Ltd. He has just received statement of work as a part of winning the bid from its customer. What is the first thing he should do? | 4 | Estimate Costs | Develop Project Charter | Develop Project Management plan | Control Schedule |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Key word is "just received the SoW". That means the project is not initiated yet & the Project Charter has to be created & signed-off next
292 | SINGLE | "Statement of Work" is input to? | 4 | Project Plan | Project Schedule | Risk Register | Project Charter |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | SoW is the clear input to the Charter. SoW is clearly not an input to other options
293 | SINGLE | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Statement of Work (SOW) can be part of which of the following document? | 4 | Business Need | Project Charter | Request for Information | All of the above |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | SoW is needed to create the Project Charter & SoW is not part of it. RFI is the other document that can have SoW as a part
294 | SINGLE | Thomas is a project manager working on a construction project near New York City. He has just received Statement of work (SOW) for a new internal project. Who provides the SOW for internal Project? | 4 | Project Manager | Project Initiator or Sponsor | Contractor | All of the above |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Sponsor or the Project Initiator clearly knows about the work required to be accomplished. Hence they are accountable to get the SoW done. (They may prepare or get it prepared by SMEs)
295 | SINGLE | You are working as a manager in a chemical firm. Your company has received a Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. The SOW references: | 4 | Business Need | Product Scope Description | Strategic Plan | Constraint |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Low storage temperature is a constraint under which the project's product has to be delivered. It is neither a business need nor product scope as this just an attribute of the deliverable
296 | SINGLE | You are working as a manager in a chemical firm. Your company has received Statement of Work (SOW) containing order of delivering a chemical that is highly sensitive at room temperature and requires -10 degree centigrade temperature for storage. You need to create a document that provides necessary information from a business standpoint to determine whether a project is worth the required investment. What document are you preparing? | 4 | Business Case | Statement of Work | Bid Document | All of the above |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Business Case provides justification for taking up the project. This also includes feasibility analysis
297 | SINGLE | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case is a document which provides: | 4 | The necessary information from business standpoint to determine whether or not the project is worth the required investment. | The necessary information about what all work he have to do in project and what not to do. | Both A & B | Statement of Work |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis
298 | SINGLE | Nick is a project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. In Business case document, one of the Project selection methods is mentioned as: | 4 | The business need | Cost Benefit Analysis | Bid Document | Both B & C |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Business Case provides justification for taking up the project. This also includes feasibility & Cost/Benefit analysis. The question is about project selection method: Cost/Benefit analysis is done among different alternatives
299 | SINGLE | Project Initiation's main objective is: | 4 | Develop a broad scope Statement of Work. | Create a mission statement. | Define cost and timelines broadly. | Commit organization to start the next phase. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning
300 | SINGLE | Nick is a Project Manager working in ABC SOFT CORP LTD. He has been told to work on a new external project and has just received Project Statement of Work. Further, he is told to provide Business Case document by this weekend. The Business case may be created as a result of which of the following? | 4 | Technological Advancement | Ecological Impacts | Both A & B | Change Control Meetings |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Business Case provides justification for the project, hence both technological advancement & ecological impacts as a project outcome has to be analyzed for the justification
301 | SINGLE | Nick is a Project Manager working in ABC SOFT CORP LTD. He is working on an External Project. Which document he should refer while creating a Project Charter? | 4 | Contract Document | Request for Information | Request for Bid | All of the above |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | RFP/RFB & all associated contract documents should be referred whilst creating the SoW
302 | SINGLE | Project Initiation's main objective is to: | 4 | Develop a broad Scope Statement of Work. | Develop milestones and cost broadly. | Create a Mission Statement. | Commit organization to start the next phase. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Among all the options, project's are initiated to get the commitment about starting the next phase of the project. Developing scope & determining costs & timelines are done in planning
303 | SINGLE | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You are taking help of Subject Matter Experts for creating Project Charter. You are using which of the following tool? | 4 | Expert Help | Expert Judgment | Expert SME | All of the above |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | SME inputs are considered as Expert judgement, i.e. judgement provided by SME. SME itself is an expert (no Expert SME). It is not expert's help as you are collaborating with the SME
304 | SINGLE | You have recently joined as a Project Manager in a manufacturing company called CORP LTD in Australia. You have just received SOW (Statement of Work) Document. What tools can be used to create the Project Charter? | 4 | Expert Judgment | Change Control Meetings | Delphi Technique | Focus Groups |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Refer to the ITTOs (Inputs, Tools Techniques, Outputs) of the "Develop Project Charter" project management process
305 | SINGLE | In a project you are presented with the following four options. Which project should you select? | 4 | Project A with an opportunity cost of $100,000 | Project B with a Benefit Cost Ratio of 0.75 | Project C with IRR of (-) 5,000 | Project D with NPV of 10,000 |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | IRR is negative & Benefit Cost Ratio is less that 1, hence options are not feasible. Positive NPV is the only feasible option, hence select this project
306 | SINGLE | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He is currently working on a document which includes initial requirement that satisfies the stakeholder's need and expectations. Which of the following document he is creating? | 4 | Scope Document | Project Charter | Project Plan | Both A & B |  |  | 2 | 1 | PMP | Process | Project Stakeholder Management |  |  |  | Predictive | "Initial requirement" is the key word here. Project Charter outlines this need
307 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is in the initial stages of the Project and is documenting business needs, current understanding of the customer needs, high level requirements, high Level risks and high level project description. Which document is he working on? | 4 | Project Charter | Project Plan | Both A & B | Scope Document |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | "Initial stage" is the key word here. Project Charter encompasses all the actions outlined in the question
308 | SINGLE | Rick has been promoted to Project Manager. He has been assigned a work on a new upcoming project. He needs to find the business benefits and as to why this project started. Which document should he refer to? | 4 | Project Plan | Project Charter | Both A & B | Scope Document |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Project Plan or scope statement do not contain the business benefits or justification of the project delivery. Project Charter is the only artefact that outlines it
309 | SINGLE | Rick is a Senior Manager. He has been assigned to work on a new upcoming project. He finds that the project cost for doing this is justified and will be a success. He is documenting the same. What else he needs to write in that document? | 4 | Measurable Project Objectives | Project Title and Description | Project Manager Assigned and Authority Level | All of the above |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Rick is creating the project justification document (Business Case). It has all the sections outlined in the first three options
310 | SINGLE | Rick is a senior manager. He has been assigned to work on a new upcoming project. He is currently documenting Project Manager Assigned and Authority Level, High Level Projects Risks. What else he need to write in that document? | 4 | Measurable Project Objectives | Project Approval Requirements | Stakeholders Requirements | All of the above |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Rick is creating the project charter. It has all the sections outlined in the first three options
311 | SINGLE | Company "A," which is highly profitable, is willing to spend $250,000 to develop a proposal for a $1 billion contract; Company "B," which is operating at break-even, is not interested to bid. This is defined as: | 4 | Expected Monetary Value | Sources of Risks | Potential Risk Events | Organization Risk Tolerances |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Organization B is at huge Opportunity Cost risk. Organization A can tolerate the huge risk as it is a highly profitable company
312 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much more money the project would need to complete its objectives. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate to Complete (ETC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 7,89,286.00 | Her sponsor has asked for Estimate to Complete which is INR 7,89,286.00 |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 ETC=EAC-AC=7,89,286
313 | SINGLE | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has been already spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the budget at completion. Please specify which statement is TRUE? | 4 | Her sponsor has asked for To-Complete Performance Index (TCPI) which is 1.3 | Her sponsor has asked for To-Complete Performance Index (TCPI) which is 0.7 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 7,89,286.00 | Her sponsor has asked for Estimate to Complete which is INR 7,89,286.00 |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3
314 | SINGLE | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likelihood of the project being able to meet the estimate at completion. Please specify which statement is TRUE? | 4 | Her sponsor has asked for To-Complete Performance Index (TCPI) which is 0.7. | Her sponsor has asked for To-Complete Performance Index (TCPI) which is 1.3. | Her sponsor has asked for Estimate at Completion (EAC) which is INR 7,89,286.00 | Her sponsor has asked for Estimate to Complete which is INR 7,89,286.00 |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 TCPI=(BAC – EV)/(BAC – AC)=552500/425000=1.3
315 | SINGLE | Manjushree is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor wants to know the likely variance for the project based on current performance. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Variance at Completion (VAC) which is INR -3,91,284.00 | Her sponsor has asked for Variance at Completion (VAC) which is INR 3,64,286.00 | Her sponsor has asked for the Cost variance which is INR -1,27,500.00 | Her sponsor has asked for the Schedule Variance which is INR - 42,500.00 |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 EAC=BAC/CPI=12,41,284 VAC=BAC-EAC=-391284
316 | SINGLE | Jasmine is working in a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. What is the BCWP of the project? | 4 | INR 3,40,000.00 | INR 4,25,000.00 | INR 2,97,500.00 | None of the above |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 BCWP (Budgeted Cost of Work Performed)=EV=2,97,500
317 | SINGLE | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Cost Variance for this project is INR -1,27,500. Which statement is TRUE? | 4 | The Project is under budget. | The Project is over budget. | The project is exactly on budget. | The project is ahead of the schedule. |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 CPI=EV/AC=0.7 As the CPI is less than 1, it is over budget by 30%
318 | SINGLE | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. The Schedule Variance for this project is INR (-) 42,500. Which statement is TRUE? | 4 | The project is under budget. | The project is on budget. | The project is ahead of the schedule. | The project is behind the schedule. |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | BAC=8,50,000 EV=2,97,500 PV=3,40,000 AC=4,25,000 SPI=EV/PV=0.875 As the SPI is less than 1, it is behind schedule by 12.5%
319 | SINGLE | Your project has a CPI of 0.59. Which statement is TRUE? | 4 | The project is earning only INR 0.59 for every Rupee 1 spent. | The project is over budget by 59%. | The project costs 59% of the initially planned budget. | The project is progressing at 59% of the rate originally planned for schedule. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | CPI (Cost Performance Index) is the rate of return / rate at which the project is getting returns. CPI of 0.59 indicates only 0.59 paise is being earned
320 | SINGLE | Your project has an SPI of 0.59. Which statement is TRUE? | 4 | The project is earning only INR 0.59 for every Rupee 1 spent. | The project is over budget by 59%. | The project costs 59% of the initially planned budget. | The project is progressing at 59% of the rate originally planned for schedule. |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | SPI (Schedule Performance Index) measures the timeline percentage of project progress.
321 | SINGLE | You are working on a project where the SPI is 0.875 and the planned value is INR 3,40,000.00. What is the schedule variance? | 4 | INR -1,27,500.00 | INR 1,27,500.00 | INR -42,500.00 | INR 42,500.00 |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | SPI=0.875 PV=3,40,000 EV=SPI*PV=2,97,500 SV (Schedule Variance)=EV-PV =-42,500
322 | SINGLE | You are working on a project where the SV is INR -42,500.00, actual cost is INR 4,25,000.00 and PV is INR 3,40,000.00. What is the CV? | 4 | INR -1,27,500.00 | INR 1,27,500.00 | INR -42,500.00 | INR 42,500.00 |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | EV=SV+PV=297500 CV=EV-AC=-127500
323 | SINGLE | You are working on a project where the SV is INR -42,500.00, CV is INR -1,27,500.00 and PV is INR 3,40,000.00. What is the Actual Cost? | 4 | INR 42,500.00 | INR 4,25,000.00 | INR 2,97,500.00 | None of the above |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | SV=EV-PV EV=SV+PV=2,97,500 AC=CV+EV=425000
324 | SINGLE | Phyla has been asked to calculate the CPI of the project. Which tool should be BEST for her? | 4 | Earned Value Management | Forecasting | Both A & B | None of the above |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | EVM is the right tool to used to compute CPI. Forecasting will give EAC & TCPI, but not CPI
325 | SINGLE | Phyla is monitoring the status of the project to update the project budget and managing changes to cost baseline. Which process is she in? | 4 | Estimate Costs | Determine Budget | Control Costs | Executing Process |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | Tracking & monitoring project budget is done in controlling process
326 | SINGLE | Tools and techniques for performance reporting include all of the following EXCEPT: | 4 | Trend Analysis | Earned Value Analysis | Information Distribution Tools and Techniques | Decision Tree Analysis |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | EXCEPT is the keyword. Decision Tree Analysis (DTA) is a decision making tool rather than a performance reporting tool. All other options are performance reporting tools
327 | SINGLE | Which formula you should use to calculate TCPI if you want to find out the likelihood of the project being able to meet the budget at completion? | 4 | (BAC-EV)/(BAC-AC) | (BAC-EV)/(EAC-AC) | Both A & B | None of the above |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive | The question states "to meet BAC" & not "to meet EAC". Hence option-1 is the right answer
328 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. Nick as a project manager checks all the work in order to see if the vendors are performing their part of work properly or not. What can be BEST described as to what he is doing? | 4 | Contract Reviews | Performance Reviews | Performance Reporting | Claim Controlling |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Nick is reviewing the performance of the motherboard configuration. Nick is not reporting the performance, but reviewing the performance. He is not reviewing the contract terms & conditions either
329 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the motherboard is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration. Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs a better way to manage information about how the vendor is performing. Which of the following do you think could have helped Nick? | 4 | Inspection and Audits | Payment System | Records Management System | Claims Administration |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Records management system provides the real-time or up to date status of the deliverables or procurement items The vendor is not claiming anything here, so Claims Admin & Payment System are not the right choices
330 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The sponsor of the project asks Nick to let him know what is the status of the motherboard configuration? Nick had no information about it and had to wait for the vendor's response which came after 3 hours and then only he could update the sponsor. Nick realizes that he needs to make sure that the vendor is delivering the quality they promised. Which of the following do you think could have helped Nick? | 4 | Inspection and Audits | Payment System | Records Management System | Claims Administration |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Nick has to do a procurement audit to ensure that the procured deliverables are as per the terms & conditions outlined in the contract. These quality of deliverables, on-time delivery, invoicing, incentives/penalties, etc.
331 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. After couple of days Nick receives an email from the Accounts Department that due to an Accounting Software error, the vendor has been paid twice as 2 invoices were generated for the same batch of work. Which of the following do you think could have helped Nick? | 4 | Inspection and Audits | Payment System | Records Management System | Claims Administration |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | All vendor payouts are tracked by the Payment System. Question is specifically about payments, hence other option do not hold good.
332 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required material. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now, however the seller says that they are supposed to deliver the same within 4 weeks. It raises disputes between the 2 parties. Which of the following do you think could have helped Nick? | 4 | Inspection and Audits | Payment System | Records Management System | Arbitration |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | As there is a dispute between buyer & seller over contract terms, Arbitration is the right option from which as amicable resolution can be expected. Both the conflicting parties will abide by the arbitration decision
333 | SINGLE | Nick is working on a project in an organization which manufactures laptops. His company has introduced a new range of light weight laptops. In this laptop the mother board is configured and built by an external vendor. The vendor has also delivered the first batch of the required materials. Nick's company has accordingly paid the vendor for the first batch. The next batch is supposed to be delivered within 2 weeks from now. Everything is going fine, however, the sponsor is not happy with Nick and his team as he has no updates about what is happening in the project. Which of the following do you think could have helped Nick? | 4 | Inspection and Audits | Performance reviews | Records Management System | Performance Reporting |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Nick & his team do not have proper control or governance over the project. They are not pro-actively tracking project progress. If they had done proper performance reporting, then the situation would have been better
334 | SINGLE | Which of the following is NOT a part of Control Procurements? | 4 | Understand the legal implications of your actions. | Manage interfaces among sellers. | Make payments. | Perform a procurement audit. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | NOT is the keyword. Procurement audits are done during contract administration & not during controlling procurements
335 | SINGLE | Jasmine records all transactions and maintains the Record Management System during the Control Procurement Process. Which of the following is NOT required to be recorded? | 4 | Proposal | Project Statement Of Work | Terms and Conditions | Negotiation Process |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Negotiation process & formalities are finalized & baselined during contract signature/contract awarding. It is not documented during the control procurement process
336 | SINGLE | What is/are the main difference(s) between Performance Review and an Inspection? | 4 | Performance review is about the work while Inspection is about the deliverables and products. | Performance review is done when the buyer wants the seller to perform certain quality control and Inspection is done when the buyer wants to make sure that the products produced by the seller meets the standards. | Both A & B. | None of the above. |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Both options 1 & 2 outline the major differences between performance reviews & audits
337 | SINGLE | Petal has outsourced a work package of her project to an external vendor. What should be her next step? | 4 | Conduct Procurement | Close Procurement | Control Procurement | None of the above |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive | Keyword is "outsourced". As the procure is in place, Petal has to control procurements next
338 | SINGLE | A claim can be resolved between both parties through a _________ before it is escalated to lawsuit. | 4 | A legal notice. | Stopping to deliver the products/services by the seller or stopping to make payments by the buyer. | Closing the deal then and there. | Alternative dispute resolution. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Arbiration is the best option to resolve buy-seller disputes. This is done through alternate dispute resolution techniques. Sending legal notices or stopping delivery will only aggiviate the situation
339 | SINGLE | When should one use Inspection and Audit? | 4 | When the buyer wants to make sure that the product or service is actually meeting the standards. | When the buyer wants to make sure that the seller is performing as per agreed contract terms. | Both A & B | None of the above. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Procuement audits are conducted to ensure that the procured product/service meets the agreed standard
340 | SINGLE | When should one use Performance Review? | 4 | When the buyer wants to make sure that the product or service is meeting the standards. | When the buyer wants to make sure that the seller is performing as per agreed contract terms. | Both A & B | None of the above. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Performance reviews are done to ensure that the performance of the seller is as per the contract
341 | SINGLE | Why is Performance Reporting necessary at Control Procurement process? | 4 | So as to enable the buyer to make sure that the product or service is meeting the standards. | So as to make sure that the seller is performing the agreed quality control. | So as to provide the management with information about how effectively the seller is achieving the contractual objectives. | None of the above |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Performance reviews are like appraisals for the sellers. It is to measure the level of contractual obligations of the seller
342 | SINGLE | Which of the following is TRUE? | 4 | Claims are always documented. | Claims are not necessarily be always documented. | Claims are always settled through Legal action. | Claims are always settled through mutual negotiation. |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Claims have to documented to ensure that all claims are reviewed & honoured. If they are documented, then there are chances that the claims may be misplaced or forgotten
343 | SINGLE | Payments to sellers should always be made according to the _______. | 4 | Buyer's convenience | Seller's convenience | Project Management Plan | Contract Terms and Conditions |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | All payments are governed by the contract terms & conditions. It helps to main cordial buyer-seller relationship. Payments are not governed by conveniences of the involved parties
344 | SINGLE | Petal has replaced Jack as a project manager in an interior designing project. The painting work in the project is being done by ALF Interiors which has been a vendor of Petal's organization for last 3 years. However, Petal wants to make sure that whether she should outsource more work to ALF Interiors or not? Which should be of Petal's BEST help? | 4 | Inspections | ALF Interiors performance evaluation documentation | Performance reviews | Audits |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  |  | Predictive | Performance review of the seller will provide more information for Petal to make an informed choice about seller's performance. This in turn will help her to decide the extent of outsourcing
345 | SINGLE | Which one of the following techniques explains the effects of risk interdependencies? | 4 | Flow Chart | Fishbone diagram | Control Chart | Decision tree |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | Decision tree analysis outlines the interdependecies among the risks. All other options are used to identify or analyse risks
346 | SINGLE | Jacob is a project manager to provide computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00. Jacob has identified that the building owner is taking more than the expected time and the risk is now affecting the project schedule and the probability of it is now 100%. What is the impact of the same on the project? | 4 | Schedule delays that can also grow if the risk is not solved quickly | The EMV will be USD -3,00,000.00 | Both A & B | None of the above |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | EMV = Probabiliy x impact amount = 1.00 x 3,00,000.00 Also there will be more schedule delays if the inspection is not completed quickly. Both A & B are correct here
347 | SINGLE | Jacob is a project manager to provide entire computerized system and internet connectivity in an old resort renovation project. Around 100 workstations will be installed, 200 network connections, 10 servers and 22 printers. They will be networked through LAN. All the risks have been identified and have gone through quantitative analysis. Also a contingency reserve has been created. One of the risks identified was "Building owner must inspect the work which could cause additional delays or rework, the probability of it was 0.55 and impact USD -3,00.000.00". The other risk identified was "The network printers need to be centrally located, but the cables should not be visible, with a probability of 50% and impact of USD -7,50,000.00". Jacob has identified that the cabling risk will actually cost USD 9,00,000.00. What is the impact of the same in the project if both the risk happens? | 4 | Schedule delays that can also grow if the risk is not solved quickly | The contingency reserve will be reduced by USD 12,00,000.00 | Both A & B | None of the above |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | When both the risks occur, then contigency reserve will be reduced by $3,00,000+$9,00,000=$12,00,000. There will also be schedule delays. Both A & B are correct here
348 | SINGLE | Perilya is a project manager in a software development project. After the completion of every milestone, she does identify new risks and also confirms that the risks are the risk register still apply to the project. Which tool is she using? | 4 | Risk Reassessment | Risk Audit | Technical Performance Measurement | Trend Analysis |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | New risks are identified only during risk reassments. Secondary risks & Residual risks are also identified
349 | SINGLE | Perilya is a project manager in a software development project. She checks to confirm that the software has all the features built in that she wanted. However, she identifies that one of the features is missing and realized that a new risk has come up - missing feature which was to be developed as per functional specifications. Which tool is she using? | 4 | Risk Reassessment | Risk Audit | Technical Performance Measurement | Trend Analysis |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | "Checks to confirm" is the key here. Perilya is conducting Technical Performance Measurement.
350 | SINGLE | Perilya is a project manager in a software development project. She asks her newly appointed risk expert Petal to relook at the risk response strategies. She identifies that few secondary risks that might be caused by the risk responses planned are missing. She updates the risk register accordingly. Which tool is she using? | 4 | Risk Reassessment | Risk Audit | Technical Performance Measurement | Trend Analysis |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | Petal is reviewing the Risk Management process. She is auditing the process & unearthing secondary and/or residual risks
351 | SINGLE | Perilya is a project manager in a software development project. She is going through all the risk events in the project and plans to implement a risk response that would cost INR 1,50,000. She also cross checks to make sure that she has enough money left to cover the rest of the risks that might happen in future. Which tool is she using? | 4 | Reserve Analysis | Risk Audit | Technical Performance Measurement | Trend Analysis |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | Perilya is reviewing the contingeny resrves burned on responding to known unknowns. She is conducting reserve analysis
352 | SINGLE | Which of the following is NOT done at Control Risks? | 4 | Look for the occurrence of risk triggers. | Monitor residual risks. | Evaluate the effectiveness of the risk management plan. | Plan risk responses. |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive | Risk responses are planned during Risk Response Planning & not durinf controlling risks. Residual risks, effectiveness of risk management plan are done during risk controlling
353 | SINGLE | The purpose of the review of deliverables and project performance at the conclusion of a project phase is to: | 4 | Determine how many resources are required to complete the project according to the project baseline | Adjust the schedule and cost baselines based on past performance | Obtain customer acceptance of project deliverables | Determine whether the project should continue to the next phase |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Phase End/Release End reviews would be done to analyze the feasibility and justification for project continuation. It will also be done during sprint retrospectives
354 | SINGLE | A project is considered complete when the : | 4 | SPI is 1 | CPI is 1 | The PV is equal to the AC. | The BAC is equal to the EV. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | The Project is complete when BAC(Budget At Completion i.e. Estimated Project Cost+Contingency Reserve) is equal to the EV(Budget value of actual work done) which means the budgeted work is completed.
355 | SINGLE | Each project phase is marked by completion of one or more: | 4 | Tasks | Milestones | Deliverables | Life cycles |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  |  | The Project is divided into phases based on key deliverable(s) that are to be delivered. The governance & tracking the progress of these key deliverables is the main purpose of having project phases.
356 | SINGLE | The project closing process is essential to overall project planning. What is considered one of the most important steps in closing the project? | 4 | Insuring that plans are produced to implement the project by phases. | Issuing work orders so that financial data can be collected. | Transition the lease of equipment to the owner | Satisfying the contractual obligations |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | The Project can be closed only after all the contractual obligations are fulfilled. The project cannot be closed even if any one contractual obligation is not fulfilled.
357 | SINGLE | Formal acceptance by the client or the sponsor of the project indicates that they have accepted the products of the project. This document should be signed off during which phase of the project? | 4 | Administrative closure | As the last task in the project plan | After the project is closed out | When requested by the program manager |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Formal acceptance is done only during Administrative Closure (Formally closed). During Scope Validation or UAT deliverables are tested against the acceptance criteria outlined in the RTM
358 | SINGLE | Historical records during close-out are useful to __________ and ____________ for future projects: | 4 | Predict trends, highlight problems. | Analyze successes, shortfalls | Analyze strengths, document results | Justify results, set standards |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Historical records including Lessons learned are use to highlight the issues and/or for trend predictions
359 | SINGLE | Part of the project closure process is to gain formal acceptance. From whom do you need to gain this formal acceptance? | 4 | The qualify director | The head of the project management office | Vice President Finance | The customer |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | It is the customer (or the core stakeholder that provided the product/service requirements) should provide formal acceptance/sign-off
360 | SINGLE | Which of the following would be the most appropriate thing to do during the closing process group? | 4 | Hold Inspections of work packages. | Do Project performance review. | Obtain formal acceptance of the project scope from the customer. | Perform Procurement audits. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project performance reviews are done during closure. All other options are done during monitor & control domain
361 | SINGLE | The customer on a project tells the PM that he has run out of money to pay for the project. What should the PM do first? | 4 | Shift more of the work to later in the schedule to allow for the customer to get the funds | Stop work | Release part of the project team | Call for a Steering meeting to discuss Next steps |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Key words are "which action is done first?". Steer Comm is the most appropriate body empowered to decide the further course of action
362 | SINGLE | The customer has accepted the completed project scope. However, the lesson learned required by the project management office have not been completed. What is the status of the project? | 4 | Complete and closed | Incomplete | Closed | All good to go |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project status is incomplete till all the activities / processes are completed
363 | SINGLE | All the following are always part of the close project/phase process EXCEPT: | 4 | Complete lesson learned | Updating the archives | Releasing the team | Performing closure of the outside contract |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Close Procurement is done in Control Procurement process that is in Monitor & Control domain. All other options are done during closure
364 | SINGLE | The project has been going relatively well, although the project scope has changed more than was expected. The project is now completing one of its phases. Of all decisions the sponsor must consider during an end-of-phase review meeting, the most CRUCIAL is: | 4 | Authorize the scope change for the next phase | Authorize the budget increases for the next phase based on scope changes | Decreasing scope to maintain the budge | Cancelling the project |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | The primary purpose of the phase end review is to check the project viability. Cancelling or killing the project is an option that has to be considered by the process, hence it is also called as "Kill Point"
365 | SINGLE | You have just completed the design phase for a client's project and about to enter the implementation phase. All the following need to be done except:- | 4 | Lesson learned | Updating records | Formal acceptance | Completion of the product features |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | This is a single negative question-key word is except. Product features are completed in implementation phase & not in design phase
366 | SINGLE | All the following are required to bring a project to closure except:- | 4 | Customer Acceptance | Procurement closure | Team appraisals | Raising Change Request |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | CRs cannot be raised during the project closure. Project cannot be closed even if a single CR is pending
367 | SINGLE | With a clear statement of work, a seller completes work as specified, but the buyer is not pleased with the results. The contract is considered to be:- | 4 | Null and void. | Incomplete. | Complete. | Waived. |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  |  |  | All work outlined in the SoW is completed, hence the contract is considered to be completed
368 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. You are currently checking the team performance. Which of the following is NOT an objective of developing a project team? | 4 | Improve the communication skills of the team for effective communication between team members | Improve the feeling of trust and agreement among team members in order to raise morale, lower conflict and increase team work | Create a dynamic and cohesive team culture to improve both individual and team productivity | Improve knowledge and skills of team members and to stop them from sharing knowledge and expertise |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key words is "NOT". Objective of team development is encourage team members to share knowledge &/or expertise
369 | SINGLE | As for any project, the project manager's responsibilities, consist of the four basic functions of _____________ | 4 | Thinking, planning, controlling, and monitoring | Planning, doing, briefing, and reviewing | Planning, controlling, tracking, and acting | Planning, organizing, leading, and controlling |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | All project responsibilities including planning, organizing, leading, and controlling are project manager competencies required for successful delivery of projects
370 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is concerned about improving team competencies, team member interaction, and overall team environment to enhance project performance. Which of the following would be LEAST helpful? | 4 | Issue Log | Project Staff Assignment | Human Resource Management Plan | Resource Calendars |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Issue log is not a tool/technique used to improve team competencies. It is used to track & monitor issues only
371 | SINGLE | Zaria is working as manager in pharmaceutical firm. His project is in Executing State. He is currently performing Develop Project Team Process. Which of the following is an output of the above process? | 4 | Team Performance Assessment | Human Resource Plan | Resource Management Plan | Resource Calendars |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | All other documents are NOT produced during this process. This is a direct ITTO question
372 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. You are organizing interpersonal skills training for your team members . Interpersonal skills is also known as: | 4 | Hard Skills | Soft Skills | Communication Skills | Ground Rules |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Interpersonal skills are always considered soft skills as they are not core technical skills
373 | SINGLE | Renée is a working as project manager in Muddy Pharmaceutical Pvt Company. She is concerned as one of her team members lacks sufficient knowledge on a scheduling software which they use to prepare schedules. Which of the following tools can be of BEST use? | 4 | Training | Interpersonal Skills | Recognition and rewards | Co-Location |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Training Renée on the scheduling tool is the best option here. R&R or co-location do not improve her tool skills neither does interpersonal soft skills
374 | SINGLE | Ronaldo has been assigned a new project that needs working on new technology that has never been used by the company, for any of the projects. Therefore, new skilled people are hired to work on new technology. Which of the following tool you can use to help individual team members work as a group together? | 4 | Training | Interpersonal Skills | Team-Building activities | Co-Location |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key words here are "work as a group". Team building is the only option here to help individual team members work as a group together.
375 | SINGLE | Conflict within a project team can be avoided with prior planning and by maintaining effective communications between the project manager and the team. The most important information for the project manager to convey to the team is ________. | 4 | The system of rewards that permits recognition of team members through monetary or nonmonetary awards | That top management will not be interfering with this project as it usually does with other projects | That key decisions have been made and how the key decisions impact the team | Clear, unambiguous goals as to where the project is headed |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | RASCI or RAM charts are most effective tools for project work assignment. Hence this is most important information to convey to the team. This will reduce if not completely avoid conflicts among project team members.
376 | SINGLE | Thomas is a Project Manager working on a construction project near New York City. This is the company's first project in the city so they have made acquisition of resources living nearby. Therefore, Thomas will be working with a new team members. Which of the following is NOT a stage of team development? | 4 | Adjourning | Forming | Norming | Selection |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Obviously Selection is not a team development stage. The stages are Forming-Storming-Norming-Performing-Adjourning
377 | SINGLE | Jonnie is working as a Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is working with new team members. Which of the following among the five stages of team development is a phase where team meets and learns about the project and about their formal roles and responsibilities ? | 4 | Forming | Storming | Norming | Performing |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Team members meet for the first time (in the project) and learn more about the project and their roles and responsibilities in initial stage (Forming)
378 | SINGLE | Roxanne is working as a Project Manager in a Ford Corp Ltd which is in process of designing a new two-wheeler. She is working with new team members. Which of the following among the five stages of team development is a phase where team begins to address the project work, technical decisions and the project management approach? | 4 | Forming | Storming | Performing | Adjourning |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Project approach & project work (including competing technical decisions) are intensely discussed in the Storming phase
379 | SINGLE | Muddy is working as a manager in an Export House who wants to develop an In-house software. Therefore, he has hired few developers, designers and testers on contract basis. Which of the following among the five stages of team development is a phase where team begins to work together and adjust work habits and behaviors that support the team? | 4 | Forming | Norming | Performing | Adjourning |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Ground rules are established team members will start adjusting the work habits to create a conducive work environment in Norming stage
380 | SINGLE | Muddy is working as an IT manager in an Financial Services company who are looking to upgrade desktop software on all computers. Therefore he had hired few system administrators & IT support staff on contract basis. He completed the project successfully. Which of the following among the five stages of team development is the phase where team completes the work and moves on from the project? | 4 | Forming | Departing | Performing | Adjourning |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Project completion is the key word here. Team is disbanded after project completion that is in the Adjourning stage
381 | SINGLE | Muddy is working as a manager in an Export House who wants to develop an In-house Software. In develop project team process, which of the following tool is concerned with establishing clear expectations regarding acceptable behavior by project team members? | 4 | Ground Rules | Co-Location | Team-Building activities | Performing |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Clear behavioral expectations are established that avoids favoritism or groupism among team members. These expectations that have to be complied with are called Ground Rules
382 | SINGLE | Jonnie is working as a Project Manager in a large multinational two-wheeler company which is in the process of designing a new two-wheeler. He is facing difficulties handling teams at different locations. Which of the following develop project team tool and technique he should use? | 4 | Ground Rules | Co-Location | Project Management Software | Performing |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Co-location is the most effective technique to develop teams from different geographical locations
383 | SINGLE | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. Whenever his team members meets certain deadline in advance, he takes them out for a dinner and give away small gifts to his team. This is an example of: | 4 | Ground Rules | Co-Location | Tight-Matrix | Reward and Recognition |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Rewarding team members for good performance is most effective technique to motivate them to complete the activities on or before targets. Recognizing them is form of shout outs in news letter or halls of fame is included in this technique
384 | SINGLE | The project usually has a high degree of conflict during its life cycle, and the Project Manager must be an effective manager of that conflict. The most common sources of conflict are ________. | 4 | Project office, functional divisions, field sites, and corporate offices | Scarce resources, scheduling priorities, and personal work styles | Team building, team integration, functional coordination, and customer coordination | Planning phase, implementation phase, execution phase, and close-out phase |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Easiest way to tackle this question is by elimination. All other options are not the sources of conflicts. Scarce resources, scheduling priorities, and personal work styles are the main sources of conflicts
385 | SINGLE | Ronaldo has been assigned new project that needs working on new technology that has never been used by the company before for any of their projects. Therefore, he arranged a training for his team members so they get used to the new technology. What is the output of the above process in description? | 4 | Project Staff Assignment | Team Performance assessment | Human Resource Plan | Resource Calendars |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | This is a twisted ITTO question. Training is the main tool/technique in "Develop Team" process. Output of this process is Team Performance assessment
386 | SINGLE | The key way for a Project Manager to promote optimum team performance in project teams whose members are not collocated is to:- | 4 | Exercise his/her power and authority | Establish a reward and recognition system | Obtain support of functional managers in other locations | Build trust |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | When team members are not collocated, there is a lack of trust among team members as they do not physically meet each other. Hence building trust among them is the key technique
387 | SINGLE | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. He used all the tools and techniques of the develop project team process. Which of the following is LEAST EFFECTIVE in evaluating team's performance? | 4 | Project Organization Chart | Reduced Staff turnover rate | Increased team cohesiveness where team members share information and experiences openly. | Improvement in competencies that help the team perform better as a team. |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Do not miss the key word "LEAST". Team's performance cannot be effectively assessed by creating an org chart
388 | SINGLE | In addition to improving the success rate for goal achievements, team building has many benefits for individuals, but one characteristic that is not a benefit of team building is - | 4 | Clear organizational structure | Clear aims / goals | Improved individual creativity | Improved monetory rewards |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Though rewards & recognition is a technique in Develop Team process, increasing ONLY monetary reward is NOT a clear benefit.
389 | SINGLE | A friend of yours is working as Project Manager in real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following process helps you to keep the team motivated towards the project goals? | 4 | Plan HR management | Acquire Project Team | Develop Project Team | Manage Project Team |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Team development is the effective tool to keep higher motivation levels and bump up team morale
390 | SINGLE | A friend of yours is working as a Project Manager in a real estate firm. Since you are a PMP certified professional and have 15 years of experience in construction, he asks for an advice. He says that he is not able to keep the team motivated. Which of the following Is MOST effective way to keep the team motivated towards the project goals? | 4 | Recognition and rewards | Training | Team building activities | Co-Location |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Look at all the options first. Amongst all options R&R is the most effective technique to motive the team members
391 | SINGLE | Russell is working as a Project Manager in KW.com which is a multinational IT firm. All of his team is located in a single room that helps him in better communication and help the team members build a sense of community. The room is called as: | 4 | War Room | Project Room | Help Room | Management Room |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | When entire project team is located in a single room, they get better visibility on the project performance. This command center is also War Room. (Clue: All other options do not make much sense anyway)
392 | SINGLE | Ken is managing a project where the morale of the team is very low. The team members have been on the project for more than a year and though the project is due to end in a few weeks' time, they do not know what is in store for them. What should Ken have planned better to avoid such a situation? | 4 | Bonuses at the end of the project | 360-degree feedback | Job rotation within the project | Release criteria |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | The key words here is " they do not know what is in store for them". This situation can be avoided by informing the team members about their release dates, so that they can plan for their further course of action or other projects
393 | SINGLE | A Project Manager needs to be forward-reaching in addressing the conflicts early and obtaining a consensus. However, it would be counterproductive to an attempted resolution of an issue if the Project Manager said, "________." | 4 | Let's work on it and try to find the root problem | Let's gather more information and then analyze it properly | I have another point for discussion if this is too difficult to solve now | I feel we can now come to agreement on this issue |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | The key words here is "counterproductive" (single negative). Option 3 is right here as the PM is trying to push the current conflict under the carpet.
394 | SINGLE | You are working as a manager in a computer hardware manufacturing firm. Your team members always listen to you because they know you are very good in managing the project and team. This is an example of which kind of power? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Expert power is exhibited here as the team members very well know that the Manager has a good reputation in managing projects. It is SME power
395 | SINGLE | Philip is working as a Project Manager for AUTOCARS PVT LTD. His team members always obeys him because they know he is among one of the dear ones of the CEO. The above is an example of which of the following powers? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Referent power is exhibited here as Philip is being respected only because of his association with the CEO
396 | SINGLE | Jessie has just started working on a new IT project that has zero float. She has met all the deadlines till now and every time she and her team has met the deadline, she has taken them for either lunch or dinner in nearby restaurants. The above is an example of which of the following powers? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Reward power is exhibited here as Jessie has the ability to reward her team for good performance.
397 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He has just assigned some task to one of his team leader. Which form of power has he used? | 4 | Expert power | Legitimate power | Reward power | Referent power |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key word here is "promoted". Rick is using formal or legitimate power as PM to get the work done.
398 | SINGLE | Thomas is a Project Manager working on a construction project near New York City. He finds that one of the wall with a window has not been built, as per the company's standard. So he asks his team to work on holidays and weekends and rebuild the wall. Which form of power has he used? | 4 | Expert power | Legitimate power | Punishment power | Referent power |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Thomas is using coercive power to get the work done on weekends. He is not providing any incentives or rewarding them for the weekend effort, hence is punishment power
399 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that people needs achievement, power and affiliation to be motivated. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation-Hygiene Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | This is a straight forward wording of McClelland's Achievement Theory wherein three elements - achievement, power and affiliation are required for team motivation
400 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. He recently read an article about motivating theories. He read that there are two types of managers one who trusts their team and other who do not. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation-Hygiene Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | "Two types of management theory" is the key give away here. The two types being X & Y, hence the correct option
401 | SINGLE | Michael is working as a manager in Printing Press of large printing house. He always keep an eye on his team as to what are they working upon and how are they performing etc. Which type of project manager is he according to McGregor's Theory X and Theory Y? | 4 | Theory X | Theory Y | Theory Z | None of the above |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Mike is trying to micro-manage team members' activities that is categorized as Theory X
402 | SINGLE | Ramie is working as a Project Manager in Four-Wheeler CORP LTD located in Japan. He always trust his team member and their ability to deliver quality and timely products. Which type of project Manager is he according to McGregor's Theory X and Theory Y? | 4 | Theory X | Theory Y | Theory Z | All of the above |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | "Trust" is the key word here. Theory Y managers always trust their teams and they usually follow "management by exception" principle.
403 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a project involving new technologies. He recently read an article about motivating theories. He read that it is difficult to motivate people unless hygiene factors like a paycheck and job security are already in place. Which of the following motivation theory did he read? | 4 | Maslow's Hierarchy of needs | Herzberg's Motivation Theory | McGregor's Theory X and Theory Y | McClelland's Achievement Theory |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Take away here is hygiene factor. Herzberg's theory outlines the hygiene factors
404 | SINGLE | Simpson is working as a manager in an Exhibition House working on a large scale event. He is currently tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance. Which of the following process is he currently in? | 4 | Plan HR management | Acquire Project Team | Develop Project Team | Manage Project Team |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Tracking team member performance , providing feedback, resolving issues and managing changes to optimize project performance are all part of managing project team. Develop project team is not an option here as it involves training & co-location & follows 5 stages of team development
405 | SINGLE | Ground rules are established to set clear expectations regarding acceptable behavior by the project team members. Whose responsibility is it to enforce ground rules? | 4 | The project manager | All project team members share the responsibility for enforcing the rules once they are established | The HR team | The project manager and senior team members |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key word here is "responsibility". All team members are responsible to follow the ground rules. PM & escalation to HR executive comes under "accountable" preview where they ensure that the ground rules are being followed.
406 | SINGLE | In building team confidence in himself/herself, a project manager should ________ with team members and avoid ________. | 4 | Set limited times and opportunities for discussions; social contacts | Practice what s/he preaches; social contacts | Encourage frank discussions; making promises | Encourage open conversations; politics |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Option 4 perfectly fills both the blanks. In all other options one or both of the sentences are not applicable to building team confidence. Having open conversations and avoiding politics will bring in more trust among team members and helps build team confidence
407 | SINGLE | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of BEST help? | 4 | Activity Resource Requirements | Resource calendars | Work Performance Reports | Training |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | By assessing & analyzing team performance reports, you can track team member performance. This will in turn let us know if any additional resources are required. All other options here do not help in tracking team member performance.
408 | SINGLE | You are working as project manager in ABC Constructions. You are currently trying to track team member performance and identify if there is any requirement of more resources. Which of the following would be of LEAST help? | 4 | Resource Calendars | Work Performance Reports | Team Performance assessments | Project Staff Assignments |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | All options other and the resource calendars will help in tracking team member performance. Resource calendars will only outline the resource loading patterns
409 | SINGLE | Win-lose rewards that reward a limited number of project team members (ex: Team member of the month) have the following effect: | 4 | They unfairly get bagged by the best of the team members | They help in inculcating a healthy competition amongst the team | They positively impact team cohesiveness | They negatively impact team cohesiveness |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key word here is win-lose reward. This will negatively affect the team cohesiveness. You will be tempted to select option-2, but it is applicable on win-win situations
410 | SINGLE | You are managing a project and an audit team wants to know where they can find information on training plans for the team members and certification requirements. This would be found in the: | 4 | Resource Breakdown Structure | HR Management plan | Staffing Management Plan | Work Management plan |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Staffing Management Plan outlines the staff training requirements and plans to fulfill the requirements. All other artefact options do not outline training plans
411 | SINGLE | As per Herzberg's theory, which of the following is not a motivating agent? | 4 | Recognition | Advancement in career | Responsibility | Salary |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Keywords here are "motivating agent". Salary is hygiene factor where as all other options are motivating agents
412 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with watching, what is happening and specifically talking to team members for understanding, how things are going on? | 4 | Observation and conversation | Project performance appraisals | Conflict management | All of the above |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | keywords to watch out here are "watching" & "talking". This clearly leads to the right option that is observations & conversation. Appraisals do not lead to understanding how things are going on, hence not an option
413 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is concerned with clarification of roles and responsibilities, constructive feedback to team members, discovery of unknown or unresolved issues, development of individual training plans, and the establishment of specific goals for future time periods? | 4 | Observation and Conversation | Project Performance Appraisals | Team Performance Assessments | Conflict Management |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Performance assessments do not outline training plans or provide constructive feed back, hence option-3 is not the right key. All the actions outlined in the question are performed only during appraisals, hence the right key. Obviously training plans and goal setting are not done during conflict management
414 | SINGLE | Russell is working as a Project Manager in KWSoft.com. He is currently executing the customer care project for a large BPO. Which of the following tools and techniques is useful for monitoring elements under discussion or in dispute between project team members? | 4 | Observation and Conversation | Project Performance Appraisals | Issue Log | Conflict Management |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Key give away here is "monitoring". Monitoring is not done during conflict management or appraisals or observations. Tracking & monitoring is done through Issue Logs
415 | SINGLE | When should a Project Manager get involved in resolving a conflict? | 4 | Immediately when Project Manager notices the conflict | If conflict escalates, the Project Manager should help to facilitate a solution | When conflict is about to occur | Project Manager should ignore the conflicts among team members |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  |  |  | Usually conflicts will get resolved without PM's involvement. PM should act only when it has been escalated to him/her
416 | SINGLE | Zaria is working as a manager in pharmaceutical firm. She is managing a 15 member team. Which of the following is NOT a valid Conflict Management Technique? | 4 | Force | Withdraw | Focus Groups | Avoid |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | This is very straight forward. Focus groups is not a conflict management technique. It is a data gathering technique.
417 | SINGLE | Which of the following is an appropriate management style to use when the project manager wants to encourage the staff to pool its knowledge to make the best decision possible? | 4 | Laissez-faire | Antipodal | Directive | Democratic |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Involving staff in decision making process is the democratic management style
418 | SINGLE | You are working as manager in a computer hardware manufacturing firm. You are managing a 25 member team and thus you have to handle a lot of conflicts. Which of the following is a conflict resolution technique? | 4 | Observation | Communicating | Avoid | Ground Rules |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | All options but "Avoid" is not a conflict management/resolution technique
419 | SINGLE | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and finding a lot of conflicts. Which of the following is NOT a conflict resolution technique? | 4 | Collaborating | Forcing | Smoothing | Observing |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | Observing is not a conflict resolution technique. Conflicts cannot be resolved by mere observation. All other options are used to resolve conflicts. Of course not all of them together.
420 | SINGLE | Ronaldo has just finished his project and has been assigned a new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which of the following is a conflict resolution technique in which there is win-win situation? | 4 | Collaborating | Forcing | Smoothing | Avoid |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Keyword here is win-win which is collaboration. Forcing is win-lose & smoothing & avoid are lose-lose situations
421 | SINGLE | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. He is working with a new team and is finding a lot of conflicts. Which if the following conflict resolution techniques incorporate multiple view points to come to a consensus? | 4 | Collaborating | Avoid | Smoothing | Compromising |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Collaboration involves analyzing multiple view points & forming a win-win resolution where all conflicting parties form a consensus
422 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique in which the parties retreat or postpone a decision on the problem? | 4 | Collaborating | Compromising | Smoothing | Withdrawal |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  |  |  | The conflicting parties are retreating or withdrawing from the conflicting situation.
423 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is managing a big team. Which of the following is a conflict resolution technique that emphasizes agreement rather than differences in opinion? | 4 | Collaborating | Compromising | Smoothing | Withdrawal |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | The conflicting parties are agreeing with each other rather than enforcing one party's decision on other party, hence it is smoothing. The parties are not agreeing for lesser tangible things as in compromising or not completely avoiding the conflict as in withdrawal.
424 | SINGLE | Philip is working as a Project Manager for AUTOCARS PVT LTD. There is a conflict between two members of the team. He pushes first member viewpoint over the other. Which type of conflict resolution technique is he using? | 4 | Collaborating | Compromising | Forcing | Withdrawal |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | This is a case of clear imposing one party's viewpoint on other conflicting party by force.
425 | SINGLE | Ronaldo has just finished his project and has been assigned new project that needs working on new technology that has never been used by the company before. Therefore, new resources have been hired. He is working with a new team and is facing a lot of conflicts. Which if the following is a conflict resolution technique in which there is win-lose situation? | 4 | Problem Solving | Compromising | Forcing | Collaborating |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  |  | Give away here is win-lose situation. Of all the options only forcing has win-lose resolution
426 | SINGLE | Jonnie is working as Project Manager in a Ford Corp Ltd which is in process of designing new two-wheeler. He is managing a big team and hence, needs to handle number of conflicts. Which of the following is the best way of conflict resolution? | 4 | Problem Solving | Compromising | Forcing | Withdrawal |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  |  |  | Problem solving involving multiple viewpoints and consensus brings in win-win situation for all the conflicting parties, hence it is the best
427 | SINGLE | Your company manufactures memory chips for workstation computers. Your project involves manufacturing a very high capacity memory chip of 128GB. You have worked on the same project two years ago to manufacture low capacity memory chip of 2GB. You are in 'DEVELOP PROJECT CHARTER' process. Which of the following inputs is least helpful? | 4 | The project statement of work documenting the characteristics of the project | Check historical information on the previous project manufacturing of 2GB capacity memory chip. This information could be helpful since this new project is similar in nature. | Enterprise environmental factors, such as stakeholders risk tolerances and marketplace condition | The project constraints and assumptions to make sure that any significant project risk can be identified and mitigated |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | "Least" is the keyword. As you were already involved in a similar project earlier, SoW is the last document that will help you in creating the Project Charter. All other options are very helpful in developing the Charter.
428 | SINGLE | Your project selection committee used a weighted scoring model and found that the desktop application development project, with a score of 57, should be selected over other competing projects. Which of the following is true? | 4 | Weighted scoring models are constrained optimization methods, which are used as a tool and technique in both the Initiating process group processes. | Weighted scoring models are benefit measurement methods, which are used as a tool and technique during the Develop Project Charter process. | Weighted scoring models are a type of mathematical model that can be used both for project selection and vendor selection. | Weighted scoring models are benefit measurement methods and are the least efficient method of project selection. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Option 2 is the BEST in this case as weighted scoring model is a T&T in Develop Project Charter process. Option-1 is incorrect as it is not used in "Identify Stakeholders" process. Options 2 & 4 are incorrect statements
429 | SINGLE | Consider the following projects with their expected IRR (Internal rate of return): Project A has an IRR of 25%. Project B has an IRR of 17%. Project C has an IRR of 31 %.Project D has an IRR of 16%. Which of the following will be a better project for the company? | 4 | Project A | Project B | Project C | Project D |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Project giving maximum returns (i.e. IRR) is considered to be better
430 | SINGLE | You are nearing the end of your project when additional requirements were demanded by a group of stakeholders. This has become a problem for you because you have not taken the time or cost into account in the project plan to perform these requirements. What is the best thing you can do to prevent such a problem in future? | 4 | Pay more attention to the stakeholder management | Review the charter more thoroughly, examine the business case for gaps. | Do a more thorough job of solicitation planning | Review the WBS dictionary more thoroughly, look for incomplete descriptions |  |  | 1 | 1 | PMP | Process | Project Stakeholder Management |  |  |  |  | Key sentence here is "group of stakeholders". So this group of stakeholders were not taken into confidence and engaged properly. Hence you would need to pay more attention to stakeholder management going forward
431 | SINGLE | Your management has decided that all the orders will be treated as "Projects". The Project managers will be required to update orders daily, resolve the issues, and ensure that the customer formally accepts the product within 30 days of completion. The revenue from the individual orders can vary from US $100 to US $150,000. The project manager will not be required to perform planning or provide documentation other than daily status. How would you define this situation? | 4 | Because each individual order is a "temporary endeavor", each order is a project. This is truly a project management. | This is a recurring process. | This is program management since there are multiple projects involved. | Orders incurring revenue over US $100,000 would be considered projects and would involve project management. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | The PM is not planning or creating exhaustive documentation for these orders. The activities are routine and repetitive (business as usual), hence it is a recurring process. It is not a program as the orders/projects are not inter-related. Options 1 & 2 describe true project management involving planning and all other PM domains. So they are not the options
432 | SINGLE | Velma has been assigned with the responsibility to write a document to identify the business need for a project and to include a description of the product . In addition, she has included a list of stakeholders and pre-assigned resources. What is the role of Velma in the project? | 4 | The project manager for the project or a company functional manager | A member of the project management team working as per the direction of the project manager | The sponsor or the project manager | A manager or executive in the organization who is higher in the corporate hierarchy than the project manager |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Project Sponsor is accountable for developing the problem statement involving identifying business need & developing product description. PM is accountable to identify stakeholders and resources. Hence Velma is playing the role of Sponsor and/or PM
433 | SINGLE | You are a project manager for the Oriental food airlines division. You're considering two different projects regarding food services on the airlines. The initial cost of Project Fish'n for Chips will be $800,000, with expected cash inflows of $300,000 per quarter. Project Picnic's payback period is six months. Which project should you recommend? | 4 | Project Fish'n for Chips, because the costs on Project Picnic are unknown. | Project Picnic, because Project Fish'n for Chips' payback period is two months longer than Project Picnic's. | Project Picnic, because Project Fish'n for Chips' payback period is four months longer than Project Picnic's. | Project Fish'n for Chips, because its payback period is two months shorter than Project Picnic's. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | We have to compare apples to apples. We need to compare payback periods of both projects. By doing the math, pay back period for project fish n chips is $300,000 per quarter and $800,000 can be recovered in 2 quarters & 2 months (8 months). It is given that project picnic's payback period is 6 months. So Fish n Chips takes 2 months longer to pay back.
434 | SINGLE | Suppose, you are appointed as the project manager for a new project and you have collected the necessary input information and delivered the project charter to the stakeholders. What should you do next? | 4 | Develop the preliminary project scope statement. | Get the project charter signed. | Start to create project plan | Start the initial project planning process. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project Charter (& the project) will not become effective unless signed. Next natural step after stakeholder approval is the signature on the Charter
435 | SINGLE | You are a project manager for Fit Cloth Line. Your selection committee has selected a project you recommended for implementation. Your project involves manufacturing a line of body fit shirts for different body types. Your project sponsor thinks you've really impressed the big boss and wants you to jump to manufacturing process right away. What is your response? | 4 | Require a preliminary budget to be established and a resource list be put together to alert other managers of the requirements of this project. This should be published and signed by the other managers who are impacted by this project. | Agree with the project sponsor because that person is your boss and has a lot of authority and power in the company. | Require a project charter to be written and signed off by concerned stakeholders before proceeding further. | Suggest that a preliminary scope statement to be written because this will outline the objectives of the project and it will greatly assist in the development of the scope statement in the planning processes. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project can NEVER start without a signed Charter. Charter is the required document though your boss or people with higher authority are happy
436 | SINGLE | Which of the following is true regarding IRR? | 4 | IRR is a constrained optimization method | IRR assumes reinvestment at the cost of capital. | IRR is the discount rate when NPV is equal to zero. | Both B&C |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Definition of IRR (Internal Rate of Return) is the discount rate when NPV (Net Present Value) is equal to zero.
437 | SINGLE | You've been hired as a manager for the "Rectification department" of Central Post office. The Rectification department is responsible for making necessary changes and remove the errors of customer accounts. This is a huge department, with several smaller departments that deal with specific accounts, such as personal data and Commercial details checking. You've received your first set of management reports and can't understand the information provided in it. Each department appears to be using different techniques to audit their work and record the data for the management report. You request a project manager from the PMO to come down and get started right away on a project to streamline this process and make the data and reports consistent. This project has come out as a result of which of the following? | 4 | Customer request | Technological advancement | Business need | Legal requirement |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | This is pure business need of the CPO. It is neither legal or customer requirement.
438 | SINGLE | You have been assigned a new project in ABC Corp. You have a good rapport with sponsor and senior management. Your senior management and sponsor have asked you to start project immediately. What is your response? | 4 | Suggest that a preliminary scope statement to be written. | Suggest that a project plan should be written. | Start project immediately because your senior management is asking the same. | Requires a project charter to be written and which needs to be signed off by all stakeholders before proceeding further. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project Charter is a MUST to initiate the project. As the Sr. Mgmt. & the sponsor have requested you to start the project immediately, prepare the Charter ASAP & get it signed-off
439 | SINGLE | You work for a large, paint manufacturing plant. Your organization has planned to launch a new project to be released as an overseas product line. This is the company's first experience in the overseas market, and it wants to make a big splash with the introduction of this product. The project entails producing your product in a concentrated formula and packaging it in smaller containers than: | 4 | The project manager should document the project's objectives and business justification in a project charter document and recommend that the project should proceed. | The project manager should document the business need for the project and recommend that a feasibility study be performed to determine viability of the project. | The project manager knows that the project has a go ahead and should document the project's objectives and known deliverables in a scope statement document. | The project manager should document the high-level product requirements and stakeholder expectations in a scope statement. |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | This is a new entry for the organization in the overseas market (new market). Hence project viability has to be determined as the concentrated formulas has to be shipped & exported. Business need to expand to the overseas market also has to be determined
440 | SINGLE | You are a project manager for Dreamboats, Inc. You've been asked to perform a cost benefit analysis for two proposed projects. Project A costs $2.4 million, with potential benefits of $12 million and future operating costs of $3 million. Project B costs $2.8 million, with potential benefits of $14 million and future operating costs of $2 million. Which project should you recommend? | 4 | Project A, because the potential benefits plus the future operating costs are less in value than the same calculation for Project B. | Project A, because the cost to implement is cheaper than Project B. | Project B, because the potential benefits minus the implementation and future operating costs are greater in value than the same calculation for Project A. | Project B, because the potential benefits minus the costs to implement are greater in value than the same calculation for Project A. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Cost/Benefit for both the projects is 0.2. Hence it boils down to operating costs. Project B has lower ops cost of $2M against $3M for Project A.
441 | SINGLE | You're counting on the delivery from your vendor to arrive on Nov 30th and you are confident of the delivery of the deliverable as you have worked with the vendor several times before. This is an example of a/an | 4 | Constraint | Objective | Requirement | Assumption |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  |  | You are making an assumption (informed based on your experience with the vendor) that the delivery will happen by Nov 30th. This is not a constraint as the risks for late delivery is not mentioned in the question.
442 | SINGLE | Your selection committee is debating between two projects. Project A has a payback period of 18 months. Project B has a cost of $125,000, with expected cash inflows of $50,000 in the first year and $25,000 per quarter after that. Which project should you recommend? | 4 | Project A, because Project B's payback period is 24 months | Project A, because Project B's payback period is 20 months | Either Project A or Project B, because the payback periods are equal | Project A, because Project B's payback period is 21 months |  |  | 4 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Project B's cost of $125,000 can be recovered in $50K in first 12 months & 75K in 3 quarters i.e. 9 months. Total payback is 12+9=21 months
443 | SINGLE | Which of the following is the most complex type of project selection method? | 4 | Random choice method | Benefit measurement | Constrained optimization models | Optimistic random method |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Of all the project selection methods, Constrained optimization models is most complicated one as all the options have to optimized
444 | SINGLE | You are a project manager of Ventera organization. The company has to choose the best between two projects X and Y. Project X will take 3 years to complete and has NPV value $70,000 and Project Y will take 5 years to complete and has NPV value $60,000. What is the opportunity cost of selecting Project X? | 4 | $130,000 | $30,000 | $60,000 | $35,000 |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Project X is selected as it has higher NPV. Project Y is not selected which is the opportunity cost
445 | SINGLE | You are the project manager for Trigometrics International. Since you don't sleep much, you get a lot of project work done. You're considering recommending a project that costs $575,000; expected inflows are $25,000 per quarter for the first two years and then $75,000 per quarter thereafter. What is the payback period? | 4 | 39 months | 41 months | 40 months | 38 months |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | Project cost of $575K can be recovered in $200K in first 24 months & $375K in subsequent 15 months.
446 | SINGLE | You are a project manager for the "Jazz by the Bay" Club chain, with stores in 12 states. JBC is considering opening a new club in Kansas City or New Jersey. You have derived the following information: Project Kansas City: The payback period is 27 months, and the IRR is 35 percent. Project New Jersey: The payback period is 25 months, and the IRR is 32 percent. Which project should you recommend to the selection committee? | 4 | Project Kansas City, because the IRR is the highest | Project Kansas City, because the payback period is the longest | Project New Jersey, because the IRR is the lowest | Project New Jersey, because the payback period is the shortest |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  |  |  | When IRR & pay back periods are present, we usually go with IRR method as it gives a clear picture of % returns considering the future value of money
447 | SINGLE | You are working on a film production company, and the team has just completed the storyboard phase of the project. Which of the following is true? | 4 | The division of phases and determining which processes to use in each phase is called tailoring. | The storyboard phase marks the end of the Initiation process group, and the next phase of the project should begin. | The storyboard is a deliverable that marks the end of the phase. The deliverable must be approved before the next phase begins. | All the phases of this project together make up a program. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  |  | Project is divided into phases based on a major deliverable that has to be completed. Here Storyboard is the major deliverable & it has to be approved to progress into the next phase. During the phase gate project viability will be checked.
448 | SINGLE | ATEL is preparing to host its first annual 6K half marathon in Delhi. You have worked on a similar project for the organization two years ago, when it co-hosted the 10k walk through Mumbai Pune expressway. Which of the organizational process assets might be helpful to you for your new project? | 4 | The project SOW, which describes the high-level details of the run/walk program | The strategic plan, because you'll want to make sure the project reflects the overall strategic direction of the organization | Historical information on the 10K run project | The organization's PMIS system |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  |  | Predictive Approach | You are looking at the previous similar project information that was delivered by the same organization. The question is specifically asking about the OPAs, so a few options are not OPAs
449 | SINGLE | You are a project leader and have been asked to review the statement of work provided by customer. Which of the following is most often overlooked? | 4 | Customer-furnished equipment and facilities | Long-lead procurement items | Data item deliverables | Customer-imposed milestones |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | SoWs apart from other items will include deliverables. PMs & project teams will often tend to overlook this item as they will worry more about deadlines & milestones
450 | SINGLE | Which of the following is the logical flow of any project? | 4 | Planning, Initiating, Executing, Controlling, Closing | Initiating, Planning, Controlling, Executing, Closing | Planning, Initiating, Controlling, Executing, Closing | Initiating, Planning, Executing, Controlling, Closing |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | This is very straight forward. IPECC is the natural flow of domains in the project flow
451 | SINGLE | Which of the following is the correct order of the Monitoring & Controlling processes for Scope Management? | 4 | First Validate Scope and then Control Scope | First Control Scope and then Validate Scope | There is not enough information to decide. | Both happen simultaneously. |  |  | 4 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | Both the processes happen simultaneously as both include minimizing scope creep & gold plating
452 | SINGLE | Phyla has replaced Jack as the project manager of a telecom project. The project is going in a satisfactory manner in terms of time and budget. She is now using ETC and EAC calculations for future. ETC and EAC are used for? | 4 | Forecasting | Reporting | Manage Communications | Variance analysis |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | Jack was using EVM to measure project performance. It can be assumed that time & budget are satisfactory as SPI & CPI are below 1. So the next step in EVM is to look at forecasts that include EAC (Estimate At Completion), ETC (Estimate to Complete) & TCPI (To Complete Performance Index)
453 | SINGLE | Phyla is working as a Project Manager in an IT company. She is using historical data as the basis for estimating future outcomes of her project. Which forecasting methods is she using? | 4 | Time Series Methods | Casual Methods | Econometric Methods | Judgmental Methods |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | By definition: Time series forecasting is the use of a model to predict future values based on previously observed values. i.e. Time Series method includes forecasting future outcomes based on historical data (previous project data)
454 | SINGLE | Jasmine is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the budgeted value for the project work actually completed by this point of time. Which statement is TRUE? | 4 | Her sponsor has asked for the Planned Value which is INR 3,40,000.00 | Her sponsor has asked for the Earned Value which is INR 3,40,000.00 | Her sponsor has asked Earned Value which is INR 2,97,500.00 | Her sponsor has asked for Planned Value which is INR 2,97,500.00 |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | Key words here are "work actually completed" which means EV. Here is the math: EAC = INR 8,50,000 PV=40% of 8,50,000 = INR 3,40,000 EV=35% of 8,50,000 = INR 2,97,000 AC=INR 4,25,000
455 | SINGLE | A project manager discovers a defect in a deliverable which is due to be submitted to the customer today. The project manager knows the customer does not have the technical understanding to notice the defect. The deliverable meets the contract requirements, but it does not meet the project manager's quality standard. What should the project manager do in this situation? | 4 | Issue the deliverable and get formal acceptance from the customer | Note the problem in the lessons learned so future projects do not encounter the same problem | Discuss the issue with the customer | Inform the customer that the deliverable will be late |  |  | 3 | 1 | PMP | People | Project Quality Management |  |  |  | Predictive Approach | This is more moral & ethical that does not meet or exceed PM's quality standard.
456 | SINGLE | As a Project Manager for setting up a new manufacturing product line, part of your job is to determine if there are changes to the project scope, schedule, budget and technical requirements. These responsibilities are part of which process group: | 4 | Executing | Monitoring & Controlling | Planning | Closing |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | The question is updated (made the last word as "process group" instead of "process". Scope, budget, schedule, quality are all controlled in the M&C domain which includes measuring variance between baseline against actuals & trying to reduce it or keeping it under acceptable limits
457 | SINGLE | You are a project manager for developing a new desktop application software that will reduce time for document sharing. After you started working on the project, you thought of adding more reporting features, which the customer did not request. This is an example of:- | 4 | Good customer service | Scope creep | Due diligence | Gold plating |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | You are providing extra features or functionalities that the customer has not asked for nor it is part of Scope / WBS. You must be careful as gold plating often leads to other adverse impact on schedule, cost, quality, or scope
458 | SINGLE | You have been appointed as a project manager of a project which is in trouble and to resolve it, you held a meeting with the key stakeholders in your company for demonstration of the new product prototype. They came well versed with the product requirements and upon inspection, inform you that this prototype is not what the customer has specified. Your boss instructs you to get the prototype corrected and match the requirements with customer specifications before holding a demo with the customer. She also wants you to take a look at the project work. She is concerned that things aren't happening as planned and that the last project manager was not paying close enough attention to the project plan. Corrections might be needed. What knowledge area does this describe? | 4 | Project Time Management | Project Scope Management | Project Integration Management | Project Risk Management |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | Protype (or Proof of Concept) has to be built to demonstrate customer requirements being addressed/fulfilled. Requirements management, translating it to scope & controlling are processes of Scope Management KA
459 | SINGLE | A project manager's boss and the head of engineering department discuss change to a major task with the project manager. After the meeting, the boss contacts the project manager and tells him to make the change. This is an example of which of the following? | 4 | A project coordination position. | Management planning | A change control system | Management attention to scope management |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | The question is not outlining CR or CCB, hence it is not change control. Management (Head of Engineering & PM's boss) are clearly paying attention to scope details
460 | SINGLE | You are in the middle of a new product development project for your publicly traded company. You have discovered that the previous project manager made a US $3,000,000 payment and it was not approved in accordance with your company policies. The project CPI is 1.2. What should you do? | 4 | Bury the cost in the largest cost center available | Inform Project Sponsor | Put the payment in an escrow account | Ignore the payment |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  |  | Predictive Approach | Though project is under budget by 20% (CPI=1.2) at this point in time, You as PM are ethically & morally bound to report the breach of company policy
461 | SINGLE | You discovered that you have not planned for unknown risk events while preparing your risk responses. Now you are required to make adjustments to the project to compensate for known risk events. These adjustments are based on your past project experience when known risk events occurred and knocked the project off track. What should you do? | 4 | Document the unknown risk items and calculate the expected monetary value based on probability and impact that result from the occurrence | Apply a general contingency to try to compensate | Determine the unknown risk events and the associated cost, then add the cost to the project budget as reverses | Add a 10% contingency |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Changed "Unknow" to "known" risks in the question. Usually Contingent reserves are used to respond to known risks & management reserves are re used to respond to unknown risks. You cannot quantify the contingency reserve % as enough data is not provided. Hence is general contingency reserve is applied
462 | SINGLE | An organization is using non-linear probability impact scales for Risk assessment (ex: 0.05, 0.1, 0.2, 0.4, 0.8). What would this indicate? | 4 | The organization is relatively inexperienced in handling risks and wishes to take a cautious approach in handling risk. | The organization perceives that negative risk is a higher possibility than positive risk. | The organization is highly experienced in handling risk and has factored this into a model. | The organization wishes to avoid high-impact threats or exploit high-impact opportunities even if they have relatively low probability. |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | The PI (or Severity) value is weighted by impact. The nonlinear Impact score means that High and Very High impact risks are always overweighed to give a higher PI, whereas Low and Very Low impact risks are underweighted to give a smaller product.
463 | SINGLE | Which of the following is NOT true about configuration management ? | 4 | Configuration management describes the physical characteristics of the product of the project. | Configuration management requires acceptance decisions for all change requests to be made through the CCB. | Change control systems are a subset of the configuration management system. | Configuration management controls changes to the product of the project. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | This is a single negative question. NOT is the key word. CCB decisions do not come into play in configuration management
464 | SINGLE | As a project manager, you are performing activities like reporting and comparing actual project results against the project management plan, analyzing performance data and determining whether corrective or preventive action should be recommended, documenting all appropriate product information throughout the life of the project, gathering and recording project information, and monitoring approved change requests. Which project management process are you performing? | 4 | Perform Quality Assurance | Monitor and Control Project Work | Performance Reporting | Manage Stakeholders |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Key sentence here is "reporting & comparing actuals against plan" which is the main driver of Monitor & Control Project Work
465 | SINGLE | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she would have performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time as a result of this missed activity. All of the following statements are true EXCEPT:- | 4 | You've created a forecast, an output of the Monitor and Control Project Work process, using past performance to predict what the project's future condition might look like. | You should recommend a preventive action to reduce the possibility of future project performance veering off track because of this employee's failure to perform this activity. | You should recommend a corrective action to bring the expected future project performance back into line with the project management plan because of this employee's failure to perform this activity. | You might have to request a change to the project schedule as a result of this missed activity. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | The incident has already occurred, hence preventive action will apply in this context. EXCEPT is the keyword you should at which is a single negative
466 | SINGLE | You are a project manager for Rupert Technologies which develop custom CRM applications for several Call Centers. A schedule change has been requested. You know change is concerned with all of the following except which one? | 4 | Determining that a change occurred | Influencing causes of change | Verifying change | Managing change |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Except is the single negative keyword here. Verifying the change is not part of change management, but verifying the correct implementation of change is part of change management
467 | SINGLE | Identify where Comparing actual to baseline schedules, examining the statement of work, understanding cost overruns, and assessing risk occur? | 4 | Stakeholder meeting. | Resource leveling activity. | Project audit. | Contract negotiation. |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Examining SoW, understanding cost over runs, & assessing risks are key actions here. These are performed during audits. These actions are not done during any of the other options
468 | SINGLE | You are a project manager of BlindTrust Medical Technologies. You are experiencing lot of cases of scope creep in your project due to which your project seems to become never ending. For this purpose, all of the following scope management process can be utilized EXCEPT? | 4 | Create WBS | Scope reporting | Control Scope | Validate Scope |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | The question is to identify a non PM process & "Scope Reporting" is not a PM process in scope management process.
469 | SINGLE | According to the PMBOK, scope change control deals with all of the following EXCEPT: | 4 | Preventing changes from occurring | Influencing the factors that result in scope changes to ensure that changes are agreed upon | Determining that a scope change has occurred | Managing the true changes when and if they occur |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Nobody can prevent changes from occurring. We can only react when a change event has occurred.
470 | SINGLE | You are currently working as a project manager on a major telecom infrastructure project. Your project sponsor has asked you for changes to be implemented in current scope of project. What should you do? | 4 | Tell him that the scope cannot be changed after the baseline is set. | Prepare a scope change document. | Adapt a passive-aggressive stance and do nothing. | Advise him about the potential impact to the timeline and resource allocation. |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | First thing you do when a CR is raised (even requested by the Sponsor or customer) is to analyze the impact & report the potential impact to the change requestor
471 | SINGLE | In all of the following form change requests can occur EXCEPT: | 4 | Externally or internally initiated | Legally mandated or optional | verbal or written initiated | Informal |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Except is key word that should not be missed. CRs cannot be informal
472 | SINGLE | Which of the following BEST describes the impact of scope change requests? | 4 | Either expansion or shrinking of the scope | Only expansion of the scope | Only shrinking of the scope | It depends on the original scope of the project |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Scope change may be both increase in scope (expansion) and decrease in scope (contraction/shrinking)
473 | SINGLE | You are in the middle of the project when you got to know that because of a new government regulation you will need to change your project's product specifications. What should you do next? | 4 | Set up a meeting with the government to discuss this regulation. | Create a new project plan. | Create a new WBS. | Prepare a change request |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Government is the external stakeholder & the regulation (stakeholder requirement) is beyond your control. Raising CR is the first activity you perform.
474 | SINGLE | Which of the following statements are FALSE regarding Monte Carlo analysis? | 4 | Monte Carlo analysis uses Expected Monetory Value (EMV) calculations as one of its inputs | Monte Carlo is used to determine potential project outcomes by simulating the project under different scenarios | Monte Carlo analysis can be used during the Schedule Development and Quantitative Risk Analysis process | Monte Carlo is simulation technique that can help quantify risks associated with the project |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Monte Carlo as the name suggests is a risk simulation technique used to identify high probability event occurrence (as in gambling). It does use not EMV where finite number of variables are used (only events most od the time). FALSE is the single negative that should not be missed.
475 | SINGLE | Your customer has requested a change for which amendments in the contract are agreed upon and signed. For the requested changes, you have followed change control system and have modified the appropriate planning documents. As a result of the approved change, changes to the costs and schedule have also been made. Which of the following must occur next and why? Choose the BEST answer. | 4 | Baselines must be adjusted to reflect the new project costs and schedule. | Corrective actions are taken, which in turn generate change requests that are managed through the scope change control system. | Development and Quantitative Risk Analysis process | Lessons learned are documented so that future projects take into consideration the impact of the change to this WBS. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | You do not make any changes to project docs unless the CR is approved by the CCB. The question outlines that the CR is approved and appropriate planning docs are updated. Next clear step is to update the baselines.
476 | SINGLE | Variance analysis , trend analysis and earned value management techniques are:- | 4 | Quality control tools and techniques | Performance reporting techniques | Process analysis techniques | Cost benefit analysis techniques |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive Approach | Variance, trend, or EV uses metrics that outline project performance. QC may use variance or trend, but not EVA. Cost Benefit is used mostly in cost management
477 | SINGLE | What should the project manager be most concerned before moving to the final phase? | 4 | Control Quality | Performance reports | Validate Scope | Control Costs |  |  | 3 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | Project scope has to be validated (that reflects all applicable stakeholder requirements being fulfilled & accepted) before moving into the final phase.
478 | SINGLE | A customer has provided you the scope of work for an eight-month project that has a few unknowns. The customer has asked you to just get it done and wants to see you only at the end of eight months i.e. when you deliver the finished project. Under these circumstances, which of the following is the best thing to do? | 4 | Complete the project within eight months without contacting the customer during this time | Complete the project as requested, but Validate its scope with the customer occasionally, throughout the project | Ask management to get in touch with the customer occasionally | Complete the project, but document that the customer did not want contact |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | "Few unknowns" is the key word here. So the PM would follow management by exception management style as customer has asked not to be contacted frequently. However it is a good practice to get the scope validated when a major deliverable has been produced & QC activities are completed. Customer can check the project viability at that points in time.
479 | SINGLE | While executing a project, a deliverable has been submitted to the customer. The customer neither acknowledges the deliverable nor says if it is acceptable although an approval is required. What is the best thing to do in such a case? | 4 | Contact management for help | Continue with the project | Document the situation | Call a meeting of the team |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | Calling the team meeting or just documenting will not help in getting customer approval. Escalating the situation to the Management is the best action to take.
480 | SINGLE | You are the project manager and your project has reached the end. Your project has been successful in terms of requirements, scope, schedule and cost. The functional manager under whom various team members used to work, is upset because many of his staff quit while working on the project. This is because of the long hours at the project and lack of management support. Which of the following is the MOST CORRECT statement about this project? | 4 | The project manager did not obtain adequate resources and did not set a realistic deadline based on resources available. | The project was within budget and time and achieved its objectives. Upper management is responsible for providing adequate resources, and the project manager managed the project well with available resources. | The project should be measured against how successfully it met its charter. This was not done during this project. | The functional manager is responsible for his staff and obtaining adequate resources to meet the schedule once it has been set. The project and project manager achieved all of its goals set forth in the charter. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Many resources quit during the course of the project. This infers that the PM did not plan require requirement well & did not acquire (on board) enough resources & set their expectations/deadlines
481 | SINGLE | Management has assigned you a high priority project. You find it very difficult to finish the project with the available resources and scheduled time. Project manager talked to management to either assign more resource or change the end date. But management is not convinced. What should project manager do? | 4 | Coordinate with team members the overtime necessary to complete the work. | Provide the management with an analysis, which shows how much amount of work of the entire scope can be completed with the available resource | Provide the team with opportunities to do a great job on the work that can be accomplished. | Use more experienced resources to complete the work faster |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Always provide "basis of estimates" when any estimates are provide (time/budget/effort/resource estimates). For limited resource availability always provide the impact analysis that outline how muck work (%) can be completed by the available resources
482 | SINGLE | During project Executing you discover that you are working on a task requested by the customer but not included in the contract. The customer is already upset about the cost of several items she claims your company left out of the contract. No one in your company wants to discuss the change with the customer for fear of losing the contract. What is the best course of action in this case? | 4 | Initiate an escalation meeting & renegotiate a new scope of work & new contract | Have a meeting with the customer to identify all the items she thinks were left out of the contract | Contact your senior management and contract department to determine options. Then, schedule a meeting with management and the customer to discuss these options. | Look for ways to save time on other tasks so the new work can be done |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Contract is driving the project & it's outcome. The contract has to be amended to cover all project deliverables (leading to tasks)
483 | SINGLE | All the changes that needs to be done in scope must be written and approved. Which of the following conflict management strategy should you use if a team member tries to change the scope without approval? | 4 | Problem solving | Punishment | Negotiating | Withdrawal |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | The team member is trying to change the scope unilaterally. We cannot punish, withdraw, or negotiate in such a situation. We have to enough research and try to resolve it by using problem solving technique
484 | SINGLE | As you monitor your project progress, you discover that final deliverables cannot be completed as per the planned schedule. What should the project manager do? | 4 | Look for options with stakeholders using some combination of scaling back work, re-evaluating discretionary dependencies or adding resources. | Evaluate the impact on the company of completing this project late. | Drive the project team to work faster to make up for lost time. | Recalculate the project schedule and distribute it according to the communications management plan. |  |  | 1 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | You are running the risk of schedule over run due to completion of final deliverables. You should look for options to reduce delays by schedule compression/utilizing unused floats/optimizing resources and/or dependencies
485 | SINGLE | Which of the following is NOT needed to be done in case there is a major delay on a non-critical path activity? | 4 | Investigate the delay. | Re-evaluate the critical path. | Change the project schedule. | Review the float time for the activity. |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | NOT is the keywork here. We do all other options except changing the project schedule
486 | SINGLE | A big, multi-year construction project experienced weather related schedule delays which is supposed to be a typical for that area. Which of the following should project manager do to integrate this information into the project schedule? | 4 | Lengthen the estimated activity duration for all activities scheduled to occur the following winter. | Reevaluate the revised schedule to determine the potential impact and then raise a Change Request. | Leave the current project schedule unchanged and work the issues as they arise next year. | Make changes to the project management plan in order to maintain the current project schedule. |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  |  | Predictive Approach | This is a typical delay & the weather related delay is bound to impact your project. Raising a CR will lead to impact analysis and once approved it can be integrated into the schedule
487 | SINGLE | You are the project manager of Friend Bees Pvt Ltd. The sponsor of your project has asked you to compress the schedule. Which of the following is CORRECT? | 4 | Crashing always shortens the timeline but often increases risk. | Fast tracking often results in rework, and crashing often results in increased cost. | Crashing is only a viable alternative if earned value analysis indicates that the project is ahead of schedule and under budget. | Fast tracking will result in less parallel activities than crashing the project. |  |  | 2 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | Correct is the keyword. In fast tracking the dependencies are to be re-evaluated to see if come activities can be completed in parallel rather than sequentially. And yes, crashing always leads to cost increase due to learning curve costs. (also law of diminishing returns)
488 | SINGLE | Hazel is working on a project which has a Budget at Completion (BAC) of USD 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that USD 4,25,000.00 has already been spent on the project. Her project sponsor has asked for the difference between the budgeted value of the project work performed and where the project should have been at present. Please specify which statement is TRUE? | 4 | Her sponsor has asked for the Cost Variance which is USD - 42,500.00 | Her sponsor has asked for the Cost Variance which is USD - 1,27,500.00 | Her sponsor has asked for the Schedule Variance which is USD - 42,500.00 | Her sponsor has asked for the Schedule Variance which is USD - 1,27,500.00 |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 SV = EV-PV = -42,500
489 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on budget or not. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.7 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.875 | Her sponsor has asked for Schedule Performance Index (SPI) which is 0.7 | Her sponsor has asked for Schedule Performance Index which is 0.875 |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 CPI = EV/AC = 0.7
490 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked whether the project is on schedule or not and if he is getting any value from the project. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.7 | Her sponsor has asked for Cost Performance Index (CPI) which is 0.875 | Her sponsor has asked for Schedule Performance Index (SPI) which is 0.7 | Her sponsor has asked for Schedule Performance Index which is 0.875 |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | BAC = $8,50,000 EV = 35% of 8,50,000 = $2,97,500 PV = 40% of 8,50,000 = $3,40,000 AC = $4,25,000 SPI = EV/PV = 0.875
491 | SINGLE | Phyla is working on a Project as a Project Manager. Her Earned Value is more than Actual Cost. Which statement holds TRUE? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of the schedule. |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | PV is not given, hence schedule metrics cannot be determined. The project has earned more than what is actually spent, hence is under budget
492 | SINGLE | Phyla is working on a Project as a Project Manager. Her Earned Value is less than Actual Cost. Which statement holds TRUE? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 2 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | PV is not given, hence schedule metrics cannot be determined. The project has earned less than what is actually spent, hence is over budget
493 | SINGLE | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is more than Planned Value. What is the status of her project? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | As we have earned is more than planned, we are clearly ahead of schedule
494 | SINGLE | Ruby is working as a Project Manager. Upon calculating Earned Value and Planned Value, she finds that Earned Value is less than Planned Value. What is the status of her project? | 4 | Her project is under budget. | Her project is over budget. | Her project is behind the schedule. | Her project is ahead of schedule. |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | As we have earned less than what was planned, we are clearly behind schedule
495 | SINGLE | Which of the following statement is NOT true about CPI and SPI? | 4 | CPI and SPI can be less than 1. | CPI and SPI can be more than 1. | CPI and SPI can be equal to 1. | CPI and SPI can be less than 0. |  |  | 4 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | "NOT true" is the key word. CPI & SPI cannot be less than 0
496 | SINGLE | Phyla is working on a project which has a Budget at Completion (BAC) of INR 8,50,000.00 and is 24 months long. As on date her project is 35% complete, while it was supposed to be 40% complete at present. She has also reported that INR 4,25,000.00 has already been spent on the project. Her project sponsor has asked how much the project will cost based on the project's current performance on cost. Please specify which statement is TRUE? | 4 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate to Complete (ETC) which is INR 12,14,286.00 | Her sponsor has asked for Estimate at Completion (EAC) which is INR 7,89,286.00 | Her sponsor has asked for Estimate to Complete which is INR 7,89,286.00 |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | BAC = $8,50,000 EV = 35% of 8,50,000 = INR2,97,500 PV = 40% of 8,50,000 = INR3,40,000 AC = INR4,25,000 CPI = EV/AC = 0.7 EAC = BAC/CPI = INR 12,14,286 (rounding off)
497 | SINGLE | Which of the following shows roles and responsibilities on your project? | 4 | Bar Chart | Resource Histogram | RACI Matrix | Human resource Plan |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  |  | Predictive Approach | RACI (Responsible, Accountable, Consulted, Informed) chart is used assign roles (and responsibilities)
498 | SINGLE | In a project environment which is very uncertain or where there are lot of rapid change, which approach should be BEST recommended? | 4 | Sequential Phases Approach | Overlapping relationship approach | Iterative approach | Constrained relationship approach |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | Iterative is the best approach where requirements are not certain and rapid changes are required. The changes can be applied in every iteration
499 | SINGLE | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is TRUE about Project? | 4 | It is a temporary endeavor undertaken to create unique product, service or result. | It has a definitive beginning and an end | A Project is an ongoing task undertaken to create product, service or result | Both A & B |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Option 3 is operation (ongoing task). Both options 1 & 2 define the project
500 | SINGLE | Michael has just joined ABC Enterprises. He finds that his role in organization is to keep track of status and make some of the minor decisions on the project without having to run them by the functional manager. He is working as: | 4 | Project Manager | Project Coordinator | Project Expediter | Team Member |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Michael does not have full authority over the project & his primary role is to track the project progress
501 | SINGLE | You have recently joined ABC Enterprises as Project Manager. You find that the team members report both to you and the functional head. But you have more authority then functional head. Which type of organization structure you are working in? | 4 | Strong Matrix | Tight Matrix | Weak Matrix | Balanced Matrix |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | You have slightly more authority over the Functional Head (Department Head), hence it is a strong matrix where a PM belonging to Projects Department is managing the project
502 | SINGLE | Thomas is a project manager working on a construction project near New York City. He is currently sequencing the activity list. Which Process Group is he currently working on? | 4 | Initiating | Executing | Planning | Closing |  |  | 3 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | Activities are sequenced in Planning & re-sequenced if required in "Monitoring & Controlling". M&C is not given as an option, hence Planning is the right answer
503 | SINGLE | Thomas is a project manager working on a construction project near New York City. He is currently Sequencing the activity list. Which Knowledge Area is he currently working on? | 4 | Risk Management | Schedule Management | Project Integration Management | Procurement Management |  |  | 2 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | Activities are created & sequenced in Schedule Management KA
504 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statements is NOT True? | 4 | Project management decisions needs to be taken from functional managers. | Project Manager has more authority than functional manager | The project team maintains a HOME | Both B & C |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | NOT TRUE is the key word. All project management decisions are taken by the PM in strong matrix organization
505 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is working in Strong Matrix Organization. Which of the below statement is TRUE? | 4 | Functional manager has more authority than project manager | The Project team maintains a HOME. | Major decision needs to be made with functional manager approval | All of the above |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | In Strong Matrix (All Matrix & Functional) organizations the project team always has a home. All other statements are false
506 | SINGLE | Which of the following phase has maximum impact on product reliability and maintenance characteristics? | 4 | While meeting schedule constraints | While meeting cost constraints | During implementation phase | During design phase |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | Product reliability & its sustenance (maintenance) attributes are considered whilst designing, hence it has maximum impact during design phase
507 | SINGLE | Muddy is working as a manager in an Export House who want to develop an in-house, Customer Relationship Management Software. He finds that he needs to take approval from department head for each of project decisions. Which of the following is true about such functional organizations? | 4 | Project management decisions needs to be taken from functional managers. | Functional Manager has more power than the project manager. | Team reports to functional managers | All of the above |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | All the three options outline the characteristics of functional organization
508 | SINGLE | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and is required to release them after the project has been completed. He finds that he is working in a projectised organization. Who has the decision making power in such organizations? | 4 | Project Manager | Project Coordinator | Functional Manager | Both A and C |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | In projectized organization, all decisions are taken by the PM and PM has maximum authority
509 | SINGLE | Ramie is a working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project he has been assigned 10 resources and have to release them after the project is completed. All project management decision lies with him. Which of the following is true about such organizations? | 4 | He shares authority with functional managers | Team members report to him and functional equally | He is acting as project expeditor | Teams are organized around project, once the project gets complete, the team is released |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | The project org team (OBS) structure is built around the project. Other Functional departments or its Managers have no or limited authority
510 | SINGLE | Ramie is working as a project manager in Four-Wheeler CORP LTD located in Japan. For a new project, he has been assigned 10 resources and have to release them after the project is completed. All project management decisions lies with him. Which of the following is NOT true about such organizations? | 4 | Teams are organized around project, once the project gets completed, the team is released | The project manager makes all the decisions about budget, schedule, quality and resources | Project manager is responsible for success or failure of the project | Project managers work as an assistant to functional managers |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | Ramie has complete authority & control over the project. He is not working as the assistant to the Functional Managers. (Do not miss the key word "NOT TRUE")
511 | SINGLE | Two project managers are working in different organizations. They were having dinner together and found that they are working in weak matrix organization. One finds that he is a project coordinator and other finds that he is a project expeditor. How does a project expeditor differ from project coordinator? | 4 | Expeditors have no authority at all, Coordinator has some authority | Coordinator have no authority at all, Expeditors has some authority | Expeditors are project managers | Coordinators are actually functional managers |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | PE's main role is the expedite the assigned work & they will not have any authority. PC's role is to co-ordinate all activities cutting across all Knowledge Areas. They will have limited authority that is required to co-ordinate project activities
512 | SINGLE | You have been given responsibility of upgrading old server farm to the latest Quad Core Xeon Intel processors. The Up-gradation includes changing complete server hardware and may require restoring of data on these new servers. You ask PMO for historical records for similar projects that company has earlier worked upon. What are you making use of? | 4 | Organizational Process Assets | Project Management Plan | Network Diagram | Statement of Work |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | You are referring to historical information from the process assets that were created in earlier projects. These are the OPAs you are referring to.
513 | SINGLE | You are currently working as manager in BCL Logistics. You have been given responsibility for moving Infrastructure of ABC Software IT CORP LTD to the newly procured office in Los Angeles. You have determined the overall cost for your project. What should be your next step? | 4 | Determine Budget | Perform Quality Assurance | Develop Schedule | Define Scope |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  |  | Predictive Approach | You have already computed the project cost (fixed costs, variable costs, resource costs, etc.). Next step is to compute the project budget by adding "Management Reserve" that can be used when unknown unknown events occur
514 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals with prioritizing risk for further analysis or action by assessing and combining their probability of occurrence and impact? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Jessie is not quantifying the risks as he is not using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis. He is computing Risk Severity (=P*I) which is qualifying the risk
515 | SINGLE | Jessie has just started working on a new IT project that has zero float. He is currently identifying risk for the project. Which of the following process deals numerically analyzing the effect of risk on overall project objective? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Jessie is quantifying the risks as he is using definitive numbers (Expected Monetary Value or sensitivity analysis) for analysis.
516 | SINGLE | Jack has just taken over a project. He is currently identifying risk for the project. Which of the following process deals with developing option and actions to enhance opportunities and to reduce threats to the project objectives? | 4 | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Plan Risk Responses |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Jack is planning response options when the risk occurs. (Enhance, mitigate, escalate, accept, avoid, transfer, exploit, etc. are some risk response strategies)
517 | SINGLE | Franklyn is working as a project manager in a Real Estate Company who are developing a state of the art commercial complex. He is currently working on Risk analysis. The kind of risks that the organization or stakeholders are willing to accept to an certain extent is known as: | 4 | Risk Acceptance | Risk tolerance | Risk Avoidance | Both A & C |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Risks are accepted if the impact is within the threshold that is also known as risk tolerance
518 | SINGLE | You are just assigned a project. Though you are working in the organization for many years, still the project is new for you. The project performance till date is with in baseline thresholds, still customer is not happy. What would be the best action to be considered at the very outset:- | 4 | Motivating your own team first | Identifying the problems faced so far and ensure actions are taken | Verifying that the changes are done as per process | Verification of customer's needs and expectations |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | You have to reassess if the customer expectations are documented & are being fulfilled. Customer is not happy though the overall project performance metrics are within the baseline is because their needs and/or expectations are not being addressed
519 | SINGLE | Philip is working as a project manager for AUTOCARS PVT LTD. He is currently conducting meetings for creating the high level plan for creating the risk management activities. Which process is he currently working in? | 4 | Plan Risk Management | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Documentation reviews |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Phillip is creating plan for risk management activities. This is done during "Plan Risk Management" PM process
520 | SINGLE | Phil has been assigned a new marketing project in BCL Marketing Pvt. Ltd. You are currently identifying risks. Which of the following people should be part of identifying risk process? | 4 | Project Manager | Stakeholders | Team Member | All Project Personnel |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Entire project team is involved in identifying risks.
521 | SINGLE | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane which can cover 1500KM per hour. You are currently identifying risks. While checking Activity Cost Estimates , which of the following types of risks can be identified? | 4 | Risks indicating whether funds are sufficient for completing the activities or not? | Risks indicating whether activity duration estimates are correct or not? | Risks indicating whether cost benefit analysis is done for all quality activities? | Both A & B |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Known unknowns & unknown unknowns have to be considered during activity cost estimation process. This will help you to determine if the allocated funds are enough to complete the project
522 | SINGLE | You are working as project manager in an Aerospace Firm and you are currently given in charge of manufacturing a new technology airplane, which can cover 1500KM per hour. You are currently identifying risks, while checking Scope Baseline, which of the following types of risks can be identified? | 4 | Uncertainty in project assumptions | Uncertainty in project cost | Uncertainty in project Schedule | All of the above |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Scope baseline consists of scope statement that outlines, in scope, out of scope, assumptions, and constraints. Option 1 is the right answer as cost or schedule risks cannot be identified whilst checking scope baseline
523 | SINGLE | Contingency allowance is fixed at 9% of total project cost to cover risks. When the project is near completion, total dollars in contingency reserve are:- | 4 | Spent to ensure that there is no extra money shown in the budget. | Reduced to decrease unnecessary extra accounting work | Retained at the balance dollar level | Reduced to reflect the true percentage of work performed. |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | When the project is near completion (as outlined in the question), the contingency reserve that is quite significant (9%) will be removed / reduced to measure real percentage of work performed.
524 | SINGLE | Suppose, the project manager is appointed to manage a new project that has just been given approval to start the planning requirements. The project manager is new to the organization and has inherited a project team previously selected by the top management. The best method of initiating the communication process with the team and to establish the expectations of the project team is to __________________ | 4 | Send a formal memorandum to each team member to outline the objectives, the requirements of the team, and the time frame for work | Personally talk to each team member to determine what he/she would like to do on the project and how that can be accommodated | Call a briefing session to set objectives of the management and direct how these objectives will be met | Call a kickoff meeting to present the objectives and open the floor for discussion on how the objectives will be achieved |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Project kick-off is the ideal forum for breaking ice & get to know each other. After initial introductions and determining strengths & weaknesses, work can be assigned based on resource availability and capability
525 | SINGLE | To come out with staffing requirement , Project Manager first needs:- | 4 | Organisation breakdown structure | Responsibility assignment matrix | Resource Breakdown structure | Work breakdown structure |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | WBS is the main artefact that outlines the work required for every project deliverable. Staffing levels cannot be determined if the exact required project work is not available & WBS provides it
526 | SINGLE | Russell is working as a project manager in KWSoft.com. You are currently identifying risks by using information gathering techniques. Which of the following is NOT an information gathering diagramming technique that can be used to identify risks? | 4 | Ishikawa Diagram | Process flow chart | SWOT analysis | Influence Diagram |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | NOT is the keywork here. SWOT (Strengths, Weaknesses, Opportunities, & Threats) is not an information gathering technique but is a data analysis technique
527 | SINGLE | You are working as a manager in a chemical firm. Your company has received an order of delivering a chemical that is highly sensitive at room temperature and requires (-)10 degree centigrade temperature for storage. You have been given responsibility of making this chemical from the compound manufacture and delivered to you by a firm that is 500KM away from your location. You are currently identifying risks for your project. Which of the following technique is used to identify any opportunities arising from organizational strengths and any threats arising from organizational weakness? | 4 | Expert Judgment | SWOT Analysis | Ishikava Diagrams | Delphi Techniques |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | You are analyzing opportunities arising from organizational strengths and any threats arising from organizational weakness. This is SWOT analysis
528 | SINGLE | Natasha has been assigned a new telecom project as a project manager. Her project team and stakeholders are based out of different locations. She has 6 team members, 2 sponsors, and 1 client. She wants to inform all of them about the progress of her project. How many communication channels will she have? | 4 | 45 | 36 | 3 | 50 |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive Approach | Natasha+6 team members+2 sponsors+1 client = 10 stakeholders # Comm channels = [10*(10-1)]/2 = 45
529 | SINGLE | Due to recent recession, 5 out of 8 of Jack's project team members have been laid off. There are 3 sponsors in his project. How many communication channels does Jack have in his new team? | 4 | 21 | 15 | 132 | 20 |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive Approach | Jack's team is left with 3 members + 3 sponsors + Jack = 7 # Comm channels = (7*6)/2 = 21
530 | SINGLE | 3 members have been added in Natasha's team. Now she has 7 team members, 1 sponsor and 1 client. How many communication lines have been added? | 4 | 24 | 21 | 45 | 40 |  |  | 1 | 1 | PMP | Process | Project Communications Management |  |  |  | Predictive Approach | Before, 4 team members+1 sponsor+ 1 client + Natasha=7 stakeholders & 21 comm channels After, 7 team members+1 sponsor+ 1 client + Natasha=10 stakeholders & 45 comm channels 45-21 = 24 comm channels have been added
531 | SINGLE | Natasha is working in a project where the next phase can start only when the previous phase is 100% complete. What does this mean? | 4 | The project has overlapping phases | The project has sequential phases | The phases of the project has iterative relationship | None of the above |  |  | 2 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | the project life cycle has sequential phases & earlier phase has to be completed, pass through a phase gate before next phase is initiated (phase gate is applicable in most of the cases though not explicitly mentioned in the question)
532 | SINGLE | Shirley has been assigned a project where she is required to install new computers in the office and have Windows 7 as the Operating System in all of them. She is required to install 100 computers and similar number of operating systems. She has two teams working on it. One, which will install the computers and the other will install the operating system in the computer. When the first team has installed 10 computers, the other team has started to install the Operating Systems in the new installed computer. What does this mean? | 4 | The project has overlapping phases | The project has sequential phases | The phases of the project has iterative relationship | None of the above |  |  | 1 | 1 | PMP | Process | Project Time Management |  |  |  | Predictive Approach | OS upgrades are not waiting for all 100 computer hardware to be upgraded. Both the phases are overlapping
533 | SINGLE | You are working in ABC Enterprises and just been promoted to Project manager. You have been assigned a new project. Which of the following is NOT a characteristic of a Project? | 4 | Temporary | Ongoing | Unique | Definite beginning and end |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  |  | Predictive Approach | NOT is the key. Project is not ongoing as operations
534 | SINGLE | Barriers to communication can be invisible to a casual observer but can often be greater obstacles than physical barriers. However, barriers do not include- | 4 | Difference in frames of reference | Lack of credibility or trust | Perceived difference in status | Overly technical approach in communication |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  |  | Predictive Approach | Technical approach is not considered a communication barrier. Do not miss "NOT Include" in the question
535 | SINGLE | Project is in execution phase. It has however run into various unexpected problems. Many of the risks have surfaced which you did not think earlier. The project is already behind schedule and has gone over-budget. What should be done? | 4 | Create updates to risk response plan | Create a revised project plan | Perform risk response audits | Perform updated risk identification and analysis |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Many new risks that were not identified have surfaced. Additional risks have to identified immediately. Risk analysis will follow
536 | SINGLE | Renee is working as project manager in a Pharmaceutical Company. While executing the project, he finds certain events that can change the outcome of certain activities. Which of the following is a way to handle RISK? Choose the best answer. | 4 | Avoid, Mitigate | Avoid, Mitigate, Transfer | Avoid, Mitigate, Transfer, Accept | None of the above |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | All risk responses have to be considered in this case
537 | SINGLE | Thomas is a project manager working on a construction project near New York City. While project executing, Thomas find certain events that can change the outcome of certain activities. He decided to reduce the impact of the event. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Reducing the magnitude of impact due to occurrence of an uncertain event is the mitigation. It is acceptance as some minimum impact will remain after risk mitigation
538 | SINGLE | Rick has been promoted to Project Manager. He is currently working on a Project involving new technologies. While project executing, you find certain events that can change the outcome of certain activities. You decided to reduce the impact of the event and bought an insurance policy to cover the risk. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Rick is transferring the risk impact to a third party by insuring the activity (purchasing the insurance policy to cover for the loss due to high impact)
539 | SINGLE | A diagram that explains the decision taken and implications of choosing it over other available alternatives, helps in:- | 4 | Getting a quantitative analysis of the risk | Determining the risks that can impact the project ,most | Translating the uncertainties at a detailed level into potential impact on objectives expressed at the level of total project. | Determining the decision that yields the greatest expected value |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | EMV is a decision tree analysis tool that numerically analyzes that out come of every decision and helps determine the greatest expected value (highest EMV)
540 | SINGLE | Michael is working as a Manager in Printing Press of large Printing House. He decided to put a surge protector to make sure lightning wont blow out the electrical instruments. Which of the following way he has chosen to handle RISK? | 4 | Avoid | Mitigate | Transfer | Accept |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | The surge protector will reduce the impact & power overloading on the electrical instruments. Electrical instruments will not be used if "Avoid" option is considered
541 | SINGLE | Jack has just taken over a project. He is now currently identifying risks in the project. He gets all Team member in a room and started to pump out ideas. Which among the following information gathering techniques is he using? | 4 | Brainstorming | Interviews | The Delphi technique | Root Cause Identification |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | Jack is encouraging all teams members to provide their inputs in identifying risks. He is not masking the identity of the team members as in Delphi technique. He is not conducting 1 on 1s as in interviews.
542 | SINGLE | You are Project Manager working in IT CORP LTD. You have been assigned a new project of Inventory management System. You are currently identifying risks in your project. You decided to send questionnaires to experts asking about important project risks. Which type of the following information gathering technique is he using? | 4 | Brainstorming | Interviews | The Delphi technique | Root Cause Identification |  |  | 3 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | You are gathering inputs without other team members knowing the identity of the team member providing inputs which is Delphi technique.
543 | SINGLE | You are Project Manager working in IT CORP LTD. You have been assigned a new project on Inventory management System. You are currently identifying risks in your project by looking at plans, requirements and documents from your organization process assets. Which type of the identify risk technique you are using? | 4 | Document Review | Assumption Analysis | SWOT Analysis | Checklist Analysis |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  |  | Predictive Approach | You are reviewing historical information of similar past projects to identify potential risks that may be applicable for the current project. You are using "Document Review" technique. You are neither analyzing assumptions/constraints nor doing SWOT analysis not analyzing checklists
QuestionID | QuestionType | Question | NoOfOptions | Option1 | Option2 | Option3 | Option4 | Option5 | Option6 | CorrectOption | Marks | LevelOne | LevelTwo | LevelThree | LevelFour | LevelFive | DifficultyLevel | Question Category | Explanation | RecordUpdated | RecordStatus | AssessmentID | QuesImg | Option1Img | Option2Img | Option3Img | Option4Img | Option5Img | Option6Img
211 | SINGLE | Carrie is a project manager. Two of her team members are engaged in a conflict and they reach out to her for a solution. However, one team member wants them to resolve the conflict on their own. Which conflict resolution Technique did she use? | 4 | Withdrawal | Smooth | Compromise | Force |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | When one stakeholder wants to resolve the confict any of the techniques can be used. In the current scenario all the others barring Withdrawal need both stakeholders to be engaged. Hence most logical choice is Withdrawal. PMBOK® Guide Sixth Edition (2018) 9. Project Resource Management / 9.5.2.1 Interpersonal and Team Skills, p348 | 44198 | N | 4 | [5 empty] | NA | NA
212 | SINGLE | Project A has a NPV of $1 million and IRR of 4%. Project B hand a NPV of $1.1 million and IRR of $3.9%. Which project should you select? | 4 | A | B | A & B | Insufficient Information |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Predictive Approach | Since the IRR are almost similar one should choose the project with greater NPV. Best choice in this situation will be Project B. | 44198
213 | SINGLE | Kirti works for a non-profit organization. On one of her projects, a customer wants her to use the schedule compression technique, so that they can complete the work ahead of schedule. Which are the two schedule compression techniques that can be used and what is the difference between them? | 4 | Fast Tracking and Resource Levelling. In Fast Tracking, you add more resources and in Resource Leveling, you allot the work of over allocated resources to somebody else | Fast Tracking and Crashing, In Crashing, you add more resources and in Fast Tracking, you do things in parallel. | Resource Leveling and Crashing. In Resource Leveling, you allot the work of an over allocated resource to somebody else and in Crashing, you add more resources | Fast Tracking and Crashing. In Fact Tracking, you add more recourses and in Crashing you do things in parallel. |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Medium | Predictive Approach | To execute the project quickly, Kirti needs to fast track and Crash which combines is called schedule compression. In Crashing, you add more resources and in Fast Tracking, you do things in parallel. PMBOK® Guide Sixth Edition (2018) PMI/PMI/6.5.2.6/253 | 44198
214 | SINGLE | You work as project manager for a construction company and you are at a stage in the project where you have to decide whether to lease or rent the construction equipment. Leasing requires an base investment of $40,000 followed by a charge of $120/day. However renting costs $200/day. How many days will it be until leasing becomes more economical than renting? | 4 | 500 days | 501 days | 200 days | 201 days |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | 40,000 + 120x = 200x X= 500 days Intial Investment + Cost per day for lease needs to be equal to cost per day of the rent. | 44198
215 | SINGLE | Jerry is managing a project which is running little behind schedule because a key resource took an unexpected leave of absence. The resource will be resuming next week and will make up for the lost time. Meanwhile, Jerry has not been able to complete his assessment of the project delay. However, as the delay is only minor and is expected to be covered next week. Jerry does not want to unnecessarily worry the project stakeholders. What will be his project status report for the meeting? | 4 | Report that the project progress is as planned by using the contingency reserve to compensate for the delay. | Report the actual status of the meeting and that the key resource will be back next week and make up for lost time | Report that the project progress is slightly behind schedule and that the contingency reserves will be used to cover the delay. | Do not report the delay; instead report that there are no major issues. |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  | Complex | Predictive Approach | Project manager needs to report and be 100 % transparent and truthful in the reports. If the reports are true, some stakeholders may not like the same but Project Manger will get needed support in the interest of the project. In the current scenario, option B is the best choice with the PM. PMBOK® Guide Sixth Edition (2018), 10. Project Communication Management / Project Communications Plan, pp359-362 | 44198
216 | SINGLE | Simon is working on a project that is running on an aggressive schedule. Initially the customer had requested for a weekly update but now they have requested for update on daily basis. Simon reviews the current and desired engagement levels and make necessary changes. Which tool did Simon use? | 4 | Stakeholder Engagement Assessment Matrix | Project Management Information System | Mind Mapping | Stakeholder Analysis |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | The stakeholder engagement strategy matrix needs to be redefined if the stakeholder is asking for changes in agreed level of engagement. Once the assessment matrix is defined, we can appropriately enagage with them. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, pp379-381 | 44198
217 | SINGLE | PM complained to project sponsor that he did not get the correct number of resources as planned. Sponsor agreed the PMs complaint is genuine and decided to cancel the project. Which process would have prevented this extreme step from Project Sponsor? | 4 | Estimate Activity Resources | Manage Team | Control Resources | Acquire Resources |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager. PM needs to acquire right resources for him to manage the project well failing which all the estimates will go wrong leading to failure of the project. PMBOK® Guide Sixth Edition (2018), Project Resource Management / 9.3.1 Acquire Resources: Inputs, p330 | 44198
218 | SINGLE | On one of your projects, you used ROM to estimate the high- level budget of the project. The next step is to identify the stakeholders on the project. You don't want to start from scratch, so you look for a template. What will you find that information? | 4 | Organizational Process Assets (OPA) | Project Management Office (PMO) | Internal Department Repository (IDR) | Enterprise Environmental Factors (EEF) |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Organizational process assets (OPAs) are the plans, processes, policies, procedures, and knowledge bases specific to and used by the performing organization. These assets influence the management of the project. | 44198
219 | SINGLE | You are in the process of selecting a vendor for a large mobility project. One of the shortlisted vendors is your close friend; however, you are unaware that he has bid for the contract. Later, you meet your friend at a social gathering and he tells you that he is bidding for the contract in your company. What should you do? | 4 | Inform your management immediately that one of the vendors is your friend and excuse yourself from the selection committee | Inform your management immediately that one of the vendors is your friend and let the committee decide whether you should be part of the selection committee or not. | Since it is simple social networking, you should not worry about it. | Inform your management immediately that one of the vendors is your friend but only recommend him if you think he is worthy of the contract. |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | Any conflict of interest sitution needs to be informed to Sponsor or to leadership team quickly so the situation can be handled in best interest of the project and the organisation. Choice B is the best choice which is also one of PMI code of conduct. | 44198
220 | SINGLE | Your senior manager is not pleased with your display of identified project risk categories to senior leadership. They recommend a hierarchical representation of project risks. What should you be delivering to them? | 4 | Work Breakdown Structure | Risk Breakdown Structure | Milestone Chart | Org Chart |  |  | 2 | 1 | PMP | People | Project Risk Management |  |  | Complex | Predictive Approach | The project manager must first identify the risks, put them into Risk hierchy also called as Risk breakdown Structure for first level review. Best choice in current situation is B. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, pp409-411 | 44198
221 | SINGLE | Scranton is managing a project to design printers. A brainstorming session is held to determine an ideal setting for the printer. During the session, the quality manager of the company recommends that the team try out various scenarios for printing by varying certain parameters on the printer. What this process called? | 4 | Process Analysis | Design of Experiments | Flowcharts | Root Cause Analysis |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | The project manager and project team may use the organization’s quality assurance department, or other organizational functions, to execute some of the Manage Quality activities such as failure analysis, design of experiments, and quality improvement. This kind of method is more experimental in nature but can help arrive at final parameters of quality management. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.1 Manage Quality | 44198
222 | SINGLE | Jack is a project manager who is going through the stakeholder register to make sure she knows who the powerful stakeholders are. She proactively communicates with them on a regular basis to avoid any escalations in the future. Which tool is she using? | 4 | Cultural Awareness | Political Awareness | Networking | Leadership |  |  | 2 | 1 | PMP | People | Project Communication Management |  |  | Complex | Predictive Approach | Political awareness. Political awareness helps the project manager to plan communications based on the project environment as well as the organization’s political environment. Political awareness concerns the recognition of power relationships, both formal and informal, and also the willingness to operate within these structures. An understanding of the strategies of the organization, knowing who wields power and influence in this arena, and developing an ability to communicate with these stakeholders are all aspects of political awareness. PMBOK® Guide Sixth Edition (2018), 10. Project Resource Management / 10.1 Plan communications management. | 44198
223 | SINGLE | One of the modules of Kaya's project is to create a social networking platform, where the users are posting questions, writing blogs, and reviewing the comments of users. Which technique defines this type of scenario? | 4 | Information Management | Knowledge Management | Expert Judgment | Political Awareness |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | From an organizational perspective, knowledge management is about making sure the skills, experience, and expertise of the project team and other stakeholders are used before, during, and after the project. Because knowledge resides in the minds of people and people cannot be forced to share what they know (or to pay attention to others’ knowledge), the most important part of knowledge management is creating an atmosphere of trust so that people are motivated to share their knowledge. PMBOK® Guide Sixth Edition (2018), 9. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, pp 133 ¦ Knowledge management, 133, 365 | 44198
224 | SINGLE | You recently concluded the validate scope process of the current phase of the project. The customer reviewed your work and gave her approval to move onto the next phase of the project. Which of the following is an incorrect way of describing this review? | 4 | Phase entrance | Phase exit | Kill point | Stage gate |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Reviews can happen at Phase exit or at kill point or at stage gate but never at the Stage entry point. Hence option A is not in place and is the incorrect choice. | 44198
225 | SINGLE | Lorenzo is a project manager for a construction organization. He has to provide the duration estimates to the steering committee. He has created a draft schedule after discussing this with the team; however he did not get a chance to conduct a final review before the start of the meeting. What is the best thing to do in such a scenario? | 4 | Present the estimate to the steering committee as is and tell them that it may be wrong. | Present the estimate to your senior manager only and then make a decision whether to present it to executive steering committee or not | Show the estimate as a rough order magnitude (ROM) | Don't present it to the executive steering committee as it is not accurate. |  |  | 1 | 1 | PMP | Business Environment | Project Schedule Management |  |  | High Complex | Predictive Approach | Duration estimates are quantitative assessments of the likely number of time periods that are required to complete an activity, a phase, or a project.Duration estimates may include some indication of the range of possible results. Also truthful & transparent reporting is the key for the project manager to manage stakeholder engagement. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 6.4 Manage Activity Durations, p23 | 44198 | N | 4 | [5 empty] | NA | NA
226 | SINGLE | Sam is working on implementing a security solution for a customer. One of the tasks to be accomplished for a smooth project execution is to identify all the stakeholders involved. And for any complex project, such as this, once the project stakeholders are identified, the next step is to classify these stakeholders based on their current and desired engagement levels. What is the benefit of classifying the project stakeholders? | 4 | To help define an approach strategy | To help populate the stakeholder register | To help identify the project scope | It is a mandatory step in stakeholder analysis |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Once the stakeholders are classified it becomes easy for project manager to stategise and handle requirements of each project stakeholders differently. Best choice in current scenario is option A. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 13.1 Identify Stakeholders , pp 549-550 | 44198 | N | 4 | [5 empty] | NA | NA
227 | SINGLE | A quality audit is a -------, -------- process to determine if project activities comply with the organizational and project policies, processes and procedures. | 4 | Structured and independent | Process-oriented and independent | Formal and independent | Structured and internal |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Simple | Predictive Approach | By Defination : A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 8.2 Manage Quality , 8.2.2.5- Audits pp 331 | 44198 | N | 4 | [5 empty] | NA | NA
228 | SINGLE | During the hiring process, you are asked the difference between project and product life cycles. What should be the correct response? | 4 | Project life cycle is the series of phases that a project passes through, from its initiation to its closure Product life cycle is the series of phases that represent the evolution of a product, from concept through delivery, growth, maturity, to retirement. | Project life cycle is the series of phases that a project passes through, from its initiation to its closure. Product life cycle is where iterations develop the product through a series of repeated cycles, while increments successively add to the functionality of the product. | Project life cycle is the series of phases in which the project scope, and the time and cost required to deliver that scope, are determined as early as possible. Product life cycle is where iterations develop the product through a series of repeated cycles, while increments successively add to the functionality of the product. | Project life cycle is the series of phases that a project passes through, from its initiation to its closure. Product life cycle where the product scope is generally determined early but the time and cost estimates are routinely modified as the project team understanding of the product increases. |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  | Simple | Predictive Approach | By Defination: Product Life Cycle. The series of phases that represent the evolution of a product, from concept through delivery,growth, maturity, and to retirement. Project Life Cycle. The series of phases that a project passes through from its start to its completion. | 44198 | N | 4 | [5 empty] | NA | NA
229 | SINGLE | You are a project manager working on a financial project. Your manager has requested that you brainstorm the projects potential risks. You start the process by prioritizing the identified project risks and also start working on the mitigation plan. What is the recommended method to accomplish this? | 4 | RACI chart | Probability and impact matrix | Control chart | Fishbone diagram |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | PI matrix is the first step to analyse the risk before finalising on risk handling strategy. Best choice is option B. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. PMBOK® Guide Sixth Edition (2018), 11 Project Risk Management / 11.1.3.1 , p442 | 44198 | N | 4 | [5 empty] | NA | NA
230 | SINGLE | You are working on a construction project that suddenly comes to a halt because of an unseasonal hail storm. What type of risk is this? | 4 | Variability Risk | Ambiguity Risk | Resilience Risk | Event Based Risk |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Predictive Approach | By Defination: Variability risk. Uncertainty exists about some key characteristics of a planned event or activity or decision. Examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase Ambiguity risk. Uncertainty exists about what might happen in the future. Areas of the project whereimperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Best choice is option A. | 44198 | N | 4 | [5 empty] | NA | NA
231 | SINGLE | Sam is building a multi-story government apartment with his construction company. He is in the process of ensuring that the team follows the risk management policies. Which process is he currently in? | 4 | Plan Risk Management | Plan Risk Responses | Implement Risk Responses | Monitor Risks |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The key words here are process of ensuring. This is a monitoring and control. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 44198 | N | 4 | [5 empty] | NA | NA
232 | SINGLE | Michael is a project manager working on a project. He finds out that several regulatory requirements have not captured in the requirements document. If those requirements are met, his project will exceed its budget, scope, duration, and possibly get cancelled. What should Michael do in this scenario? | 4 | Put forth a Change Request to the change control board. | Don't do anything because it is too late. | Michael should request more money from senior management so he can implement these requirements. | Set up a meeting to discuss why these requirements were missed. |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Any changes to baseline needs to be handled via change request. Regulatory requirments are mandatory requirements and needs to be handled immediately. Best choice is option A Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, project documents, and the project management plan; and communicating the decisions. This process reviews all requests for changes to project documents, deliverables, or the project management plan and determines the resolution of the change requests. The key benefit of this process is that it allows for documented changes within the project to be considered in an integrated manner while addressing overall project risk, which often arises from changes made without consideration of the overall project objectives or plans. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 4.6 Perform Integrated change control , Page 150 | 44198 | N | 4 | [5 empty] | NA | NA
233 | SINGLE | Sal is a project manager in biochemical organization. In his industry, identification of risk is the highest priority. To achieve this, he wants to make sure he gets unbiased response from all the critical and non-critical stakeholders on his project. What is the most appropriate technique Sal can use to identify project risks? | 4 | Interviews | Assumption and constraint analysis | Brainstorming | Delphi technique |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Interviews. An interview is a formal or informal approach to elicit information from stakeholders by talking to them directly. It is typically performed by asking prepared and spontaneous questions and recording the responses. Assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. Brainstorming. This technique is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Delphi method is a forecasting process framework based on the results of multiple rounds of questionnaires sent to a panel of experts. Several rounds of questionnaires are sent out to the group of experts, and the anonymous responses are aggregated and shared with the group after each round. Given the current scenario SAL should use interviews to identify the risks. Best choice by defination is option A. | 44198 | N | 4 | [5 empty] | NA | NA
234 | SINGLE | Shasha is a project manager on an HR system development project. The customer has requested a change in the projects timeline. Whose responsibility is it to perform an integrated Change Control Process? | 4 | Shasha | The customer | The CCB manager | The sponsor |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Simple | Predictive Approach | PM is responsible to perform CCB process. Best choice is option A. | 44198 | N | 4 | [5 empty] | NA | NA
235 | SINGLE | You are bidding for a contract, however, you are not clear on one of the critical components of the Request for Proposal (RFP). One of your professional references with whom you have worked in the past offers to provide his professional expertise. What will be the advantage of using his service? | 4 | To understand which contract type should be used. | To understand how to conduct the project funding limit reconciliation. | To make sure that you as a seller are safe while dealing with a buyer | To understand and offer the best solution possible. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | Independent cost estimates help understand and offer best solution.The procuring organization may elect to either prepare its own independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Significant differences in cost estimates can be an indication that the procurement SOW was deficient or ambiguous, or that the prospective sellers either misunderstood or failed to respond fully to the procurement SOW. Best choice is option D. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 12.1.3.7 Independent cost estimates, p503 | 44198 | N | 4 | [5 empty] | NA | NA
236 | SINGLE | You are working on a project where you have outsourced the work to a seller's company. Based on your discussion with the seller, you are revisiting your project assumptions defined in the scope statement to check whether they are still valid or not. Which process are you currently performing? | 4 | Monitor Risks | Control Scope | Validate Scope | Control Procurements |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Since you are revisiting your project assumptions defined in the scope statement, means PM is monitoring Risk and will take actions as needed. Hence the best choice is D. Monitor Risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. PMBOK® Guide Sixth Edition (2018), Part 2 The Standard for Project Management / 11.7 Monitor Risk, Page 490 | 44198 | N | 4 | [5 empty] | NA | NA
237 | SINGLE | A successful project manager should be both proficient at work and at managing relationships. To maintain good relationships, nterpersonal skills are important. Which of the following is not an interpersonal skill? | 4 | Trust Building | Conflict Resolution | Political Awareness | Resisting Change |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Project managers accomplish work through the project team and other stakeholders. Project managers rely on important interpersonal skills, including, but not limited to: Leadership, Team building, Motivating, Communicating, Influencing, Decision making, Political and cultural awareness, Negotiating, Facilitating, Managing conflict, and Coaching. Resisting change cannot be an interpersonal skill. Best choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
238 | SINGLE | You are working on the schedule for a large infrastructure project. You use all types of precedence relationships except.one. Which of the following is least commonly used in Precedence Diagramming Method? | 4 | Start-to-Start | Finish-to-Finish | Finish-to-Start | Start-to-Finish |  |  | 4 | 1 | PMP | Process | Project Schedule Management |  |  | Medium | Predictive Approach | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. For example, installing the operating system on a PC (successor) cannot start until the PC hardware is assembled (predecessor). Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example, writing a document (predecessor) is required to finish before editing the document (successor) can finish. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example, level concrete (successor) cannot begin until pour foundation (predecessor) begins. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. For example, a new accounts payable system (successor) has to start before the old accounts payable system can be shut down (predecessor). Start to finish is the least used Precedence diagraming method. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 44198 | N | 4 | [5 empty] | NA | NA
239 | SINGLE | Joe is a new PM who needs to procure a software from a vendor. He decides to put in a purchase order for the software. However, after speaking to his peers, he is doubtful that this is the correct way to go about it. Which of the following is the most appropriate way to go about purchasing the software? | 4 | Request for a Proposal instead of using a simple purchase order | Processes are guidelines for helping the PM. However Joe will have the final authority to make the decision based on the project needs | As long as the vendor is approved by the organization, Joe can go ahead with a simple purchase order | Joe will first need to verify the organizations policy. Certain organizations have policies that constrain procurement decisions, and require use of a longer form of contract for projects above a certain value. |  |  | 4 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | PM needs to follow the process and never understimate the kind of procurement. Usage of procured product and services may have legal implications and hence needs to be vetted and should follow complete contracting procedure. The best choice for Joe is D. | 44198 | N | 4 | [5 empty] | NA | NA
240 | SINGLE | You have divided the project into two phases. You are in the process of closing phase 1. Which process should you follow next? | 4 | Develop Project Charter | Develop Project Management Plan | Identify Stakeholders | Collect Requirements |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Once a phase is done, phase 2 will be started and first action under initiation is Identify stakeholders. Best choice is C. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1 Identify Stakeholders, p507 | 44198 | N | 4 | [5 empty] | NA | NA
241 | SINGLE | Brian is the project manager of a global project located across the world. Due to the nature of the project, a lot of the communication happens virtually across multiple time zones. As the project is progressing, Brian notices that there has been a gradual deterioration in the quality of communication between the team members. What is the called? | 4 | Noise | Encoding | Medium | Message |  |  | 1 | 1 | PMP | People | Project Communications Management |  |  | High Complex | Predictive Approach | Transmit message. The message is sent via a communication channel. The transmission of this message may be compromised by various physical factors such as unfamiliar technology or inadequate infrastructure. Noise and other factors may be present and contribute to loss of information in transmission and/or reception of the message. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.1.2.4 COMMUNICATION MODELS/ p408 | 44198 | N | 4 | [5 empty] | NA | NA
242 | SINGLE | The Customer wants to increase the authorized budget on the project. It is a minor change and it will not have a major impact. What should your next step be? | 4 | Do a detailed impact analysis to be sure. | Perform the integrated change control present | Accept the change as it does not have any major impact. | Continue doing the project-related activities. |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | The project manager must follow the documented and agreed upon change control processes. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.6 Perform Integrated Change Control, p113 | 44198 | N | 4 | [5 empty] | NA | NA
243 | SINGLE | Jen and her project management team are taking over a project for their new client. The project was previously handled by another firm. As a part of clean-up effort, Jen and team are currently inspecting the project deliverables. The team is recording the count and nature of defects found in these deliverables in a defect detail list. The defect Details list in this case is on example of? | 4 | Defect Log | Work performance data | Work performance report | Work performance information |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. Data are often viewed as the lowest level of detail from which information is derived by other processes. Data is gathered through work execution and passed to the controlling processes for further analysis. Examples of work performance data include work completed, key performance indicators (KPIs), technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, schedule progress, number of change requests, number of defects, actual costs incurred, actual durations, etc. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.3.3.2 WORK PERFORMANCE DATA / p132 | 44198 | N | 4 | [5 empty] | NA | NA
244 | SINGLE | Mahesh works as project manager for a construction company. His company has secured a new contract to remodel a kitchen in two months. The budget of the project is $10,000. Before awarding the contract to Mahesh's company, the client informs him that the scope is well-defined lord the project. For this scenario, which contract type in recommended? | 4 | Commission | Cost reimbursable | Fixed price | Time and material |  |  | 3 | 1 | PMP | Process | Project procurement Management |  |  | Medium | Predictive Approach | Fixed price contractss are the most favored for buying organizations because the price for goods is set at the outset and not subject to change unless the scope of work changes. PMBOK® Guide Sixth Edition (2018), 12. Project Risk Management /12.1.1.6 Contract Types, p508 | 44198 | N | 4 | [5 empty] | NA | NA
245 | SINGLE | Sara is the Scrum Master for the Project ABC. Rohan, development team member, developed one feature in his spare time and then discussed with Maria, Product Owner, to show the usefulness of this feature. However, Maria rejected the feature which cause some conflict between Maria and Rohan. How should Sara handle this situation? | 4 | Ask both of them to resolve the issue among themselves | Agree with Maria and explain Rohan how new features should be incorporated in the product | Support Rohan and discuss with Maria how can this feature be included in the product | Take the middle path by telling Maria that from next time onward, new features should be included in the product. |  |  | 2 | 1 | PMP | People | Project Integration Management |  |  | High Complex | Agile Hybrid | Correct answer is B. Product Owner owns the responsibility of deciding which features should be included in the product and what would be their priorities. | 44198 | N | 4 | [5 empty] | NA | NA
246 | SINGLE | Cathrina, Product Owner, is quite busy and shared with Scrum Master that she would not be available for the sprint planning meeting. What might happen if Cathrina is not available for the Sprint Planning? | 4 | Scrum Master will play the Product Owner role | Senior most development team member will play the Product Owner role | Sprint planning meeting will be postponed | Product increment may not meet the required expectations |  |  | 4 | 1 | PMP | People | Project Integration Management |  |  | High Complex | Agile Hybrid | Correct answer is D. Since Cathrina is not available for the sprint planning meeting, therefore, in case any query comes regarding requirement clarification or definition of done then that might not be clarified. | 44198 | N | 4 | [5 empty] | NA | NA
247 | SINGLE | An agile team of a large organization decided to use earned value management (EVM) metrics to report to senior management and provided metrics at the iteration level. What could the team improve upon? | 4 | Nothing. The agile team used EVM metrics appropriately | The agile team should avoid using EVM metrics | The agile team should avoid using EVM metrics at the iteration level | The agile team should provide metrics at the user story level |  |  | 3 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | Answer: C In agile projects, when providing earned value management (EVM) metrics to senior management of a large organization, reporting at the iteration level, which would have typically happened every two weeks, could be too detailed. Reporting at the user story level is even more granular. In large organization, it’s reasonable to assume that senior managers would be interested to see the project progress at the release level. Release level would allow them to understand the cadence and the progress of the agile project without going too deep into details, and, on the other hand, to see the big picture of the project as a whole. Therefore, to address the question at hand, i.e. to improve reporting to the senior management of a large organization, the agile team should avoid using EVM metrics at the iteration level. | 44198 | N | 4 | [5 empty] | NA | NA
248 | SINGLE | You are a project manager working on an enterprise resource planning project. In one of the meetings, you find that your team is not at its best behavior and not following proper meeting etiquette. To establish the rules of acceptable behavior which document should you refer to? | 4 | Organization Chart Template | Team Performance Assessments | Resource Management Plan | Team Charter |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The team charter establishes clear expectations regarding acceptable behavior by project team members. Early commitment to clear guidelines decreases misunderstandings and increases productivity. Discussing areas such as codes of conduct, communication, decision making, and meeting etiquette allows team members to discover values that are important to one another PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.1.3.2 TEAM CHARTER, pp356 | 44198 | N | 4 | [5 empty] | NA | NA
249 | SINGLE | A multinational organization was established in 1989. Recently, they have bagged one of the big contracts they have ever worked on. The organization is excited about it and is preparing to work on the project charter. Who will authorize the project charter? | 4 | A project sponsor delegates the work to the project manager | A project sponsor or initiator internal to the project | The customer | A project sponsor or initiator external to the project |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | The project charter is defined as a document issued by the project sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. PMBOK® Guide Sixth Edition (2018), 4. Project Intergration Management / 4.1 Develop project charter , p112 | 44198 | N | 4 | [5 empty] | NA | NA
250 | SINGLE | Buns is a senior software engineer. His company plans to launch the Google Pay feature on their app so that the end user can pay for orders in a more convenient fashion. The team is working on the scope baseline and it is almost complete. All of the following are parts of the scope baseline except | 4 | Scope Management Plan | Project Scope Statement | WBS | WBS Dictionary |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | The scope management plan is a component of the project or program management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The development of the scope management plan and the detailing of the project scope begin with the analysis of information contained in the project charter the latest approved subsidiary plans of the project management plan, historical information contained in the organizational process assets, and any other relevant enterprise environmental factors. PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.1 Plan scope management , pp 171 | 44198 | N | 4 | [5 empty] | NA | NA
251 | SINGLE | Fill in the blank: In the Create WBS process, deliverables are identified at the ______ Level in Work Breakdown Structure (WBS) | 4 | Lowest | Highest | Control Account | Maximum |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Simple | Predictive Approach | Lowest level item in WBS are the deliverables. Best choice is A. | 44198 | N | 4 | [5 empty] | NA | NA
252 | SINGLE | You are a project manager. You plan to introduce the Requirements Traceability Matrix in your organization and start documenting its key benefits. The requirements traceability matrix help trace all of the following except: | 4 | Requirements to project scope | Requirements to project objectives | Requirements to project risk | Requirements to test strategy |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. It provides a means to track requirements throughout the project life cycle, helping to ensure that requirements approved in the requirements documentation are delivered at the end of the project. Finally, it provides a structure for managing changes to the product scope. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.2.3.2 REQUIREMENTS TRACEABILITY MATRIX, p185 ¦ Project Managers Portable Handbook, 3rd Ed (2010) Section 5 Project Leadership / 5.8.2 Decision-Making Considerations | 44198 | N | 4 | [5 empty] | NA | NA
253 | SINGLE | Soniya is evaluating the resources required create a team. She realizes that she needs a technical expert for the project as the project is running in crtical design stage. She would have put in a request for the resource to be assigned but she is aware of the fact that the resource manager is currently strained for resources. Which of the following techniques should she use to convince the resource manager to assign the required resource? | 4 | Expert Power | Negotiation | Force or Direct Power | Referent Power |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | When ever there is convincing required, there should be negotiation involved as referrent power may work for very short time but right negotiation may lead to right resources at right time hence the best choice is B. | 44198 | N | 4 | [5 empty] | NA | NA
254 | SINGLE | You are in the process of creating an activity list. One of your colleagues recommends that you subdivide the project into smaller components, called activities. Which tool are they talking about? | 4 | Decomposition | Rolling Wave Planning | Expert judgment | Parametric Estimating |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | High Complex | Predictive Approach | Decomposition is a technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts. The work package is the work defined at the lowest level of the WBS for which cost and duration can be estimated and managed. The level of decomposition is often guided by the degree of control needed to effectively manage the project. The level of detail for work packages will vary with the size and complexity of the project. PMBOK® Guide Sixth Edition (2018) 5. Project Scope Management / 5.4.2.2 DECOMPOSITION, p195 | 44198 | N | 4 | [5 empty] | NA | NA
255 | SINGLE | While working on the development of an e-commerce website, your customer is really interested in the approach you will be using to design a specific functionality as it will help reduce the lead times. Which technique are you using here? | 4 | Process Analysis | Decision Making | Problem Solving | Design for X |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can be different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management/ 8.2.2.6 DESIGN FOR X, p332 | 44198 | N | 4 | [5 empty] | NA | NA
256 | SINGLE | Agile promotes servant-leadership. Which of the following is usually not considered a servant-leadership skill? | 4 | Remove impediments to the progress | Shield the team from interruptions | Carry food and water | Backlog grooming |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | Backlog grooming is the responsibility of Product Owner. Best choice is option D. | 44198 | N | 4 | [5 empty] | NA | NA
257 | SINGLE | Your company receives a new contract. It's your responsibility to look at different vendors on one of the modules of the project. However, you will make this decision once you actively start working on the project. To be prepared, you plan on increasing the existing list of sellers. Which technique can you use? | 4 | Bidder conferences | Advertising | Make-or-buy analysis | Independent estimates |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | Advertising is communicating with users or potential users of a product, service, or result. Existing lists of potential sellers often can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications. Most government jurisdictions require public advertising or online posting of pending government contracts. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management /12.2.2.2 ADVERTISING, p534 | 44198 | N | 4 | [5 empty] | NA | NA
258 | SINGLE | Mary is at a senior position in the procurement team. She only gets Involved if there is major escalation. It so happens that the team is not happy with the way a vendor is currently working on the project. Stacy, another project manager reaches out to Mary to discuss the performance of the vendor. Which process is Stacy performing? | 4 | Plan Procurement Management | Control Procurements | Conduct Procurements | Monitor Risks |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Best choice as PM is trying to manage issues in the project. Best choice is B. PMBOK® Guide Sixth Edition (2018) 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 44198 | N | 4 | [5 empty] | NA | NA
259 | SINGLE | Your organization has quality standards that need to be implemented for each project. In which process can you achieve this? | 4 | Plan Quality Management | Control Quality | Manage Quality | Manage Project Knowledge |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and all the projects need to do the same. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 44198 | N | 4 | [5 empty] | NA | NA
260 | SINGLE | Kapil is a senior security analyst for a company. Recently, his company faced criticism for their new product. So, the CEO has instructed the quality team to conduct more stringent checks on deliverables. What process should Kapil perform now? | 4 | Plan Communications Management | Validate Scope | Control Quality | Manage Quality |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Manage Quality uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders. This process is performed throughout the project and is best suited when root cause analysis needs to be done. Best choice is C. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2 MANAGE QUALITY pp325 | 44198 | N | 4 | [5 empty] | NA | NA
261 | SINGLE | The total budget for your project is $200,000 and there is a total of 1000 hours of work scheduled to be completed during the project. At this point, you have spent $30,000 and you should have completed 300 hours worth of work. However one of your critical resources is not allocated 100% on this project which has resulted in completion of only 200 hours, worth of work. What is projects status? | 4 | CPI= 1.3, SPI= 0.6 Under Budget, Behind Schedule | CPI=0.6 , SPI=1.3 Under Budget, Ahead of Schedule | CPI=0.8 , SPI= 0.9 Over Budget, Behind Schedule | CPI=1.6, SPI= 0.9 Under Budget, Behind Schedule |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | Cost per day = 200000/1000= 200 EV = 200 *200= 40000 PV= 300*200= 60000 AC= 30000 CPI = EV/AC = 1.3 SPI= EV/PV=0.6 Best choice is A. A CPI over 1 means the project is under budget and SPI under 1 means Behind schedule. PMBOK® Guide Sixth Edition (2017), 7. Project Cost Management / 7.4.2 Control Costs: Tools and Techniques, pp260-263 | 44198 | N | 4 | [5 empty] | NA | NA
262 | SINGLE | You are a project manager of a transformation project. Initially, the team was not collaborative and open to different ideas and perspectives which created a counterproductive environment. However, you work with your team lead and the situation improves. The environment improving and team is wanting to collaborate. Which stage is your project in? | 4 | Forming | Storming | Norming | Performing |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Normalising with each other and is in Norming phase. hence the best choice is C. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 44198 | N | 4 | [5 empty] | NA | NA
263 | SINGLE | Justin is working on call center implementation project where requirements and market assessment are complete. However, he is not sure of the total effort involved in implementing the whole call center. Since the scope of work cannot be accurately estimated, Justin wants to agree to the per unit rates for all the services. What type of Contract should Justin use? | 4 | Cost-Plus-Fixed-Fee (CPFF) | Time & Material (T&M) | Lump Sum Contract | Cost-Plus-Award-Fee (CPIF) |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Medium | Predictive Approach | Time and material contracts (T&M). Time and material contracts (also called time and means) are a hybrid type of contractual arrangement with aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. rate card is a must for a T &M contract which is true in the current case. Best choice is B. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement management / 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS, p509 | 44198 | N | 4 | [5 empty] | NA | NA
264 | SINGLE | Rita is a product owner responsible for the company’s line of smart digital music devices. During an afternoon working session, she works with the team to review user stories in preparation for the next sprint. Her intention is to ensure the team knows enough about the stories and how large they are in relation to each other. What activity is Rita performing? | 4 | Sprint planning | Backlog refinement | Sprint retrospective | Daily stand-up |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Agile Hybrid | Rita is in the process of refining the backlog in order to prepare for the next iteration. Engaging the team allows everyone to be aligned on the stories, relative to one another. Best choice is B. | 44198 | N | 4 | [5 empty] | NA | NA
265 | SINGLE | You are working with the customer to confirm whether she has formally accepted the deliverable or not. Which process are you presently in? | 4 | Validate Scope | Close Project or Phase | Control Quality | Control Procurements |  |  | 1 | 1 | PMP | Process | Project Scope Management |  |  | Medium | Predictive Approach | Validate Scope is the process of formalizing acceptance of the completed project deliverables. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. This process is performed periodically throughout the project as needed. Project Manager's Portable Handbook, 3rd Ed (2010), 5 Project Scope Management / 5.3 VALIDATE SCOPE, pp 655 | 44198 | N | 4 | [5 empty] | NA | NA
266 | SINGLE | Mohammad is in the process of identifying the project risks. Which of the following is the most essential for him and his team members to identify all the important risk and work more effectively during the identification process? | 4 | Urgency | Probability | Impact | Risk categories |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | Risk categories. Provide a means for grouping individual project risks. A common way to structure risk categories is with a risk breakdown structure (RBS), which is a hierarchical representation of potential sources of risk. An RBS helps the project team consider the full range of sources from which individual project risks may arise. This can be useful when identifying risks or when categorizing identified risks. The organization may have a generic RBS to be used for all projects, or there may be several RBS frameworks for different types of projects, or the project may develop a tailored RBS. Where an RBS is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Right category helps identify right owner, hence it is very important to have the accurate risk categories. Best choice is D. The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 11. Communication Planning / Communication process, Determine Communications Requirements | 44198 | N | 4 | [5 empty] | NA | NA
267 | SINGLE | Recently two of your direct reports had a heated discussion on the core implementation of the platform. They tried to resolve it between themselves but things got out of control. You intervened and started discussing the promotion scenario, which will eventually increase their yearly salary packages. The two direct reports became calm and continued doing their work. What type of conflict management technique did you use? | 4 | Withdrawal | Smooth | Reconcile | Motivation and Recognition |  |  | 2 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Smooth/accommodate. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.In this situation, since manager is not talking about differences and working on PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 44198 | N | 4 | [5 empty] | NA | NA
268 | SINGLE | You are working on an enterprise project whose purpose is to replace the already existing application monitoring tool with a more cost-effective solution. To achieve this, you write the RFP to request additional fund. Which communication style should you choose? | 4 | Formal and horizontal | Formal and upward | Informal and external | Formal and downward |  |  | 2 | 1 | PMP | Process | Project Communication Management |  |  | Complex | Predictive Approach | RFP is always formal and any request for fund will always be directed Upward to the sponsor or project governance board. Hence the best choice is Formal & upward communication for making RFP successful. | 44198 | N | 4 | [5 empty] | NA | NA
269 | SINGLE | You are in the process of implementing some steps to ensure that the impact of a risk is minimized, Which process you currently performing? | 4 | Implement Risk Responses | Plan Risk Responses | Plan Risk Management | Direct and Manage Project Work |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | High Complex | Predictive Approach | Implement Risk Responses is the process of implementing agreed-upon risk response plans. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities. This process is performed throughout the project. In the current scenario PM is implementing risk responses to reduce the impact. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.6 IMPLEMENT RISK RESPONSES, p486 | 44198 | N | 4 | [5 empty] | NA | NA
270 | SINGLE | You are a project manager working on revamping the company's website. Your team has developed the project's deliverable. Before going into the user acceptance phase, you want to ensure that your team does all the necessary testing. Which type of cost is this? | 4 | Prevention Cost | Appraisal Cost | Internal Failure Cost | External Failure Cost |  |  | 2 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Appraisal costs. Costs related to evaluating, measuring, auditing, and testing the products, deliverables, or services of the specific project. This is the best suited cost for testing. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Managemment / 8.1.2.3 DATA ANALYSIS, p319 | 44198 | N | 4 | [5 empty] | NA | NA
271 | SINGLE | Monalisa is a project manager for a big multinational construction company. She is giving a presentation to the project governance board to display the project schedule which contains the key deliverables. Which tool/diagram is she displaying? | 4 | Project schedule network diagram | Gantt chart | Milestone chart | WBS |  |  | 3 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Milestone charts. These charts are similar to bar charts, but only identify the scheduled start or completion of major deliverables and key external interfaces. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.5.3.2 PROJECT SCHEDULE, p254 | 44198 | N | 4 | [5 empty] | NA | NA
272 | SINGLE | Three of your stakeholders have approached you regarding the difficulty they are having with one of your team members. This team member is making inappropriate jokes, continually interrupts others, and is argumentative and unwilling to listen to the stakeholders’ ideas. What is the offending team member lacking in this situation? | 4 | Training | Ground rules | Interpersonal and team skills | Team-building activities |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Medium | Predictive Approach | While all options listed may help the situation, interpersonal and team skills is the prominent area that the offending team member lacks. Best choice is C in the current situation. The interpersonal and team skills used when developing the project management plan include: Conflict management, Facilitation & Meeting management. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.2.2.3 INTERPERSONAL AND TEAM SKILLS, p123 | 44198 | N | 4 | [5 empty] | NA | NA
273 | SINGLE | Your sponsor wants you to provide more details about the final report you have submitted. Which process will you perform to fulfill her request? | 4 | Manage Communications | Monitor Communications | Manage Stakeholder Engagement | Close Project or Phase |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 44198 | N | 4 | [5 empty] | NA | NA
274 | SINGLE | You are the functional lead of your project. Recently, a team member has joined your project and you are impressed with the functional knowledge he possesses. For the past few weeks, you are having multiple conflicts with him over technical decisions that need to be taken. Both of you explain the situation to the project manager and instead of having a dialogue, she decides in favor of the new team member. Which resolution technique did the project manager use? | 4 | Problem Solving | Avoid | Reconcile | Direct |  |  | 4 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | Force/direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. This approach often results to a win-lose situation. In the current situation Project manager has taken decision to take decision in favour of new team member hence Forcing style of conflict resolution works here. PMBOK® Guide Sixth Edition (2018), 4. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p386 | 44198 | N | 4 | [5 empty] | NA | NA
275 | SINGLE | You are the risk manager for your organization. One of the project managers from the PMO departments asks you about who all should be involved in the risk identification process. What should your response be? | 4 | Those who are invited to the risk identification process. | Risk management is not done by all organizations, so only the key project stakeholders should be involved in identifying the risks. | The project manager only | All project stakeholders |  |  | 4 | 1 | PMP | People | Project Risk Management |  |  | Complex | Predictive Approach | All the project stakeholders need to participate in the risk management process. Hence PM should incude all the stakeholders. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management / 11.2 Identify Risks, p446 | 44198 | N | 4 | [5 empty] | NA | NA
276 | SINGLE | Your sponsor has requested that you update all the records to ensure that the final results updated with right results. Which process are you currently performing? | 4 | Validite Scope | Close Project or Phase | Control Quality | Monitor Communications |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | Close Project or Phase is the process of finalizing all activities for the project, phase, or contract. The key benefits of this process are the project or phase information is archived, the planned work is completed, and organizational team resources are released to pursue new endeavors. This process is performed once or at predefined points in the project. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.7 CLOSE PROJECT OR PHASE, p158 | 44198 | N | 4 | [5 empty] | NA | NA
277 | SINGLE | You are working on a project where one of the components require you to outsource the work. So you conduct a bidder conference where you invite all the vendors in one room to ask questions. As a result of the bidder conference, all the sellers submit their bids. What should you do next? | 4 | Select a seller | Select the seller with the lowest bid | Receive the seller proposal | Sign an agreement with the selected seller |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | Once the bidder conference is done and proposals have come from Bidders, as a process, we will have to select the Seller. In the current situation best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management | 44198 | N | 4 | [5 empty] | NA | NA
278 | SINGLE | Jack is a new project manager who is using a multi-dimensional model to identify the stakeholders on his project. He believes that this technique will help him develop an effective communication strategy. What tool is Jack using? | 4 | Salience Model | Power/Interest Grid | Prioritization Matrix | Stakeholder Cube |  |  | 4 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Stakeholder cube. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. It provides a model with multiple dimensions that improves the depiction of the stakeholder community as a multidimensional entity and assists with the development of communication strategies. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management / 13.1.2.4 DATA REPRESENTATION, p549 | 44198 | N | 4 | [5 empty] | NA | NA
279 | SINGLE | Your team is comprised of engineers, technicians and system solution architects. Since there are many technical people in your project, you have to resolve conflicts between team members often. Initially the team was not collaborative and was not open to differing ideas. But now they are working as a well-organized unit. What Stage is your project in? | 4 | Forming | Storming | Norming | Performing |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. The team is Performing with each other.Hence the best choice is D. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 | 44198 | N | 4 | [5 empty] | NA | NA
280 | SINGLE | You are managing a project that is running smoothly without risks or insues. Suddenly, you have been hit by an unknown risk and you have decided to stop work immediately. The contracted work has already begun and you are not sure how to handle this situation. What should you do next? | 4 | Refer contract documents. | Instruct the contractor to stop the work immediately | Refer to Risk register to find response to the risk. | Setup a meeting with the team to discuss the work that can be completed before officially bringing the project to a halt. |  |  | 1 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Whenever the unknown risks hit the project, the best situation is to refer the contract documents to understand the impact of the unknowm risk and see the coverage the agreement provides due unknown risk. Best choice is A. PMBOK® Guide Sixth Edition (2018), 11. Project Risk Management | 44198 | N | 4 | [5 empty] | NA | NA
281 | SINGLE | Our team has done an outstanding job, and you have notified their functional managers that their assignment is over. They are all reluctant to go back to their functional work group and are sorry to see the project come to an end. They enjoy working for you and say this project, and working for you, has been one of the best experiences of their career. Which of the following does this describe? | 4 | The adjourning stage of team development | That you are likely a Theory Y manager | Maslow’s performing level on the Hierarchy of Needs | Recognition and rewards |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | This describes the adjourning stage of team development. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. In the current scenario, the best choice is A. PMBOK® Guide Sixth Edition (2018), 7. Project Resource Management / 9.4 DEVELOP TEAM, p375 PMBOK® Guide Sixth Edition (2018), 5. Project Scope Management / 5.5.3.1 Accepted Deliverables, p166 ¦ The Project Management Tool Kit: 100 Tips and Techniques for Getting the Job Done Right (2010), 88. Scope verification / Scope Process | 44198 | N | 4 | [5 empty] | NA | NA
282 | SINGLE | You are in the final stages of your project. You are creating new information which will eventually contribute to organizational learning. Which process are you currently performing? | 4 | Manage Project Knowledge | Direct and Manage Project Work | Close Project or Phase | Validate Scope |  |  | 1 | 1 | PMP | Process | Project Integration Management |  |  | High Complex | Predictive Approach | PM is manafing project knowledge to contribute to oranisational learning through Manage project Knowledge. Manage Project Knowledge is the process of using existing knowledge and creating new knowledge to achieve the project’s objectives and contribute to organizational learning. The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes, and knowledge created by the project is available to support organizational operations and future projects or phases. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.4 MANAGE PROJECT KNOWLEDGE, p 135 | 44198 | N | 4 | [5 empty] | NA | NA
283 | SINGLE | Kelly is a manager for the Machine designe team. She has acquired a critical resource who is disabled. Because of this, the resource is unable to come to office on a daily basis but is doing a great job. Which tool was used to acquire this resource? | 4 | Decision Making | Interpersonal and Team Skills | Pre-Assignment | Virtual Teams |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | The use of virtual teams creates new possibilities when acquiring project team members. Virtual teams can be defined as groups of people with a shared goal who fulfill their roles with little or no time spent meeting face to face. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Best choice is D. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.4 VIRTUAL TEAMS p370 | 44198 | N | 4 | [5 empty] | NA | NA
284 | SINGLE | Laurie is working as a project manager for a luxury sports car manufacturer. A key stakeholder reaches out to her asking for a budget related change. Laurie, without hearing much detail says "No."What conflict resolution techniques Laurie using? | 4 | Withdrawal | Smooth | Compromise | Laurie did not use proper change control process |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Laurie is using the Withdrawal style which is Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.5.2.1 INTERPERSONAL AND TEAM SKILLS, p385 | 44198 | N | 4 | [5 empty] | NA | NA
285 | SINGLE | You are working to implement the WBS process for a new project in your organization. Prior to this project, nobody has formally used this process. One of your colleagues tells you that the lowest level of WBS is known as work package but they are not sure about the most detailed level of WBS. What is your response to them? | 4 | WBS element is the most detailed level of WBS. | Work package is the most detailed level WBS. | Control account is the most detailed level of WBS. | Planning package is the most detailed level of WBS. |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  | High Complex | Predictive Approach | By Defination: Work Package. The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed. PMBOK® Guide Sixth Edition (2018), 5. Project scope management / 5.4.2.2 DECOMPOSITION, p195 | 44198 | N | 4 | [5 empty] | NA | NA
286 | SINGLE | Jason is working with a customer's core team to identify the stakeholders on the project. Prior to setting up a face to face session with the group, he develops a questionnaire and sends it out to the core team. He gives them a week to go through the questions and then they can continue the process. Which technique did Jason use? | 4 | Brain Writing | Brainstorming | Expert Judgment | Stakeholder Analysis |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Brain writing. A refinement of brainstorming that allows individual participants time to consider the question(s) individually before the group creativity session is held. The information can be gathered in face-to-face groups or using virtual environments supported by technology. PMBOK® Guide Sixth Edition (2018),13. Project Stakeholder Management / 13.1.2.2 DATA GATHERING, p548 | 44198 | N | 4 | [5 empty] | NA | NA
287 | SINGLE | You sent out the weekly status report to stakeholders. After that, you call up the sponsor to make sure he has received the report. What process are you in? | 4 | Plan Communications Management | Manage Communications | Monitor Communications | Monitor Stakeholder Engagement |  |  | 2 | 1 | PMP | Process | Project Communications Management |  |  | Medium | Predictive Approach | Manage Communications is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. PM is doing manage communications by making sure that the report has been recieved by the sponsor. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management / 10.2 Manage Communications, p416 | 44198 | N | 4 | [5 empty] | NA | NA
288 | SINGLE | You work for an organization that typically follows a functional organization. But, in this instance, you have been assigned as project manager. Your team shares many characteristics of a project team in a project-oriented organization. What kind of organization are we talking about? | 4 | A hybrid organization | A functional organization | A strong matrix organization | A composite organization |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Medium | Predictive Approach | The current situation is a combination of Functional and Projectised organisation. This the correct case of composite organisation. Best choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
289 | SINGLE | Recently you have been given an opportunity to establish a PMO department. You have created a plan for the implementation which included a 3-week training period in the project schedule. During the training phase, colleague asks about the difference between a project stakeholder and a key stakeholder. Who are considered key stakeholders? | 4 | Individuals, groups, or organizations in the decision-making positions | Individuals, groups, or organizations actively involved in the project | Individuals, groups or organizations affected by the project | Individuals, groups, or organizations that carry out the project work |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Key stakeholders are people in decision making positions who can make or break the project. ( Power & Influence of these stakeholders is high). | 44198 | N | 4 | [5 empty] | NA | NA
290 | SINGLE | Neil has been assigned an extra-large project. Due to the nature of the project, Neil requested an additional PM who can help him on few of the modules within the project. His request was rejected due to shortage of resources. Neil started working on the charter with the help of project sponsor and documented it as a risk. The sponsor is fully aware of the risk, but approved the project charter anyway. What should Neil do next? | 4 | Develop the project management plan | Analyze the risk and its impacts | Document the findings of the approved project charter | Identity the project stakeholders |  |  | 4 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | In the intiation phase of the project after charter is prepared, PM needs to identify stakeholders irrespective on any kind of risks in the project. Best choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
291 | SINGLE | Sandra is working with the quality team to make sure deliverable requirements are met. She has identified the defects and is checking the frequency of those defects on different-different dates. Which technique is Sandra using? | 4 | Checklists | Control Chart | Fishbone | Check Sheets |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Check sheets. Check sheets are also known as tally sheets and are used to organize facts in a manner that will facilitate the effective collection of useful data about a potential quality problem. They are especially useful for gathering attributes data while performing inspections to identify defects Best choice is D in current scenario. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.3.2.1 DATA GATHERING, p339 | 44198 | N | 4 | [5 empty] | NA | NA
292 | SINGLE | You are a PM in the PMO department. You are currently working on a project for a different department. As part of this project, you are gathering suggestions for improving the policies of the organization. Which process are you currently performing? | 4 | Manage Communications | Monitor Communications | Manage Stakeholder Engagement | Close Project or Phase |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 44198 | N | 4 | [5 empty] | NA | NA
293 | SINGLE | You are in the process of gathering feedback from stakeholders based on the tools documented in the Stakeholder Management Plan. You want to evaluate whether the stakeholders were satisfied or not. Which process group are you currently in? | 4 | Planning | Execution | Monitoring and Controlling | Closing |  |  | 4 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | Lessons learnt and process improvement documentation in done during close project or phase. In the current scenario, PM is doing the same. Hence best choice is D. PMBOK® Guide Sixth Edition (2018), 4.Project Integration Management / 4.7 CLOSE PROJECT OR PHASE p158 | 44198 | N | 4 | [5 empty] | NA | NA
294 | SINGLE | You are conducting your weekly meeting which involves the virtual team. After clarifying some module-related information, you ask your team whether your response has answered their question or not. Which technique did you use? | 4 | Cultural Awareness | Active Listening | Meeting Management | Feedback |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  | Complex | Predictive Approach | SInce PM is listening to all the points and responding to them, PM is Active listening. Techniques of active listening involve acknowledging, clarifying and confirming, understanding, and removing barriers that adversely affect comprehension. PMBOK® Guide Sixth Edition (2018), 10. Project Communications Management/ 10.2.2.6 INTERPERSONAL AND TEAM SKILLS, p423 | 44198 | N | 4 | [5 empty] | NA | NA
295 | SINGLE | You completed all the requirements for the project as per the requirements document. However, the customer is still not happy with the project. Being new to the business, you try to determine the cause so you don't lose any future business prospects. Which chart/diagram could be used in this scenario? | 4 | Why-Why Diagrams | Pareto Chart | Scatter Chart | Run Chart |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Cause-and-effect diagrams. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management / 8.2.2.4 DATA REPRESENTATION, p330 | 44198 | N | 4 | [5 empty] | NA | NA
296 | SINGLE | Craig is reviewing an agreement against its deliverables. He is ensuring that the vendor's performance is acceptable. Which process is he currently performing? | 4 | Conduct Procurements | Close Project or Phase | Control Procurements | Validate Scope |  |  | 3 | 1 | PMP | Process | Project Procurement Management |  |  | Medium | Predictive Approach | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process isthat it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 44198 | N | 4 | [5 empty] | NA | NA
297 | SINGLE | The total budget of 12-month project is $100,000. You have completed three months worth of work and are in the fourth month of your project. The total amount spent till now i $35.000. What is the project status? | 4 | Under Budget, Behind Schedule | Under Budget, Ahead of Schedule | Over Budget, Behind Schedule | Over Budget, Ahead of Schedule |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  | Medium | Predictive Approach | At the end of 3 months project should have spent 25,000 while the spent is 35,000 so project is over the budget & money spent is equal to 4.2 mont work so we are behind schedule as well. best choice is C. | 44198 | N | 4 | [5 empty] | NA | NA
298 | SINGLE | Recently, two of your team members went on a customer visit. You were in the process of making sure the expenditures submitted by them were accurate. Which process are you currently performing? | 4 | Control Resources | Control Procurements | Control Costs | Monitor risks |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | Control Resources is the process of ensuring that the physical resources assigned and allocated to the project are available as planned, as well as monitoring the planned versus actual utilization of resources and taking corrective action as necessary. The key benefit of this process is ensuring that the assigned resources are available to the project at the right time and in the right place and are released when no longer needed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.6 Control Resources, p389 | 44198 | N | 4 | [5 empty] | NA | NA
299 | SINGLE | A project manager using probability distributions to display data is most likely to use which of the following: | 4 | Uniform distributions | Normal distributions | Beta distributions | Lognormal distributions |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Best choice is C. All options provided are forms of probability distribution. The most commonly used probability distributions are beta distributions and triangular distributions. Since beta is the only one of the two included as an option, it is the best choice. PMBOK® Guide Sixth Edition (2018), / 7.2.2.5 THREE-POINT ESTIMATING, p281 | 44198 | N | 4 | [5 empty] | NA | NA
300 | SINGLE | You accepted your customer's request to involve your SME, James, in all important decision-making processes. You worked with your functional manager to acquire James. Which tool did you use to acquire James? | 4 | Virtual Teams | Interpersonal and Team Skills | Pre-Assignment | Decision Making |  |  | 3 | 1 | PMP | People | Project resource Management |  |  | Complex | Predictive Approach | When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent upon the expertise of particular persons. Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Since James was preassigned, hence best choice is pre-assignment. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management / 9.3.2.3 PRE-ASSIGNMENT, p370 | 44198 | N | 4 | [5 empty] | NA | NA
301 | SINGLE | Customer reached out to your team member to implement a cost related change which was initially rejected by the CCB. Your team member told you about it and you contacted the customer to prevent any unapproved changes from being included in the reported cost. Which process are you in? | 4 | Control Cost | Perform Integrated Change Control | Monitor Communications | Monitor Stakeholder Engagement |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | High Complex | Predictive Approach | Managing Changes is the part of Control cost which is being done by PM here. Control Costs is the process of monitoring the status of the project to update the project costs and managing changes to the cost baseline. The key benefit of this process is that the cost baseline is maintained throughout the project. This process is performed throughout the project. PMBOK® Guide Sixth Edition (2018), 7. Project Cost Management / 7.4 CONTROL COSTS, p294 | 44198 | N | 4 | [5 empty] | NA | NA
302 | SINGLE | You are in the initial stages of a project where you have to decide on which project methodology to use. You are in favour of the normal software development life cycle approach; however the SMEs want to do agile methodology instead. Which of the following is not a true statement regarding the generic life cycle of a project? | 4 | Cost and Staffing Levels are low at the start | Risk and uncertainty are greatest at the start of the project | The ability to influence the final characteristics of the project's product is highest at the start of the project | Risk and uncertainty factors do not decrease over the life of the project. It remains constant throughout the project |  |  | 4 | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Predictive Approach | Option A,B,C are all true statements. Project Risk and uncertainties cannot remain constant through out the lifecycle of the project. Best choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
303 | SINGLE | You are a project manager in an advertising firm and one of your advertisements recently won the Best Advertisement of the Year award. You want to replicate the same success in your new project. Since time is critical for the new project, you want to save time during the WBS creation process. How can you achieve this? | 4 | Allocate a new resource from the bench and assign this work to her. | Use a previous WBS from a similar project as a template. | Using the WBS is not mandatory. It changes from project to project and industry to industry You can skip the process it time is a constraint. | Since time is a constraint, don't create a detailed WBS. |  |  | 2 | 1 | PMP | Process | Project Scope Management |  |  | Complex | Predictive Approach | Any OPA can be used on the new project. If there is a similar WBS in the previous project, PM can use the same to save on time. best choice in current situation is B. | 44198 | N | 4 | [5 empty] | NA | NA
304 | SINGLE | Mary is a seasoned project manager who is working on the stakeholder analysis of the project. Some people from different departments of the organization are not supporting the project. These people have the power to directly impact the project. Why should Mary add these people to the stakeholder register? | 4 | Such people are called negative stakeholders and as project manager, Mary should ensure that she is closely managing them. | Since these people are not part of the same department, they are not considered stakeholders; however thay should be added to the stakeholder registar because they can have a huge impact on the project. | They can be potential project stakeholders, so Mary is ahead of the game by adding them to the stakeholder register. | She needs to add them as their names have been identified during the identify Stakeholders process. |  |  | 1 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Stakeholders have 3 characteristics: Power, Interest and Influence. These stakeholders have power and not positive stakeholders. Mary needs to manage them closely. hence the best choice is A. | 44198 | N | 4 | [5 empty] | NA | NA
305 | SINGLE | You are a project manager working in the construction industry. Your team has decided on the following the tasks: Task A: Design the architecture. Task B: Use the architecture to create the rooftop. Tack C: Procure tiles for the floor. What kind of relationship exists between Task A and Task B and between Task B and Task C? Kindly note that Task B must finish before Task C can finish. | 4 | Finish-to-Start between Task A and Task B and Finish-to-Finish between Task B and Task C. | Finish to Start between Task A and Task B and Start-to-Finish between Task B and Task C. | Start-to-Finish between Task A and Task B and Finish to-Finish between Task B and Task C. | Start-to-Finish between Task A and Task B and Finish-to-Start between Task B and Task C. |  |  | 1 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Predictive Approach | Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started. In the current scenario only choice A fits the best response to the relationship defined in the question. PMBOK® Guide Sixth Edition (2018), 11. Project Schedule Management / 6.3.2.1 PRECEDENCE DIAGRAMMING METHOD, p227 | 44198 | N | 4 | [5 empty] | NA | NA
306 | SINGLE | The project budget is $100,000 You have completed 20% worth of work, however you should have completed 30% of the work. The total money spent so far is $15,000. What in the projects status? | 4 | Under Budget, Behind Schedule | Under Budget, Ahead of Schedule | Over Budget, Behind Schedule | Over Budget, Ahead of Schedule |  |  | 1 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | 20 % of project is completed for you PV would be 20,000 but actual spent is only 15000 so it is under budget. Also we were supposed o finish 30 % work but only 20 % work is completed, so we are behind the schedule. Best choice is A. | 44198 | N | 4 | [5 empty] | NA | NA
307 | SINGLE | You are using a chart/diagram/technique where you are displaying the amount of work you have completed against the amount of work you need to deliver on a certain data. Which technique are you using to track your project? | 4 | Earned Value Analysis | Iteration Burndown Chart | Performance Reviews | Trend Analysis |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | High Complex | Agile Hybrid | Iteration burndown chart. This chart tracks the work that remains to be completed in the iteration backlog. It is used to analyze the variance with respect to an ideal burndown based on the work committed from iteration planning . A forecast trend line can be used to predict the likely variance at iteration completion and take appropriate actions during the course of the iteration. A diagonal line representing the ideal burndown and daily actual remaining work is then plotted. A trend line is then calculated to forecast completion based on remaining work. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6.2.1 DATA ANALYSIS, p263 | 44198 | N | 4 | [5 empty] | NA | NA
308 | SINGLE | You have procured one business analyst, two quality assurance analysts and two senior level developers from a vendor. Now the project is almost finished and you are in the process of closing out the contracts. Which process are you currently performing? | 4 | Control Procurements | Close Project or Phase | Close Procurements | Conduct Procurements |  |  | 1 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | Control Procurements is the process of managing procurement relationships; monitoring contract performance, and making changes and corrections as appropriate; and closing out contracts. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet the project’s requirements according to the terms of the legal agreement. This process is performed throughout the project as needed. Procurement closure is part of control Procurements. Best choice is A. PMBOK® Guide Sixth Edition (2018), 12. Project Procurement Management / 12.3 CONTROL PROCUREMENTS, p529 | 44198 | N | 4 | [5 empty] | NA | NA
309 | SINGLE | Nikhil is a project manager who recently delivered a product to a customer. After few months, the customer found out that there was a major bug in the product so they will no longer do business with Nikhil's company in the future. What type of cost is/was this? | 4 | Prevention Cost | Appraisal Cost | Internal Failure Cost | External Failure Cost |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Internal Failure Costs (Failures found by the project) • Rework • Scrap External Failure Costs (Failures found by the customer) • Liabilities • Warranty work • Lost business In current case, because customer found the issue hence it is External failure cost. Best choice is D. PMBOK® Guide Sixth Edition (2018), 8. Project Quality Management /8.1.2.3 DATA ANALYSIS ( Cost of Quality) , pp320 | 44198 | N | 4 | [5 empty] | NA | NA
310 | SINGLE | You have been asked to handle a project whose PM left the project without a formal handover. The first thing you notice is that the stakeholders are not happy. While determining the root cause, you find out that the project manager made a few decisions without the stakeholders consent. These decisions resulted in the change of the project's scope, without going through the integrated change control process. What should your first step be? | 4 | Do nothing because it's not your project and you are a temporary project manager. | Request your team members to update the requirements document to include the scope changes. | Inform the project's stakeholder that project scope has been changed without following the change control process | Talk to the CCB and put forth a formal change to include the proviously unauthorized changes made to the scope. |  |  | 3 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | First thing that PM needs to do is to talk to stakholders transparently and explain them the curret state of the the scope of project and once stakeholders agree get the formal cahnge request through CCB. Best choice in current scenario is option C. | 44198 | N | 4 | [5 empty] | NA | NA
311 | SINGLE | You have been tasked with creating the project charter for your new project. Who are you? | 4 | Director, as it in my job to assign resources on the project | Sponsor, as it is my job to authorize the project | Customer, as I need to provide the buyer organization with some sort of official documentation | Project manager, as I have been authorized by the sponsor |  |  | 2 | 1 | PMP | People | Project Integration Management |  |  | Simple | Predictive Approach | The project charter is the document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. It documents the high-level information on the project and on the product, service, or result the project. Sponsor is the person who authorizes the project through Project Charter. Best choice is B. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.1.3.1 PROJECT CHARTER p118 | 44198 | N | 4 | [5 empty] | NA | NA
312 | SINGLE | You are a project manager for a website development project. While analyzing the project network diagram, you determine that there are two paths that share the same duration and they are also the highest duration. You are reviewing high-risk taking activities on these paths. What type of tools and technique did you use? | 4 | Critical Path Method | Schedule Network Analysis | What-If Scenario Analysis | Resource Smoothing |  |  | 2 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Since PM is looking at the network diagrams closely and trying to derisk the same. This is part of schedule network analysis. Best choice is B. Schedule network analysis is the overarching technique used to generate the project schedule model. It employs several other techniques such as critical path method, resource optimization techniques, and modeling techniques.Additional analysis includes but is not limited to: 1. Assessing the need to aggregate schedule reserves to reduce the probability of a schedule slip when multiple paths converge at a single point in time or when multiple paths diverge from a single point in time, to reduce the probability of a schedule slip. 2.Reviewing the network to see if the critical path has high-risk activities or long lead items that would necessitate use of schedule reserves or the implementation of risk responses to reduce the risk on the critical path. PMBOK® Guide Sixth Edition (2018), 6 Project Schedule management /6.5.2.1 SCHEDULE NETWORK ANALYSIS, p246 | 44198 | N | 4 | [5 empty] | NA | NA
313 | SINGLE | Because of the high risk associated with the project, the sponsor has explicitly montioned that the project should run as smoothly as possible. If the project is not completed within the specified timeline, then the organization will loose million of dollars. Which of the following is not an example of monitor and control project work. | 4 | How to maintain integrity of project baselines. | Tracking project work to make sure that risk response plan is being executed. | Providing information to support status reporting | Providing forecasts to update current cost and scheduling information. |  |  | 1 | 1 | PMP | Process | Project Schedule Management |  |  | Medium | Predictive Approach | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan. The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. it doesnot acertain that integrity of baselines will be maintained. Best choice is A. PMBOK® Guide Sixth Edition (2018), 4. Project Integration Management / 4.5 MONITOR AND CONTROL PROJECT WORK, p142 | 44198 | N | 4 | [5 empty] | NA | NA
314 | SINGLE | Susan is a project manager who managing recruitment for the PMO office. While talking to her, the PMO director uses the term Progressive Elaboration often as it is heavily used on their projects. Which of the following is not a correct representation of the term Progressive Elaboration? | 4 | Rolling wave planning | One change request leading to another change | Working on the requirements that are currently filled and carrying out the remaining at later stages of the project. | Building a prototype and completing the requirements per prototype as things become clearer on the project |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Once change leading to other Is never a progressive elaboration. Best choice is B. Progressive Elaboration. The iterative process of increasing the level of detail in a project management plan as greater amounts of information and more accurate estimates become available. | 44198 | N | 4 | [5 empty] | NA | NA
315 | SINGLE | Abhishek has been chosen to manage a very large project for constructing a shopping mall. As a part of the project , Alan is creating a list of stakeholders to be involved in the project and their impact on the project. Who among the following people/group of people may not be actual stakeholders in the project? | 4 | The staff that will be maning the shopping mall parking | The shop owners of the shopping mall | A project manager in Abhiskek organization who just completed a similar project. | The accounting team of Abhishek Team |  |  | 3 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | All are stakeholders barring a PM who has completed a similar project. Best choice is C. | 44198 | N | 4 | [5 empty] | NA | NA
316 | SINGLE | The organization han identified multiple projects that are aimed at improving the infrastructure of the organization, productivity of workforce, and human resource management among others. These projects are geared towards satisfying different needs of the organization. What is this type called? | 4 | Management System | Program | Operations | Portfolio |  |  | 4 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | A portfolio is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. Portfolio management is defined as the centralized management of one or more portfolios to achieve strategic objectives. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 1.2.3.3 PORTFOLIO MANAGEMENT p52 | 44198 | N | 4 | [5 empty] | NA | NA
317 | SINGLE | Dave is a project manager who has bean assigned a new projecct. The project is critical as it contains high profile stakeholders in the project, Dave starts to acquire the resources as soon as he received the project charter from the sponsor. Did he do the right thing? | 4 | Yes.It is very important project, Dave has decided to acquire the team immediately, so that he can begin and deliver the work. | Yes. It is the right thing to do because project manager needs his team on the project to begin working | No. The project sponsor should have given him minimal resources to at least begin the work | No. Acquisition of the project team is primarily an Executing Process Group activity |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | Complex | Predictive Approach | PM cannot acquire team immediately post receiving charter as he needs to understand scope, timelines for deliveries, cost before he can come up with Kind of resources. Best choice in current scenario is D. | 44198 | N | 4 | [5 empty] | NA | NA
318 | SINGLE | You have recently been hired as project manager in an organization. On one of the project, the IT manager requests the project to be halted đue to a major network outage and you comply. What kind of organization are you working in? | 4 | Functional Organization | Hybrid Organization | Composite Organization | Balanced Matrix Organization |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Complex | Predictive Approach | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. The best choice in the current scenario is A. | 44198 | N | 4 | [5 empty] | NA | NA
319 | SINGLE | You recently received a new project for which you will have to provide training to the team members because some of the functionality lock difficult implement without the training. What type of cost will you classify this as? | 4 | Prevention Cost | Appraisal Cost | Internal Failure Cost | External Failure Cost |  |  | 1 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Prevention Costs (Build a quality product) • Training • Document processes • Equipment • Time to do it right Best choice is A as per the defintion of Prevention cost. | 44198 | N | 4 | [5 empty] | NA | NA
320 | SINGLE | Ram is a project manager. One of his recent project is scheduled to finish in 1.5 years is running on time However, due to a regulatory requirement, the customer requested him to complete the project in 1 year instead. Based on Ram's first reaction, he believes that the request is unachievable. What should Ram do next? | 4 | Since the project duration has decreased by 5 months, Ram should decrease the budget of the project by 30% which is equivalent to 6 months worth of work | Reduce the scope by 10% because critical path has changed. | Inform customer to not to do anything as it will result in product of lower quality | Inform the customer of the impacts, Then crash the project. |  |  | 4 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | PM should keep stakeholders informed about the impacts of crashing and then move forward. best choice is option D. Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration. PMBOK® Guide Sixth Edition (2018) PMI/PMBOK 6.5.2.6 SCHEDULE COMPRESSION/ p252 | 44198 | N | 4 | [5 empty] | NA | NA
321 | SINGLE | You are working for an organization that recently bagged a prestigious contract. Because of the size of the contract, the organization decided to create a special team to handle it. Your team may include full time staff from different departments who are developing their own set of operating procedure. What type of organization are you working in? | 4 | PMO | Strong Matrix Organization | Hybrid Organization | Composite Organization |  |  | 4 | 1 | PMP | Business Environment | Project Integration Management |  |  | Medium | Predictive Approach | Composite organisations are combo organisations which have characteristics of Functional and Projectised. Teams report to PM but have own processes that they follow. Best choice is option D as no other choice meets the kind of organisation mentioned in the scenario. | 44198 | N | 4 | [5 empty] | NA | NA
322 | SINGLE | Mahesh is a project manager who developed the Change Control Process that the customer has approved. The baseline are not established yet and the customer just requested a change in scope, What should he do in current situation | 4 | Ask the customer to go through the Change Control Process | Carry out the impact analysis and share the results with customer. | Reject the change until the baseline is established. | Share the Change Control form with the customer |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | Change request is any change from baseline. But sincethe baseline is not established yet, it is best to carry out impact analysis and include the same in the baseline. Best choice is B. | 44198 | N | 4 | [5 empty] | NA | NA
323 | SINGLE | Alyssa is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She is using a waterfall approach to carry out initial planning activities and will execute the work using an Agile-based approach. Alyssa is currently facilitating the estimating process to calculate the duration of the project’s activities. When she gets to the “run cable” activity, one team member tells her that in a past similar project, they ran a similar length of cable in 13 hours; another team member tells her that they can run 110 meters of cable per hour. The team will need to run a total of 1,320 meters of cable. Using the parametric estimating technique, how many hours will it take the team to run the cable? | 4 | 9 | 13 | 10 | 12 |  |  | 4 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Correct Answer- D. Parametric estimating is a quantitatively based estimating method that multiplies the quantity of work by the rate or uses an algorithm in conjunction with historical data to determine cost, budget, or duration estimates. Based on this definition, take 1,320 and divide by 110 to get 12. | 44198 | N | 4 | [5 empty] | NA | NA
324 | SINGLE | Your sponsor is not happy with the process you have used to prioritize the risks. She wants you to use more stringent way to re-prioritize the risks and update risk register. Which process are you currently performing? | 4 | Identify Risks | Perform Quantitative Risk Analysis | Perfom Qualitative Risk Analysis | Monitor Risks |  |  | 2 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. The key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. This process is not required for every project, but where it is used, it is performed throughout the project. Best choice is B as sponsor is asking Pm to do the Quantitative Risk Analysis. PMBOK® Guide Sixth Edition (2018) PMI/11.4 PERFORM QUANTITATIVE RISK ANALYSIS, p 465 | 44198 | N | 4 | [5 empty] | NA | NA
325 | SINGLE | Nancy is a new project manager who has just been assigned on a project which is in its early stages. She has been given the task to estimate the costs, but limited information is provided to her. Which of the following techniques will not be beneficial to her? | 4 | Top-down Estimating | Analogous Estimating | Three Point Estimating | Bottom-up Estimating |  |  | 4 | 1 | PMP | Process | Project Schedule Management |  |  | Complex | Predictive Approach | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. In the current situatipn PM is at tha beginning of the project and will not have lower level components. Hence Choice D is not a logical choice. | 44198 | N | 4 | [5 empty] | NA | NA
326 | SINGLE | You are a project manager. While calculating the estimate, you realize that you will need six resources for six months. You can only got four resources after nogotiating with the functional manager and a per the organizational policy, you can hire two more every six months. As a project manager what will be your next step? | 4 | Hire contractors in accordance with your organizational policy | Negotiate with functional menager to get the remaining 2 resources | Talk to project sponsor to get more resources | Don't do anything and request your signod resources to fast track the project |  |  | 1 | 1 | PMP | Business Environment | Project Integration Management |  |  | Complex | Predictive Approach | PM should follow organisation policy and procedures. PM should work on impact analysis and keep the stakeholders updated about the same.The best choice is A. | 44198 | N | 4 | [5 empty] | NA | NA
327 | SINGLE | Ronnie has classified the stakeholders on following thing: Group A Stakeholders who have ability to change the outcomes of this project. Group B: Stakeholders who want this projoct to be done ASAP. Group C: Stakeholders who are daily users and their involvement is appropriate. Which Technique is Ronnie using? | 4 | Power / Interest Grid | Power/impact Grid | Interest/Impact Grid | Salience Model |  |  | 4 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Salience model. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). There is an adaptation of the salience model that substitutes proximity for legitimacy (applying to the team and measuring their level of involvement with the work of the project). The salience model is useful for large complex communities of stakeholders or where there are complex networks of relationships within the community. It is also useful in determining the relative importance of the identified stakeholders. Best Choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
328 | SINGLE | One of your colleagues is experiencing trouble managing his project, which is already showing signs of poor performance. He feels that the project is too complex and has asked for your advice. Where should you direct him? | 4 | Offer to help him manage the project, even though you are currently at max capacity | Direct him to his functional manager, since it is his manager’s job to provide him with training | Direct him to the PMO | Explain that he must take responsibility for his own project, since you are dealing with your own project issues |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | Of the options provided, the project management office (PMO) would be the best choice. The PMO is responsible for providing project managers with training and resources. They also have archived organizational process assets, which would help in this scenario, along with training. Offering to manage the project with him is implying that you will take on part of his project and responsibility, which is an incorrect answer. Not offering any type of assistance is a poor choice, since part of our responsibility as project managers is to encourage and educate other project managers, although not at the expense of your own projects. | 44198 | N | 4 | [5 empty] | NA | NA
329 | SINGLE | A project manager of a retail chain of hardware stores is in the process of generating the project schedule. After the project manager issues the project assignments, a team member approaches him to say that he has a two-week planned vacation right in the middle of a critical activity. What did the project manager fail to do? | 4 | Call the team member in advance to see if their vacation can be rescheduled | Check the resource requirements for the affected activities | Cancel the team member’s scheduled vacation in advance | Check the resource calendars for team member schedule conflicts. |  |  | 4 | 1 | PMP | People | Project Stakeholder Management |  |  | Medium | Predictive Approach | It’s clear that the project manager did not check the resource calendars when creating the schedule. Resource calendars contain working and nonworking days of resources. This includes holidays, vacations, and when resources are idle. | 44198 | N | 4 | [5 empty] | NA | NA
330 | SINGLE | Kishore is in Las Vegas and works remotely from his home. Bryan is also remote and works from home as well. Carolyn, the project manager, resides on the same campus as four other team members, although they are in different buildings. To help the team feel connected, Carolyn opens a video conferencing link every workday beginning at 8 a.m. and closing it at 5 p.m. Each team member joins the stream and leaves the video open so that they feel as though they are in a virtual open workspace. What is this an example of? | 4 | Remote pairing | Web conference | Virtual desktop | Fishbowl window |  |  |  | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Agile Hybrid | A fishbowl window is a method of creating a shared virtual workspace to accommodate team members who are dispersed across multiple locations. Individuals can join a live video stream at the start of their workday and close it out at the end of the workday. This method is intended to increase collaboration. | 44198 | N | 4 | [5 empty] | NA | NA
331 | SINGLE | The project manager shifts to an agile approach for a project with an aggressive go-to-market timeline. The project manager needs to revise the stakeholder plan so that it follows agile principles. What should the project manager do to meet this need? |  | Design a digital communication system that allows for virtual submission, logging, reviewing, and escalation of issues. | Remove unnecessary layers of management to promote direct communication between the project team and stakeholders. | Modify templates to include product backlog progression and the burndown rate and encourage use of standups. | Increase the number of formal training workshops to cover all relevant issues for all stakeholders, including the project sponsor and client. |  |  | 3 |  |  | Business Environment | Project Integration Management |  |  | High Complex | Agile Hybrid | To facilitate timely, productive discussion and decision making, adaptive teams engage with stakeholders directly rather than going through layers of management. Often the client, user, and developer exchange information in a dynamic co-creative process that leads to more stakeholder involvement and higher satisfaction. In order to accelerate the sharing of information within and across the organization, agile methods promote aggressive transparency. PMBOK® Guide Sixth Edition (2018), 13. Project Stakeholder Management, p506 ¦ The Agile Practice Guide, Annex A1 PMBOK® Guide Mapping, p95 | 44198
332 | SINGLE | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project manager receives a request for completion within 9 months. How should the project manager respond to this proposed change in timeline? |  | Work with key stakeholders to identify project requirements that could be reduced. | Immediately ask project team members to increase the pace of each task within the project. | Ensure that substantial scope creep is included in the original project schedule, so that revised deadlines can be met. | Meet individually with project team members to discuss how aspects of the project can be completed more quickly than planned. |  |  | 4 |  |  | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | To execute the project quickly, the project team should discuss on the whole scope together and find out the way to complete tasks at individual level within short time. By the discussion, many tasks could be by-passed from the base tasks and new tasks can be identified, which might help the project to reduce the total time frame of the project. This is an agile mindset of the project manager, by which a better value can be served in terms of time. Effective Project Management: Traditional, Agile, Extreme, Hybrid (No Date) Robert K. Wysocki, Chapter 12 / Most of the solution is clearly known | 44198
333 | SINGLE | During an agile iteration, Task 1 cannot be completed on time due to unexpected challenges. Another team within the project is depending on timely completion of Task 1 in order to fulfill their part of the project. How should the project manager resolve this issue? |  | Meet with both teams separately, and ask them to figure out a way to meet the required deadlines and complete the project on time. | Meet with the product owner to reprioritize the iteration backlog, so that it does not impact other teams or obligations. | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule. | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in lessons learned. |  |  | 2 |  |  | Process | Project Integration Management |  |  | High Complex | Agile Hybrid | Hybrid approach might also involve evaluating iteration backlog items priorities to resolve time constraints. PMBOK® Guide Sixth Edition (2018), 6. Project Schedule Management / 6.6 Control Schedule, 224 ¦ The Agile Practice Guide (2017), 5. Implementing Agile: Delivering in an Agile Environment/5.3 Troubleshooting Agile Project Challenges, 58 | 44198
334 | SINGLE | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which two actions will help to resolve the issue? |  | Discuss the conflict with the project sponsor and formulate a response. | Replace the key team member with a new resource who has the same skills. | Meet with the change control board (CCB) to discuss the requested change. | Engage in the change management process to resolve the resource issue. |  |  | 3 |  |  | Process | Project Integration Management |  |  | Complex | Predictive Approach | PM should know how to handle key personnel changes and keep the team motivated and productive. PMBOK® Guide Sixth Edition (2018) 9, Project Resource Management / 9.5 Manage Team, 345-346 ¦ Project Managers Portable Handbook, 3rd Ed (No Date), Section 5/ 5.3.4 Coaching Techniques and Tools | 44198
335 | SINGLE | During a meeting, a project manager learns that a business result needs to be delivered in four weeks, although the original plan was sixteen weeks. The project manager also hears that there is no available technical resource who might be able to join the team. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? |  | Notify the project sponsor about the lack of a technical resource. | Immediately escalate the issue to decision makers in the organization. | Check with the technical resource manager to see if there is an available technical resource. | Since time is short, hire an outside party to meet the need for a technical resource. |  |  | 1 |  |  | Process | Project Resource Management |  |  | High Complex | Agile Hybrid | Per Agile manifesto, it values individual and interactions over processes and tools. Thus, it is best to meet with the resource manager to understand the real situation rather than informing sponsor first which might be the false alarm. PMBOK® Guide Sixth Edition (2018) Project Communications Management / 10.2.2.6 Interpersonal and Team Skills / Networking, p386 ¦ The Agile Practice Guide, 2.2 The Agile Manifesto and Mindset , p8 | 44198
336 | SINGLE | A project manager believes that a delay in developing a prototype was due to a lack of knowledge in a specific skill that was needed by the cross-functional team. How could the project manager prevent this situation on future projects? |  | Offer more specialized training throughout the project to the team. | Identify required strengths, and organize the team based on those strengths. | Meet with the project sponsor and team members to assign training for specific skills. | Empower team members to problem solve in situations where skills may be lacking. |  |  | 2 |  |  | People | Project Resource Management |  |  | Complex | Predictive Approach | Develop the human resource management plan by defining the roles and responsibilities of the project team members in order to create a project organizational structure and provide guidance regarding how resources will be assigned and managed. PMBOK® Guide Sixth Edition (2018), 9. Project Resource Management, 309 ¦ The Agile Practice Guide (2017), 4 Implementing Agile: Creating an Agile Environment / 4.3.3 Generalizing Specialists, p42 | 44198
337 | SINGLE | A new project manager joins the project’s daily standups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, standups often last well over two hours. What process should be used to deal with this issue? |  | Ask team members to invite their managers to standup sessions, in order to find solutions more quickly. | Explain to team members that long discussions take time away from actual work on the project. | Insert a new team member who will manage obstacles and schedule additional meetings to discuss possible solutions. | Tell the team members that they are required to shorten the standup meetings and improve on finding solutions. |  |  | 2 |  |  | Business Environment | Project Schedule Management |  |  | High Complex | Agile Hybrid | Most project manager's think if he has the daily startup, then he can apply agile way to manage the projects. But it is important for agile is how to implement the daily standup. Teams run their own standups. When run well, standups can be very useful, provided the nature of the team’s work requires intense collaboration. Identify the blockers on the standups but have separate meetings to discuss the blockers and the solution. The Agile Practice Guide (2017), Chapter 5 / 5.2.4 Daily Standups, 53 | 44198
338 | SINGLE | You have been given a responsibility to launch a new product. You decide to launch a prototype in your department first. Based on the positive feedback recoivod, you decide to launch it to a larger target group. Which technique are you using to take a decision? | 4 | Six Sigma | Problem Solving | Plan-Do Check Act | Cause and effect diagram |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | Medium | Predictive Approach | Continual improvement. The plan-do-check-act (PDCA) cycle is the basis for quality improvement as defined by Shewhart and modified by Deming. In addition, quality improvement initiatives such as total quality management (TQM), Six Sigma, and Lean Six Sigma may improve both the quality of project management, as well as the quality of the end product, service, or result. Best Choice is C. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p312 | 44198 | N | 4 | [5 empty] | NA | NA
339 | SINGLE | You are working for the quality control team. Your project in progress and is ready for inspection by the internal quality control team Since you have many projects in the pipeline, you were instructed to reduce the number of quality inspections, which would result in reduction of the project cost. Which technique would be best in this scenario | 4 | Control Chart | Matrix Bosed Charts | Statistical Sampling | Pareto Chart |  |  | 3 | 1 | PMP | Process | Project Quality Management |  |  | Medium | Predictive Approach | Statistical sampling. Statistical sampling involves choosing part of a population of interest for inspection (for example, selecting 10 engineering drawings at random from a list of 75). The sample is taken to measure controls and verify quality. Sample frequency and sizes should be determined during the Plan Quality Management process. PMBOK® Guide Sixth Edition (2018) PMI/PMI/p340 | 44198 | N | 4 | [5 empty] | NA | NA
340 | SINGLE | Stuart worked for company in the past. He learns that X is one of the vendors bidding on a project in his present company. Stuart has been selected to manage the project. In addition to being the manager on the project, he will also be a part of the committee that is in charge of selecting the vendor. What must Stuart do? | 4 | Stuart should excuse himself from the selection process as it is unethical. | Stuart should provide an honest feedback to his present company as it is an ethical thing to do | Notity the project stakeholders immediately and comply with the company's policies on how to handle in such a scenario. | Notify the stakeholders immediately and then Stuart should excuse himself from the selection process |  |  | 3 | 1 | PMP | People | Project Stakeholder Management |  |  | High Complex | Predictive Approach | Stuart should notify the stakeholders immedietaly to avoid any conflict of interest. Best choice is C. | 44198 | N | 4 | [5 empty] | NA | NA
341 | SINGLE | You are a project manager who has to deliver a presentation on his project status, Just before the meeting, you are informed that one of his key resources has been removed from the project. This can result in a significant delay in his project. However you are sure that you can use alternative resources to fill the gaps until a new resource is hired. What should you communicate in the meeting? | 4 | Don't communicate anything until you have all the facts to communicate to the group | Add this in the risk register | Inform the executive of the situation as is | Don't communicate anything to them as you have the workaround by adding the replacement. |  |  | 3 | 1 | PMP | People | Project Stakeholder Management |  |  | Complex | Predictive Approach | PM should report the true status to stakeholders, Best choice for PM is C as he needs to inform the situation as is. | 44198 | N | 4 | [5 empty] | NA | NA
342 | SINGLE | Anita is a new project manager who has recently started working on her first project. She is focused on controlling the key stakeholder engagement. This is one component of the project management plan which is not likely to be utilized during this process of the following, which is that one component? | 4 | Stakeholder expectations and communication management | Project management processes selected for the project | Human resource requirements | Change management process |  |  | 2 | 1 | PMP | Process | Project Stakeholder Management |  |  | Medium | Predictive Approach | Stakeholder engagement is needed all the following except B. Project Management process selection is done way before the start of the project. | 44198 | N | 4 | [5 empty] | NA | NA
343 | SINGLE | After discussing with stakeholders, your team come up with the list of risks. Now you are plotting these risks as bubbles. Few other parameters are depicted on X and Y axis. Moreover, the bubble size also depicts parameter. Which technique are you using? | 4 | Probability and Impact Matrix | Hierarchical Charts | Iteration Burndown Chart | Inice Diagram |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Simple | Predictive Approach | Hierarchical charts. Where risks have been categorized using more than two parameters, the probability and impact matrix cannot be used and other graphical representations are required. For example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are represented by the x-axis value, the y-axis value, and the bubble size. An example bubble chart, with detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. PMBOK® Guide Sixth Edition (2018) PMI/PMI/11.3.2.6 DATA REPRESENTATION/p462 | 44198 | N | 4 | [5 empty] | NA | NA
344 | SINGLE | A business analyst has just facilitated a requirements-gathering session. The following week, the project manager begins the process of capturing and documenting the project’s deliverables and creating a WBS. The business analyst and project manager are carrying out processes that belong to which of the following Knowledge Areas? | 4 | Project Schedule Management | Project Integration Management | Project Requirements Management | Project Scope Management |  |  | 4 | 1 | PMP | Process | Project Scope Management |  |  | Simple | Predictive Approach | The business analyst and the project manager have carried out activities relating to the following processes: Collect Requirements, Define Scope, and Create WBS. These processes belong to the Project Scope Management Knowledge Area. Project Requirements Management is not an official Knowledge Area. | 44198 | N | 4 | [5 empty] | NA | NA
345 | SINGLE | You have been hired as a contract project manager for Grapevine Vineyards. You are carrying out activities relating to procurement planning. Grapevine wants you to head up a project to design a new visitor center, tasting room, and gift shop. They also want to double the number of fermenting tanks and increase the size of the warehouse (which requires extensive temperature and environmental controls). Grapevine would like to have the bar in the tasting room constructed out of specialty marble that is available from only two places in the world. Grapevine management estimates this project will take three years. You are concerned about the availability of the specialty marble and know that the following are true. (Select three.) | 4 | The project schedule can influence this process. | The Determine Budget process can be influenced by this process. | The make-or-buy analysis can be influenced by this process. | Your organization’s business cycle might have an impact on this process. |  |  | 1,3,4 | 1 | PMP | Process | Project Procurement Management |  |  | High Complex | Predictive Approach | The Plan Procurement Management process can influence the project schedule (and vice versa). The Estimate Activity Resources process, make-or-buy decisions, and the organization’s business cycle may have an impact on the Plan Procurement Management process. Best choice is A,C & D. | 44198 | N | 4 | [5 empty] | NA | NA
346 | SINGLE | You are considered a rockstar project manager in your organization. You are in a project where your responsibility is mainly towards project coordination and you have little authority over project resource. Which type of organization is this? | 4 | Functional Organization | Weak Matrix | Balanced Matrix | Composite Organization |  |  | 1 | 1 | PMP | People | Project Integration Management |  |  | Simple | Predictive Approach | Functional Organization. An organizational structure in which staff is grouped by areas of specialization and the project manager has limited authority to assign work and apply resources. Best Choice is A since PM has no powers inspite being a Star PM. | 44198 | N | 4 | [5 empty] | NA | NA
347 | SINGLE | Quality is one of the most important aspect for your organization, As quality manager, you need one of the tools to show the relationship between two variables to help your team better understand the quality impacts. Which tool and technique did you use? | 4 | Design of Experiments | Fishbone Diagram | Pareto Chart | Scatter Diagram |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | Complex | Predictive Approach | Scatter diagrams. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Best Choice is D. | 44198 | N | 4 | [5 empty] | NA | NA
348 | SINGLE | Which of the following statement is true with respect to a typical project scenario? | 4 | It is very expensive to change anything in the beginning of the project. | Irrespective of whatever phase the project is in the influence of the stakeholders will remain the same throughout the project. | The request for resources increases during the executing stage of the project. | All the phases follow a finish-to-start relationship. You cannot start the next phase until all the deliverables are accepted and approved by the customer. |  |  | 3 | 1 | PMP | Process | Project Resource Management |  |  | Complex | Predictive Approach | The only correct scenario is C. Changes at beginning are not costly. Stakeholders change through out the project & FS cannot be only true in Project world. | 44198 | N | 4 | [5 empty] | NA | NA
349 | SINGLE | You work within a team that uses a feature-driven development approach to manage software projects. As the senior project manager on the team, you know from experience the criticality of communication. You often coach other project managers on the various elements of communication, which are incorporated within the models of communication exchange. Which of the following best explains these communication elements? | 4 | The elements of communication include encode, transmit, acknowledge, and feedback/response, and the communication model includes senders, receivers, and messages. | The elements of communication include senders, receivers, and messages, and the communication model includes verbal and written. | The elements of communication include senders, receivers, and messages, and the communication model includes encode, transmit, acknowledge, and feedback/ response. | The elements of communication include encode, transmit, acknowledge, and feedback/response, and the communication model includes verbal and written. |  |  | 2 | 1 | PMP | People | Project Communications Management |  |  | Medium | Predictive Approach | The best choice is B as The elements of communication include senders, receivers, and messages and the communication model includes verbal and written. This is the only true statement. | 44198 | N | 4 | [5 empty] | NA | NA
350 | SINGLE | Daisy is working for a product-based company which specializes in creating products for the automobile sector. A customer has asked for a specification change on the product and it has been approved by the CCB. Now Daisy is in the process of implementing it. Which process is she currently performing? | 4 | Manage Quality | Direct and Manage Project Work | Monitor and Control Project Work | Perform Integrated Change Control |  |  | 2 | 1 | PMP | Process | Project Integration Management |  |  | Complex | Predictive Approach | Best choice is B. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success. PMBOK® Guide Sixth Edition (2018) PMI/PMI/4.3 DIRECT AND MANAGE PROJECT WORK/p127 | 44198 | N | 4 | [5 empty] | NA | NA
351 | SINGLE | Shawn is a project manager in a foreign location On his first day, he receives a gift from his vendor The gift is not valuable in his home country but is extremely valuable in the foreign country. Shawn's corporate office policy prohibits employees from accepting gifts from vendors. However, since he is new to the location, he is not aware of local customs. What is the best way PM can respond to such a situation? | 4 | Accept the gift and, in return, gift something of equal value. | Reject the gift as it is against the company's corporate policy | Respectfully talk to the vendor and communicate to them that he is not sure of the corporate policy, and he needs to ask his management before accepting any gifts. | Accept the gift this time, as he doesn't want to hurt the vendors feeling, but later enquire about the corporate policy and inform the vendor so that vendor doesnot repeat this. |  |  | 3 | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Predictive Approach | PM needs to always follow policy as per organisations. If he is not sure, he needs to find out before any actions as implications of not following policy is high as this can be conflict of interest situation. Best choice is C to move forward. | 44198 | N | 4 | [5 empty] | NA | NA
352 | SINGLE | You are in the process of making sure team member conflicts are resolved amicably. You take strict actions as and when required. Which process are you currently in? | 4 | Plan Resource Management | Develop Team | Manage Team | Control Resources |  |  | 3 | 1 | PMP | People | Project Resource Management |  |  | Medium | Predictive Approach | Manage Team is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues. This process is performed throughout the project. Best choice is option C as PM is managing team based on current situation. PMBOK® Guide Sixth Edition (2018) PMI/PMI/9.5 MANAGE TEAM/p382 | 44198 | N | 4 | [5 empty] | NA | NA
353 | SINGLE | Monty is a new project manager in the vendor management department of the organization. He wants to make sure that none of the bidders receive preferential treatment while bidding for a contract. Which technique should he use to ensure unbiased bidding? | 4 | Expert Judgement | Bidder Conferences | Screening Techniques | Weighted Criteria |  |  | 2 | 1 | PMP | Process | Project Procurement Management |  |  | Complex | Predictive Approach | Bidder conferences (also called contractor conferences, vendor conferences, and pre-bid conferences) are meetings between the buyer and prospective sellers prior to proposal submittal. They are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment. PM is ensuring that process is fair and it is done in Bidder conferences. PMBOK® Guide Sixth Edition (2018) PMI/PMI/12.2.2.3 BIDDER CONFERENCES/p524 | 44198 | N | 4 | [5 empty] | NA | NA
354 | SINGLE | You have a very energetic project team. One of your team members has been classified by his teammates as brilliant. The team members are motivated by results, have good conflict-resolution skills, and are highly committed to the project, among other things. They have a solid understanding of the project goals and objectives and understand the direction the project is headed in. When their brilliant teammate questions the approach the team is using regarding one of the goals, you ask the team for their input and gather the facts before making a decision. You ask the team what they would do, and their conclusion is that the brilliant teammate is right and it’s better to go with his solution than the one they planned. What type of power is the teammate displaying, and what leadership style does the project manager possess based on this question? | 4 | Expert, democratic | Referent, democratic | Expert, situational | Legitimate, situational |  |  | 1 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Predictive Approach | This question describes expert power on the part of the brilliant teammate and a democratic leadership style because team members were asked for input before a decision was made. | 44198 | N | 4 | [5 empty] | NA | NA
355 | SINGLE | Your colleague has reported to their manager that they passed their PMP certification exam. You know this is inaccurate, since you both took your exams at the same time and the colleague shared the results with you. What should you do? | 4 | Give them an opportunity to correct their behavior and report them to PMI if they do not. | Don’t say anything. Since this is your friend, the code states that you must look out for each other. | Give your friend a difficult time to teach them a lesson and disassociate with them. | Tell their manager immediately and report the violation to PMI directly. |  |  | 1 | 1 | PMP | Business Environment | Project Resource Management |  |  | Complex | Predictive Approach | When you hold the PMP certification, one of the responsibilities is to report violations of the PMP code of conduct. In some cases, we make poor judgments that can be corrected. To maintain the integrity of the profession, everyone who holds the PMP certification must adhere to the code of conduct that makes all of us accountable to each other. | 44198 | N | 4 | [5 empty] | NA | NA
356 | SINGLE | You are using a hybrid life-cycle approach to manage your project and are creating the cost management plan. You have talked with your project sponsor and CFO and will document that you are rounding to the nearest thousand and will be using weeks to estimate resources. What two elements of the plan does this describe, respectively? | 4 | Control thresholds and units of measure | Units of measure and control thresholds | Rules of performance and level of accuracy | Level of accuracy and units of measure |  |  | 4 | 1 | PMP | Process | Project Quality Management |  |  | High Complex | Agile Hybrid | Level of accuracy describes your rounding precision, and units of measure describes how you will measure resources, for example, days, weeks, months. | 44198 | N | 4 | [5 empty] | NA | NA
357 | SINGLE | Making small, incremental improvements within a product or process is known as: | 4 | Halo effect | Kaizen | Kanban | Muda |  |  | 2 | 1 | PMP | Business Environment | Project Quality Management |  |  | Complex | Agile Hybrid | The concept of continuous improvement centers around the idea that small or incremental improvements within a product or process has the ability to reduce cost and keep consistency of performance. The word kaizen in Japan translates to “change for the better.” | 44198 | N | 4 | [5 empty] | NA | NA
358 | SINGLE | You are a project manager for Community Trends, a nonprofit organization. Your project has come about because of a social need. You’re calculating performance measurements, and you know the following information: BAC = 900, ETC = 65, PV = 500, EV = 475, and AC = 425. Which of the following statements is true? | 4 | This project is ahead of schedule, and costs are higher than planned. . | This project is behind schedule, and costs are higher than planned. | This project is behind schedule, but costs are lower than planned. | This project is ahead of schedule, and costs are lower than planned |  |  | 3 | 1 | PMP | Process | Project Cost Management |  |  | Complex | Predictive Approach | The SV for this project is –25, which means the project is behind schedule. The CV for this project is 50, which means the costs are lower than what you had planned for this point in time. | 44198 | N | 4 | [5 empty] | NA | NA
359 | SINGLE | You are the project manager for a company that produces mobile phone applications. Currently, the director of the consumer division is evaluating two projects. Funding exists for only one project. Project UV aims to produce a mobile phone application that sends alerts when the UV rays are at dangerous levels, alerting users to stay indoors; Project Fun aims to send alerts when it detects that users have not visited any destinations outside of their usual routine. The director asks you to calculate the payback period and NPV for both projects, and here is what you derive: Project UV: The payback period is 12 months, and the NPV is (100). Project Fun: The payback period is 18 months, and the NPV is 250. Which project would you recommend to the director? | 4 | Project UV, because the payback period is shorter than Project Fun | Project Fun, because the NPV is a positive number | Project UV, because the NPV is a negative number | Project Fun, because the NPV is a higher number than Project UV |  |  | 2 | 1 | PMP | Business Environment | Project Integration Management |  |  | High Complex | Predictive Approach | Projects with NPV greater than 0 should be recommended; the key determining factor in selecting Project Fun is that the NPV is positive. Had both NPVs been positive, then the determining factor would have been the greater NPV number, since the scenario notes that funding exists for only one project. Payback period is considered the least precise selection method and is not typically the sole determining factor. | 44198 | N | 4 | [5 empty] | NA | NA
360 | SINGLE | Marysil is an enterprise project manager for Cups on Fire. She is managing the implementation of an enterprise relationship management system using a hybrid of waterfall and Scrum. This is the most complex project the team has undertaken to date. For this reason, she puts careful attention to risk management activities. She recently learned that a risk had materialized and become an issue. Because of the nature of the issue, Marysil will need to follow the escalation process to inform the appropriate individuals. Where will she need to look in order to find the escalation processes? | 4 | Project management plan | Issue log | Risk management plan | Communications management plan |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | The communications management plan describes how communication throughout the project will be planned, structured, implemented, and monitored for effectiveness. It is a component of the broader project management plan. One of the elements captured within the communications management plan includes the escalation processes. | 44198 | N | 4 | [5 empty] | NA | NA
361 | SINGLE | Within Agile, a “T” shaped person refers to what? | 4 | A generalist who can take on any work within the backlog, regardless of skills needed | An individual who is early in their career and requires coaching in tandem with an assignment | An individual who has deep specializations in one domain and rarely contributes outside of it | An individual who supplements their expertise in one area with less-developed skills in associated areas |  |  | 4 | 1 | PMP | People | Project Resource Management |  |  | High Complex | Agile Hybrid | Within Agile there is a concept that describes the degree to which individuals can take on work, according to their depth and breadth. “T” shaped people are considered generalizing specialists who have expertise in an area but can also contribute to other areas. “I” shaped people refers to those who have deep specialization in one domain and rarely contribute to work outside of that domain. | 44198 | N | 4 | [5 empty] | NA | NA
362 | SINGLE | You are the project manager of a software organization leading a project to develop a new reservation system. A new scheduling risk has been identified and determined to be critical to the project. As a result, you need to meet with project stakeholders to discuss the situation. What is the best method for dealing with stakeholders? | 4 | Call each stakeholder individually to get feedback | Schedule one-on-one meetings with all of the stakeholders | Schedule a phone conference with all of the stakeholders | Schedule an in-person meeting with all of the stakeholders |  |  | 4 | 1 | PMP | Process | Project Risk Management |  |  | Complex | Predictive Approach | A face-to-face meeting is the preferred method for dealing with stakeholders. There is nothing within the question to indicate that a one-on-one meeting with stakeholders is required, which makes “an in-person meeting” the best and most efficient choice. | 44198 | N | 4 | [5 empty] | NA | NA