## Sheet1
Question ID | Question | Option A | Option B | Option C | Option D | Correct Answer | Correct Answer Rationale | Why A is Incorrect | Why B is Incorrect | Why C is Incorrect | Why D is Incorrect | PMP Domain | ECO Task | Topic Category | Tested Skill / Topic | Methodology | Question Type | Difficulty | Cognitive Level | PMBOK Topic / Knowledge Area | Predictive Process Group / Lifecycle Stage | PMBOK Reference | Agile Reference | PMI Exam Tip | Exam Trap | Last Reviewed
MOCK1-001 | During the execution of a project within an operations function, the project manager encounters scope changes and a delay in the delivery of critical tasks. How should the project manager address this situation? | Conduct an impact analysis and present the results to the steering committee for approval | Communicate the concerns to the project management office (PMO) during the weekly project reports | Call for a team meeting to decide if the changes should be included. | Initiate the change request to modify the scope and adjust the timelines. | A | Mid-execution scope modifications must be quantified before action is taken. Performing an impact analysis and escalating it to the Change Control Board (CCB) adheres to the Perform Integrated Change Control sequence: assess the impact on all project constraints, then obtain formal approval. | A is Correct. Mid-execution scope modifications must be quantified before action is taken. Performing an impact analysis and escalating it to the Change Control Board (CCB) adheres to the Perform Integrated Change Control sequence: assess the impact on all project constraints, then obtain formal approval. | Simply reporting the concern in a routine weekly report is too passive for a scope change that is already causing schedule delay; it does not trigger the analysis or approval the situation needs. | Deciding with the team alone bypasses the formal change control authority (the steering committee/CCB) that scope changes of this kind require. | Initiating the change request before the impact is understood risks approving or implementing a change without knowing its true cost, schedule, or risk consequences, and skips the analysis step. | Process | Task 9 — Manage Project Changes | Project Integration | Change Control | Predictive | Situational | Moderate | Apply | Project Integration Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 9 — Manage Project Changes) and the Project Integration Management knowledge area. | Not agile-specific; the same assess-before-you-approve discipline applies when a change surfaces during a sprint. | When a scope change appears during execution, look for the option that assesses impact before approval or implementation. | Don't pick the option that jumps straight to submitting or actioning a change request — that skips the impact analysis PMI expects first. | 2026-09-12
MOCK1-002 | A project manager is struggling to figure out the performance of the project teams in an agile environment. For the same scope of work, team A has calculated 100 story points and team B has calculated 125 story points. Which team is performing better? | The team that completes the most stories selected from the sprint backlog | The team with the least amount of defects in their deliverables. | Team A as they have calculated fewer story points than team B. | Team B as they have calculated more story points than team A. | B | Story points are a relative, team-specific unit of estimation — one team's point is not equivalent to another team's point, so velocity or point totals cannot be used to compare two different teams. Quality of delivery, such as defect count for the same scope, is a far more meaningful cross-team performance signal. | Completing the most stories reflects throughput, not quality, and still doesn't correct for the fact that the two teams size their stories differently. | B is Correct. Story points are a relative, team-specific unit of estimation — one team's point is not equivalent to another team's point, so velocity or point totals cannot be used to compare two different teams. Quality of delivery, such as defect count for the same scope, is a far more meaningful cross-team performance signal. | Fewer story points does not mean better performance — points are relative to the team that estimated them, not an absolute measure of effort or output. | More story points does not mean better performance either, for the same reason: velocity is not comparable across teams. | People | Task 6 — Manage Team Performance | Agile / Adaptive | Story Points | Agile | Interpretation | Moderate | Analyze | Agile / Adaptive Practices | Continuous Improvement | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO People domain (Task 6 — Manage Team Performance) and the Agile / Adaptive Practices knowledge area. | Agile Practice Guide: velocity and story points are relative, team-specific estimates and are not standardized units of work. | On the exam, remember velocity/story points are relative to a single team and cannot be used to rank two different teams. | Don't assume a higher story-point total automatically means better performance. | 2026-09-12
MOCK1-003 | A project manager has recently joined a small company. The company's chief operating officer (COO) asked the team to skip some steps in the process in order to work more quickly. The project manager wants to ensure that these steps are not skipped in the future. What should the project manager do? | Redesign the process so the team can move more quickly. | Notify all team members that all steps in the process must be completed. | Escalate the issue to the other executive leadership members. | Schedule a review of the process steps with the team and the COO. | D | Rather than unilaterally redesigning the process or issuing a directive, the PM should bring the team and the COO together to review why the steps were skipped and agree on whether the process needs tailoring or whether the steps are genuinely necessary. This addresses the root cause collaboratively while respecting governance. | Redesigning the process alone, without first understanding the COO's underlying speed concern, bypasses the collaborative review needed to reach a durable fix. | Simply dictating that all steps must be completed doesn't resolve why the COO wanted to skip them, and risks new conflict without addressing the cause. | Escalating to other executives before attempting to resolve the issue directly with the COO and team is premature. | D is Correct. Rather than unilaterally redesigning the process or issuing a directive, the PM should bring the team and the COO together to review why the steps were skipped and agree on whether the process needs tailoring or whether the steps are genuinely necessary. This addresses the root cause collaboratively while respecting governance. | Process | Task 14 — Determine Appropriate Project Methodology/Methods and Practices | Project Integration | Project Governance | Predictive | Situational | Moderate | Evaluate | Tailoring | Execution | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 14 — Determine Appropriate Project Methodology/Methods and Practices) and the Tailoring knowledge area. | Not agile-specific; the same collaborative-review principle applies when a Scrum team is pressured to skip ceremonies. | When someone asks the team to skip steps, look for the option that reviews and tailors the process collaboratively, not one that simply complies or refuses. | Avoid the options that escalate immediately or rigidly enforce the process before a collaborative conversation has happened. | 2026-09-12
MOCK1-004 | During the planning stage of a project the project manager realizes that a standard stakeholder engagement approach will not suffice. One of the client representatives, who is not a key decision maker, is extremely opinionated. This client representative could become a roadblock to progress due to their perceived level of authority during meetings. How should the project manager handle this moving forward? | Allocate time to gain buy-in from the stakeholder prior to key decision meetings. | Ask that only key decision makers attend the project meetings. | Update the risk register to consider the possible project impacts | Update the project schedule to cater to this particular stakeholder. | A | This stakeholder has influence over the room even without formal decision authority. Proactively engaging them ahead of key meetings to build buy-in tailors the engagement approach to their actual behavior and influence, reducing the chance they become a roadblock during the meeting itself. | A is Correct. This stakeholder has influence over the room even without formal decision authority. Proactively engaging them ahead of key meetings to build buy-in tailors the engagement approach to their actual behavior and influence, reducing the chance they become a roadblock during the meeting itself. | Excluding the stakeholder from meetings suppresses input, can appear exclusionary, and does not resolve the underlying influence they hold with other participants. | Logging a risk is good practice but is not itself an engagement action; it doesn't address the need to proactively manage this stakeholder's behavior. | Rearranging the schedule specifically to accommodate one stakeholder is a reactive, costly response that doesn't address the real engagement gap. | People | Task 9 — Collaborate with Stakeholders | Stakeholder Management | Stakeholder Engagement | Predictive | Situational | Moderate | Apply | Project Stakeholder Management | Planning | PMBOK Guide, Eighth Edition -- Stakeholders Performance Domain; Principle: Focus on Value. Also maps to the ECO People domain (Task 9 — Collaborate with Stakeholders) and the Project Stakeholder Management knowledge area. | Agile Practice Guide: continuous, proactive stakeholder collaboration reduces surprises during reviews and planning sessions. | Address influential stakeholders proactively before they become blockers, regardless of their formal decision authority. | Don't default to restricting attendance or simply logging a risk when direct, proactive engagement is the stronger option. | 2026-09-12
MOCK1-005 | In the daily check-in meeting, a team member informs the project team that the licenses for one of the components that will be used will expire in a couple of months. The licensing cost is significant. What should the project manager do next? | Escalate the licensing issue to the product owner. | Raise a change request to secure the renewal. | Evaluate the impact of nonrenewal of the license. | Add a spike to the backlog for an alternative design | C | Before executing a risk response—whether escalating, submitting a formal change request, or modifying the product backlog—the team must analyze the license expiration's impact on cost, schedule, and performance baseline. Assessing impact before taking action complies with the standard Perform Qualitative/Quantitative Risk Analysis sequence. | Escalating without first sizing the impact leaves the product owner without the information needed to make an informed decision. | Committing to renew via a change request selects a solution before the impact and alternatives have been evaluated. | C is Correct. Before executing a risk response—whether escalating, submitting a formal change request, or modifying the product backlog—the team must analyze the license expiration's impact on cost, schedule, and performance baseline. Assessing impact before taking action complies with the standard Perform Qualitative/Quantitative Risk Analysis sequence. | Adding a spike for an alternative design likewise commits to a specific response path before the impact is understood. | Process | Task 3 — Assess and Manage Risks | Risk | Risk Analysis | Agile | Situational | Moderate | Analyze | Project Risk Management | Daily Coordination | PMBOK Guide, Eighth Edition -- Risk Performance Domain; Principle: Adopt a Holistic View. Also maps to the ECO Process domain (Task 3 — Assess and Manage Risks) and the Project Risk Management knowledge area. | Agile Practice Guide: impediments and risks raised in daily stand-ups should be assessed for impact before the team commits to a fix. | When a new risk or issue surfaces, look for the option that evaluates impact first, before escalation, change, or new backlog work. | Don't jump to a specific fix (change request, spike) before the impact of the issue is understood. | 2026-09-12
MOCK1-006 | An organization is about to start a multiphased project. Due to strict regulations, some of the phases must be completely planned in advance. However, other phases allow for more flexibility and experimentation on scope and schedule. The sponsor wants to pursue the project objectives as planned, but also wants to accommodate new information and changes as the project progresses. Which project management approach should the project manager select for this project? | Hybrid | Agile | Incremental | Phased | A | The project needs some phases fully planned up front (predictive) and others left flexible and adaptive — that combination of predictive and agile elements, tailored to the needs of each phase, is the definition of a hybrid approach. | A is Correct. The project needs some phases fully planned up front (predictive) and others left flexible and adaptive — that combination of predictive and agile elements, tailored to the needs of each phase, is the definition of a hybrid approach. | A purely agile approach would not satisfy the phases that must be completely planned in advance due to regulation. | Incremental describes a delivery cadence (delivering the product in increments), not a full lifecycle approach that blends planned and flexible phases. | "Phased" only describes that the project is divided into phases; it does not capture the deliberate blend of predictive and adaptive planning styles described here. | Process | Task 14 — Determine Appropriate Project Methodology/Methods and Practices | Hybrid | Predictive + Agile Integration | Hybrid | Conceptual | Easy | Understand | Hybrid Practices | Initiation | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Adopt a Holistic View. Also maps to the ECO Process domain (Task 14 — Determine Appropriate Project Methodology/Methods and Practices) and the Hybrid Practices knowledge area. | Agile Practice Guide: hybrid life cycles combine predictive and agile elements based on the needs of different parts of the project. | When some phases need heavy upfront planning and others need flexibility, the answer is almost always Hybrid. | Don't confuse delivery-cadence terms like phased or incremental with a full hybrid lifecycle approach. | 2026-09-12
MOCK1-007 | A project manager has a team of shared resources from other projects who are working on a client project. Three days before the project is due, the team informs the project manager that the project will be delayed because a component was not delivered on time. Competing priorities of the shared resources are delaying delivery of the component. What should the project manager have done to prevent this delay from happening? | Used the resource management plan to identify the impacts of the other projects | Reorganized the team for the project based on the work breakdown structure (WBS) | Updated the risk management plan and registered lessons learned for the project | Maintained constant communication with the stakeholders of the other projects | A | Proactively using the resource management plan to identify how competing demands from other projects could affect this project's shared resources would have surfaced the contention risk before it materialized, allowing the PM to plan contingencies or negotiate availability in advance. | A is Correct. Proactively using the resource management plan to identify how competing demands from other projects could affect this project's shared resources would have surfaced the contention risk before it materialized, allowing the PM to plan contingencies or negotiate availability in advance. | Reorganizing the team based on the WBS addresses how work is broken down, not resource contention across projects, so it would not have prevented this delay. | Updating the risk management plan and logging lessons learned is a reactive, after-the-fact documentation step, not a preventive planning action. | Communication alone, without proactively planning for resource conflicts through the resource management plan, would not have prevented the scheduling conflict. | Process | Task 5 — Plan and Manage Budget and Resources | Resources | Resource Allocation | Predictive | Situational | Moderate | Analyze | Project Resource Management | Planning | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO Process domain (Task 5 — Plan and Manage Budget and Resources) and the Project Resource Management knowledge area. | Not agile-specific; shared-resource contention is primarily a predictive resource-planning concern. | "What should the PM have done to prevent X" questions usually point to a planning-phase action, not a reactive fix. | Don't pick a reactive action (updating the risk register after the fact, reorganizing the team) when the question asks what would have prevented the problem. | 2026-09-12
MOCK1-008 | A project team is prioritizing the creation of project artifacts and enforcing it rigidly, while they face issues with delays in deliverables. How should the project manager respond? | Recognize the team's efforts for documenting artifacts and motivate them with an incentive mechanism. | Implement stricter controls so that project artifact creation is given the utmost importance. | Advise the team that solely focusing on artifacts will not produce successful project deliverables. | Facilitate the implementation of an automated tool for the team to manage project artifacts. | C | The team's rigid focus on documentation is coming at the cost of actual delivery. The PM should redirect the team toward the real goal — producing successful deliverables — by making clear that artifacts exist to support delivery, not to replace it. | Rewarding the team for continued heavy documentation focus reinforces the very behavior that is causing the delivery delay. | Adding stricter controls that emphasize artifact creation would make the underlying problem worse, not better. | C is Correct. The team's rigid focus on documentation is coming at the cost of actual delivery. The PM should redirect the team toward the real goal — producing successful deliverables — by making clear that artifacts exist to support delivery, not to replace it. | An automated tool could improve documentation efficiency, but it doesn't address the root cause — the team valuing artifacts over delivering outcomes — and won't resolve the current delay on its own. | Process | Task 13 — Manage Project Artifacts | Business Environment | Business Value | Agile | Decision-Making | Moderate | Evaluate | Value Delivery | Continuous Improvement | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Integrate Sustainability. Also maps to the ECO Process domain (Task 13 — Manage Project Artifacts) and the Value Delivery knowledge area. | Agile Manifesto principle: working deliverables over comprehensive documentation. | When a team over-indexes on documentation or process at the expense of delivery, look for the option that redirects focus to value and outcomes. | Don't pick an option that rewards or reinforces process-heavy behavior when that behavior is causing the delivery delay. | 2026-09-12
MOCK1-009 | During the implementation of a project, the project team discovered a new opportunity. After an internal review, the project team agreed that the opportunity is outside of the project scope. The project manager decided to update the risk register and escalate the opportunity to a higher level. What should the project manager do next with this opportunity? | Share this opportunity with another project. | Further monitor the opportunity. | No more action is required. | Establish a contingency reserve to support the opportunity. | B | When an opportunity is classified as outside the project scope and is escalated to program or portfolio management, ownership shifts to the higher governance level. The project manager's responsibility is restricted to monitoring the item in the risk register for status updates, ensuring no unauthorized project-level resources are allocated to its execution. | Deciding to share the opportunity with another project is a decision for portfolio/program management or whoever received the escalation, not a unilateral next step for this PM. | B is Correct. When an opportunity is classified as outside the project scope and is escalated to program or portfolio management, ownership shifts to the higher governance level. The project manager's responsibility is restricted to monitoring the item in the risk register for status updates, ensuring no unauthorized project-level resources are allocated to its execution. | "No more action" is incorrect — the opportunity still needs to be tracked/monitored per the risk register; the PM shouldn't disengage from it entirely. | A contingency reserve funds a planned response to an identified project risk within scope; it isn't appropriate for an opportunity that is out of scope and has already been escalated. | Process | Task 3 — Assess and Manage Risks | Risk | Opportunities | Predictive | Decision-Making | Moderate | Evaluate | Project Risk Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Risk Performance Domain; Principle: Adopt a Holistic View. Also maps to the ECO Process domain (Task 3 — Assess and Manage Risks) and the Project Risk Management knowledge area. | Not agile-specific; the escalate-then-monitor pattern applies across delivery approaches. | After escalating an out-of-scope item, the PM's role typically shifts to monitoring it, not taking further unilateral action. | Don't pick an option that oversteps the PM's authority for an item that has already been escalated to a higher level. | 2026-09-12
MOCK1-010 | A retail chain is evaluating a project to replace payment systems across all its stores in multiple locations. The project does not pass the financial threshold but is also expected to increase market share, improve customer services, and retain more customers. The project is planned as a phased implementation, building on learning from the retrospectives during each phase. How should the business increase the value of the project? | Use a fishbone diagram to find the root cause of the lower financial benefits with the benefits owner. | Consult with experts on methods to reduce costs and increase the financial value of the project. | Ask the benefits owner to reassess the identified risks that are impacting the outcomes of the financial benefits | Quantify the expected tangible and intangible benefits in the benefits management plan for each phase. | D | To prevent the undervalued assessment of the project based strictly on financial criteria, the benefits management plan must capture both tangible and intangible business value. Progressively quantifying these metrics phase-by-phase enables accurate benefit realization monitoring and provides decision-makers with a comprehensive view of the initiative's true organizational value. | A fishbone diagram is a root-cause analysis tool for quality/process problems; it is not the right tool for capturing or quantifying broader business value. | Consulting experts purely to cut costs and raise financial return ignores the intangible benefits already identified and misses the fuller value picture the sponsor cares about. | Reassessing risk doesn't quantify the benefits case; the core gap here is that intangible value isn't yet reflected in benefits planning, not that the risks are wrong. | D is Correct.To prevent the undervalued assessment of the project based strictly on financial criteria, the benefits management plan must capture both tangible and intangible business value. Progressively quantifying these metrics phase-by-phase enables accurate benefit realization monitoring and provides decision-makers with a comprehensive view of the initiative's true organizational value. | Business Environment | Task 2 — Evaluate and Deliver Project Benefits and Value | Business Environment | Benefits Management | Hybrid | Decision-Making | Difficult | Evaluate | Benefits Management | Predictive Planning | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Integrate Sustainability. Also maps to the ECO Business Environment domain (Task 2 — Evaluate and Deliver Project Benefits and Value) and the Benefits Management knowledge area. | Agile Practice Guide: phased delivery with retrospectives supports continuously reassessing and quantifying value across phases. | When a project has strong intangible benefits, look for the option that quantifies overall value rather than narrowly chasing financial metrics. | Don't default to root-cause analysis or risk reassessment tools when the real gap is that benefits — especially intangible ones — haven't been properly quantified. | 2026-09-12
MOCK1-011 | A project requires the procurement of a large amount of equipment that needs to be on-site before any other activity can begin. The procurement department has a lengthy approval process. What should the project manager do? | Work with the procurement team to find alternative options. | Contact the vendor that supplied similar equipment for a previous project | Use the existing equipment and replace it later with the new equipment. | Ask the project sponsor to expedite the vendor selection process. | A | The Project Manager must engage with Procurement Management to identify alternative sourcing strategies that adhere to organizational Governance Frameworks—such as expedited procurement procedures, pre-qualified secondary sellers, or a phased Deliverable schedule—rather than bypassing established Organizational Process Assets (OPAs) or implementing unauthorized Workarounds that introduce unmanaged project risk. | A is Correct. The Project Manager must engage with Procurement Management to identify alternative sourcing strategies that adhere to organizational Governance Frameworks—such as expedited procurement procedures, pre-qualified secondary sellers, or a phased Deliverable schedule—rather than bypassing established Organizational Process Assets (OPAs) or implementing unauthorized Workarounds that introduce unmanaged project risk. | Contacting a specific vendor directly bypasses the procurement process and doesn't necessarily solve the timing problem within organizational governance. | Substituting ill-suited existing equipment as a stand-in risks compromising quality or scope and creates rework; it doesn't address the underlying timing problem. | Escalating to the sponsor to expedite or bypass a formal process is premature; the PM should first work within procurement's own team to find options. | Process | Task 10 — Plan and Manage Procurement | Procurement | Procurement Planning | Predictive | Situational | Moderate | Apply | Project Procurement Management | Planning | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 10 — Plan and Manage Procurement) and the Project Procurement Management knowledge area. | Not agile-specific; long-lead procurement constraints are primarily a predictive planning concern. | When a formal process (like procurement approval) is creating a schedule risk, look for the option that works within that process for alternatives before escalating or bypassing it. | Don't jump to bypassing procurement governance (contacting a vendor directly, expediting via the sponsor) before exploring options with the procurement team itself. | 2026-09-12
MOCK1-012 | A company is initiating a project to enhance one of its existing products. All of its products are developed internally. What should the project manager do? | Review the lessons learned from the previous project. | Identify the risk of implementing the new solution and evaluate the impact on the project. | Create a lessons learned document for the initiation phase. | Ensure the stakeholder engagement plan is accurate and properly documented. | D | Even though this project enhances an existing, internally developed product, it is still a new project effort. In initiation, the PM's priority is to confirm who the stakeholders are for this specific project and ensure their engagement approach is accurate and properly documented, since a new effort can have a different stakeholder mix than prior work. | Reviewing lessons learned is valuable but secondary to first confirming stakeholders and their engagement approach for this new effort. | Identifying and evaluating solution risk is a planning-oriented activity; it is premature relative to first establishing stakeholder engagement in initiation. | Lessons learned are captured throughout a project and formally at closure, not authored as a deliverable of the initiation phase itself. | D is Correct. Even though this project enhances an existing, internally developed product, it is still a new project effort. In initiation, the PM's priority is to confirm who the stakeholders are for this specific project and ensure their engagement approach is accurate and properly documented, since a new effort can have a different stakeholder mix than prior work. | People | Task 9 — Collaborate with Stakeholders | Stakeholder Management | Stakeholder Engagement | Predictive | Conceptual | Moderate | Understand | Project Stakeholder Management | Initiation | PMBOK Guide, Eighth Edition -- Stakeholders Performance Domain; Principle: Focus on Value. Also maps to the ECO People domain (Task 9 — Collaborate with Stakeholders) and the Project Stakeholder Management knowledge area. | Agile Practice Guide: continuous stakeholder engagement starts at the very beginning of the effort, regardless of how familiar the product is. | In Initiating, prioritize identifying stakeholders and setting up their engagement approach, even for a project that looks similar to prior work. | Don't assume risk analysis or lessons-learned documentation is the first priority in Initiating; those belong more to Planning and Closing. | 2026-09-12
MOCK1-013 | Due to organizational changes, several key stakeholders are replaced by new ones in the middle of a project. As a result, numerous new requirements are raised. What should the project manager do to ensure success of the project? | Seek immediate approval to amend the project timeline and budget in order to deliver all new requirements. | Review and prioritize new requirements with stakeholders to determine which change requests are needed | Emphasize to the new stakeholders that new requirements are not allowed at this stage of the project. | Escalate the issue to the project sponsor and seek support to keep the original requirements | B | New stakeholders bring new requirements. Before committing to timeline/budget changes or rejecting them outright, the PM should collaboratively review and prioritize the new requirements with the stakeholders to determine which genuinely warrant a formal change request. | Committing to deliver all new requirements before they've been reviewed and prioritized risks unnecessary scope creep and cost/schedule impact. | B is Correct. New stakeholders bring new requirements. Before committing to timeline/budget changes or rejecting them outright, the PM should collaboratively review and prioritize the new requirements with the stakeholders to determine which genuinely warrant a formal change request. | Rigidly refusing all new requirements ignores legitimate stakeholder needs arising from the organizational change; requirements should be evaluated, not blanket-rejected. | Escalating to preserve the original scope without first assessing the new requirements' merit bypasses proper stakeholder engagement and change evaluation. | Process | Task 9 — Manage Project Changes | Scope | Requirements Analysis | Predictive | Situational | Moderate | Evaluate | Project Scope Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Scope Performance Domain; Principle: Focus on Value. Also maps to the ECO Process domain (Task 9 — Manage Project Changes) and the Project Scope Management knowledge area. | Not agile-specific; the review-and-prioritize response applies whenever new stakeholders surface new needs. | When new stakeholders bring new requirements, review and prioritize with them before deciding on formal changes — don't default to blanket acceptance or blanket refusal. | Avoid the extremes: committing to deliver everything, or refusing everything — the correct action is always evaluation and prioritization first. | 2026-09-12
MOCK1-014 | During the final stage of the launch for a new design, team members are having a conflict about some features of the design. What should the project manager do? | Ask stakeholders to reduce the scope in order to meet project deadlines. | Ask the project sponsor to make the decision about the design features. | Review the design with the team members and propose a new launch date. | Call a stakeholder meeting along with team members and seek consensus. | D | Because the conflict involves design attributes that directly impact both Project Stakeholders and the Project Team, utilizing a Collaborate/Problem Solve conflict management technique to achieve Consensus satisfies the competing needs of all parties while ensuring the final Deliverable aligns with Stakeholder Expectations and project requirements. | Jumping to reducing scope is premature and doesn't address the underlying design disagreement; it assumes a scope cut is needed without first exploring consensus. | Escalating a design decision to the sponsor bypasses the team's and stakeholders' collaborative input and may not resolve the actual disagreement. | Introducing a schedule delay is a reactive step that doesn't necessarily resolve the design conflict itself, and may be unnecessary if consensus can be reached without one. | D is Correct. Because the conflict involves design attributes that directly impact both Project Stakeholders and the Project Team, utilizing a Collaborate/Problem Solve conflict management technique to achieve Consensus satisfies the competing needs of all parties while ensuring the final Deliverable aligns with Stakeholder Expectations and project requirements. | People | Task 1 — Manage Conflict | Leadership & Team | Conflict Resolution | Predictive | Situational | Moderate | Apply | Team / Leadership | Closing / Transition | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO People domain (Task 1 — Manage Conflict) and the Team / Leadership knowledge area. | Agile Practice Guide: facilitating consensus among the team and stakeholders is preferred over unilateral decisions, even late in delivery. | Design or scope disagreements late in a project are best resolved by bringing the affected team members and stakeholders together to build consensus. | Don't default to scope cuts, schedule delays, or a single-person (sponsor) decision before trying facilitated consensus. | 2026-09-12
MOCK1-015 | A member of a testing team in an agile project works well with the project team. However, in the previous two iterations, this team member's performance was poor, and the team had difficulty meeting the iteration goals. How should the project manager handle this situation? | Inform the human resource (HR) department about the issue. | Speak to the team member regarding the need to improve performance. | Allow the project team to discuss the problem with this team member. | Discuss the issue with the team member's functional manager. | B | The PM should address a team performance issue directly and privately with the individual first, giving them the chance to understand expectations and improve, before escalating to HR, functional management, or the wider team. | Involving HR immediately, without first having a direct conversation, is disproportionate for a performance issue that hasn't yet been discussed with the team member. | B is Correct. The PM should address a team performance issue directly and privately with the individual first, giving them the chance to understand expectations and improve, before escalating to HR, functional management, or the wider team. | A performance conversation should come from the PM (or the team's leadership) directly and privately, not be delegated to open team discussion, which could embarrass the individual. | Going to the functional manager first bypasses the PM's own responsibility to directly address team performance and could undermine trust with the team member. | People | Task 6 — Manage Team Performance | Leadership & Team | Team Performance | Agile | Situational | Easy | Apply | Team / Leadership | Iteration / Sprint Execution | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO People domain (Task 6 — Manage Team Performance) and the Team / Leadership knowledge area. | Agile Practice Guide: the Scrum Master/PM addresses individual performance concerns directly and supportively, protecting team trust. | Performance issues should be addressed directly with the individual first — that's almost always the correct first step. | Don't pick options that escalate to HR or a functional manager before the PM has had a direct conversation. | 2026-09-12
MOCK1-016 | On a project with multiple international locations, a trend for delays has been flagged. When looking into the issue, the project manager realized that some of the key activities were scheduled over the holiday periods in the overseas offices. What should the project manager do next? | Request that the offices in overseas locations work overtime to mitigate schedule slippages. | Hire additional personnel on a temporary basis to cover the extra workload during the holiday seasons. | Update the schedule to reflect the holidays and notify the project sponsor of the delayed completion | Update the schedule to reflect the holidays and share the workload among offices to mitigate schedule slippage. | D | The best response both corrects the schedule for the newly identified constraint (holidays) and proactively mitigates the resulting slippage by redistributing work across offices, addressing the root cause and its schedule impact together. | Asking overseas staff to work overtime during their holiday periods is not a sustainable or considerate response and doesn't fix the planning gap. | Hiring additional temporary personnel is a costly, slower solution and doesn't address the immediate scheduling conflict as directly as updating the schedule and sharing workload. | This only updates the schedule and informs the sponsor of a delay, without taking the proactive mitigation step of sharing workload to avoid or reduce that delay. | D is Correct. The best response both corrects the schedule for the newly identified constraint (holidays) and proactively mitigates the resulting slippage by redistributing work across offices, addressing the root cause and its schedule impact together. | Process | Task 6 — Plan and Manage Schedule | Schedule | Schedule Control | Predictive | Situational | Moderate | Apply | Project Schedule Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Schedule Performance Domain; Principle: Embed Quality. Also maps to the ECO Process domain (Task 6 — Plan and Manage Schedule) and the Project Schedule Management knowledge area. | Not agile-specific; distributed-team calendar constraints are primarily a predictive scheduling concern. | When a scheduling conflict is discovered, look for the option that both corrects the schedule and actively mitigates the impact, not just one or the other. | An option that only documents or escalates the delay, without mitigating it, is usually weaker than one that also takes mitigating action. | 2026-09-12
MOCK1-017 | At the end of a project with multiple suppliers, the project manager is reviewing the closing process and finds that an unexpected financial balance is remaining. What will help the project manager understand why this has occurred? | Lessons learned | Project audit | Organizational process assets (OPAs) | Procurement audit | D | A procurement audit reviews supplier and contract performance and financial transactions across the procurement lifecycle, making it the right tool to investigate why an unexpected financial balance remains among multiple suppliers at project closure. | Lessons learned capture general knowledge and insights for future projects; they are not a structured financial or contract review tool for explaining a specific balance discrepancy. | A project audit reviews overall project management practices and compliance broadly; a procurement audit is the more targeted, correct tool for a procurement/financial discrepancy specifically. | Organizational process assets are inputs and historical references (templates, policies, historical data), not an analysis tool that would explain a specific financial discrepancy. | D is Correct. A procurement audit reviews supplier and contract performance and financial transactions across the procurement lifecycle, making it the right tool to investigate why an unexpected financial balance remains among multiple suppliers at project closure. | Process | Task 10 — Plan and Manage Procurement | Procurement | Procurement Closure | Predictive | Conceptual | Moderate | Understand | Project Procurement Management | Closing / Transition | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 10 — Plan and Manage Procurement) and the Project Procurement Management knowledge area. | Not agile-specific; procurement audits are primarily a predictive/contract-management tool. | For procurement- or contract-related financial discrepancies at closure, think procurement audit specifically, not a general project audit. | Don't confuse a general project audit with a procurement audit — pick the tool that matches the specific problem domain (contracts/financials) in the question. | 2026-09-12
MOCK1-018 | A company wants to increase the commercial value of one of its products in a highly competitive market. In order to do this, the company commissions a project to create a prototype. The team constructs the prototype incrementally. Which action should the project manager take as a priority? | Deliver business value as soon as possible. | Emphasize the use of Kanban methodology. | Ensure the project sponsor is aware of the go-to market date. | Implement a plan-do-check-act (PDCA) cycle. | A | In a competitive market where commercial value depends on speed to market, the PM's top priority when building incrementally should be delivering business value as early as possible, consistent with incremental/agile delivery principles. | A is Correct. In a competitive market where commercial value depends on speed to market, the PM's top priority when building incrementally should be delivering business value as early as possible, consistent with incremental/agile delivery principles. | Mandating a specific method (Kanban) is a tactical/process choice, not the strategic priority the situation calls for. | Keeping the sponsor informed is good communication practice, but it's not the priority action that drives the actual outcome (value delivery) the company needs. | PDCA is a continuous-improvement technique; it isn't the primary strategic priority when the goal is to maximize commercial value quickly in a competitive market. | Business Environment | Task 2 — Evaluate and Deliver Project Benefits and Value | Business Environment | Business Value | Agile | Conceptual | Easy | Understand | Value Delivery | Continuous Improvement | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Integrate Sustainability. Also maps to the ECO Business Environment domain (Task 2 — Evaluate and Deliver Project Benefits and Value) and the Value Delivery knowledge area. | Agile Manifesto principle: deliver working, valuable product early and continuously, especially under competitive time pressure. | When a scenario emphasizes competitive/commercial urgency with incremental delivery, the priority is almost always delivering value early and often. | Don't pick a specific technique or method (Kanban, PDCA) when the question is really asking about the overarching value-delivery priority. | 2026-09-12
MOCK1-019 | A project team is conducting sprint planning. Based on the estimated effort, only 95% of the items included in the sprint may be delivered. The product owner asks the project manager for advice on how to prioritize the backlog items. What should be used to prioritize the backlog items? | Risk to delivery | Business value | Technical complexity | Estimation accuracy | B | When not all backlog items can be completed, items should be prioritized by the business value they deliver, ensuring the most valuable outcomes are completed within capacity — this reflects agile's value-driven delivery approach. | Risk is a factor to manage, but it isn't the primary prioritization criterion for backlog items relative to what stakeholders value most. | B is Correct. When not all backlog items can be completed, items should be prioritized by the business value they deliver, ensuring the most valuable outcomes are completed within capacity — this reflects agile's value-driven delivery approach. | Prioritizing by technical complexity (easiest or hardest first) doesn't ensure the team delivers the most valuable outcomes within sprint capacity. | How accurately something was estimated doesn't determine its importance to the business; it is not a valid prioritization basis. | Process | Task 1 — Execute Project with the Urgency Required to Deliver Business Value | Agile / Adaptive | Prioritization | Agile | Conceptual | Easy | Understand | Agile / Adaptive Practices | Iteration / Sprint Planning | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO Process domain (Task 1 — Execute Project with the Urgency Required to Deliver Business Value) and the Agile / Adaptive Practices knowledge area. | Agile Practice Guide / Scrum Guide: backlog prioritization is fundamentally value-driven. | Backlog prioritization in agile is fundamentally value-driven — when in doubt, pick business value. | Don't be pulled toward risk, complexity, or estimation-accuracy answers — those inform planning but aren't the prioritization criterion itself. | 2026-09-12
MOCK1-020 | A project manager is managing a project that will engage resources from multiple countries in different time zones. What should the project manager do to ensure that team members are effective? | Schedule meetings every 2 days at the same time with all team members. | Schedule meetings every 2 days that align with team members' time zones. | Organize a daily meeting for all team members and extend it, if required. | Organize a standard meeting time to engage all of the team members. | B | For a globally distributed team, effectiveness depends on scheduling meetings that reasonably accommodate different time zones, rather than picking one fixed time that favors some team members over others or holding daily meetings that could become burdensome across time zones. | Scheduling all meetings at the exact same time for everyone likely disadvantages team members in unfavorable time zones. | B is Correct. For a globally distributed team, effectiveness depends on scheduling meetings that reasonably accommodate different time zones, rather than picking one fixed time that favors some team members over others or holding daily meetings that could become burdensome across time zones. | A daily meeting extended as needed adds a heavier cadence than necessary and doesn't itself solve the time-zone fairness issue. | A single 'standard' meeting time for everyone doesn't account for the different time zones team members are actually working in. | People | Task 11 — Engage and Support Virtual Teams | Leadership & Team | Distributed/Virtual Teams | Predictive | Situational | Easy | Apply | Team / Leadership | Execution | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO People domain (Task 11 — Engage and Support Virtual Teams) and the Team / Leadership knowledge area. | Not agile-specific; time-zone-aware meeting scheduling is a standard virtual-team-effectiveness practice. | For globally distributed teams, schedule meetings with time-zone fairness in mind rather than a single fixed time for everyone. | Don't default to one fixed meeting time or a higher meeting cadence without considering time-zone fairness across the team. | 2026-09-12
MOCK1-021 | A project manager was recently assigned to a project that is in the execution phase and is experiencing roadblocks. During a review of the processes and procedures, the project manager notices similarities to a previous project that experienced similar roadblocks. The project manager reviews the task schedule and finds that certain tasks are well behind expectations. In speaking with the project team, the project manager confirms that the team is following the processes exactly. What should the project manager do? | Update the variation register to account for the extended project time | Review the resources allocated to the project and change accordingly. | Review and amend the processes to ensure only value-adding activities are present. | Update the schedule to account for the unexpected delays in the project tasks. | C | Since the team confirmed it is following the process exactly yet tasks are still falling behind — a pattern that has recurred on a prior project too — the process itself, not the team's execution, is the likely source of waste. Reviewing and amending it to keep only value-adding activities addresses that root cause. | There is no standard 'variation register' used to simply absorb extended time; this doesn't address why the delay keeps recurring. | The team confirmed it is following the process correctly, so reallocating resources targets the wrong lever when the process itself appears to be the bottleneck. | C is Correct. Since the team confirmed it is following the process exactly yet tasks are still falling behind — a pattern that has recurred on a prior project too — the process itself, not the team's execution, is the likely source of waste. Reviewing and amending it to keep only value-adding activities addresses that root cause. | Simply updating the schedule accepts the delay without addressing the recurring inefficiency causing it. | Process | Task 1 — Execute Project with the Urgency Required to Deliver Business Value | Quality | Continuous Improvement | Predictive | Situational | Moderate | Analyze | Project Quality Management | Execution | PMBOK Guide, Eighth Edition -- Scope Performance Domain; Principle: Embed Quality. Also maps to the ECO Process domain (Task 1 — Execute Project with the Urgency Required to Deliver Business Value) and the Project Quality Management knowledge area. | Agile Practice Guide: recurring waste in a process the team is following faithfully is a signal to inspect and adapt the process itself. | Recurring schedule slippage despite correct process execution points to the process itself needing improvement, not the team or the schedule. | Don't just adjust the schedule or resources when the real signal is a process/waste problem. | 2026-09-12
MOCK1-022 | A project has completed design activities ahead of schedule. Suddenly, the project manager is informed by a vendor that a deliverable may not meet the agreed delivery time frame due to a resource shortage. The internal team asked if they should continue to deliver as per the schedule. What should the project manager do? | Discuss with the project team alternative options to deliver as planned. | Inform the project team that some of them will work for the vendor. | Discuss with the team the need for longer hours to minimize the impact. | Inform the project team that they may proceed at a more relaxed pace. | A | With the project ahead of schedule, the PM has some buffer to work with. The best first step is to explore alternative options with the team to still deliver as planned, before resorting to overtime, reassigning people to the vendor, or abandoning the schedule. | A is Correct. With the project ahead of schedule, the PM has some buffer to work with. The best first step is to explore alternative options with the team to still deliver as planned, before resorting to overtime, reassigning people to the vendor, or abandoning the schedule. | Sending internal team members to work for the vendor is an unusual, premature step before exploring more direct alternatives. | Jumping straight to longer hours skips exploring other mitigation options first. | Relaxing the pace abandons the schedule prematurely when the team still has a buffer and options haven't been explored. | Process | Task 3 — Assess and Manage Risks | Risk | Risk Response Planning | Predictive | Situational | Moderate | Analyze | Project Risk Management | Execution | PMBOK Guide, Eighth Edition -- Risk Performance Domain; Principle: Adopt a Holistic View. Also maps to the ECO Process domain (Task 3 — Assess and Manage Risks) and the Project Risk Management knowledge area. | Not agile-specific; this is primarily a predictive risk-response and schedule-buffer scenario. | When a vendor risk threatens a milestone, look for the option that first explores mitigation and alternatives with the team before adjusting pace or reassigning people. | Don't default to relaxing effort or moving people around before exploring ways to still hit the original plan. | 2026-09-12
MOCK1-023 | A project manager has been assigned to an important project that will help set the future of the company. Meanwhile, the project management office (PMO) is implementing adaptive tools in a mostly predictive environment and has requested that the project manager follow this process as well. However, the functional manager has expressed concerns about the use of new tools on such an important project. What should the project manager do? | Make the decision on which project approach to use that would best fit the project. | Follow the functional manager's recommendation to implement only predictive tools in the project | Follow the project management office's (PMO's) request to implement the adaptive tools in the project | Review the adaptive tools' impact and obtain agreement from the functional manager. | D | The PM should assess the actual impact of introducing adaptive tools on this specific, high-stakes project and build agreement with the concerned functional manager — a data-driven, collaborative tailoring decision that balances the PMO's initiative with legitimate risk concerns. | Deciding unilaterally without engaging the functional manager or assessing impact ignores the collaborative input this important project needs. | Dismissing the PMO's initiative outright, without assessment, doesn't objectively evaluate whether the tools would help. | Implementing the new tools without assessing impact or addressing the functional manager's valid concerns risks the important project. | D is Correct. The PM should assess the actual impact of introducing adaptive tools on this specific, high-stakes project and build agreement with the concerned functional manager — a data-driven, collaborative tailoring decision that balances the PMO's initiative with legitimate risk concerns. | Process | Task 14 — Determine Appropriate Project Methodology/Methods and Practices | Project Integration | Decision Frameworks | Hybrid | Decision-Making | Difficult | Evaluate | Tailoring | Planning | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 14 — Determine Appropriate Project Methodology/Methods and Practices) and the Tailoring knowledge area. | Agile Practice Guide: introducing adaptive tools into a predictive environment should be assessed and tailored, not mandated top-down. | When adopting new methods/tools on a high-stakes project, assess the actual impact and build agreement with concerned stakeholders rather than deciding unilaterally or picking a side. | Don't simply defer to either the PMO or the functional manager without first evaluating impact and seeking alignment. | 2026-09-12
MOCK1-024 | The change control board (CCB) rejects a change request submitted by a subject matter expert (SME). The SME refuses to accept this rejection and does not want to continue the project without the change. What should the project manager have done to avoid this situation? | Assessed the change's overall impact to the project before submission. | Submitted the change request directly to the CCB. | Ensured that the change request was aligned with the project scope. | Requested that the sponsor approved the change request first. | A | Properly assessing the change's overall impact before submitting it to the CCB would have surfaced concerns and trade-offs early, letting the PM manage the SME's expectations proactively and avoid a rejection that triggers conflict. | A is Correct. Properly assessing the change's overall impact before submitting it to the CCB would have surfaced concerns and trade-offs early, letting the PM manage the SME's expectations proactively and avoid a rejection that triggers conflict. | Submitting to the CCB is what happened; it doesn't explain what should have been done differently to avoid the outcome. | Scope alignment is only part of impact assessment; the more complete preventive action is a full impact assessment (cost, schedule, risk), not scope alignment alone. | Adding another approval layer (the sponsor) doesn't address managing the SME's expectations or properly assessing the change up front. | Process | Task 9 — Manage Project Changes | Project Integration | Change Control | Predictive | Situational | Moderate | Evaluate | Project Integration Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Governance Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 9 — Manage Project Changes) and the Project Integration Management knowledge area. | Not agile-specific; the same impact-assessment discipline applies before any formal change decision. | 'What should have been done to avoid X' questions about a rejected change usually point back to properly assessing impact before submission. | Don't pick a procedural step already implied by the scenario (like submitting to the CCB); focus on what was missing beforehand. | 2026-09-12
MOCK1-025 | A real estate developer awards a project to construct three multistoried buildings. The awarded contractor assigns this project to a project manager who starts the work on one building. Three months later, the client informs the project manager that they need only one building and that the other two buildings are not required. What should the project manager do? | Apply the change management process with the applicable provisions in the contract. | Continue with the project schedule and escalate the change to the project sponsor. | Begin construction of all the buildings immediately per the project charter and project management plan. | Submit a claim against the real estate developer for the loss of revenue and profits. | A | A reduction in contracted scope should be handled through the formal change management process, referencing the contract's own provisions for scope changes, to ensure it is properly documented and any contractual implications are addressed. | A is Correct. A reduction in contracted scope should be handled through the formal change management process, referencing the contract's own provisions for scope changes, to ensure it is properly documented and any contractual implications are addressed. | Continuing the original schedule while merely escalating ignores the client's clear instruction and formal change process the contract requires. | Proceeding with all three buildings directly contradicts the client's updated request and ignores the need to formally change the contract. | Filing a claim for lost revenue is premature; the appropriate change process — which may itself address compensation — should be followed first. | Process | Task 9 — Manage Project Changes | Procurement | Contract Management | Predictive | Situational | Moderate | Apply | Project Procurement Management | Monitoring & Controlling | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Be an Accountable Leader. Also maps to the ECO Process domain (Task 9 — Manage Project Changes) and the Project Procurement Management knowledge area. | Not agile-specific; contractual scope reductions are a predictive procurement/change-control concern. | When a client requests a contractual scope reduction, route it through the formal change process and the contract's own provisions, not straight to escalation or a claim. | Don't jump to filing a claim before working the change through the proper contractual change process. | 2026-09-12
MOCK1-026 | A project to implement a new online landing platform has started. After the first sprint, the project sponsor requested a change. What should the project manager do next? | Escalate the change request to the sponsor. | Inform the stakeholders of the change. | Validate the work completed | Facilitate the update of the product backlog | D | In agile, a stakeholder-requested change is captured and prioritized through the product backlog; the PM/Scrum Master facilitates adding or refining this item in the backlog for the product owner to prioritize, rather than routing it around that process. | The sponsor is the one requesting the change, so escalating to them doesn't make sense as a next step. | Simply informing other stakeholders doesn't actually incorporate the request into the team's workflow. | Validating completed work is a separate activity (sprint review); it doesn't address how to handle a new change request. | D is Correct. In agile, a stakeholder-requested change is captured and prioritized through the product backlog; the PM/Scrum Master facilitates adding or refining this item in the backlog for the product owner to prioritize, rather than routing it around that process. | Process | Task 7 — Plan and Manage Scope | Agile / Adaptive | Backlog Refinement | Agile | Situational | Easy | Apply | Agile / Adaptive Practices | Backlog Refinement | PMBOK Guide, Eighth Edition -- Resources Performance Domain; Principle: Build an Empowered Culture. Also maps to the ECO Process domain (Task 7 — Plan and Manage Scope) and the Agile / Adaptive Practices knowledge area. | Scrum Guide: new requests are captured in the product backlog, where the product owner prioritizes them. | New change requests in agile normally flow into the product backlog for prioritization, not around it. | Don't escalate a change to the very stakeholder who requested it, and don't confuse validating completed work with handling a new request. | 2026-09-12